## Sheet1
| Outcome 1: Capacity and Coordination for EU-UN implementation of UNSCRs on Women Peace and Security and the EU’s Comprehensive Approach is strengthened. | [6 empty] | 2012 UNDP alocation | 2012 UNDP exp | 2013 UNDP Aloc | 2013 UNDP Exp
UN Women Output ID | OUTPUT | ACTIVITY | Atlas Activity ID | Responsible | Time Frame | INDICATORS | MEANS OF VERIFICATION
DR421 | Output 1.1: Advisory group and 1325 technical committee established, strengthened and operational | Activity 1.1.1: Project coordination staff is recruited and equipped | DR421-111 | UN Women | 2012-05-01 | Completed recruitment | Project reporting and filed recruitment process | 15000
|  | Activity 1.1.2: Advisory group’s functions are outlined in agreed TORs and convened, to meet three times a year. | DR421-112 | UN Women | Starting 1 May 2012 | 3 advisory group meetings a year | Meeting minutes and action points
|  | Activity 1.1.3: Review 1325 communication strategy, reports on implementation strategy and revise where necessary | DR421-113 | UNDP | 2012-12-31 | Development and dissemination of communication strategy | Meeting minutes and action points |  |  |  | 20361.65
|  | Activity 1.1.4: The advisory group provides regular feedback to the EU, GOL and the UN on UNSCR 1325-related processes, UNDAF and PRS. |  | UN Women | Starting 1 May 2012 | Improvement in EU and UN’s implementation of 1325 priorities | Reporting
|  | Activity 1.1.5: The advisory group provides advice for the development of projects on women’s participation in peace building. |  | UN Women | Starting 1 May | Increased allocataion of PBF to gender equality | Reporting
DR422 | Output 1.2: Harmonized EU / UN agenda and accountability frameworks for 1325 | Activity 1.2.1: WPS relevant indicators are integrated into the EU and UN planning frameworks, harmonized with the LNAP and PRS | DR422-121 | UN Women | 2012-12-31 | National 1325 Steering Committee is meeting regularly and integrating gender into national frameworks | Evaluation | 15000 |  | 30000
|  | Activity 1.2.2: Country strategies for the implementation of the EU Comprehensive Approach and Gender Action Plan reviewed and/or revised, in line with LNAP and PRS | DR422-122 | UNDP | 2012-12-31 | Validation of country strategies and Gender Action Plan | Review of country strategies and Gender Action Plan; |  | 5097.07
|  | Activity 1.2.3: Technical support is provided for the harmonization of the EU, UN, LNAP and PRS indicators on Women, Peace and Security, through inter alia the development of a database. | DR422-123 | UNDP | Year two | WPS data reported in EU and UN evaluations; Establishment of a database on WPS | Review of UNDAFs and PRS; 1325 database
|  | Activity 1.2.4: Contribution to reporting on WPS in UN mission and SG reports. |  | UN Women | Ongoing | WPS data included in SGs reports | SG's reports
1.2.5 N/A
DR411 | Output 1.3. Knowledge-building on WPS through events at Global and Country level | Activity 1.3.1: Organize thematic training workshops on Women, Peace and Security for EU and UN | DR411-131 | UN Women | 2012-12-31 | 2 training workshops; 30 evaluations received by participants | Workshop evaluations
1.3.2 N/A
1.3.3 N/A
| Subtotal Outcome 1: | [6 empty] | 30000 |  | 30000
Outcome 2: Regular spaces for dialogue with civil society, targeted capacity building, and direct support allow women’s organizations to engage meaningfully and regularly on peacebuilding processes
| OUTPUT | ACTIVITY |  |  |  | INDICATORS | MEANS OF VERIFICATION
DR412 | Output 2.1: Open Days on Women, Peace and Security. | Activity 2.1.1: Support to women’s organizations to create forums and lobby international and national decision making bodies |  | N/A | N/A |  |  | 20000 |  | 20000
|  | Activity 2.1.2: Preparatory sessions with women’s civil society are held leading up to WPS Open Days (establishment of regular mechanism). | DR412-212 | UNDP | October 2012 and October 2013 | # of Open Days held | Reporting; Open Day outcome statement |  |  |  | 20079.54
|  | Activity 2.1.3: Training and guidance for women leaders on high level representatives, rapporteur, relevant experts | DR412-213 | UN Women | Year two | Increased capacity of women leaders to engage with high-level representatives. | Reporting; workshop ecalution
Activity 2.1.4: NA
|  | Activity 2.1.5: Support to UN and EU to organize 16 days of activism events | DR412-215 | UN Women | November 2012 and November 2013 | # of 16 days events held | Reporting; media coverage; outcome statement
DR412 | Output 2.2: Dialogue and reconciliation workshops held with women and men from different sides of the conflict | Activity 2.2.1 Dialogue with men’s groups are organized in 2 counties | DR412-221 | UN Women | Starting 1 October 2012 | # of dialogues held between men, community and police | Reporting from implementing partner and local authorities
Activity 2.2.2. NA
DR423 | Output 2.3. Micro-grants provided to organizations in Kosovo, Liberia and Timor-Leste. | Activity 2.3.1: Country-level consultations with women’s organizations and government counterparts take place to identify suitable micro-grants economic empowerment model | DR423-231 | UN Women | 2012-09-01 | Micro-grants model established | Implementing partner report, Assessment mission, consultation reports
|  | Activity 2.3.2: Establishment of micro-grants / rural financing mechanism promoting peacebuilding and economic empowerment for women | DR423-232 | UN Women | Starting 1 October 2012 | # women group loans disbursed, # subprojects completed, #empowerment centres built, # of women participating in activities | Implementing partner report, Assessment mission
|  | Activity 2.3.3: Expansion of community-based women’s Peace huts” in Liberia to three additional communities | DR423-233 | UN Women | Starting 1 October 2012 | # of peace huts built | Implementing partner reports, assessment missions, case studies
|  | Activity 2.3.4 |  | NA
Subtotal Outcome 2:
| Subtotal | [6 empty] | 50000 | 5097.07 | 50000 | 40441.19 | 95538.26
| General Management Support (7%) | [6 empty] | 3500 |  | 3500
| GRAND TOTAL | [6 empty] | 53500
| Sum of Sum Amount |  |  |  |  | Account Type |  | General ledger data
| Year | Fund | Oper Unit | Project | Donor | EXPENDITURE
| 2012 | 26952 | LBR | 00074211 | 00032 | 27466.33
| 2012 Total |  |  |  |  | 27466.33
| Sum of USD Amount |  |  |  |  | Type |  | Fund Status as of 3 Dec 2013
| Budget Period | Fund | Budget Dept Description | Project | Donor | EXPENDITURE
| 2013 | 26952 | Liberia - Monrovia | 00074211 | 00032 | 20363.65
| 2013 Total |  |  |  |  | 20363.65