Election Project Document

Support to the 2015-2018 Liberian Electoral Cycle

DRAFT ONE - October 2014

UNITED NATIONS DEVELOPMENT PROGRAMME:

PROJECT OF THE GOVERNMENT OF LIBERIA

Support to the 2015-2018 Liberian Electoral Cycle (draft)

| Title/Number | LIBERIA - Support to the Liberian Electoral cycle CRIS N°2013/025-071 |
| --- | --- |
| Total cost | Total estimated cost: EUR 10 769 000 Total amount of EDF contribution: EUR 10 000 000. This action is co-financed in joint co-financing by - UNDP: USD 1 000 000 |
| Method of implementation | Project Approach Indirect management with international organization as the Contracting Authority |
| DAC-code | 15151, Elections | Sector | Elections |

# PROJECT BRIEF

The Republic of Liberia held democratic Presidential and Legislative Elections in 2005 and 2011 after 14 years of devastating civil war and decades of misrule. The 2005 elections featured extensive support from the international community under the leadership of the United Nations Mission in Liberia (UNMIL).. Though led by the National Elections Commission of Liberia (NEC), the 2011 elections received significant technical and advisory support from international partners through USAID/IFES support project and the UNDP managed Electoral Assistance Basket Fund. With two successive (and successful) post-war elections, it is clear that future electoral processes will not enjoy such broad-based international support. This means that Liberia must strengthen its national institutions and processes to conduct future elections in a credible, competent and sustainable manner. While significant work has been undertaken in the three years since the 2011 elections in strengthening NEC’s institutional capacity, there is now an urgent need to consolidate and build upon these gains with specific attention on staff capacity, enhancing gender sensitization and conflict preventative work with political parties and security forces, among other priorities. This is critical for NEC in establishing readiness to conduct a possible national referendum and the national elections proper in 2017.

The successful conduct of the 2011 elections was considered as significant step in the consolidation of democracy in Liberia. To ensure success in all future elections in Liberia, a series of administrative, policy and legal reforms, together with institutional capacity strengthening measure must be addressed.  This project  aims to provide a platform to undertake these reforms and execute the necessary measures to ensure that NEC, as the premiere Electoral Management Body (EMB) has the ability to preside over and deliver free, fair and democratic elections for Liberia. By so doing, it will help deepen the democratization process and foster long-term stability in Liberia.. The project will also help to establish links with other on-going reforms, to which it will contribute to and benefit from, such as the decentralization process, rule of law reform, and more importantly, the ongoing constitutional review process that has reached the critical stage of holding a constitutional review conference following a nation-wide consultation process.,.  The project will also promote effective election coordination and seek to mainstream gender and conflict preventative approaches in its activities. Finally, the project will also aim to support the revitalization of the Inter Party Consultative Committee (IPCC), and in turn build the capacities of the its member political parties to play an effective role in building an open and competitive political space and building mechanisms for information sharing and resolving conflicts between political parties and NEC on the one hand and amongst political parties, on the other.

The project is designed within the framework of a “One UN”, drawing on the expertise and mandates of various UN actors, including UNMIL, to deliver assistance throughout the electoral cycle. This document also summarizes activities carried out by other key partners such as the IFES project funded by USAID and with which a close coordination will be established within the framework of a Technical Working Group to harmonize activities.

At the corporate level, UNDP has continued to make significant contributions towards strengthening electoral systems and processes and its framework for electoral assistance is well-conceived, enabling an effective response across countries. The UNDP Strategic Plan (2013-2017) identifies this as an area in which to stay engaged, seeking to introduce further improvements to ensure consistent application of UN values in electoral programming and implementation, developing sustainable solutions better tailored to country settings, managing partnerships differently given the nature of assistance in this area, and adapting UNDP’s operational procedures and performance to meet the fast-paced needs of electoral support.  These principles and values will be applied in designing and rolling out of this electoral assistance programme in Liberia.

# SIGNATURE PAGE

Outcome(s)/Indicator(s) 3:	Democratic, accountable and transparent governance is advanced in a participatory and inclusive manner and in accordance with human rights standards.

Expected Outcome(s):	Strengthened capacity of the NEC; enhanced electoral stakeholders including IPCC; and constitutional changes adopted relating to elections.

Indicator (s):	2017 Presidential and legislative elections considered free, fair, professionally administered and credible.

Expected Output(s)/Annual Targets:	Implementation of the NEC Strategic Plan and greater NEC professionalism; improved electoral processes within purview of the NEC and in which the NEC plays a key role (voter registration, civic and voter education, women’s participation, capacity development for political party and political party coordination, conflict prevention, gender mainstreaming, strengthening of NEC/Political party and inter-party consultative process, security training, election-specific support).

Execution Modality:				NIM

Implementing Agencies:	The Government of Liberia, the NEC, UNDP, UNMIL, UNPOL, IFES, Political Parties, CSOs including women’s groups, Media, other key partners

| Approved on behalf of | Signature | Date | Name/Title |
| --- | --- | --- | --- |
| Ministry of Finance and Development Planning | ------------------------------- | ---------------- | Minister for Development and Finance |
| National Elections Commission | ------------------------------- | ---------------- | Chairman – NEC |
| UNDP | ------------------------------- | --------------- | Resident Representative |

Table of Contents

PROJECT BRIEF	1

SIGNATURE PAGE	2

PART I: INTRODUCTION AND SITUATIONAL ANALYSIS	4

1.1 Introduction	4

2.1 Situation Analyses and Country Profile	4

3.1 Background	6

3. SECTOR CONTEXT	7

3.1 Electoral Systems	7

3.2. Election Administration	8

3.3. Assessing the Electoral Landscape and Electoral Stakeholders	8

3.4. The role of the United Nations and partner organizations	9

4. PROJECT STRATEGY AND JUSTIFICATION	10

4.1. Scope	10

4.2. Justification	10

5. PROJECT OBJECTIVES AND RESULTS	11

6. RISK MANAGEMENT MEASURES	23

7. MANAGEMENT ARRANGEMENTS	24

Project Organizational Structure	26

Project Reporting Schedule	26

8. PERFORMANCE MONITORING	27

9. PROCUREMENT	28

10. FINANCIAL ARRANGEMENTS	28

Indirect management with an international organization	28

11. COMMUNICATION AND VISIBILITY	29

12. EXIT STRATEGY	29

13. LEGAL CONTEXT	29

# PART I: INTRODUCTION AND SITUATIONAL ANALYSIS

## 1.1 Introduction

UNDP Liberia is committed to long term, sustainable support to democratic development in Liberia through the full 4 year election cycle, including support to key democratic institutions and processes. These include the election management body NEC in their responsibilities to plan for, organize and carry out general elections every five years. UNDP partnerships with NEC and other national partners are well established based on previous support provided through the five year periods: 2010-2014. This election cycle support approach is in recognition that free and fair elections are but only one element of democratic development and democratic practice. Along with the NEC, support has been requested and can be usefully provided to other key actor’s including the Inter Party Consultative Committee (IPCC), the Constitution Review Committee, Liberia National Police, the Media, and Civil Society Organizations (CSOs). Unlike its predecessor, the new project will support adoption of conflict prevention mechanisms and Civil Society in terms of their interface with the electoral process, such as strengthening political party efforts to promote inclusive participation for women, youth and people with disabilities and civil society to undertake voter education and conflict management programs.

The United Nations Basket funding to the NEC, supported by the EU, SIDA and other donors, has been in place since June 2010 and was instrumental for the credible conduct of the 2011 electoral events. The 2011 election review process with inputs of the lessons learned conference, the institutional assessment provided by UNDP and IFES, a review of the electoral laws, the observer reports (EEM and TCC) and consultations with stakeholders and the international community clearly sees a need to further work with the NEC to enhance the staff ability to implement NEC’s mandate.

The European Union Election Expert Missions report on the 2011 election, the NEC lessons learnt, NEC Needs Assessment, and the NEC Strategic Plan 2012-2017 concluded that elections have been, in the overall, satisfactory, when measured against international standards but alluded also to a number of institutional, legislative and legal shortcomings. The recommendations offered included the importance of the continued implementation of the NEC capacity building programs covering the institutional, management and coordination mechanism setup for both the headquarters and magistrate offices and strengthening of complaints and appeals system. Needs assessment reports also identified inadequate voter education, logistical challenges, lack of consultation with key collaborating national institutions and insufficient communication with key stakeholders including political parties and CSOs.

## 2.1 Situation Analyses and Country Profile

The Republic of Liberia, is located in West Africa bordered by Sierra Leone to its west, Guinea to its north and Ivory Coast to its east. It covers an area of 111,369 square kilometers (43,000 sq mi) and is home to about 4 million people. English is the official language and over thirty indigenous languages are also spoken within the country. Its coastline is composed mostly of mangroves, while its more sparsely populated inland consists of forests opening onto a plateau of drier grasslands. The climate is hot and equatorial, with significant rainfall during the May–October rainy season and harsh harmattan winds the remainder of the year. The country possesses about forty percent of the remaining Upper Guinean rainforest.

Liberia is the only country in Africa founded by United States colonization while occupied by native Africans. Beginning in 1820, the region was colonized by African Americans, most of whom were freed slaves. The colonizers (who later became known as Americo-Liberians) established a new country with the help of the American Colonization Society, a private organization whose leaders thought former slaves would have greater opportunity in Africa.

In 1847, this new country became the Republic of Liberia, establishing a government modeled on that of the United States and naming its capital city Monrovia after James Monroe, the fifth president of the United States and a prominent supporter of the colonization. The colonists and their descendants, known as Americo-Liberians, led the political, social, cultural and economic sectors of the country and ruled the nation for over 130 years as a dominant minority.

The country began to modernize in the 1940s following investment by the United States during World War II and economic liberalization under President William Tubman. Liberia was a founding member of the United Nations and the Organization of African Unity. In 1980 a military coup overthrew the Americo-Liberian leadership, marking the beginning of political and economic instability and two successive civil wars. These resulted in the deaths of between 250,000 and 520,000 people and devastated the country's economy. A peace agreement in 2003 led to democratic elections in 2005. Today, Liberia is recovering from the lingering effects of the civil wars and their consequent economic upheaval, but about 85% of the population continue to live below the international poverty line, and the country's economic and political stability has recently been threatened by a deadly Ebola virus epidemic, one of the worst such outbreaks in history resulting in a global emergency response of an unprecedented scale.With a regional total of 9,060, Liberia had become the epi-center of the outbreak despite the first case being reported in neighboring Guinea. The EVD has had significant impact on the electoral process in Liberia, forcing the postponement of election form the constitutionally set date of second Tuesday in October. The current legal and constitutional framework on Liberia does not provide apparent alternatives and is forcing a re-think of constitutionally set elections dates without clear force majeure clauses in instances of natural disasters such as the EVD crisis.

Although Liberia has enjoyed relative peace and stability since the end of the war in 2003, it remains one of the poorest countries in the world with one of the lowest levels of human development (ranking 174 out of 186 countries), weak state capacity, and a high level of dependence on international donors. The foreseen drawdown of the UN Mission to Liberia (UNMIL) represents an important milestone in the transition to peace, as it will expose the resilience of Liberian society to maintain peace after ten years of post-war reconstruction. It will be an enormous challenge for the government to gradually take over the functions of UNMIL in such a way as to avoid major security gaps that could upset the fragile situation, and provide services across the territory.

With high levels of poverty and income inequality, there is a wide perception among many Liberians that only few are benefitting from the economic growth. Concession agreements that are bringing in needed foreign investment have often been granted without following the law or consulting communities, whose livelihood depends on the same land, exacerbating the perception of injustice and increasing tensions. Land ownership, right to land and use of land remains a tense issue. Underemployment is a critical issue with 78% of the labor force holding only “vulnerable employment”, including a large, urbanized youth population. The effects of EVD have added a new dimension to this problem that the country will have to grapple with.

Governance, justice and public institutions remain weak. There has nevertheless been progress in the reform of the civil service and public financial management reform, although much still needs to be achieved in the fight against corruption and to improve transparency and accountability. There is nevertheless a strong political will and commitment to enhance governance reform and maintain peace in Liberia. Liberia has shown regular progress since 2006 in governance indicators. Liberia’s ratings are above the African average for voice and accountability and political stability, but much remains to be done to improve the rule of law. Transparency International‘s 2012 (2011) Corruption Perception Index ranks Liberia 75 (91) out of the 176 (183) countries and territories assessed. In 2005, the country was ranked 137 out of the 158 surveyed.

## 3.1 Background

The National Elections Commission (NEC) conducted the 2005 and 2011 Presidential and Legislative elections under the Electoral Reform Law (2004) with the support of the European Union, EU member States (notably Sweden, Spain and Denmark), the United Nations Development Program (UNDP) and United Nations Mission in Liberia (UNMIL) and other members of the international community. Liberia’s 2011 presidential and legislative elections were an important milestone in the political evolution of post conflict Liberia and were widely recognized as an opportunity to consolidate peace and speed up Liberia’s political and economic recovery. In 2017 Liberia will be conducting its third general elections since the signing of the 2003 Accra Comprehensive Peace Agreement (CPA) that ended fourteen years of conflict. These elections mark an important milestone in Liberia's political landscape.

Right after the 2011 elections NEC developed the six-year (2012-2017)strategic plan which presented the NEC’s strategic objectives for the period and established a rational agenda and commitments to make the Commission more responsive, effective and efficient electoral institution. NEC has identified five key strategic areas, as follows: (i) improving the electoral legal framework by reviewing electoral laws and guidelines, reviewing voter registration requirements and reviewing the complaint management mechanism; (ii) strengthening the political party system and enhancing public confidence in elections and strengthening the capacity of political parties; (iii) improving public participation in elections through the development and implementation of a civic and voter education strategy; (iv) strengthening the institutional capacity of the NEC; and, (v) delivering free, fair and credible elections through voter registration and updating and reviewing boundaries where needed.

As a follow up to the implementation of the NEC strategic plan, the NEC, with support from UNDP, initiated an electoral legal reform process in early 2013 which has provided the platform for an on-going dialogue involving its key stakeholders to discuss the merits and demerits of a comprehensive electoral reform in Liberia. As a result of this process, an electoral reform bill was approved by the Legislature. The major amendments to the law provide the NEC with greater autonomy in appointing its staff, improves the process for party registration and complaints mechanisms, as well as sets the level for political party registration fees, also promotes greater gender balance by setting a 30% minimum gender representation of candidates.

A Constitutional review process is underway in Liberia, led by the Constitutional Review Committee. Due tothe Ebola Virus Disease (EVD) epidemic, however, the process has been suspended temporary due to limitations imposed as a result of a state of emergency. Despite, the Constitutional Review Committee (CRC) operates with timeline aimed at delivering a new/revised constitution before the 2017 general elections with a referendum to be conducted possibly in 2016. Since this process is extremely important from the electoral standpoint, the NEC should coordinate with the CRC constitutional reform as it relates to elections, harmonization of electoral law reform and constitutional review process and the Legislature to ensure that discussions on the conduct of constitutional referendum are adequately executed and in a timely manner.

Following a request from the National Electoral Commission (NEC), the Under­ Secretary-General for Political Affairs/the UN Focal Point for Electoral Assistance Division (EAD) deployed a Needs Assessment Mission (NAM) to Liberia from 2 to 13 May 2014. The NAM was tasked with evaluating the political and electoral environment and the capacity and needs of various election stakeholders with a view of ascertaining the parameters for future UN electoral assistance towards the 2017 elections. The NAM followed a DPKO-Ied Strategic Review Mission to Liberia in February 2014 and took note of its conclusions. The needs assessment team held consultations with various stakeholders including the relevant national authorities such as the electoral administration, the legislature, political parties, civil society and media groups, as well as the UN Country Team, UNMIL, international partners, donors and heads of missions and bilateral cooperation. During the formulation stage of the Identification Action document was used the findings and recommendations of the NAM mission which defined the basic areas of the electoral support in Liberia, mainly focusing on improving electoral institutions, electoral processes and communications. The NAM report which forms the basis for UNDP’s Electoral support in Liberia included the following guiding recommendations:

- Capacity development and support to NEC institutional management reforms;

- NEC institutional strengthening including staff professional development based on management and BRIDGE training methodology;

- Civic and voter education, and related communication activities, including support to capacity building of civil society organizations;

- Support enhancement of women’s political participation and leadership;

- Strengthen the electoral legal framework and the constitutional review process as it relates to elections;

- Support to fostering inclusive participation in elections: targeting women, youth and people with disabilities and rural voters.

- Operational and technical support to NEC covering various phases of the electoral process:  voter registration and the general elections;

- Conflict prevention/community dialogues and support to creating a peaceful environment for the elections, including NEC/stakeholder outreach and partnership building, and revitalization of the Inter party Consultative Committee (IPCC);

- Support to the establishment of a regular election security coordination mechanism.

This project proposal, titled: “Support to the Electoral Cycle in Liberia,” has been developed in response to the request for United Nations assistance from the Government of Liberia which will be implemented through the NEC with support from key national and international partners. The project uses the electoral cycle approach, which looks at the electoral process over time and seeks to engage with different actors. The activities of the project are in line with the recommendations of the domestic, regional and international 2011 election observation missions (such as the ones of the African Union, ECOWAS, European Union, Carter Centre) and the lessons learned of the 2011 elections held by the NEC in 2012. With this approach in mind, the project looks beyond the 2011 elections and will cover the period of 2014 through 2018. Substantively, the focus is on improving electoral institutions, processes and laws, mainstreaming of gender through specific support to women’s political participation and enhancing conflict prevention.

# 3. SECTOR CONTEXT

## 3.1 Electoral Systems

Elections in Liberia occur solely at the national level. The head of state, the President of Liberia, is elected to a six-year term in a two-round system, in which a run-off between the two candidates with the highest number of votes is held should no single candidateganner a majority of the vote in the first round. The Legislature has two elected chambers. The House of Representatives has 73 members, elected to six-year terms by the first-past-the-post electoral system in single-member districts. The Senate has 30 members, 2 from each county, elected at-large to nine-year terms by the first-past-the-post method.

All citizens who are 18 years or older may register to vote in elections. Under Article 83(a) of the Constitution, elections are held on the second Tuesday of October every election year, with presidential run-off elections being held on the second Tuesday following the announcement of the results of the first round. Elections are managed by the National Elections Commission of Liberia (NEC).

## 3.2. Election Administration

Established under the article 89 of the Constitution, the NEC is an autonomous body that organizes and supervises the national elections of Liberia. The primary duties of NEC include administering and enforcing all laws related to the conduct of elections throughout the Republic of Liberia. Besides, NEC proposes to the National Legislature for enactment, suspension of, and amendment to, and repeal of, any provision of the Elections Law. The Commission further provides accreditation to, and registers all political parties and independent candidates who meet the minimum requirements set by the Commission. NEC also revokes the registration and accreditation of an already legal party only upon the judicial determination by a court of competent jurisdiction, in accordance with due process. Also included in NEC’s functions include conducting all elections for elected public offices, including chieftaincy and all referenda and declaration of the results thereof.

The Commission also formulates and enforces guidelines and regulations controlling the conduct of all elections to elective public offices, which guidelines shall not be inconsistent with the provisions of the Constitution and Elections Law of Liberia. NEC maintains a register of all qualified voters which shall be subject to inspection.

## 3.3. Assessing the Electoral Landscape and Electoral Stakeholders

The NEC has improved significantly over the last years of which the positive observer reports of the last elections give witness. However, the 2011 elections also showed that NEC was still affected by operational and institutional weaknesses which must be overcome to create more independent, professional and transparent election management body. The NEC, as a relatively young institution, is faced with a number of challenges documented in a series of reports (UNDP and IFES 2012 needs assessment reports). These include lack of capacity of the electoral administration both at headquarter level and magisterial/field level, insufficient collaboration with key electoral stakeholders such as CSOs and political parties as well as lack of the internal administrative policies and procedures. Election-specific deficiencies including the NEC's procurement, human resources and finance sectors still requires substantive attention in the form of capacity enhancement and technical support. Full focus should be given to improvement of the NEC complaint adjudication mechanisms and enhancement of communication strategy with external stakeholders such as political parties and CSOs. Beyond election-specific needs, however, the NEC would benefit from longer-term professionalization as an institution to ensure that it builds the sustainable all-level internal capacity over time to administer elections in Liberia.

Political parties are in need of sustained capacity development which is tailored to the dynamics of the electoral system in Liberia. There is also need to promote dialogue and consensus building between NEC and political parties on critical issues such as legal or administrative reform and mandate and workings of the NEC.

Another key stakeholder group in the electoral process is the civil society, including women and youth. Civil society is relatively vibrant in Liberia, comprising of an extensive range of pro-democracy and human rights organizations, trade unions, women's groups, religious organizations, youth and student groups, diaspora and refugees groups. In 2011, the presence of domestic observer groups, perceived as neutral and impartial, enhanced citizens’ confidence in the process. However, the lack of resources and poor logistics restrict the work of many of organizations, most of which are based in Monrovia.

The 2011 saw a drop in female representation in the legislature from 22% to 13% due to the non-return of several female legislators. The 2005 election was conducted under a voluntary framework which saw the party of list of major political parties with 30% female representation. This framework was no longer applicable in 2011 elections and may have contributed to decline in elected female in the legislature. However the involvement of civil society in the 2011 elections was robust. UNDP developed a training manual for female candidates and over 400 women were trained. The UNDP Basket Fund also supported the organization of Women’s Situation Room, which observed and monitors the Election Day proceeding with a specialized focus on women participation. This has become an African Union model and good practice for female participation.

The Media has a key role in the electoral process. Radio is the main source of information in Liberia. The coverage of newspapers and local TV stations is limited and with the exception of community radio stations, local media barely exists outside Monrovia. The civil war left most of the media with capacity and resource constraints. Several components of the project will include media elements, such as civic education and enhancing women's participation.

The Liberia National Police (LNP) is in the process of taking over functions and national coverage from UNMIL security personnel due to UNMIL’s drawdown process. Recruitment and training is on-going but has experienced delays and challenges in planning for UNMIL drawdown. On the quota for female police officer, LNP is on track, but the police force is facing lack of trust from the population namely because of perceived corruption. LNP is operating under the Ministry of Justice. While other projects cover the security-related elements, it was confirmed the need for more specialized training for police on roles and responsibilities during the electoral cycle.

The Government of Liberia (GoL) plays a key role in the process, essentially by committing resources from the state budget for NEC's running costs and election preparations. Government of Liberia has indicated to provide the funds to NEC's recurrent budget during financial years 2015-2017 reflecting its commitment to the elections. If the delays continue in carrying out the electoral reforms necessary for the conduct of the 2017 elections, this risks raising concerns over the commitment among some of the national authorities to the elections.

## 3.4. The role of the United Nations and partner organizations

The UN and more specifically the UNDP has long supported Liberia’s democratization process and towards this end it has identified specific goals to improve the democratic environment in the country. These include efforts to strengthen key democratic institutions to have improved capacity to fulfill their electoral functions. Various governments, both programme countries and donors, have entrusted UNDP with the task of facilitating donor coordination and donor support to elections. UNDP has a proven track record in delivering electoral assistance primarily because it has been regarded as a trusted and non-partisan partner. UNDP has been able to implement electoral programmes in the most politically divisive countries, because it is viewed as an impartial organization. UNDP’s status as an unbiased development partner will allow for closer management relationships with donors, government, political actors and civil society partners. As indicated at the corporate level, UNDP has continued to make significant contributions towards strengthening electoral systems and processes and its framework for electoral assistance is well-conceived, enabling an effective response across countries, viewing this as a key pillar in strengthening democratic governance

UNDP is well positioned and prepared to take the lead in managing and coordinating a new project funds drawing on lessons learned from previous projects, global and national experience and well established partnerships with the election management bodies and others. As was the case with the previous 2010-2012 election project, UNDP is also well placed to establish the necessary arrangements and provide expert personnel for the project’s implementation, taking into account the value of early recruitment and project start up as learnt from past experience and recommendations from past election evaluations.

The project has apparent links with other programmes which support the deepening of democratic processes such as constitutional review process, decenteralization and support to the justice and security sectors. UNDP implements programmes and projects in these critical sectors and is hence uniquely placed to exploit synergies and ensure a coordinated approach to programme implementation across these programmes, along with the partnerships that come with this.

As UNMIL draws down, it is unclear at this stage whether it will be present in the country at the time of the 2017Presidential elections, the size of the mission or their support to the electoral process. In addition, a special relationship will be developed between the project and other possible international (e.g. UN) and regional actors with a mandate or expertise in electoral assistance (e.g. ECOWAS, African Union). International donors and other partners such as Sweden, NDI, IDEA, may also collaborate on substantive activities. It should be taken into consideration that the Government may request for an EU EOM for the 2017 Presidential and National assembly elections.

USAID awarded a five-year (60 month) $18,000,000 cooperative agreement as an associate award through the CEPPS III mechanism to the potential election partner organizations such as IFES and NDI (and possibly IRI). In particular, USAID funds give full support to CSO for oversight of electoral processes.  Also envisaged in USAID support is specific support to NEC functions as regards human resources, procurement, and asset management and budgeting. The project also envisages working directly with strengthening political parties' capacities.

The proposed intervention falls within the EU's draft 11th EDF NIP for Liberia's focal sector on good governance. Complementary measures will include budget support (state building contract) which will support complementary areas such as rule of law and justice, decentralization and the capacity of the state to provide security provision to its citizens in the face of UNMIL drawdown. The 11th EDF draft NIP also foresees continued support to strengthening the General Audit Commission (GAC) and other Liberian Institutions and Non State Actors that could complement certain aspects of the project.

# 4. PROJECT STRATEGY AND JUSTIFICATION

## 4.1. Scope

The project’s overall objective is to enhance the democratization process in Liberia through improved electoral institutions and processes. The project purpose is to strengthen the capacity of NEC and core electoral stakeholders to conduct their core activities in an impartial, transparent and sustainable manner and successfully carry out scheduled electoral processes within the electoral cycle 2015-2018. Towards this end, the following democratic institutions have been identified for support: a) NEC fostering sustainable electoral processes through technical and operational support and capacity building, b) IPCC, c) civic society and media for effective engagement with democratic processes through dialogue and peace building initiatives. The project will also support the Police to effectively contribute to election-related conflict mitigation and dispute resolution. A gender equality perspective will be mainstreamed through all areas. The total estimated costs for the project in Liberia amount is EUR 10 769 000, where the EDF will contribute EUR 10 000 000 and UNDP cost for the project amount is USD 1 000 000 (approx. EUR 769 000). This amount excludes the NEC recurrent budget (GoL contribution), IFES and UNMIL support.

## 4.2. Justification

Liberia has shown commitment to democratic reform through a number of initiatives including recent reformation of the electoral legislation and the current ongoing constitutional reform process. Previous UNDP election project as indicated by the partners and stakeholders attested to the success of past electoral support and indicated the need for continuity in order to consolidate Liberia’s democratic achievements over the last few years as well as to keep the electoral coordination mechanisms alive for partners and donors.

Unlike in 2005-2011 when the United Nations provided significant institutional and logistical support to the elections, the NEC will be the lead institution for the next electoral cycle to organize and deliver the national elections as well as the possible referendum in 2016. It is unlikely that partners will be as forthcoming with expert and funding assistance for future elections. It is therefore essential to expose the staff of NEC at all levels to continuous election management skills and institutional changes as early as possible.

The NEC needs institutional changes and capacity support in order to enhance their independence and credibility as a way of inspiring public and stakeholder confidence in their ability to deliver credible and peaceful elections including the possible referenda which may be held in 2016. Successful and transparent elections are critical for ensuring conflict mitigation and peace building especially in a country like Liberia with a long 14 years history of conflict and violence. Continued electoral support will assist in building the capacity and reputation of the NEC and other democratic institutions thereby reducing incidents of election-related violence.

The current project is furthermore informed by the principles that are central to the UN electoral assistance, including i.e. the goal of decreasing donor (external) support as national (internal) capacity increases. Therefore in order to work towards an exit strategy, the project budget will be EUR 10 769 000 compared to its predecessor which was USD 27 million – need in EURO? The project activities are more focused on capacity development of NEC and national stakeholders and less on direct support of election operations.

# 5. PROJECT OBJECTIVES AND RESULTS

The election project’s overall objective is to enhance the democratization process in Liberia through improved electoral institutions and processes. The program purpose is to strengthen the capacity of NEC and core electoral stakeholders to conduct their core activities in an impartial, transparent and sustainable manner and successfully carry out scheduled electoral processes within the electoral cycle 2015-2018. The project will have the following 8 Results and Main Activities as per Action Fiche which based on the recommendations of recent reports and studies including the NAM, project evaluations and observer missions:

Result 1: Strengthened capacity at NEC for efficient implementation of its mandate;

Result 2: Voter registration is updated and voter registration process is improved;

Result 3: Women’s political participation and leadership is enhanced;

Result 4: Political parties' capacity is enhanced, political parties are coordinated and conflict prevention measures are in place;

Result 5: Elections security forces act is in line with international standards;

Result 6: Civic and voter education strengthened;

Result 7: Strengthen the electoral legal framework and the constitutional review process as it relates to elections and harmonization of the election law and regulations;

Result 8: Successful conduct of national elections through logistics and operational support provided to NEC and core electoral stakeholders.

Result 1: Strengthened capacity at NEC for efficient implementation of its mandate

The NEC has improved significantly over the last years, however, the 2011 elections showed that NEC still is affected by operational and institutional weaknesses which must be overcome to create more independent, professional and transparent election management body. The NEC as a relatively young institution, is facing a number of challenges documented in a series of reports (UNDP and IFES 2012 needs assessment reports). Those include lack of capacity of the electoral administration both at headquarter level and magisterial/field level, insufficient collaboration with key electoral stakeholders such as CSOs and political parties as well as lack of the internal administrative policies and procedures. Election-specific deficiencies including the NEC's procurement, human resources and finance sectors still requires substantive attention in the form of capacity enhancement and technical support. The extent to which Liberia is able to generate and sustain confidence in the democratic and in the electoral process in particular greatly depends on the ability of key stakeholders such as the CSOs, media, IPCC to fulfill their function for better democratic consolidation in the country.

A critical consideration for the NEC will be retention of the knowledge and experience that has been acquired in conducting the elections in 2011. The prime method envisaged is to retain staff who has acquired the necessary skills and knowledge both at the headquarters and field level. In addition, the expertise of the NEC commissioners and staff need to be enhanced and in-house training capacity needs to be developed to provide further training to newly recruited staff. NEC will need to re-visit reformation of the organizational structure, policies and practices, with due attention to gender, staff recruitment, staffing and management and budgeting.

Indicative activities:

(1) Operational trainings and peer-to-peer missions with focus on election administration, media, CSOs, women group, youth, political parties and members of the legislature.

Support study missions and staff exchanges to promote experience sharing and skills transfer between the two EMBs and beyond. Peer-to-peer mission will be organized to gain exposure on the particular subject and develop the best suited road map to establish accurate electoral skills in that particular subject which will allow for updating or improving the structure of NEC prior to the conduct of elections. Missions will be organized on particular areas of election operations, such as logistics, procurement, and civic education, external relations where participants will be involved in study process and gain knowledge on how these particular tasks are dealt with in other election management bodies.

There is a need for the NEC to undertake comprehensive and sustained efforts to professionalize their staff especially during non-election periods. Therefore special operational trainings will be organized for the NEC focusing on the procedures drafting techniques, for example developing polling and counting manual, trainer’s guides, budgets and procurement specifications. Participants will be given practical assignments to develop procedures for different processes of the electoral cycle.

(2) Long term capacity development programs

Develop NEC capacity to conduct the training of trainer’s course using BRIDGE program and expand a pool of fully accredited trainers in Liberia. For more benefits and interaction with different stakeholders BRIDGE training courses will be organized not only for NEC staff but for representatives of youth and gender groups, CSOs, IPCC and the Legislature who jointly with NEC participate each training courses starting with the ToT program. The BRIDGE Version II will be utilized for NEC and other stakeholder’s capacity development process. It is anticipated to conduct 6 trainings courses per year excluding the election year 2017.

The need of the management courses for NEC staff is paramount. Having management skills developed is a critical part of the entire election operation. It is recommended to strengthen the staff skills of NEC at HQ and Magisterial level through organization of following courses: report writing, office management, planning etc. In order to ensure that the staff is trained to take on responsibilities in specialized NEC functions, agreements will be signed by UNDP with specialized electoral training institutions in Liberia or overseas to conduct management trainings. Additional needs assessments will be conducted as required by independent expert or specialized agency. Qualified training experts will be hired to conduct these courses. These consultants/experts could be recruited as individuals in some cases, but it is generally recommended to subcontract implementing agencies to take care of their identification and all other necessary arrangements.

(3) Support to the NEC Election Resource Centre (ERC)

Document and knowledge management, which has gained credibility as the trusted way of handling records and documents within organizations worldwide, has suffered a growing challenge in many developing countries like Liberia due to the absence of effective systems for managing records/data by both government and private sector institutions. In 2012 UNDP elections project as part of its institutional capacity building agenda developed a resource centre to preserve institutional memory of the NEC. A records management system was developed with an automated database system for digital and hardcopy archiving, a library and training facility. The overall benefit of the ERC system was that UNDP has made a one-off investment which added enormous value to NEC for many years.

The new election project will maintain support and seek to make further improvements in the re-profiling of the ERC and will make it more frequently useable for students; first time voters as well as stakeholders and facilitate the process of transformation of the current ERC into the venue for research and awareness building. The project will recruit short term consultant to work closely with the NEC and ERC staff on improvement of the Archive and Library systems.

(4) Support to the magisterial offices and warehouses

It is a known fact that implementing a satisfactory Warehouse Management System is daunting. With this in mind, most Logisticians tend to hold on to outdated methods to avoid the possible effect of implementing a new system or a new way of doing things. Currently NEC possesses 19 magisterial warehouses which required re-organization to ensure security and protection of the electoral materials. Support to the warehouses outlines the design and implementation plan for the packing, accountability and protection of electoral materials stored at NEC magisterial warehouses throughout the country. It is expected that, the project will ensure physical stock-taking of all electoral materials, reduce risk and make the operation of the warehouses simpler and user friendly as well as provide readily, stock report on daily and on need basis.

The Project will provide support for improvement of the magisterial office infrastructure and will supply solar panels to 19 magisterial offices which will reduce the operational cost, provide 24 hours electricity and strengthen security of electoral materials.

(5) Development of integrated administrative system in NEC

Following an assessment of the capacity needs of the NEC in 2012 a process that provided ground for the development and eventual approval of the NEC Administration Manual in 2013. The UNDP election project continues further support of the NEC Institutional changes through installation of the integrated administrative systems. The proposed system is to be integrated to automate processes in procurement, HR and finance. Automation has already been undertaken for NEC assets and warehousing management hence the proposed system will be linked with these two areas. The system will involve e-requisitions, system based authorizations that will link to procurement for processing, finance for payments and to assets/warehouses for records.  HR systems will link recruitment to the payroll, performed by finance. Thus, the sub-systems will be integrated.

To successfully put the integrated system in place, the following general processes will be supported:

- Identification of various processes within procurement, HR and Finance that need to be automated;

- Link with assets management and warehousing procedures. This will also define information needs of each area and how that feeds to another;

- Identifying roles to be played by staff in each area (i.e. HR, procurement, etc),

- Develop clear and detailed specifications that meet the needs identified for a truly integrated system to work;

- Identify a systems developer through a competitive process to provide the services required;

- Monitor installation and implementation over time. Implementation will include training key staff prior to installation, during installation and provide post installation support.

- Test the system and begin its use, continue monitoring and provide necessary support

- Evaluate the entire process and make modifications based on lessons learned.

In addition, USAID Liberia provides funds to support the institutional changes in the NEC related. This work will be jointly coordinated to achieve maximum effect and avoid duplication.

(6) Inclusive post-elections lessons learned & review exercises following conclusion of the 2014 and 2017 electoral processes

For the better planning of future elections is required that NEC reviews and apply lessons learned from the past throughout a program’s life cycle and to document any significant lessons to the Board of commissioners and all stakeholders. A lesson must be significant in that it has a real or assumed impact on future operations and applicable in that it identifies a specific design, process, or decision that reduces or eliminates the potential for failures or reinforces a positive result. The NEC recognizes the importance of learning from the past to ensure future mission success and will use the best practices in consultation with all stakeholders involved in elections to capture and disseminate lessons learned. The project jointly with IFES will support lessons learned activities right after 2017 elections with involvement of all international and national stakeholders to the process.

After conduct of 2014 general elections there will be an urgent need to work with the NEC to conduct capacity building and enhance the NEC staff knowledge and ability to manage upcoming elections. Therefore capacity building work needs to be carefully structured based on the institutional and management assessment of the NEC. The project will recruit agency or independent expert specialized in needs assessment type of work to define areas and programs required for building the capacity of the NEC staff.

Result 2: Voter registration is updated and voter registration process is improved

The amendment of the proposed electoral law revising the population threshold for constituencies and the delimitation of those constituencies, are required for the 2017 voter registration process. At the same time, there are preparatory steps that the NEC can take with respect to voter registration to facilitate the process such as procurement of voter registration materials, training of voter registration staff and logistics. Should the NEC decide to proceed with adopting a biometric voter registration system in Liberia, proper studies will need to be carried out taking into account sustainability of the process and ensuring that the infrastructural issues (electricity and capacity of the magisterial offices), as well as the outstanding issue of  administrative  and  constituency delimitation,  are resolved.

Indicative activities:

(1) Provide technical support and guidance for a comprehensive feasibility study on the voter registration system;

A careful study of voter registration and the use of appropriate technology would be needed in order for the NEC and other stakeholders to make an informed decision on how and to what degree the voter registration system should be modified. This should include a consideration of the cost, sustainability and environmental factors required to implement voter registration in Liberia, as well as an assessment of the real and perceived weaknesses of the current method. The project will envisage helping the NEC review the registration process overall, with a view to ensuring that the voter register is nationally owned, comprehensive, up to date, accurate, cost-effective and sustainable. The project will support consultancy to provide guidance and feasibility study on the voter registration systems.

(2) Based on comprehensive feasibility studies, support the conduct of voter registration operations before the 2017 elections

Activities in this area will provide support specifically aimed at the 2016 Voter registration process (including logistics). Support will include operational planning, procurement of essential VR materials, delivery and retrieval of materials, training of VR staff, including possible UNMIL logistical and communications support, under the overall coordination of UNDP.

Result 3: Women’s political participation and leadership is enhanced

Lack of civic and voter education programs for women, absence of enthusiastic and energetic women’s groups, the absence of the properly functioning national institutions and weak political parties are potential challenges that prevent women from electoral participation. The elections saw a decline in the overall representation of women, from 9 representatives out of a total of 64 in the 52nd Legislature, to 8 representatives out of a total of 73 in the 53rd Legislature. A total of 15 out of 30 seats were contested in the Senate in 2011, resulting in a reduction in the number of female senators from 5 to 4. Furthermore, preliminary data from the 2014 update of the voter registration for the Senatorial elections indicated that only 37% of registered voters were women compared with the 2011 voter registration process where registered women were 49%. This correlates with the 2008 Population Census which gives the female population 49%.

Women remain underrepresented in political life in Liberia, including within the Legislature, leadership in political parties, senior ranks of the public service and electoral administration. The gender sensitization needs are arguably the greatest among rural populations. The promotion of women within political parties, which serve as a training ground for future leaders, is an area needing more attention and support. Initiatives to date have also tended to focus on women’s role in elections per se (as candidates and voters) rather than adopting a holistic approach that looks at the social, economic and political barriers to greater involvement by women in political life in Liberia.

The NEC has put in place a policy to more effectively mainstream gender in the electoral process. The NEC gender section, established recently, oversees the implementation of the gender mandate. However, limited financial and human capacity precludes from the implementation of the gender mainstreaming task and in promoting women participation in elections. Strong advocacy and unanimity are required amongst civil society groups and political parties and NEC can coordinate this work for further promotion of women participation in elections. In the gender mainstreaming efforts political parties should be encouraged to introduce affirmative measures in their polices and party structures to ensure that party lists and governing bodies have at least 30% from each gender, as specified in the recently reformed electoral law.

IFES will provide substantial support to the NEC gender section in implementation of gender mainstreaming activities. Therefore the election project jointly with IFES will coordinate support to the gender section.

Indicative activities:

(1) Advocacy and training on gender issues targeting political parties, women, youth, CSOs and Media

It is within this context that the NEC, recognizing its roles and responsibilities and being fully cognizant that governance cannot be effective if it does not advance gender equality and the realization of women’s rights in the electoral processes; decided to mainstream gender and increase women political participation and leadership through its Gender Section. Inadequate efforts were made by NEC to work with political parties to engender their manifestos and to reform their internal processes to include women. Limited efforts were made in working with women groups and CSOs to promote women’s political participation and leadership in all of the electoral processes.  The election project will support NEC gender unit in organization of:

- Trainings and workshops with participation of gender groups, CSOs and political parties on gender issues what will lead gender unit to development of guidelines for mainstreaming gender in political parties using the 30% quota and advocate with parties to commit to applying them during the electoral processes;

- Regional sensitization program targeting women groups, CSOs, youth and the media for cross-cutting perspectives on the social, cultural, political and legal challenges preventing equal participation in the electoral processes;

- Regional symposiums with political parties high level leadership on gender and political leadership using the factsheet and analyzed manifestos.

(2) Support NEC for institutional and internal reform targeting gender balanced initiatives;

Despite efforts to integrate gender perspectives into the electoral management body and to increase women’s political participation in the electoral processes by NEC and its partners, the overall result based on available statistics and feedback from the field shows a lower representation and participation of women in the previous process. This situation led to the gender section, with support from UNDP in 2014 to organize and hold regional consultations on Women’s political participation in the electoral processes. The findings from the seminars in addition to the CVE Baseline Survey indicated reasons for the low participation of women as well as provided practical recommendations for increasing women’s participation in the electoral processes. Some of these includes, inadequate resources (logistical and financial) as it relate to the NEC gender section as well as inadequate capacity to translate its mandate into the desired results. The election project will support the NEC to:

- Re-profile organizational structure of the NEC gender unit and provide equipments and materials for proper functioning;

- Organize three rounds of workshops at magisterial level with participation of gender groups, CSO and political parties which will strengthen NEC gender capacity to respond and address the inequalities that characterize men and women’s participation in the electoral processes. NEC’s organizational policies, systems and practices to contribute to gender equality in elections effectively are transformed;

- Establish a Gender and Elections “external coordination meetings” across the country with involvement of women’s groups, women’s CSOs, MoG, youth which will enhance information sharing and strengthen responses to women’s political participation;

- Establish periodic review forums with NEC staff & partners, CSOs to assess progress and impact of gender initiatives/policies on the internal and external environment.

(3) Conduct capacity building activities addressing the needs of women's groups in complementarily to supplementary support measures to CSOs

The election project will support women’s groups and women’s CSOs to empower and give the necessary capacity to participate in the electoral processes effectively. The project will support NEC gender section to organize series of management training courses conducted for women CSOs on the scope of campaign strategies, public speaking, engaging with media, financing etc. Ministry of Gender and Governance commission are potential partners to the process. Training courses will be facilitated by the international or national experts in the field of gender, governance and rule of law.

Result 4: Political parties' capacity is enhanced, political parties are coordinated and conflict prevention measures are in place

The relationship between political parties and the NEC has been quite contentious. After 2005 participation in several elections and by-elections, political parties remain quite weak in many cases without proper manifests on political vision and governance. Several major opposition parties expressed reservation about the NEC’s impartiality, after appointment of the new board of NEC commissioners in 2013, even though the NEC has been widely commended for handling of the various by-elections and other electoral processes successfully. The frustration and distrust of political parties further deepened following the NEC’s petition in February 2014 before the Civil Law Court for the revocation of the registration of 20 political parties due to noncompliance with requirements of the Constitution of Liberia as well as the guidelines relating to the registration of political parties and independent candidates, including the mandatory submission to the NEC of detailed statements of assets and liabilities. As a result of the petition, the Civil Law Court revoked registrations and accreditation of the 20 political parties.

There is a strong need to promote a dialogue and consensus building on critical issues of legal or administrative reform, to better sensitize parties to the mandate and workings of the NEC and to better sensitize the NEC to the needs and expectations of the political actors. The Inter-Party Consultative Committee (IPCC) is currently the only multi-party platform available to create compromise and find consensus. Considering the contentious and unfortunate political climate of recent decades, the importance of the IPCC is evident not only to the political process but also to the citizens of Liberia who benefit from political dialogue. Political parties have recognized the value of the IPCC, in particular as a conflict resolution and prevention mechanism and suggested to explore options for developing the IPCC into a more independent forum with NEC participation through which political parties can convene, discuss and resolve conflicts.

Indicative activities:

(1) Support the revitalization of the independent IPCC with secretariat including members for women and youth affairs

The IPCC has proven itself to be of value to both the NEC and participating political parties. Parties themselves recognize that establishing dialogue even on contentious issues allows them to engage in heated debate without having to resort to disengagement, political marginalization, or even potential violence. There is also room for parties to take responsibility for their own sustainable development while recognizing that the NEC has an opportunity to demonstrate to parties and to the public at large that the new leadership and membership on the NEC Board is fair, balanced, non-partisan and politically neutral. The election project will:

- Support the establishment of the IPCC secretariat to enable it to evolve into an effective platform for dialogue and consensus building among political parties as well as in their engagement with the NEC;

- Support consultations and trainings as part of regular IPCC monthly meetings to include such topics as: party fundraising, financial reporting, membership development, party strengthening during the intra-election period, consensus-building, conflict resolution, effective outreach to members and the electorate during (and after) the election cycle, horizontal management, change management.

(2) Develop IPCC Policies and Regulations and organizational structure

Work with the NEC and the IPCC to ensure sustainability, cooperation, trust and a mutually-cordial relationship between the NEC and registered political parties and among political parties during (and after) the election cycle. There is also an identified need to ensure appropriate representation by all participating political parties to the IPCC on a regular basis (e.g. party chairperson and/or party secretary general):

- Organize high level conferences to encourage political party leaders to take responsibilities for deepening democracy in Liberia while investing in institutionalizing their political parties;

- As a result of the conference support to development of IPCC Policies, Memorandum of Understanding, Code of Conduct of political parties and regulations. Consultancy to be provided;

- Organize forums where political parties will be committed to the inclusion of the 30% gender quotas in their party lists.

(3) Support to conflict prevention and inter-party dialogue with active involvement of community leaders and youth organizations in rural and urban areas

Liberia has a considerable youth population with more than 60% under the age of 35. High level of unemployment and livelihood opportunities as well as illiteracy make Liberian youth particularly vulnerable to influence. Engagement of the youth into the social life is paramount in order to avoid feeling of politically disempowered and economically abandoned. Factors related to a country's social structure also contribute to possible violence. It was noted that rapidly growing urban areas, which often have large populations living in poor conditions, can contribute to the likelihood of electoral violence in some circumstances. The role of the youth is highlighted in particular with analyses showing that risks of electoral violence increase in countries with a large youth population, especially when young generation are unemployed and not enrolled in secondary school. To address all these challenges the election project will:

- Establish a conflict monitoring and tracking regular forum with effective engagement of the   IPCC, NEC, CSOs, LNP, community leaders, youth and women organizations in conflict prevention;

- Establish the IPCC regular meetings convened to improve collaboration among NEC, political parties with media to enjoy equal access to press (once in a month during non-election period and twice in a month during election period);

- On-site mentoring and relevant advice on consensus-building, negotiation skills, conflict resolution and conflict avoidance. This will also include an external and non-partisan professional moderator to referee IPCC sessions. An individual from a regional country with similar experience to Liberia may be well-received by participants

- Support establishment of political party’s youth wings and engage them in the trainings courses organized by the NEC;

- Organize workshops of youth wings of political parties & youth civil society organizations on electoral conflict prevention mechanisms.

(4) Support direct engagement of political parties in consultation with civil society and the media to solidify the connection between political parties, community leaders, women and youth groups

- Support meetings including the NEC, political parties, the media, and civil society for direct engagement during the pre election and election periods.  This will produce benefit of reducing suspicion and mistrust among these key electoral actors while building cooperation among a broader group of stakeholders in the electoral process;

- Support IPCC effectively engagement through the permanent forums with local CSOs, community leaders, youth and women organizations in conflict monitoring and tracking;

- Support engagement of IPCC with the media to ensure that once parties have established well-developed strategic plans that their public policy, platform, and non-electoral party activities are known to the public at large;

- Engage IPCC in creation and maintenance of IPCC-themed sites and social media links.  Set up an IPCC website or utilize Face Book and Twitter to establish and maintain outreach to “followers” (e.g. party members, media, citizens interested in political party activity and the NEC as well as elections);

- Discussions of the Committee disseminated via radio

Result 5: Elections security forces act is in line with international standards

In a fragile, post-conflict environment as Liberia, the electoral process is a core element of establishing a democratic and stable country. NECs role in this regard is to, on the one hand, support and promote structures and institutions that reduce the tensions in society, and on the other hand, to promote a secure setting for the peaceful conduct of election. In 2012, the United Nations and the Government agreed on a three-year timeline for the next phase of UNMIL’s gradual military drawdown. UNMIL’s drawdown has proceeded peacefully since 2012, and joint planning between the Government and UNMIL remained constructive. But implementation has been inadequate, as national authorities have not allocated adequate resources to the military component. The current number of the LNP is slightly over 4,500 police personnel and may reach 5,000 by the end of the year. However, given the current situation of the state budget, which has been steadily declining over the past three years, it is a challenge for the LNP to be able to assume full responsibility for implementing security in the country before the 2017 elections.

Indicative activities:

(1) Support to the establishment of a regular election security coordination mechanism

Support to the establishment of a regular election security coordination mechanism chaired by the NEC which meets regularly and includes all relevant national security sector institutions and the UN. The NEC will coordinate and ensure the allocation of funds for election security in the budgets of law enforcement agencies.

(2) Technical and financial support to train security forces in election related issues and conflict preventive measures at community level

There is still a need for specialized training of to go through the roles and responsibilities of police forces during the electoral cycle. In-depth training is recommended of security forces for 2017 elections, which will focus on strengthening of the operational capacities and effective service delivery of the Liberia National Police (LNP) and other law enforcement agencies. This activity will be funded through this project but implemented by UNMIL/UNPOL. It will require:

### Development of curriculum for training of Liberian National Policy in election-related security LNP on their responsibilities on Election Day and how to ensure security of the voting process;

### Development of a clear protocols for security forces management on Election Day and during Election period. These materials will be transformed into educational materials such as manuals and pocket guide on “Election Security.”

Result 6: Civic and voter education strengthened

In the context of this project which seeks to ensure that the NEC carries out a continuous and effective Civic and Voter Education (CVE) campaigns and outreach nationwide, a number of key activities have been considered for implementation over the next four years starting in 2015. These activities were largely drawn from recommendations of the Elections Baseline Survey on CVE that was conducted with support from EU through UNDP in 2013/2014.

The implementation of these cogent CVE activities will be done on community and population specific basis so as to ensure inclusiveness thereby enhancing participation. This means activities and messages will be tailored and disseminated based on the need of target groups-Disabled People Organizations, students, literate and illiterate communities.

It is expected that the implementation of this project will among other things increase public understanding about the electoral process thereby increasing public confidence in the credibility of the Commission to deliver free, fair and transparent elections. By deepening the understanding of the policy makers on the scope of elections operation with emphasis on cost implications, budgetary support from government will not only increase but will be provided on a timely basis. Understandably, the implementation of the project will enhance equitable and increased participation in the electoral process and eventually solidify the pillars of the country’s post-conflict democracy.

Another key component of mass media is displayed media. This include print materials displayed portraying messages and information for the public. For the four-year period under this project, the Commission will develop and produce about 400,000 posters, flyers, brochures, stickers and banners in various categories and erect 23 giant size billboards in the 15 counties of the country portraying important democratization messages and illustrations. Furthermore, the election project will coordinated CVE activities with IFES which provides solid support to the NEC for following 4 years.

Indicative activities:

(1) Support the NEC in developing and implementing a comprehensive civic and voter education program taking into account the findings and recommendations of the CVE Baseline Survey with the eventual support of CSOs

The medium or channel for messaging and dissemination of civic and voter information is critical to the success of any electoral process. Thus consistent with a key recommendation of the election baseline survey, the NEC will produce a CVE toolkit that will be pilot tested and used based on results for CVE outreach activities. The tool kit will include various types of messages and materials targeting various segments of the population as well as means and procedures of dissemination. The activities will be tailored to the needs of each region, including the use of the best medium to reach voters. The project will recruit CVE consultant to assist the NEC CVE section is developing of strategy and toolkits in timely manner. The project will support:

- Development of a comprehensive strategy and toolkits on the implementation of the three-year CVE program using recommendations of the CVE;

- Pilot project for the newly adopted CVE strategy and toolkits.

(2) Strengthen the capacity of Civil Society Organizations to support the Commission in the delivery of quality CVE programs and services

In an effort to ensure the scrupulous implementation of these activities, the program through its CVE section will conduct series of training and capacity building sessions for key national partners aim at building collaboration for a nation-wide CVE outreach campaign. These partners include Civil Society and Religious Organizations, the Media, Youth and women groups, trade union organizations and national associations. The role of these actors in the electoral process is pivotal in promoting equitable and increased participation. Series of 4 regional capacity building training courses will be organized on the scope of electoral administration and operations and better engagement of SCOs in civic and voter education activities.

(3) Engage the public at three levels, policy makers, civil society organizations, ethnic, religious minorities and youths to deepen their understanding of the electoral process and conflict prevention mechanisms

4 regional engagement sessions will be organized for relevant policy makers specifically to deepen their understanding on the scope of electoral administration and operations with the aim of enhancing effective and efficient election financing. Such policy makers will be drawn from the National Legislature and Ministries and Agencies within the executive. Increased in budgetary support from government and timely availability of such support is undeniably essential in guaranteeing the credibility and integrity of the electoral process.

Sustaining Liberia’s democracy requires a robust engagement of young people who constitute the next generation of voters. Equipping them with the requisite knowledge and information regarding their roles, rights and responsibilities as citizens in the in the electoral process is critical to the sustenance of Liberia’s democracy. Thus, the CVE section will work with the Ministry of Education (MOE) and selected national CSOs to ensure the successful implementation of the school-based CVE program targeting senior secondary schools. IFES and UNDP will jointly co-share support for this particular activity.

Direct engagement method is a major mechanism in any effective CVE outreach campaign. Thus, a number of steps will be taken under this project in the form of community outreach using various means. The CVE section will organize community and town hall forums, open-air concerts using celebrities, intellectual contests, sports and recreation events to educate and inform citizens about the ongoing democratization of the country with emphasis on the importance of their participation. Furthermore, about 40 traditional group of communicators such as town criers and drama and cultural groups will be hired to serve as Community CVE Ambassadors to carry out door-to-door campaigns. These groups will be hired directly from their respective communities as a means of instilling trust and confidence in the process to encourage locals for participation.

Result 7: Strengthen the electoral legal framework and the constitutional review process as it relates to elections and harmonization of the election law and regulations

A Constitutional Review process is under way and will perhaps have implications for the conduct of the 2017 elections. The ongoing legal reform process represents an opportunity to build broad consensus among political actors on the rules of politics and promote confidence in the NEC, which will be critical for the peaceful conduct of the elections. If the proposed changes to the Constitution are approved and come into effect before the 2017 elections, a new board of commissioners will be in place to conduct the general elections. The NEC will be charged with harmonizing the electoral law and regulations with the new Constitution. Stakeholders would also need to be familiarised with the changes introduced, within short timeframe. Therefore, the project will provide technical advice to the NEC and other relevant stakeholders on the constitutional review process and the conduct of a referendum. The NEC will be closely coordinating with the CRC and the Legislature the constitutional review process to ensure that discussions on the conduct of constitutional changes relating to the elections and referendum adequately take into account the operational implications of electoral process.

Indicative activities:

(1) Support the NEC, the CRC, the Law Reform Commission (LRC); the legislature and the Government on the referendum, constitutional reform as it relates to elections, harmonisation of electoral law reform and constitutional review process and developing detailed guidelines and regulations

Deploying a legal expert as a resource within the NEC is an activity that would have immediate usefulness as well as potential impact into the post electoral period. Such an expert will help the NEC navigate the various legal and constitutional reforms being proposed/enacted, and interpret their significance for the NEC’s operating procedures, including adjudication of electoral complaints.

(2) Develop efficient and credible complaints mechanisms as a tool for prevention of electoral violence.

A legal expert will help the NEC in strengthening of the NEC hearing office. S/he will support development efficient and credible complaints mechanisms as a tool for prevention of electoral violence and violence related to intra-party conflict. This would potentially include a review of constitutional provisions relevant to the appointment of the NEC members, proclamation of Election Day, regulations, directives and instructions related to elections. Legal expert will assist NEC in organization of public information sessions on newly amended election law.

Result 8: Successful conduct of national elections through logistics and operational support provided to NEC and core electoral stakeholders

Limited infrastructure and difficult terrain and weather conditions make logistics one of the most challenging tasks for the NEC. The Constitution stipulates that presidential and legislative elections should be held throughout the country on the second Tuesday of October, when the rainy season is the heaviest. While significantly dependent on UNMIL support in 2005, the NEC has increasingly assumed logistical responsibility for the process in 2011. Notably in 2011, UNMIL provided limited logistical assistance only where national capacity was absent. UNMIL’s drawdown and loss of assets has diminished the mission’s capability to provide significant logistical support in 2014. As a rule in the last years, when election operation comes closer the NEC officially requests UNMIL to provide logistical support in the distribution and retrieval of election materials and personnel to remote and inaccessible precincts in the south-eastern and north-western regions. For the 2017 general elections, the NEC should be operationally strong and confident enough to find more sustainable, good practices and cost-effective solutions to the challenge of reaching remote areas. NEC should affectively coordinate and advocate for the resource sharing with other government institutions during logistical operation.

Indicative activities:

- Technical and financial support to the electoral operations – Elections and run-off

This will include technical and advisory capacity support in situ at the NEC to support planning and operational support.

(2) Logistics (such as elections material) and communication support to NEC

Activities in this area will provide support specifically aimed at the election events expected during the life span of the project, namely for preparation of the 2017 national elections. Support would include operational support to the NEC, including printing of ballots, communication, voter education, electoral staff training and its monitoring as well as similar support for the Run-Off, and possible UNMIL logistical and communications support, under the overall coordination of UNDP. The election project will recruit experienced operations specialist with overall responsibility to advise NEC in delivery of operational tasks for the 2017 electoral processes.

(3) Support to operational planning and budgeting exercises

The NEC's capacity for rational multi-year planning and budgeting is limited. Budgetary preparation for the 2014 elections showed pitfalls since the funds for the Senatorial elections were received late. It became obvious that the NEC is not proactive in preparing of long-term budget plan which could facilitate predictability in the allocation and disbursement of funds, including the mobilization of external resource where necessary. Therefore, the project finance specialist will support NEC operational planning and budgeting for the 2017 national elections including voter registration. For the budgeting exercise the finance specialist will work closely with the NEC finance section on timely development of the NEC electoral budget, advice on coordination mechanisms with national authorities including security agencies and ensure submission of budget to the executive and legislative branches for approval and timely allocation of funds.

# 6. RISK MANAGEMENT MEASURES

The project’s main assumptions are that the political context in Liberia will remain conducive to peace and stability, no major armed conflict or socio-political disruption will occur and that the donor community will manage to mobilize enough resources to support Liberia’s electoral cycle 2015-2017. Several risk factors could bear directly on the successful implementation of the elections assistance, mainly relating to the broader political landscape and electoral reform imperatives currently under consideration:

| Risk/potential adverse impact | Level | Risk management strategy/measures |
| --- | --- | --- |
| Lack of capacity of the state to provide security as part of the UNMIL military drawdown | Medium | There is substantial focus on this issue from almost all donors. EU is foreseeing a state building contract (Budget support) and political dialogue that will contribute to these efforts. Regular election security coordination mechanism (Project's Result 6). |
| Electoral violence triggered by lack of NEC transparency and technical capacity to prepare for elections | Low | The presence of the technical team in NEC deployed by the project is critical for conducting smooth electoral operation. The presence and training of qualified national civil observers The eventual monitoring of an Election Expert Mission to encourage increased professionalism of the NEC |
| Electoral violence triggered by Insufficient engagement of youth in electoral processes | Medium | Ensure youth is engaged in the electoral training and awareness programs Support to CSOs related activities in the rural and urban areas with active involvement of youth and gender groups |
| Political dialogue in between of the new Board of Commissioners and the political parties deteriorates | Low | Lack of dialogue with political parties may deteriorate political climate but this risk is low. The project will strive to install a culture of assuring that all objective points of critics are treated in a professional manner. |
| Delay in taking decision to conduct referendum on the constitutional amendments | Medium | Activities, including recruitment of staff, and procurement of materials would have to be reshuffled and reallocated at Steering Committee level. Contingency to be provided for in the budget of the IMDA. |
| Delay in submission of the 2017 electoral budget | Low | The project will assist in development of the calendar of activities and ensure the budget is timely submitted |
| Shortfall in the national budget leads to reduction in NEC budget | High | The project will support improved budget planning and lead to more efficient allocation of funds. Complementary actions such as budget support and PFM will also contribute. Continued dialogue with government will also take place. |

# 7. MANAGEMENT ARRANGEMENTS

On the basis of the partnership for electoral assistance EU-UNDP and with the follow-up and support of the Joint EU-UNDP Task Force on Effective Electoral Assistance, the project will also foster a special relationship with UNMIL, United Nations Police (UNPOL), UNWomen and other possible UN actors with a mandate or expertise in electoral assistance as well as conflict resolution and peace building activities. International donors and other partners such as IFES, NDI, International IDEA, ECOWAS and AU may collaborate on substantive activities.

The project will function in national implementation modality (NIM). The project will follow the best management model for an electoral assistance projects that would provide for a policy and technical oversight to ensure the project remains on track and on budget. The donor coordination mechanism will function through the TWG, where NEC activities will be discussed between different donors. The technical working group will be presided by the NEC, which will provide overall direction to all donor activities in line with its strategic plan. NEC will prepare an agenda for the meetings, which will happen quarterly. The membership of the TWG will include GoL, EU, UNDP, UNMIL, USAID, IFES, and other donors contributing or may contribute to supporting elections.

An overall Technical Working Group is the overall authority for the project and is responsible for its initiation, direction, review and eventual closure. It includes International donors and other partners and should be co-chaired by the NEC. This forum would be an important part of donor coordination, with the emphasis on high-level policy dialogue, collaboration and information-sharing and also broaden other components of potential democracy-building programs. The purpose of the TWG will be to ensure common knowledge on election activities, harmonization and to avoid duplication of programming. The agenda would include an update from the NEC on election preparations and related issues and short presentations from each group on their activities followed by general discussion on proposed or emerging issues. The TWG is the highest authority of the project responsible for making on a consensus basis management decisions for the project when guidance is required by the CTA. TWG project reviews will be made at regular intervals or as necessary when raised by the NEC or CTA. It will meet at least quarterly and more frequently nearer to the Election Day as needed.

A Project Management Unit (PMU) will be the dedicated unit that administers and manages the funds. The PMU will be responsible for the day-to-day running of the project and will serve as a Secretariat to the TWG. In addition to the PMU and TWG, the project would also seek a wider stakeholders’ forum, chaired by the NEC, which would bring together representatives of the donor community, national stakeholders and assistance providers to exchange information on a periodic basis. The PMU will prepare issues for TWG discussion and iron out in advance any outstanding controversial issues. PMU staff should include experts with proven previous comparative experiences in electoral assistance. The selection of experts shall be done in collaboration and in agreement between UNDP Country Office, the NEC and of all the donors contributing to the UNDP managed fund. A specific support can be provided by the United National Electoral Assistance Division and by the Joint EC-UNDP Task Force both maintaining rosters which can serve as source for pre-selection of experts. The selection will be carried out in conformity with requirements of competitive review and diverse applicant tools following UNDP rules and regulations. UNDP agrees that clearance for the selection of experts shall be provided in an expeditious manner and the selection of the entire set of experts required may be completed at different stages in order to allow the immediate implementation of the project.

The project will be coordinated by a Chief Technical Advisor (CTA/PMU), recruited by UNDP, who will oversee the project implementation. The project will recruit as well as Training and Capacity Building Specialist and Finance Specialist. During the election operation (year 2017) the project will additionally recruit operations specialist to support the NEC in delivery of 2017 electoral operation. Other project staff will include short term experts in the field of voter registration, legal, records management, IPCC/conflict prevention, voter education and gender. The CTA will be responsible for day-to-day management and decision-making for the project, as well as ensuring that the project produces the results specified in the project document. The full TORs for these three key positions are attached.

Regardless of reporting lines, all advisors working to implement the project should be coordinated by the CTA but will retain their reporting and supervisory lines. The CTA will report to the TWG which, as indicated above, comprises the following members:

- Representative of the NEC and GOL;

- DSRSG/UN Resident Coordinator or delegated representative;

- Representatives of the development partners to the project EU, IFES, UNMIL, USAID

There is also a need in the project organization for a means of assessing all aspects of the project’s performance and products which are independent of the CTA. This is the project assurance that will be the responsibility of the designated Team Leader of the Governance Unit of UNDP Liberia. The project will receive the support and follow up from the EC and UNDP’s members of the Joint EC UNDP Task Force on Electoral Assistance.

## Project Organizational Structure

## Project Reporting Schedule

UNDP will submit the project document including the Result and Resource Framework, Work Plans and a Budget to the EU for approval before the launch of the election project. Thereafter the following Reporting Schedule will apply:

Quarterly Progress Report to the TWG:

Activity Report:

- Activities carried out during reporting period;

- Difficulties encountered and measures taken to overcome;

- Changes introduced in implementation;

- Progress towards achievement of expected results, assessed against indicators specified in the Annual Work Plan and log frame;

- Work-plan for the next period;

- Financial update.

Annual Progress Report to the TWG:

Activity Report:

- Summary and context of the Action;

- Difficulties, challenges and risk mitigation measures;

- Recommendations for revisions in the scope and focus of project activities, with budget implications;

- Financial Report submitted quarterly;

Final Report:

- The Final Report to be submitted within six  (6) months of the financial closing of the project

Activity Report:

- Summary and context of the project;

- Activities carried out during the project;

- Difficulties/risks encountered and measures taken to overcome;

- Changes introduced in implementation;

- Lessons learned and best practices;

- Results achieved by assessing indicators outlined in the logical framework;

- Financial Report;

- Summary of expenditures by category compared;

- Recommendations, lessons learned and exist strategy for follow-up assistance projects.

The election project will invite an independent consultant(s), to carry out the project evaluation. It will be funded by the project itself.

# 8. PERFORMANCE MONITORING

An indicative logframe including performance indicators for all objectives is included as an annex. It is itself based on the Country's Agenda for Transformation and NEC's 2012-2017 Strategic plan which presented the NEC’s strategic objectives for the period. Due to outstanding limitation in the country's and the sector's M&E framework and capacities, the project will be subject to UNDP’s monitoring and evaluation procedures. In parallel, this project and other EU and donors projects are and will support the improvement of the M&E systems in the country in order to achieve sustainability.

Performance monitoring will be subject to yearly review by the TWG. Follow-up missions to be carried out by the EU-UNDP Joint Task Force may complement the monitoring activities/mechanisms of the project. In addition, ROM mission possibility should be considered. The EU Delegation in Liberia will be actively involved in the project's coordination mechanisms and supervision, and shall be invited to participate in the main monitoring and in the evaluation missions relating to the performance of actions that have received funding from the Commission. The results of such missions shall be reported to the Commission. The EU Delegation may take on additional responsibilities in the TWG and increase efforts to follow technically the implementation of the programs/projects, also with the support of external expertise. The EU Delegation may consider recruiting electoral operations experts through the Technical Cooperation Facility (TCF) that would liaise with the NEC and the UNDP Cos in the follow up of the project

Tracking of the achievement of benchmarks/indicators for each activity will monitor the performance of the project. The project activities will be closely monitored by UNDP Country Office. To this effect a Program Officer from the Governance Unit will backstop the project and support the CTA, PMU and the NEC in planning and monitoring project outputs. The mechanisms that will be used to monitor the annual work plan will include:

- An indicative project logframe;

- Quarterly progress report, technical and financial report prepared by the PMU/project office;

- Annual progress report, technical and financial report prepared by the PMU/project office at the end of the year;

- Field visits undertaken jointly by donors, the NEC and the United Nations; and

- An outcome or project evaluation.

# 9. PROCUREMENT

Over the years, UNDP has developed an extensive understanding and experience in providing technical assistance and support to the conduct of democratic elections, through either UNDP headquarters or its country offices. UNDP has become a major actor in the procurement of electoral materials, ranging from ballots and ballot boxes, stationery and digital voter registration equipment.  In addition, UNDP has recently increased its focus on the crucial pre-polling period of planning and budgeting for procurement of electoral material.

UNDP has reinforced the procurement function and related higher-level advisory services by revamping and restructuring the Procurement Services Office in New York and Copenhagen. One unit deals directly with elections, the Global Procurement Unit (GPU), which represents the operational arm of procurement. At the same time GPU has an integrated Special Advisory Team (SAT) on elections, covering advisory services.

UNDP/GPU hold Long Term Agreements (LTAs) for the most strategic and essential electoral materials. The purpose of the LTAs is to ensure efficiency in the procurement turn-around time and to limit repetitive tendering exercises within the boundaries of UNDP procurement rules and regulations. LTAs also provide guaranteed quality assurance and quality control, as well as the benefit of economy of scale, both in terms of products and logistics.

The project may procure goods and services using UNDP rules and regulations and if deemed necessary the support of UNDP/GPU/SAT (with staff in Copenhagen and Johannesburg) will be sought. However, in some cases NEC procurement process can be used for procurement of non-election materials. All funds that are advanced to implementing agents shall be accounted for within fifteen days prior to the end of the quarter. The Auditor General or her/his appointed agent would audit the accounts of the project at the end of the year. The Executing Agent and Implementing Agent will have the responsibility of following up the recommendations of the audit.

# 10. FINANCIAL ARRANGEMENTS

## Indirect management with an international organization

This action with the objective of enhancing the democratization process in Liberia with emphasis on improving electoral institutions and processes will be implemented in indirect management with the United Nations Development Programme (UNDP) in accordance with Article 58(1)(c) of Regulation (EU, Euratom) No 966/2012. This choice is justified because UNDP has acted as lead donor for elections support during the previous 2010-2012 electoral support pooled fund, it has good technical experience and resources to work in the area, as well as good relations with the beneficiary, the Liberian NEC, and an important role in other complementary governance interventions in the country. While NEC capacities remain limited, the implementation of the programme through UNDP remains the most appropriate for EU support.

The alternative entrusted entity intends to sub-delegate as yet to be defined actions to the NEC. Appropriate provisions will be included in the delegation agreement. The entrusted entity is currently undergoing the ex ante assessment in accordance with Article 61(1) of Regulation (EU, Euratom) No 966/2012. In anticipation of the results of this review, the authorising officer deems that, based on a preliminary evaluation and on the long-standing and problem-free cooperation with this entity, it can be entrusted with budget-implementation tasks under indirect management. The change of management mode from indirect to direct management, whether partially or entirely is not considered a substantial change.

# 11. COMMUNICATION AND VISIBILITY

Communication and visibility of the EU is a legal obligation for all external actions funded by the EU. This action shall contain communication and visibility measures which shall be based on a specific Communication and Visibility Plan for the Action, to be elaborated before the start of implementation and supported with the project budget.

The measures shall be implemented either (a) by the Commission, and/or (b) by the implementing partner. Appropriate contractual obligations shall be included in, respectively, procurement and grant contracts. The Communication and Visibility Manual for European Union External Action shall be used to establish the Communication and Visibility Plan of the Action and the appropriate contractual obligations.

# 12. EXIT STRATEGY

The project will formulate the exit strategy in close collaboration with NEC and donors and review gradually the progress with the NEC administrative system and policy development, staff capacity enhancement and the level of NEC’s interaction with political parties, CSOs and partner organizations. It will also identify which activities may go on without external support, which activities may need further external support and which donors may step in to replace EU. It will also explore the options and challenges to the NEC after 2018, based on the post-election assessment.

# 13. LEGAL CONTEXT

The country program action plan shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Liberia and the United Nations Development Program, signed by the parties on 27 April 1977. Revisions may be made to this project with the signature of the UNDP Resident Representative only, provided he or she is assured the other signatory of the project have no objection to the proposed changes, in the case of revisions which do not involve significant changes in the immediate objectives, output or activities of the project, but are caused by the rearrangement of inputs already agreed to or by cost increases due to inflation.

# Footnotes

As at the time of writing this project document (28th October 2014), the Ministry of Health and Social Welfare (MoHSW), reported as 6,267 the cumulative total of suspected, probable and confirmed cases of EVD in Liberia, with the cumulative deaths standing at 2,106. A major consultation process was underway led by NEC on whether or not to conduct the Senatarial elections in December having been postponed them from October due to the EVD.

The JTF is formed by EC and UNDP staff dealing with Electoral Assistance at HQ levels among Brussels, New York and Copenhagen and soon in Ghana, Dakar, Johannesburg and Bangkok. The overarching purpose of the JTF is to further strengthen and facilitate the EC-UNDP partnership in the electoral assistance field and aims to improve the overall efficiency and adherence of the projects to the common EC/UNDP strategic approach. The focus of the JTF is to provide identification, formulation and implementation support for joint EC-UNDP projects on electoral assistance whenever needed and requested by EC Delegations and/or UNDP Country Offices. The Specific support that the JTF will provide include: Operational Guidance and implementation strategies Liaison and Interactions with the different services involved, at headquarters and field level, throughout the operations cycle to ensure the application of the recommended quality standards.

# Text boxes

Technical Working Group

Presided by NEC

Board Members (GoL, EU, UNDP , UNMIL, IFES, USAID, other donors)

Project Management Unit – UNDP

UNDP Project Manager (CTA)

UNDP Operations/Finance/Programs

Project team Advisors: Finance and administration

Project Support

UNDP Operations/ Procurement Office/DEX

Joint EC UNDP Task Force

Project Assurance

UNDP ARR Governance

Programme Officer

Project team Advisors: Election operation and electoral processes