## AWP INLA2J 2017-18 -12 months
United Nations Development Programme, Sri Lanka
| Project Title | Strengthening Access to Justice and Victim and Witness Protection
| Project ID | 91115
| Output ID | 96525
| Year | 2017 & 2018
| Updated on | 12/07/2017 for system entry
ATLAS AWP Key Activities | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | Planned Budget
| Q1 | Q2 | Q3 | Q4 |  | Fund ID | Donor ID | A/C ID | Budget Description | 2017 Budget (USD) | 2017 Budget (LKR) | 2018 Budget (USD) | 2018 Budget (LKR) | Total
Project Outcome: Rule of law and access to justice are strengthened to support social integration in Sri Lanka
Output 1: Institutional capacities strengthened for improved administration of justice, strategic planning and policy development for a longer-term sector wide approach to victim and witness protection
Activity 1.1 Technical Advisory Services and Project Management Support
1.1.1 Contractual Services | x | x | x | x | UNDP | 3000 | 11710 | 71400 | Contractual Services (Service Contracts) | 44756 |  | 18252 |  | 73009
[6 empty] | 3000 | 11710 | 71300 | local consultants | 10000
1.1.2 Travel | x | x | x | x |  | 3000 | 11710 | 71600 | Travel | 2500 |  | 1500 |  | 4000
1.1.3 Equipment & Furniture | x | x |  |  |  | 3000 | 11710 | 72200 | Equipment & Furniture | 4000 |  | 100 |  | 4100
1.1.4 Training and Workshops | x | x | x | x |  | 3000 | 11710 | 75700 | Training and Workshops | 2850 |  | 1150 |  | 4000
1.1.5 Miscellaneous | x | x | x | x |  | 3000 | 11710 | 74500 | Miscellaneous | 1000 |  | 500 |  | 1500
1.1.6 Communications | x | x | x | x |  | 3000 | 11710 | 72400 | Communications | 1200 |  | 599 |  | 1799
1.1.7 DPC (5%) | x | x | x | x |  | 3000 | 11710 | 64300 | DPC (5%) | 24251 |  | 8083 |  | 32334
1.1.8 GMS (8%) | x | x | x | x |  | 3000 | 11710 | 75100 | GMS (8%) | 40741 |  | 13580 |  | 54321
Activity 1.2: Implementation of the victim and witness protection mechanism in Sri Lanka is supported
1.2.1 Conduct a review of the existing policies and legal frameworks to inform the provisions in the VWPA compliment international standards and best practices. Assist with the development of guidelines for a protection programme for the National Authority | x | x | x |  | UNDP (collaborate with Natl. Authority) | 30000 | 11710 | 75700 | Workshop/ Meetings/ trainings | 1500 | 229350 | 2500 | 382250 | 4000
| x | x | x |  |  | 3000 | 11710 |  | International Consultant | 20000 | 3058000 | 15000 | 611600 | 35000
| x | x | x |  |  | 3000 | 11710 | 71300 | local consultants | 3500 | 535150 | 5000 | 764500 | 8500
1.2.2 Undertake a stakeholder mapping and conduct consultations with victim support organizations and civil society | x | x |  |  | UNDP (collaborate with Natl. Authority) | 30000 | 11710 | 71300 | local consultant | 2000 | 305800 |  | 0 | 2000
| x | x |  |  |  | 3000 | 11710 | 75700 | Workshop/Meetings | 2000 | 305800 | 2000 | 305800 | 4000
1.2.3 Assist the National Authority in developing and carrying out orientation sensitization programmes for personnel manning the Protection Division within the Sri Lanka Police ( fresh request submitted to the Natl. Authority - UNDP). Vetting required etc.? ) | x | x | x | x | UNDP (collaborate with National Authority / Police) | 30000 | 11710 | 75700 | Workshop/ Meetings/ trainings | 5000 | 764500 | 15000 | 1529000 | 20000
1.2.4 Assist the National Authority in carrying out training and sensitization for relevant stakeholders (Judiciary, Prosecution, JMOs, BASL etc.) on the implementation of the victim and witness protection law | x | x | x | x | UNDP/Natl. Authority BASL | 30000 | 11710 | 74200 | Audio visual production/ printing costs | 2000 | 305800 | 5000 | 764500 | 7000
|  | x | x | x |  | 3000 | 11710 | 75700 | Workshop/Meetings/Trainings | 20500 | 3058000 | 50000 | 7645000 | 70500
1.2.5 Conduct quantitative and qualitative criminological research into victimology patterns vis-à-vis crime rates (disagregated according to gender, age, geographical location etc.) | x | x | x | x | Uni of Jpura/Police | 30000 | 11710 | 72600 | Grants | 30000 | 4587000 | 20000 | 3058000 | 50000
| x | x | x | x |  | 3000 | 11710 | 75700 | Workshop/Meetings | 10000 | 1529000 | 10000 | 1529000 | 20000
1.2.6 Support the National Authority in carrying out awareness programmes to inform the public on their rights and responsibilities with regard to the Act, |  | x | x | x | UNDP (collaborate with National Authority) | 3000 | 11710 | 74200 | Audio visual production/ printing costs | 30000 | 4587000 | 75000 | 7645000 | 105000
[6 empty] | 3000 | 11710 | 71300 | local consultants | 5000 |  | 5000 |  | 10000
1.2.7 Expansion of legal aid to victims. MoU with HRC LAC - exact nature of the MoU TBD (community vigilance groups ?) |  | x | x | x | Legal Aid Commission | 3000 | 11710 | 72600 | Grants | 25000 | 3822500 | 25000 | 3822500 | 50000
1.2.8 Assisting the National Authority and the Protection Division with organizational and operational support including to develop recruitment guidelines, including basic IT infrastructure (based on the identified need). | x | x | x | x | UNDP | 3000 | 11710 | 72200 | Equipment & Furniture | 25000 | 3822500 | 50000 | 3822500 | 75000
[6 empty] | 3000 | 11710 | 71300 | local consultants | 3500 |  | 5000 |  | 8500
[6 empty] | 3000 | 11710 | 71400 | Contractual Services /Companies | 10000 |  | 5000 |  | 15000
Activity 1.3 Strengthening Access to Justice Mechanisms established under Phase 1
1.3.1 Consolidation of 3 core pieces of legislation in Sinhala, Tamil, and English Language |  |  |  |  | UNDP (collaborate with Ministry of Justice) | 3000 | 11710 | 71400 | Contractual Services /Companies | 5000 |  | 25000 |  | 30000
[6 empty] | 3000 | 11710 | 71300 | local consultants | 1500 |  | 1500 |  | 3000
1.3.2 Support the availability of New Law Reports |  |  |  |  | UNDP (collaborate with Justice Ministry) | 3000 | 11710 | 71300 | local consultant | 1000 |  |  |  | 1000
[6 empty] | 3000 | 11710 | 71400 | Contractual Services /Companies | 5000 |  | 35000 |  | 40000
1.3.3 Support the development of a draft National Sentencing Policy/Guidelines/Act |  |  |  |  | UNDP (collaborate with JSC and Ministry of Justice) | 3000 | 11710 | 75700 | Workshop/ Meetings/ trainings | 1000 |  | 2000 |  | 3000
[8 empty] | 71300 | local consultants | 5000 |  | 2300 |  | 7300
[8 empty] | 71400 | Contractual Services /Companies | 2000 |  | 5000 | 764500 | 7000
Output 1 Sub Total | [9 empty] | 346798 |  | 404064 |  | 750863
Output 2: Capacities of state and non-state actors strengthened for a comprehensive and coordinated response to address sexual and gender based violence (SGBV)
Activity 2.1 Technical Advisory Services and Project Management Support
2.1.1 Contractual Services (Service Contracts) | X | X | X | X | UNDP | 3000 | 11710 | 71400 | Contractual Services (Service Contracts) | 54757 |  | 18252 |  | 73009
2.1.2 Travel | X | X | X | X |  | 3000 | 11710 | 71600 | Travel | 2500 |  | 1500 |  | 4000
2.1.3 Equipment & Furniture | X | X |  |  |  | 3000 | 11710 | 72200 | Equipment & Furniture | 4000 |  | 100 |  | 4100
2.1.4 Training and Workshops | X | X | X | X |  | 3000 | 11710 | 75700 | Training and Workshops | 2850 |  | 1150 |  | 4000
2.1.5 Miscellaneous | X | X | X | X |  | 3000 | 11710 | 74500 | Miscellaneous | 1000 |  | 500 |  | 1500
2.1.6 Communications | X | X | X | X |  | 3000 | 11710 | 72400 | Communications | 1200 |  | 600 |  | 1800
2.1.7 DPC (5%) | X | X | X | X |  | 3000 | 11710 | 64300 | DPC (5%) | 12125 |  | 4042 |  | 16167
2.1.8 GMS (8%) | X | X | X | X |  | 3000 | 11710 | 75100 | GMS (8%) | 20371 |  | 6790 |  | 27161
Activity 2.2: Support Ministry of Women and Child Affairs to roll-out the National Plan of Action to address SGBV including strengthening the referral system at district level; and sensitization of judges, law enforcement officers and public sector officials on addressing SGBV.
2.2.1. Strengthen and support Ministry of Women and Child Affairs (MWCA) to coordinate and operationalize the National Plan of Action to address Sexual and Gender-based Violence (SGBV) including relevant training on gender/ SGBV. |  | x | x | x | MWCA | 30000 | 11710 | 75700 | Workshop/ Meetings/ trainings (includes travel) | 20000 | 3058000 | 4300 | 657470 | 24300
[5 empty] | UNDP | 30000 | 11710 | 71300 | consultants | 5000 | 764500 | 0 | 0 | 5000
2.2.2 Support the Ministry of Women and Child Affairs in setting up a Monitoring and Evaluation system to track implementation of the National Action Plan on SGBV |  |  | x | x | UNDP (collaborate with MWCA for implementation) | 30000 | 11710 | 71300 | local consultant | 5000 | 764500 | 0 | 0 | 5000
2.2.3. Strengthen the referral system of SGBV cases to penal chain in the identified districts and at central level - through MWCA's Women and Child Development Units. |  |  | x | x | MWCA | 30000 | 11710 | 75700 | Workshop/ Meetings/ trainings (includes travel) | 9500 | 1452550 | 7500 | 1146750 | 17000
2.2.4. Develop (Audio Visual / print ) & disseminate materials to combat SGBV focusing on prevention, intervention and advocasy of laws and policies |  |  | x | x | UNDP linking with MWCA/ Ministry of Parliamentary Reforms and Mass Media/ CSOs (TBD)_ | 30000 | 11710 | 74200 | Audio visual production/ printing costs | 8000 | 1223200 | 8100 | 1238490 | 16100
Activity 2.3 Strengthen selected CSOs to provide legal and other support services to SGBV survivors
2.3.1. Provide legal services inclusive of legal advice and court representation to survivors of SGBV through selected CSOs |  | x | x | x | CSOs | 30000 | 11710 | 72600 | Grants | 30000 | 4587000 | 30000 | 4587000 | 60000
2.3.2 Engage active participation of CSOs in the SGBV referral network at divisional level in identified districts, linking with MWCA. | [5 empty] | 30000 | 11710 | 72600 | Grants | 10000 | 1529000 | 10000 | 1529000 | 20000
2.3.3 Conduct outreach programmes to educate women, men, girls and boys on SGBV: prevention, protection and action through CSOs | [5 empty] | 30000 | 11710 | 72600 | Grants | 5000 | 764500 | 5000 | 764500 | 10000
2.3.4 Conduct paralegal training programmes through the selected CSOs for field staff of the Ministry of Women and Child Affairs and other state institutions on issues of SGBV, including the Prevention of Domestic Violence Act. | [5 empty] | 30000 | 11710 | 72600 | Grants | 10000 | 1529000 | 10000 | 1529000 | 20000
2.3.5 Engage CSOs in providing counselling/ psycho-social support to victims of SGBV as well as support to shelters for women. | [5 empty] | 30000 | 11710 | 72600 | Grants | 20000 | 3058000 | 20000 | 3058000 | 40000
2.3.6. Develop (Audio Visual / print ) & disseminate materials to combat SGBV focusing on prevention, intervention and advocasy of laws and policies | [5 empty] | 30000 | 11710
Output 2 Sub Total | [9 empty] | 221303 | 18730250 | 127834 | 19545818.6 | 349137