Back to Office Report - General (Maximum two- three pages plus annexes) Project/ Programme Visited: Enhancing Biodiversity Conservation and Sustenance of Ecosystem services in Environmentally Sensitive Areas Project Event/ programme participated: ESA Mid Term Review - field mission, Puttalam & Anuradhapura Field sites Key Objective(s) of the Visit/ participation: To facilitate and coordinate the MTR mission. Districts/ Place visited: Anuradhapura & Puttalam District (Itinerary is attached) Participant/ Visitor (Name/ Position): Sugandhi Samarasinghe/ Technical Coordinator Date/s of Visit: 13-15/09/2018

- Observation

- Observations on project’s progress towards the objective(s).

The project objective is to operationalize Environment Sensitive Areas (ESAs) as a mechanism for mainstreaming biodiversity management into development in areas of high conservation significance. The efforts at field level are moderately satisfactory.

- Other general observations (if available)

N/A

- Learnings

      - Key learnings, including positive findings.

MTR Team found difficulties in connecting some completed activities to the overall work-plan A more focussed application of gender considerations in project implementation is needed during the balance period

      - Issues identified

The extended drought situation discourages home gardening efforts and outreach of 25,000 ha is very challenging with existing interventions The community expectations in all areas visited are high – for livelihood support

      - Recommendations

MTR recommends re-visiting the selection of current 10 ESA sites, and use the criteria in the Technical Paper to re-examine them.

- Itinerary  (pls. refer the attachments of UNDSS)

| Date/Time | Details | Remarks |
| --- | --- | --- |