## Progress Monitoring_April
ESA Project_2016 ANNUAL WORKPLAN
Key Activity Results (Annual Ouput) | AWP Activities | Key Milestone and Detail Activities | Responsible Party | QUARTER/MONTH OF COMPLETION | [11 empty] | Status | AWP Budget (USD) | Quarter 1 |  | Quarter 2 |  | Quarter 3 |  | Quarter4
|  |  |  | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec |  |  | Q1 Target | Q1 Exp. | Q2 Target | Q2 Exp. | Q3 Target | Q3 Exp. | Q4 Target | Q4 Exp.
National Enabling Framework Strengthened to Designate and Manage ESAs
Effective national policies on conservation and sustainable management of ESAs | Result 1_ National Policy and Strategy on ESA | A. Project Inception, set up Project Board & Intersectoral committees
|  | Conduct Project Board Meetings - 4 | SED | [13 empty] | 347.3428 |  |  | 20000 | bar: QUARTER/MONTH OF COMPLETION Feb; QUARTER/MONTH OF COMPLETION Jun; QUARTER/MONTH OF COMPLETION Sept; QUARTER/MONTH OF COMPLETION Dec
|  | Conduct national ESA Committees - 4 | SED | [13 empty] | 1389.3713 |  |  | 100000 | bar: QUARTER/MONTH OF COMPLETION Mar; QUARTER/MONTH OF COMPLETION Jun; QUARTER/MONTH OF COMPLETION Sept; QUARTER/MONTH OF COMPLETION Dec
|  | Conduct divisional sensitization workshops | UNDP | [13 empty] | 1042.0285 | bar: QUARTER/MONTH OF COMPLETION Mar
|  | Conduct IWS & review log frame and Pro Doc | UNDP | [13 empty] | 2778.7426 |  | 3112.95 | bar: QUARTER/MONTH OF COMPLETION Jan
|  | Develop Theory of Change | UNDP | [13 empty] | 694.6857 |  | 685 | bar: QUARTER/MONTH OF COMPLETION Mar
|  | Technical Coordinator | UNDP | [13 empty] | 19173.3241
|  | Publications | SED | [13 empty] | 2778.7426 |  |  | 200000 | bar: QUARTER/MONTH OF COMPLETION Jun; QUARTER/MONTH OF COMPLETION Dec
B. Development of a national Policy and Strategy on ESAs, based on National Environmental Act (NEA)
|  | Recruitment of a Policy Consultant and prepare ESA policy & startegy (Int - 3 wks) | UNDP | [13 empty] | 10420.2848 |  | 259.11 | bar: QUARTER/MONTH OF COMPLETION May to QUARTER/MONTH OF COMPLETION Sept
|  | Recruitment of consultant and prepare ESA policy & startegy (Local_12 wks over 9 months) | BDS | [13 empty] | 4515.4568 |  |  | 250000 | bar: QUARTER/MONTH OF COMPLETION May to QUARTER/MONTH OF COMPLETION Dec
|  | Conduct related Workshops | BDS | [13 empty] | 4168.1139 |  |  | 300000 | bar: QUARTER/MONTH OF COMPLETION Aug to QUARTER/MONTH OF COMPLETION Dec
|  | Recruitment of consultancy firm and conduct Baseline survey ( 20 days over 3 months) | BDS | [13 empty] | 10767.6276 |  |  | 50000 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Oct
| Result 3_ Updated policy to address human wildlife conflicts | Recruitment of Consultant and update the Policy (Local_12 wks over 6 months) | DWC | [13 empty] | 4515.4568 |  |  | 300000 | bar: QUARTER/MONTH OF COMPLETION May to QUARTER/MONTH OF COMPLETION Sept
|  | Conduct related workshops | DWC | [13 empty] | 6946.8565 |  |  | 500000 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Oct
|  | Announce for Public comments | DWC | [13 empty] | 2084.057 | bar: QUARTER/MONTH OF COMPLETION Dec
National stakeholders’ capacities to support planning, implementation and monitoring of ESAs | Result 5_Two ESA land use plans and annual ESA work plans approved by inter-Sectoral ESA Committees, outlining joint work. | A. Capacity building for ESA Committee members and land use planning team, through skills to incorporate biodiversity concerns into the land use plans at local level.
|  | Hire local expert institute for Landscape conservation and capacity building Assignment (120 days over 9 months) (Budgeted 9 5% in outcome 2) | UNDP | [13 empty] | 3000 | bar: QUARTER/MONTH OF COMPLETION Mar
|  | Capacity building workshops | SED | [13 empty] | 5904.8281 |  |  | 250000 | bar: QUARTER/MONTH OF COMPLETION Jul
|  | Purchase Equipments | SED | [13 empty] | 8579.3678 |  |  | 900000 | bar: QUARTER/MONTH OF COMPLETION Jun
|  | Rental of a vehicle for PMU | SED | [13 empty] | 6946.8565 |  |  | 300000 | bar: QUARTER/MONTH OF COMPLETION Mar
B. Development of 2 land use plans for the two districts
|  | Field Visits/ travel | LUPPD/ MASL | [13 empty] | 8336.2279 |  |  | 400000 | bar: QUARTER/MONTH OF COMPLETION May to QUARTER/MONTH OF COMPLETION Dec
|  | Conduct workshops/ meetings | LUPPD/ MASL | [13 empty] | 6946.8565 |  |  | 350000 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Nov
|  | Printing landuse plans | LUPPD/ MASL | [13 empty] | 694.6857 | bar: QUARTER/MONTH OF COMPLETION Dec
| Result 6_ Capacity of the key agencies at national, provincial and local level strengthened to promote effective ESA implementation | A. Provide relevant capacity building on ESAs to key public institutions at the national, provincial and local levels to design, review and endorse ESAs.
|  | Self assessment and Provide relevant capacity building trainings | SED | [13 empty] | 6946.8565 |  |  | 300000 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Dec
| Result 7_ National guideline to integrate biodiversity conservation and sustainable use into land use planning | Documentation of processses, procedures, lessons and issues in the implementation of landuse plans
|  | Conduct workshops | SED | [13 empty] | 1389.3713 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Oct
|  | Field visits / Travel | SED | [13 empty] | 3473.4283 |  |  | 100000 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Oct
| Result 10_ Online integrated biodiversity assessment tool to identify biodiversity hotspots nationwide, building on national and international data | Integrate ESA specific criteria and information in to the BDS clearing house mechanism | [14 empty] | 347.3428 | bar: QUARTER/MONTH OF COMPLETION Oct to QUARTER/MONTH OF COMPLETION Dec
Institutional capacities for biodiversity- friendly land-use planning, implementation and compliance at Kala Wewa and Wilpattu ESAs | Result 11_Two ESAs under management with inter-Sectoral partnership and quantifiable biodiversity conservation targets | A. Expand LMC & DFC to incorparate ESA planning & mgt to guide and facilitate activities at Site 1& Site 2
|  | Conduct meetings (LMCs & DFCs) | SED | [13 empty] | 4168.1139 |  |  | 200000 | bar: QUARTER/MONTH OF COMPLETION Mar; QUARTER/MONTH OF COMPLETION May; QUARTER/MONTH OF COMPLETION Jul; QUARTER/MONTH OF COMPLETION Sept; QUARTER/MONTH OF COMPLETION Nov
|  | Hire 2 field coordinators for two sites _Anuradhapura & Puttalam | UNDP | [13 empty] | 30010.4203 | bar: QUARTER/MONTH OF COMPLETION Jan to QUARTER/MONTH OF COMPLETION Dec
|  | Hire local consultants for technical inputs | UNDP | [13 empty] | 1215.6999 | bar: QUARTER/MONTH OF COMPLETION Jan to QUARTER/MONTH OF COMPLETION Feb
|  | Hire local expert institute for Landscape conservation and capacity building Assignment (120 days over 9 months) (Budgeted 5% in outcome 1) | UNDP | [13 empty] | 57000 | bar: QUARTER/MONTH OF COMPLETION April to QUARTER/MONTH OF COMPLETION Dec
|  | Rental of vehicle for Field Offices | SED | [13 empty] | 6946.8565 |  |  | 300000 | bar: QUARTER/MONTH OF COMPLETION Mar to QUARTER/MONTH OF COMPLETION Dec
|  | Establish two field offices in Anuradhapura & Puttalam/ Strengthen the capacities of "champion" institutions to act as secretariats and to provide appropriate guidance | SED | [13 empty] | 6004.2515 | bar: QUARTER/MONTH OF COMPLETION Feb to QUARTER/MONTH OF COMPLETION April
|  | Capacity building of the planning & implementation team | SED | [13 empty] | 5557.4852 |  |  | 200000 | bar: QUARTER/MONTH OF COMPLETION May to QUARTER/MONTH OF COMPLETION Aug
| Result12_Increased stakeholders’ support and capacities to implement land use/ seascape plans for conservation | A. Develop startegic communication action plan and undertake training need assessment
|  | Conduct Workshops/ meetings to prepare startegic communication action plan | CEA | [13 empty] | 3473.4283 |  |  | 100000 | bar: QUARTER/MONTH OF COMPLETION Oct
Ecosystems management and restoration at ESAs | Result 14_Protected areas management , habitat connectivity, integrity and resilience | A. Management plans updated for Wilpatthu NP, Kahalla Pallekele, Bar Reef sanctuaries
|  | Hire local consultants/ facilitators ( 60 days/ 6 mths) | DWC | [13 empty] | 6946.8565 |  |  | 500000 | bar: QUARTER/MONTH OF COMPLETION May to QUARTER/MONTH OF COMPLETION Sept
|  | Conduct Consultation workshops/ meetings (5) | DWC | [13 empty] | 6946.8565 |  |  | 600000 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Sept
|  | Field visits/ Travel | SED | [13 empty] | 3473.4283 |  |  | 200000 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Dec
|  | Field visits/ Travel | UNDP | [13 empty] | 2084.057 | bar: QUARTER/MONTH OF COMPLETION Jun to QUARTER/MONTH OF COMPLETION Dec
| Result 15_.Critical biodiversity habitats outside protected areas under effective management regimes within the ESA for habitat connectivity, integrity and resilience | Undertake a reconnaissance survey to identify critical biodiversity habitats outside protected areas in ESA 1 (kalaoya)
|  | Interpolate, declare, forest polygons and ground trothing | DFC | [13 empty] | 20840.5696 |  |  | 1000000 | bar: QUARTER/MONTH OF COMPLETION Aug to QUARTER/MONTH OF COMPLETION Dec
|  | Field Visits- Identification of unsurveyed/ undeclared forest areas to be undertaken for the landscape plan | DFC | [13 empty] | 694.6857 |  |  | 33000 | bar: QUARTER/MONTH OF COMPLETION Aug to QUARTER/MONTH OF COMPLETION Dec
|  | Workshops - Education, extension and ecotourism plan | DFC | [13 empty] | 4168.1139 |  |  | 100000 | bar: QUARTER/MONTH OF COMPLETION Sept to QUARTER/MONTH OF COMPLETION Dec
|  | Printing _Awareness materials | DFC | [13 empty] | 2778.7426 | bar: QUARTER/MONTH OF COMPLETION Oct to QUARTER/MONTH OF COMPLETION Dec
OTCOME 3 | Project Manageent | Establishment of a Project Management Unit
|  | Purchase of office equipments & Furniture | UNDP | [13 empty] | 5805.3143 | bar: QUARTER/MONTH OF COMPLETION Feb
|  | Purchase of office equipments & Furniture | SED | [13 empty] | 694.6857 | bar: QUARTER/MONTH OF COMPLETION Feb
|  | Office administration - Cost Recovery charges | SED | [13 empty] | 2778.7426 |  |  | 180000 | bar: QUARTER/MONTH OF COMPLETION Feb to QUARTER/MONTH OF COMPLETION Dec
Monitoring of ESA Activities
|  | Field monitoring viits by UNDP | UNDP | [13 empty] | 2084.057 | bar: QUARTER/MONTH OF COMPLETION Mar to QUARTER/MONTH OF COMPLETION Dec
|  | Field monitoring viits by Ministry | SED | [13 empty] | 3230.2883 |  |  | 165000 | bar: QUARTER/MONTH OF COMPLETION Mar to QUARTER/MONTH OF COMPLETION Dec
4057.06
2015 Monthly Project Delivery Monitoring Calender
Completed
On track
Delayed
Cancelled
Contracts already in system
Contracts/MCGs to be prepared
Planned
3000
3000
Note on A1: Dhanushki Abhayaratne: To be maintained monthly
Note on E2: Dhanushki Abhayaratne: please fill these in as per the AWP

## Indicator Tracking
TO BE FILLED QUARTERLY
PROJECT NAME, PROJECT DURATION, ATLAS NO,
Indicator | Baseline (year,month) | PLANNED TARGETS | ACHIEVMENT TOWRADS RESULTS | [12 empty] | Un intended results/Changes achieved | DISAGREGATION OF DATA
|  | End of the project | Quartely progress |  |  |  | Year 1 |  |  | year 2 |  |  | year 3 |  |  |  | Year 1 | [5 empty] | Year 2 | [5 empty] | Year 3
|  |  | Q1 | Q2 | Q3 | Q4 | Total results year 1 | Variance | Remarks | Actual results year 2 | Variance | Remarks | Actual results year 3 | Variance | Remarks |  | M | F | FHH | Differently abled | Youth | District | M | F | FHH | Differently abled | Youth | District | M | F | FHH | Differently abled | Youth | District
Project Outcome

## Procurement Log
Procurement Plan - 2015 - First Quarter
Country Office |  | Sri Lanka |  |  | Instructions: - Only include procurements to be done by UNDP for DIM, Management, support-to-NIM projects and UN Agencies - If you need additional lines, right-click and "Insert" rows, do not copy-paste, to keep drop-down menus & format.
Submitted by: |  | Procurement & Admin Unit
Date: |  | 2015-09-22
Q1 | Project Name (acronym or brief name) | Type of Supply | Category | Description of goods, services or works required | Unit of Measure | Quantity | Estimated Unit Price in USD | Estimated Total Price in USD | Requested delivery date (goods, works) or start of services | Finalization of services date | End user of goods, services or works/Location | Procurement Process Status
Governance for Empowerment & Social Inclusion (GESI)
Environmental Sustainability & Disaster Resilience (ESDR)
Civil Works | ESA | Individual Contractor | Workshop/Conference facilities | Venue & refreshments | days | 1 | 2500 | 2500 |  |  | Project stakeholders | Closed
| ESA | Individual Contractor | Workshop/Conference facilities | Venue & refreshments | Days | 2 | 368.5 | 737 |  |  | ESA Project team | Closed
| ESA | Individual Contractor | Individual Consultant (IC) - Intl. | Recruitment of a Policy Consultant and prepare ESA policy & startegy (Int - 3 wks) | Weeks | 3 | 3000 | 10000 |  |  | Sri Lankan Citizen | Solicitation | ToR dev. In progress
| ESA | Individual Contractor | Individual Consultant (IC) - Local | Recruitment of consultant and prepare ESA policy & startegy (Local_12 wks over 9 months) | Weeks | 12 | 376.25 | 4515 |  |  | Sri Lankan Citizen | Solicitation | ToR dev. In progress
| ESA | Individual Contractor | Individual Consultant (IC) - Local | Recruitment of consultancy firm and conduct Baseline survey ( 20 days over 6 months) | days | 20 | 538.35 | 10767 |  |  | BDS/ Sri Lankan |  | ToR dev. In progress
| ESA | Individual Contractor | Individual Consultant (IC) - Local | Recruitment of Consultant and update the HEC Policy (Local_12 wks over 6 months) | Weeks | 12 | 376.25 | 4515 |  |  | DWC |  | ToR dev. In progress
| ESA | Individual Contractor | Consulting Firm Services | Hire local expert institute for Landscape conservation and capacity building Assignment (120 days over 9 months) | days | 120 | 500 | 60000 |  |  | ESA stakeholders | Committee Review
| ESA | Individual Contractor | Vehicles | Rental of a vehicle for PMU | Months | 9 | 771.8889 | 6947 |  |  | SED | Solicitation
| ESA | Individual Contractor | Workshop/Conference facilities | Self assessment and Provide relevant capacity building trainings | days | 6 | 1157.8333 | 6947 |  |  | ESA stakeholders |  | To be planed
| ESA | Individual Contractor | IT Equipment | Establish two field offices in Anuradhapura & Puttalam/ Strengthen the capacities of "champion" institutions to act as secretariats and to provide appropriate guidance | units | 12 | 500 | 6000 |  |  | Field Offices
| ESA | Individual Contractor | Individual Consultant (IC) - Local | Hire local consultants/ facilitators ( 60 days/ 6 mths) | days | 60 | 115.7833 | 6947 |  |  | DFC |  | ToR dev.
| ESA | Individual Contractor | Other Goods | Purchase of office equipments & Furniture | units | 10 | 580.5 | 5805 |  |  | PMU | Evaluation
[7 empty] | 3730 | 24.0645
155
a
|  | Goods | Audit/HACT Assessment | [5 empty] | 2000-01-01 |  |  | Not Started
|  | Services | Communications Equipment | [8 empty] | Initiated
|  | Individual Contractor | Construction Works | [8 empty] | Solicitation
|  | Construction Works | Consulting Firm Services | [8 empty] | Evaluation
|  |  | Drugs | [8 empty] | Committee Review
|  |  | Individual Consultant (IC) - Intl. | [8 empty] | Contract Mngt
|  |  | Individual Consultant (IC) - Local | [8 empty] | Closed
IT Equipment
Medical/Lab Equipment
Office furniture
Premise rentals
Printing & Publishing
Security Equipment
Security Services
Stationery & Office consummables
Travel
Utility services
Vehicle maintenance and spareparts
Vehicles
Workshop/Conference facilities
Other Goods
Other Services
Note on C7: Select from drop-down menu
Note on D7: Select from drop-down menu
Note on F7: Eg: unit, day, month, etc.
Note on J7: Use format "10-Apr-14"
Note on K7: Use format "10-Apr-2014" Leave blank if procurement is for goods
Note on M7: Not Started= Requesting Unit not contacted Procurement yet Initiated= Requesting Unit has sent request to Procurement to initiate procurement (e.g with eRequisition, draft specs/TOR, etc) Solicitation= process has been advertised or suppliers have been contacted to submit an offer Evaluation=Offers have been received and evaluation is ongoing Committee Review= If applicable, case is being reviewed by CAP/RACP/ACP Contract Mngt= Orders have been placed/contracts signed but goods/services still have to be delivered and payments to be done. Closed= All deliverables and payments have been done.

## Risk Log
RISK & ISSUE LOG MONITORING
No. | Descripiton | Date identified | Type | Impact & Probability | Countermeasures/Mgmt Response | Owner | Submitted by | Q1 Update | Q2 Update | Q3 Update | Q4 Update | Status
1 | Budget is not sufficient to accommodate PMUstaff under Mgt budget. Due to these issues will have to do a budget revision and the Fund transfer is withhold till we agree on a amicable solution | 25/03/ 2016 | Financial | Delays in forming PMUand impact project progress |  | DA | Sugandhi

## Contract Log
Quarterly Progress - Operations
Outstanding NEX advances
Date | Amount Received | Amount Reported | Amount Outstanding | Remarks
Contract Management Tool
Procurement Contracts (CWCs, ICs)
Project No. and Name | End Date of proejct | New Extension date | PO # | Vendor Name | Type of Contract | NIM/DIM | Duration of Contract |  |  | Contract Amount $ | Milestone Payments (Y/N) | Milestone Dates
00089554 _ESA | 30/ 09/ 2020 |  | 12612 | Dayananda Kariyawasam | IC | NIM | 12 MONTHS | 2015-01-12 | 30/11/2016 | 2600000 | Y | 14 DEC 2015, 31st Janu 2016, 29 Feb 2016, 25 April 2016, 25 June, 01 Nov
00089554 _ESA | 30/ 09/ 2020
00089554 _ESA | 30/ 09/ 2020
00089554 _ESA | 30/ 09/ 2020
00089554 _ESA | 30/ 09/ 2020
00089554 _ESA | 30/ 09/ 2020
Programmatic contracts (MCGA & LOAs)
Project No. and Name | End Date of proejct | New Extension date |  | Vendor Name | Type of Contract |  | Duration of Contract |  |  | Contract Amount | Milestone Payments (Y/N) | Milestone Dates

## Field Visit Log
Field Visit Monitoring
No. | VISIT PLANNED DATE | FIELD VISIT |  |  | FIELD REPORT | Follow up Actions | Remarks
|  | PURPOSE OF THE VISIT | Field Visit members | STATUS OF THE VISIT | Status
1 | 2015-02-11 | Arrangements of E Waste Drive | Sugandhi | Completed
2 | 2015-06-11 | E waste Drive Kaduwela | Sugandhgandhi, Saranga | Planned
3 | 2015-11-11 | E waste Drive Seethawake | Sugandhgandhi, Saranga | Planned
4 | 2015-12-11 | E waste DriveWattala | Sugandhgandhi, Saranga | Planned
5 | 13/ 11/2015 | E waste Drive Kelaniya | Sugandhgandhi, Saranga | Planned
6 | 16/11/2015 | Field Visit, Kaduwela | Sugandhgandhi, Saranga | Planned
7 | 18/11/2015 | Meet TEC of SWMS, Moratuwa | Sugndhi | Planned
8
9
| Visit Status |  |  | Report Status
|  | Completed |  |  | Shared with Prog. Cluster and Senior Management, saved in shared drive
|  | Delayed |  |  | Not completed
Cancelled