## Slide 1: SELAJSI
PROJECT PROGRESS
Q2 Programme Board Meeting
9th July 2015

## Slide 2: Project progress – A2J
KEY ACHEIVEMENTS | PRIORITIES FOR Q3-Q4
MoU between the MoJ and the Attorney General’s Dept for: a. expediting case flow and clearing backlog of cases of narcotics & prolonged detention b. Support extended to strengthen Mahajana Pethsam Unit at AGs department | Victim and Witness Protection Act : - Sensitizing and awareness raising programmes for: Police, JMO, Legal Aid Commission, NCPA, Court Registrars, and General Public - Technical support to establish National Authority & Police Unit
Establishment of the Area Model Case Flow Management Committee in Batticaloa (25th June) | Establishment of Case Flow Management Committees in Anuradhapura and Ratnapura
Consolidation of Penal Code and Criminal Procedure Code in Sinhala, Tamil, and English Languages completed. Initiated consolidation of Evidence Ordinance & Judicature Act. | Completing the consolidation of Evidence Ordinance and Judicature Act in 3 languages. Dissemination of Penal & Criminal Procedure code
Preliminary Draft of the National Legal Aid Policy being finalized; to be reviewed in July. | Institutional needs assessment on Case Flow within the penal chain institutions
Training on drafting legislation in English language: completed primary & intermediate courses | National Conference on Sentencing
 | Comprehensive study of existing sentencing practices: a study of reported cases
Notes: Presented by Chandrika
Key achievements:
1. MoU between the MoJ and the AG’s Dept. to expedite the case flow and clear the backlog of narcotics cases and cases of persons held in detention for prolonged periods of time. Support extended to strengthen the Mahajana Pethsam Unit at the AG’s Department.
2. Establishment of the Area Model Case Flow Management Committee in Batticaloa (25th June). Concrete steps identified towards expediting case flow within the penal chain during the next two months.
3. Completion of the consolidation of the Penal Code and Criminal Procedure Code in Sinhala, Tamil, and English Languages. Embarked on the consolidation of the Evidence Ordinance and the Judicature Act.
4. Comprehensive training course on drafting legislation in the English language for officers of the legal draftsman’s department in collaboration with the British Council. Completion of the primary and intermediate courses
Priorities:
Sensitizing programmes on the newly enacted Victim and Witness Protection Act for the Police, Court Registrars
Technical support towards establishing the National Authority & Police Division/Unit on Victim and Witness Protection. Public awareness programmes on the rights of victims and witnesses to protection
Establishment of the Case Flow Management Committees in Ratnapura and Anuradhapura.
Consolidation of the Evidence Ordinance & Judicature Act in Sinhala, Tamil, English. Print and distribution of the Penal Code and Criminal Procedure Code to the stakeholders.
Institutional Needs Assessment on Case Flow within the penal chain institutions
National Conference on Sentencing
Comprehensive study of existing sentencing practices (A study of reported cases)

## Slide 3: Project progress – A2J Prisons & Land Mediation
KEY ACHEIVEMENTS | PRIORITIES FOR Q3-Q4
Stakeholder Discussions and operationalization plans finalized for establishment of LMBs | Facilitate stakeholder discussions and the operationalization of LMBs.
Legal Aid support for Prison inmates in area models and Colombo initiated | Conduct legal aid clinics and initiating court proceedings for identified cases.
Design a hand book/ guide book for the use of Community Based Correction Officers and training for the Community Correction Officers | Completion of the draft by the experts from the Department of Community Based Corrections and trainings are completed
A committee to be established to carryout the recommendations identified in the training needs assessment of Prison Officers | The committee implement recommendations and conduct the 5 year action plan for trainings in the prisons
Notes: Presented by Sajeed

## Slide 4: Project progress – SGBV
KEY ACHEIVEMENTS | PRIORITIES FOR Q3-Q4
National Action Plan on SGBV Commenced the formulation of the National Action Plan to address GBV Commencing technical team meetings of the 09 sectors by each lead Ministry | National Action Plan on SGBV Completion of Sector Plans by Sep 2015 Completion of first due end-Nov 2015 National Consultation in December 2015 Final Draft due by end-Dec 2015
District Referral Symposiums on SGBV Conclusion of 2 multi-sectoral Referral Symposiums in Anuradhapura & Ratnapura to strengthen the SGBV referral system to respond and prevent GBV. First meetings in all 3 area models complete. | District SGBV Referral mechanism Follow-up with District Secretary to sustainably establish and strengthen the SGBV referral system at district/ divisional level. Commence with Ratnapura.
 | “Zero Tolerance of GBV” Campaign To be launched during the 16 Days of Activism in Nov 2015
Advocacy IEC Materials printed & distributed Leaflets of key service providers (strengthening referral system) Resource note books Broadcasting of Docu-drama on Rupavahini | Follow-up with Inspector General Police: on rolling out the SGBV Training Module for in-service officers and W&C desks monitoring of equipment given
 | GBV Database Finalize one common GBV format for data entry accepted by police & training workshops
Notes: Presented by Bimali:
Commence the formulation of the National Action Plan to address GBV & commencement of technical team meetings by each of the lead Ministries
Conclusion of the remaining 2 multi-sectoral Referral Symposiums in Anuradhapura & Ratnapura to strengthen the SGBV referral system to respond and prevent GBV. First meetings in all 3 area models complete.
Advocacy IEC Materials printed & distributed: leaflets of key service providers (strengthening referral system), Resource note books, broadcasting of Docu-drama on Rupavahini
PRIORITIES FOR Q3-Q4
Completion of Sector Plans by Sep 2015
Completion of draft NAP to address GBV by end Nov 2015
National Consultation in December 2015.
Final version of NAP on GBV (incorporating feedback) ready by end Dec 2015
Follow-up with district Secretary to establish a sustainable system to strengthen the SGBV referral system at district/ divisional level. Commence with Ratnapura.
Designing a campaign on “zero tolerance of GBV” – launched during the 16 Days of Activism (Nov) , exact activities to be discussed.
-printing of IEC materials, booklet on PDVA
Write to IGP on rolling out the SGBV Training Module for in-service officers as well as monitoring of equipment given and other priorities.
GBV Database – Finalizing one common GBV format for data entry accepted by police & training workshops

## Slide 5: Project Progress – SI
KEY ACHEIVEMENTS | PRIORITIES FOR Q3-Q4
Activity Plan Review Significant review and reformulation of sub-activities within the current context and towards most relevant areas of social integration, within the broad activity themes | Essential to expedite/speedup activity implementation to meet annual targets
 | Ensure the sustainability of each activities by adopting effective M&E mechanisms
Key activities identified and initiated include: Establishment of pool of volunteer bilingual facilitators Establishment of Two (02) language labs for NILET and DOL Empower Young Journalists to act as change agents for SI with special focus on conflict sensitivity reporting (institutionalizing trainings & follow-ups ) – in liaison with Ministry of Media | To create synergies and integration between activities within SELAJSI programme, but also with other UN/UNDP programmes and other SI actors
 | Establish linkage with ONUR
Notes: Presented by Shihara:
Key achievements:
The project was able to reframe sub-activities towards most sensitive and needy areas of social integration within the broad activity themes
Those are:
initiating “ establishment of pool of bilingual facilitators” (concrete systems will be established )
Initiating establishment of Two (02) language labs for NILET and DOL(putting up systems)
Initiating to liaise with Ministry of Media to empower young Journalists to act as change agents for SI with special focus on conflict sensitivity reporting (institutionalizing trainings & follow-ups )
Priorities:
Highly required to expedite/speedup implementation to meet targets
Ensure the sustainability of each activities by adopting effective M&E mechanisms
eg: Formation of “community alert groups” to address youth drug prevention possibilities at community level
Formation of well established “pool of volunteer bilingual facilitators”
Formation of committee to monitor “ conflict sensitivity reporting” after trainings
To create integration between activities

## Slide 6: Financial Overview
Partner | 2015 MINISTRY Budget |  | 1st NIM advance (released) |  | Expenditure to Date |  | Delivery Rate
 | USD | LKR* | USD | LKR* | USD | LKR* | %
MOJ | 277,925 | 37,241,950 | 20,531 | 2,751,207 | 20,128 | 2,697,098 | 7%
MWA | 99,108 | 13,280,472 | 29,537 | 3,958,017 | 24,416 | 3,271,798 | 25%
MPubAd (NLSI) | 272,585 | 36,526,390 | 11,651 | 1,561,184 | 7,693 | 1,030,898 | 3%
TOTALS | 649,618 | 87,048,812 | 61,719 | 8,270,408 | 52,237 | 6,999,794 | 8%
Partner | 2nd NIM advance (up to October) |  | Estimated Delivery Rate
 | USD | LKR* | %
MOJ | 189,988 | 25,458,423 | 76%
MWA | 43,983 | 5,893,750 | 74%
MPubAd (NLSI) | 216,418 | 29,000,000 | 84%
TOTALS | 450,389 | 60,352,173 | 77%
* Exchange rate 1USD = 134LKR
Italics = based on expenses reported, not officially recorded/released
BOLD: Actual expenses recorded and released

## Slide 7: MAIN CHALLENGES
Elections
Sustainability of interventions
  No sustainable system which continuously supports the SGBV referral system – Therefore need to convene regular district/ divisional level meetings for information sharing & monitoring such as ‘SGBV Referral Forums’. Setting up of ‘vigilant committees’ at community level. No clear procedures/directions to enable appropriate persons to attend these meetings.
  Lack of a strong network system between national level and divisions – strengthen networking between national and divisional level through the provision of an intranet/internet facilities at all divisional level offices.
Field presence - Need to strengthen field presence through dedicated officer/s for the programme
Bulk of activities to be conducted in under 6 months – PIUs to prioritise SELAJSI work and reallocate responsibilities of PIU staff as needed
Notes: Presented by Cyrene

## Slide 8: AWP Revisions/Approvals
Changes at Sub-Activity level
  Access to Justice
    Re-focus towards greater support to operationalize Victim and Witness Protection Act
    Baseline assessment of bottlenecks in law enforcement process reprogrammed  identify bottlenecks in relation to police and JMO handling of cases
    Land mediation – due to unpredictability of case load of SLMBs when established, situation to be reassessed in August and immediate re-focus of funding towards agreed back-up plan of training community mediators on gender and land
  Social Integration
    Re-focus youth intervention towards media – capacity for diversity sensitive reporting for young journalists
Notes: Presented by Cyrene

## Slide 9
Changes at Activity level – requires Board approval
  Gender Based Violence
    Study on rape – funds moved to GBV Action Plan Activity
    Rolling out of GBV Handbook for police – most of the funds moved to referral system Activity
  Social Integration
    Developing national policy on school twinning  Teachers as change agents for social cohesion; Activity reformulated
    Youth Activity – excess funds moved to establishment of language lab at NILET
    Postal delivery system in estates – funds moved to volunteerism activity

## Slide 10: Thank you.