## Sheet1
Annual Work Plan January - June2020 "Improving Municipal Governance"
Expected Output | Task | Responsible party | 2020
|  |  | 1 | 2 | 3 | 4 | 5 | 6
|  |  | Jan | Feb | Mar | Apr | May | Jun
Component A: Consolidation and effective implementation of transferred competencies and resources | A.1: Monitoring and evaluation of the implementation of the 2015-2020 Program and Action Plan for Sustainable Local Development and Decentralization
| Annual (2015,2016 & 2017 produced) The report for 2018 and first half of 2019 has been delivered to the Ministry of Local Self-Government. The report is expected to be adopted by the Government | MLSG UNDP
IT systems to support program/plan implementation through data collection and management created and in place in the MLSG
One thematic workshop organized annually to assess the progress of the program and action plan (3 regional workshops in 2019 done)
Annual Conference convened to mark decentralization milestones and 3 regional conferences in 2019 done)
Civic dialogue platform for M&E of the program established and results integrated into policy discussions
A.2: Monitoring and evaluation of local service delivery
| Quality of Life Reports produced for all municipalities in the country | UNDP MLSG Municipalities
Quality of life Report produced on National level alongside with online platform www.kvaz.mk
Annual Citizen Satisfaction Surveys (conducted three times)
“On the job” training on the application of the Quality of Life M&E system provided to relevant staff of all municipalities
Legal recommendations for legislative amendments for transfer of addtitional competencies on local level supported through provision of expertise
A.3: Innovative and improved service delivery by LSGUs
| Secondary procurement scheme for improvement of the local services through innovation (including works and supplies) implemented for up to 30 small or rural municipalities | UNDP MLSG Municipalities
One event for launching of the secondary procurement scheme and one lessons learned and results sharing event organized
Secondary procurement scheme (works and supplies) for priority projects of the regional councils and the regional centers of the eight planning regions
Workshops organized for public consultations in definyning priority projects
Analysis on the feasibility of transfer of additional competencies (newly added)
A.4: IT solutions for local administrative procedures and processes
| Prototypes of advanced e-tools developed and installed in all municipalities: (Cancelled) | UNDP MLSG Municipalities
Necessary hardware in order to secure uninterrupted us e of the software’s provided to municipalities (Cancelled)
“On the job” training on utilization of the e-tools provided to all municipalities (Cancelled)
E-prototypes for introduction of Innovative ways of local service delivery
Necessary hardware in order to secure uninterrupted use of the software’s provided to Ministry of Local Self-Government
Component B: Facilitation of transfer and successful execution of additional competencies and resources, aimed at ensuring smart, comprehensive andsustainable local development | B.1 Activity Preparation of a comprehensive Assessment Report and enacting further improvements to the existing local social services and outsourcing framework
| Assessment report produced | UNDP MLSG Municipalities
Subsequent legislative amendments supported through provision of expertise (Cancelled)
Analysis of the status of the Neighbrhood units in Republic of North Macedonia
One consultative event organized (on validation of the analysis and providing additional input by relevant experts in the field)
Two consultative events organized (on validation of the assessment tolls and the findings and recommendations (Cancelled)
Comparative analysis for legislative amendments for transfer of addtitional competencies on local level supported through provision of expertise (newly added)
B.2: Support to establishment of local integrated and inclusive development frameworks
| "On the job” training provided on the basis of upgraded training materials and Integrated and Inclusive Local Development Plans prepared for a group of thirty (30) municipalities | UNDP MLSG Municipalities
B.3: Integration of all generated training materials, best practices and information on project activities into an e-Knowledge Platform on Local Development
| A national integrated system for data bases and knowledge management created for easy and efficient sharing of relevant data/information, knowledge products and results | UNDP MLSG
Component C: Continuation of the fiscal decentralization | C.1: Enabling the Ministry of Finance and selected municipalities to issue municipal bonds to finance priority capital investment projects
Manual on issuing municipal bonds updated and upgraded with a module on borrowing and disseminated to all municipalities in the country (Cancelled)
Comparative analysis on local government borrowing and issuing municipal bonds in the neighbouring countries (and in EU member states)
| Training on borrowing and in particular on issuing bonds for financing capital investment delivered to the staff of all municipalities and other involved stakeholders (two day’s workshop) | UNDP MF
“On the job” training delivered and feasibility studies completed on issuing bonds for capital investments for five municipalities
Financial analysis and draft legislative amendments on local financing (newly added)
C.2: Preparation and delivery of a comprehensive capacity development Program for all 81 LSGUs, covering efficient tax collection, stable financial management and internal financial control
Capacity Needs Assessment realized
| Capacity Development Program designed and curriculum developed around four high-priority training modules | UNDP
| Roster of 8 national experts/trainers created | MF
| ToT delivered for all trainers (one workshop) | Municipalities
All 81 LSGUs trained (with participation of minimum one finance officer per municipality) and a course of 16 workshops organized (four per training module)
Training concept and materials adopted and codified by the relevant MoF departments
C.3: Comparative Analysis of Local Revenue Systems in EU Countries and Feasibility Study on New and Applicable Municipal Revenue Instruments in the Country Context
| Comparative analysis of the local revenue systems in EU countries | UNDP
| Feasibility study on new and applicable municipal revenue instruments prepared in a consultative manner | MF
| Consultative event organized | Municipalities
Legal recommendations on improving financial sustainability of the municipalities regarding the newly transferred competencies comparted to other EU countries (newly added)
* the activities marked in red have been completed
** the activities marked in yellow are newly added