# EMPOWERING MUNICIPAL COUNCILS PROJECT

# WORK PLAN: January 1 – December 31, 2018

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIME FRAME | Responsible party | PLANNED BUDGET | Expected results |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of funding | Budget description | Amount in CHF |  |
|  | Organisation of Advisory Project Board Meeting | X |  |  | X | UNDP |  |  |  | During the 2018, the Project Board will meet at least twice. If needed, and at the request of its members, it may meet more frequently. |
| Outcome 1: Municipal councils become more autonomous bodies, better able to withstand the executive’s influence, by properly fulfilling their constitutionally assigned roles of oversight and representation. |
| Output 1.1: Capacity Development Programme delivered through classroom trainings to 250-300 councillors (at least one-third of whom are women); | Delivery of classroom training for capacity development Organization of the events (trainings) for training modules 1 -11 for 6 partner municipalities | X X | X X | X X | X X | UNDP/AFO UNDP/AFO | SDC SDC | Account 72145: – Service contract training and educational services (AFO) Account 75700: - Trainings and workshops | 71.250 CHF 31.000 CHF | Classroom trainings delivered for 6 municipalities in the period March – November 2018 (60-80 participants – at least one third of whom are women) XX trainings delivered to 60 – 80 councilors from 6 municipalities (at least one third are woman); members of Budget and Financing and equal opportunity Committees; members of different political parties, etc. |
|  | 1.1.3 Transportation costs for participants | X | X | X | X | UNDP/AFO | SDC | Account 72100: Transportations costs | 6.750 CHF | Expenditures for the municipal councilors participation at the trainings reimbursed or organized transport ensured |
| Output 1.2: E-knowledge platform designed and used by one-fourth of all councillors and institutionalized and made available to all 1,347 councillors | Creating interactive contents, exercises, knowledge tests and certificate options for training course completion for each module. Continuous populating of the e-knowledge platform with resource and reference materials relevant to the role and mandate of the councillors | X | X | X X | X X | UNDP/AFO | SDC | Account 72145: Service contract training and educational services (AFO) Account 72145: Service contract training and educational services (AFO) |  | Interactive contents, exercises, knowledge tests and certificate options for training course completion for each module created. |
| Output 1.3: Capacities of councillors built for improved transparency, accountability and citizens’ participation by adopting at least one innovative measure in 24 municipalities. | Creation of a group of councillors to serve as an innovation-focused sounding board for the project Installation of the e-dashboard on the municipal websites of the six directly selected municipalities and population with data on the budget execution Design of innovative ICT based tools and design and implementation of innovative citizen’s participation initiatives | X X | X X X | X X X | X X X | UNDP/AFO | SDC | Account 75700: Training, Workshops and Conferences Account 72145: Service contract training and educational services (AFO) Account 72100: Contractual Services – Companies | 72.000 CHF | Group of councillors to serve as an innovation-focused sounding board for the project Created E-dashboard installed on the municipal websites of the six directly selected municipalities and population with data on the budget execution Innovative ICT based tools and innovative citizen’s participation initiatives designed and implemented in the six directly selected municipalities |
| Outcome 2: Municipal policies are designed in a participatory manner to better meet citizens’ needs through increased transparency and accountability of municipal bodies. |
| Output 2.1: Municipal grants scheme implemented that supports priority community projects in each of 24 municipalities. | 2.1.1 Grants for supporting of 6 municipal councils |  |  | X | X | UNDP/AFO | SDC | Account 72600: Grants | 300.000 CHF | Municipal grants scheme implemented that supports priority community projects in the six directly selected municipalities through public consultations |
|  | 2.1.2. Conduction of the procedure for selection of the new 9 municipalities to work with during 2019 |  | X | X | X | UNDP | SDC |  |  | The procedure for selection conducted and the new 9 municipalities to work with during 2019 selected |
| Output 2.2: At least one mechanism for citizen participation in decision making such as community and budget forums utilized for setting community priorities in each of 24 municipalities. | 2.2.1 Preparation of the Assessment of the rate of applying newly gained knowledge by councilors during municipal budget preparation and adoption |  |  | X | X | UNDP/AFO | SDC | Accout 72145: Service contract training and educational services (AFO) |  | Assessment of the rate of applying newly gained knowledge by councilors during municipal budget preparation and adoption prepared |
|  | 2.2.2 Provision of support in organization and delivery of community forum events conducted by the 6 directly selected municipalities. |  |  | X | X | UNDP/AFO | SDC |  |  | Community forums organised and delivered as per the SDC methodology |
| Outcome 3: Improvements of the legal and institutional framework within which municipal councils function are initiated and sustained through a functional and institutionalized national network of councillors. |
| Output 3.1: Off-line and online network created in which one-fourth of all councillors participate | Creation of thematic groups consisting of 15-25 councillors each belonging to the Financing and Budget Committee, Equal Opportunities Committee, Inter-Community Relations Committee and other committees under the councils of the local self-government units (e.g. urban planning, social services). Events logistics (national events, hosting international events and study trips) Preparation of Annual and Semi-Annual Analytical Reports on the Municipal Revenues and Expenditures Design of opinion polls for councillors and analysis of responses and needs, through the e-knowledge platform. Establishment of on-line focus groups of councillors. Monitoring of networking activities and opinions and exploring opportunities to address needs. Organisation of networking events for councilors (Development of Annual calendar of events) | X X | X X X X X X X | X X X X | X X X X X | UNDP/ZELS UNDP/ZELS | SDC SDC | Account 72145: (ZELS) Account 75700: Trainings, workshops and conferences Account 71300: National municipal financing expert | 14.400 CHF 51.825 CHF 5.929 CHF | Thematic groups consisting of 15-25 councillors each belonging to the respective committees created. National events, international events and study trips organized Annual (2017) and Semi-Annual (2018) Analytical Reports on the Municipal Revenues and Expenditures prepared Opinion polls for councillors and analysis of responses and needs, through the e-knowledge platform designed At least 5 on-line focus groups of councillors established Networking activities and opinions monitored and opportunities to address needs explored. Networking events for councilors organised (Annual calendar of events developed) |
| Output 3.2: Exposure to regional and global best practices in empowered municipal councils | 3.2.1 Travel and accommodation for international events | X | X | X | X | UNDP/ZELS | SDC | Account 71600: Travel and Accommodation | 8.000 CHF | Travel and accommodation for international events organised |
| Cross-cutting | Project Management Preparation of a 2018 work plan and Budget Preparation of a 2019 work plan and Budget | X X | X | X | X X | UNDP | SDC | Account 64300: Program Quality Assurance (Head of Team) - Chief Technical Advisor for Governance Account 64300: Transparency and Accountability/Citizen Participation Specialist – Governance Programme Analyst Account 64300: Program Operations Support Account 64300: Communications Officer Account 71400: National Project Manager/Decentralization and Local Development Specialist/Advisor Account 71400: National Monitoring and Evaluation Officer Account 71400: Research assistant Account 71400: Capacity development and IMC specialist Account 71400: National Social Inclusion and Gender specialist Account 71400: National Project Associate Account 71400: Driver Account 71300: National evaluation expert Account 18000: Project vehicle Account 72400: Office equipment Account: 74500 Miscellaneous Account 73100: Office rent Account 73100: Running costs office Account 72100: Office material Account 72100: Running costs vehicles Account 72400: Communications costs Account: 74500 Miscellaneous Account 74200: Media PR/Visibility Account 72100: Maintenance, upgrade and hosting of the project web site and the e-knowledge platform Account 74200: Design of audio, video and graphic products and printing Account 74200: Translation Account 71600: Study tours and events for long term experts_Staff1 Account 71600: Study tours and events for long term experts_Staff2 | 20.463 CHF 20.861 CHF 4.050 CHF 5.621 CHF 28.715 CHF 21.499 CHF 16.056 CHF 17.052 CHF 10.673 CHF 17.205 CHF 2.360 CHF 3.953 CHF 8.273 CHF 232 CHF 1.807 CHF 10.080 CHF 7.115 CHF 2.471 CHF 3.500 CHF 2.241 CHF 2.000 CHF 10.560 CHF 1.500 CHF 10.000 CHF 26.250 CHF 6.410 CHF 6.410 CHF | Overall management, strategic guidance, project oversight and quality assurance provided and effective linkages with other UNDP initiatives ensured. Integration of citizen participation tools and platforms in the capacity development activities with emphasis on the application of innovative tools and practices ensured. Quality assurance of the overall financial management and the funds administered by UNDP, including budgeting and accounting of resources in accordance with the organization’s Financial Regulations and Rules and to organize and facilitate the auditing of the project provided. Communication and Visibility plan of the project prepared and implemented Day-to-day management of the project conducted Monitor and report on the progress of implementation of the project conducted Research and analysis of relevant data and information undertaken Project field activities coordinated and monitored Social inclusion and gender equality in all project components and activities mainstreamed Financial duties related to implementation of the project activities conducted Project web site and the e-knowledge platform maintained, upgraded and hosted Audio, video and graphic products designed and printing Written, consecutive and simultaneous translation provided Study tours and events organised Study tours and events organised |

| PLANNED BUDGET (TOTAL) CHF | 828.511 |
| --- | --- |
| Note: Additional activity – Audit services (financed by UNDP) CHF | 15.000 |