## Instruction_Workplan (hidden)
Costed Work Plan for CCM Funding Agreements
- As part of the CCM Funding Agreement, the Costed Work Plan is a legal document that supports the disbursements to cover the CCM Activities and CCM Secretariat costs financed by the Global Fund, as per the CCM Guidelines.
- The CCM Secretariat should always keep the track and documentation on the estimation of costs presented in this Costed Work Plan.
- The information reflected in this document will serve to track the execution of activities and the detailed budget that will be kept by the CCM for accountability purpose, LFA verification and Audits.
- The Costed Work Plan contains 5 sections 1. General Information 2. Fixed costs and HR positions covered by the CCM Funding Agreement 3. CCM Activities 4. Co-funding 5. Special conditions
- In general, only the yellow cells can be filled in free format. Some drop-downs (cells in grey) and formulas are part of the document, we request to please not modify them, in order to obtain a standardized document across all the CCMs financed by the Global Fund.
-The Section 1 "General information" reflects the basic information about the CCM Funding Agreement
- At the top of the document the table "Grand Total" shows the final amount to be covered by the CCM Funding Agreement. It coincides with the corresponding year amount highlighted in the Facesheet.
The Section 2 "Fixed costs and HR positions covered by CCM Funding Agreement" includes any CCM Secretariat recurrent cost. This category containes 2 separated tables to summarize the fixed costs, making sure the categories are grouped so that there is one "Cost Grouping" per line, and the costs related to the Human Resources.
- The Section 3 "CCM Activities" shows the planning of activities throughout the year, and the corresponding budget. The list of activities is standard for all the CCMs, any detailed or specific name that could refer to the CCM budget can be added in the assumptions or comments column.
- Inside the table of the Section 3, the column "Total No of Activities" must quantify the number of activities planned for the year as per the information filled in the columns "M1…M12". The column "Budget" shows the total cost for the line in the agreed currency (US$/EUR) for the CCM Funding.
- The Columns "Costs Grouping" and "Performance Area" respond to the approved terms by the Global Fund.
- The table of the section 4 "Co-funding" is mandatory only if the 3-year budget is above USD 300,000. However, all the CCMs invited to include the total financial needs for an ideal functionning of the CCM.
- The Section 5 "Special Conditions" summarizes the status of the listed Special Conditions of the CCM Fundig Agreement
- Please refer to the Spreadsheet "Definitions" for a detailed description of all the Cost Groupings and the Performance Areas used in this Costed WorPlank.
- Please refer to the Spreadsheet "Lists" for a complete overview of all the category options you can use to fill this Costed Work Plan.
Version August 2017

## Instructions_Plan de travail
Plan de travail chiffré pour les Accords de financement des CCM
-Dans le cadre de l'Accord de financement du CCM, le plan de travail chiffré est un document juridique qui soutient les décaissements pour couvrir les coûts des activités du CCM et du Secrétariat du CCM financés par le Fonds mondial, conformément aux Lignes directrices du CCM.
- Le Secrétariat du CCM doit toujours conserver la trace et la documentation sur l'estimation des coûts présentée dans ce plan de travail chiffré.
- L'information contenue dans ce document servira à suivre l'exécution des activités et le budget détaillé qui seront conservés par le CCM à des fins de responsabilité, de vérification de l'ALF et d'audit.
- Le plan de travail chiffré est composé de 5 sections: 1. Information générale 2. Coûts fixes et les postes de RH couverts par l'accord de financement du CCM 3. Activités du CCM 4. Co-financement 5. Conditions spéciales
- En général, seules les cellules jaunes peuvent être remplies en format libre. Certaines listes déroulantes (cellules en gris) et les formules font partie du document, nous vous demandons de ne pas les modifier, et ce afin d'obtenir un document standardisé pour tous les CCM financés par le Fonds mondial.
-La section 1 "General Information" ("Information générale") reflète les informations de base de l'Accord de financement du CCM
- En haut du document, le tableau "Grand Total" indique le montant final couvert par l'Accord de financement du CCM. Il coïncide avec le montant de l'année correspondante surligné dans la Facesheet.
- La section 2 "Fixed costs and HR positions covered by CCM Funding Agreement" ("Frais fixes et postes de RH couverts par l'Accord de financement du CCM") comprend tout coût récurrent du Secrétariat du CCM. Cette catégorie contient 2 tableaux séparées pour résumer les coûts fixes, en s'assurant que les catégories sont regroupées de sorte qu'il y ait un "groupement des coûts" ("Cost Grouping") par ligne et les coûts liés aux ressources humaines.
- La section 3 "CCM Activities" ("Activités du CCM") montre la planification des activités tout au long de l'année et le budget correspondant. La liste des activités est standard pour tous les CCM, tout nom détaillé ou spécifique qui pourrait se référer au budget du CCM peut être ajouté dans la colonne des hypothèses ou des commentaires.
- Dans le tableau de la section 3, la colonne "Total of activities" ("Nombre total d'activités") doit quantifier le nombre d'activités prévues pour l'année selon les informations remplies dans les colonnes "M1 ... M12". La colonne " Budget" indique le coût total de la ligne dans la devise convenue (US $ / EUR) pour le financement du CCM.
- Les Colonnes "Cost Grouping" ("Groupement de coûts") et "Performance Area" ("Zone de performance") répondent aux termes approuvés par le Fonds mondial.
- Le tableau de la section 4 "Co-financing" ("Co-financement") est obligatoire uniquement si le budget pour 3 ans est supérieur à USD 300,000. Cependant, tous les CCM ont été invités à inclure les besoins financiers totaux pour un fonctionnement idéal.
- La section 5 "Special Conditions" ("Conditions spéciales") résume l'état des conditions spéciales énoncées dans l'Accord de financement du CCM.
- Veuillez vous référer à la feuille de calcul "Definitions" (disponible uniquement en anglais) pour une description détaillée de tous les groupements de coûts et des zones de performance utilisées dans ce plan de travail chiffré.
- Veuillez consulter la feuille de calcul "Lists" (liste disponible uniquement en anglais) pour un aperçu complet de toutes les options de catégorie que vous pouvez utiliser pour remplir ce plan de travail chiffré.
Version Août 2017

## Instrucciones_Plan de trabajo (hidden)
Plan de trabajo costeado para los Acuerdos de financiamiento de los MCP
- Como parte del Acuerdo de Financiación del MCP, el Plan de trabajo costeado es un documento legal que apoya los desembolsos para cubrir los costos de las actividades del MCP y de la Secretaría del MCP financiados por el Fondo Mundial, de acuerdo con las Directrices del MCP.
- La Secretaría del MCP debe guardar siempre un registro y la documentación sobre la estimación de costos presentada en este Plan de trabajo costeado.
- La información reflejada en este documento servirá para rastrear la ejecución de las actividades y el presupuesto detallado que mantendrá el MCP para fines de rendición de cuentas, verificación del ALF y Auditorías.
- El Plan de trabajo costeado tiene 5 secciones: 1. Información general 2. Costos fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP 3. Actividades del MCP 4. Contrapartida 5. Condiciones especiales
- En general, sólo las celdas amarillas se pueden rellenar en formato libre. Algunos desplegables (celdas en gris) y fórmulas forman parte del documento, solicitamos no modificarlos, a fin de obtener un documento estandarizado para todos los MCPs financiados por el Fondo Mundial.
-La Sección 1 "General Information" ("Información general") refleja la información básica sobre el Acuerdo de financiamiento del MCP
- En la parte superior del documento, el cuadro "Grand Total" muestra el monto final que será cubierto por el Acuerdo de financiamiento del MCP. Coincide con la cantidad del año correspondiente resaltada en la Facesheet.
- La Sección 2 "Fixed costs and HR positions covered by CCM Funding Agreement" ("Costos fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP") incluye cualquier costo recurrente de la Secretaría del MCP. Esta categoría contiene 2 tablas separadas para resumir los costos fijos, asegurándose de que las categorías se agrupan de manera que haya una "Agrupación de Costos" ("Cost Grouping") por línea y los costos relacionados con recursos humanos.
- La Sección 3 "CCM Activities" ("Actividades del MCP") muestra la planificación de las actividades a lo largo del año y el presupuesto correspondiente. La lista de actividades es estándar para todos los MCP, cualquier nombre detallado o específico que pudiera referirse al presupuesto del MCP se puede agregar en la columna de supuestos o comentarios.
- Dentro de la tabla de la Sección 3, la columna "Total No of Activities" ("Número Total de Actividades") debe cuantificar el número de actividades previstas para el año según la información presentada en las columnas "M1 ... M12". La columna "Budget" ("Presupuesto") muestra el costo total de la línea en la moneda acordada (USD/EUR) para el financiamiento del MCP.
- Las columnas "Costs Grouping" ("Agrupación de costos") y "Performance Area" ("Área de desempeño") responden a los términos aprobados por el Fondo Mundial.
- El cuadro de la sección 4 "Co-funding" ("Contraparte") es obligatorio únicamente si el presupuesto a 3 años supera los USD 300.000. Sin embargo, todos los MCPs fueron invitados a incluir las necesidades financieras totales para un funcionamiento ideal del MCP.
- La Sección 5 "Condiciones Especiales" resume el estado de las Condiciones Especiales del Acuerdo de Fundación del MCP
- Consulte la pestaña "Definitions" (únicamente disponible en inglés) para obtener una descripción detallada de todas las agrupaciones de costos y las áreas de desempeño utilizadas en este Plan de trabajo costeado.
- Consulte la pestaña "Lists" (únicamente disponible en inglés) para obtener una descripción completa de todas las opciones de categoría que puede utilizar para llenar este Plan de trabajo costeado.
Versión Agosto 2017

## Instruction_Report (hidden)
Annual Expenditure report CCM Funding Agreements
- The Expenditure report is a document reflecting the annual execution of activities and financial use of the resources approved in the relative Costed Work Plan. It will be kept by the CCM Hub for accountability purpose, LFA verification and Audits.
- The CCM Secretariat should always keep the track and documentation on the expenses presented in this report.
- The Expenditure report contains 6 sections: 1.General information 2.Fixed costs and HR positions covered by CCM Funding Agreement 3.CCM Activities 4.Co-funding 5.Conditions 6.Cash Reconciliation
- In general, only the yellow cells and the grey cells concerning the approved budget can be filled in free format. Some drop-downs and formulas are part of the document: we request to please not modify them, in order to obtain a standardized document across all the CCMs financed by the Global Fund. |  |  | BUDGET | EXPENDITURE | ABSORPTION
-The Section 1 "General information" reflects the basic information about the CCM Funding Agreement. | GRAND TOTAL (Fixed Costs + Activities) =
- At the top of the document the table "Grand Total" shows the final annual amount (Budget) covered by the CCM Funding Agreement and the actual Expenditure, both in assolute terms and as a percentage of the approved budget. These cells contain formulas: they are automatic populated, and cannot be freely filled.
- The Section 2 "Fixed costs and HR positions covered by CCM Funding Agreement" includes any CCM Secretariat recurrent cost. This category containes 2 separated tables to summarize the fixed costs, making sure the categories are grouped so that there is one "Cost Grouping" per line, and the costs related to the Human Resources. For each line, the CCM Secretariat should provide both the established annual budget, as per the relative Costed Work Plan, and the actual expenditure.
- The Section 3 "CCM Activities" shows the implementation, throught the year, of the activities planned in the relative Costed Work Plan. The list of activities is standard for all the CCMs, any detailed or specific name that could refer to the CCM budget can be added in the last column, as a comment.
Inside the table of the Section 3, the column "Total Activities approved" must quantify the number of activities planned for the year, as per the information filled in the relative Costed Workplan. The column "Budget" shows the total cost for the line in the agreed currency (US$/EUR) for the CCM Funding. For each line, the CCM Secretariat should also provide the actual number of activities put into practice, the total annual budget approved, as per the relative Costed Work Plan, and the actual expenditure. | Total Activities approved | Total Activities executed | Budget approved | Expenditure
- The Columns "Costs Grouping" and "Performance Area" respond to the approved terms by the Global Fund. | Cost Grouping | Performance Area
- The table of the Section 4 "Co-funding" is mandatory only if the 3-year budget is above USD 300,000. However, all the CCMs are invited to include in the Costed Work Plan co-funded activities.
- The Section 5 "Special Conditions" summarizes the status of the listed Special Conditions of the CCM Funding Agreement. The CCM Secretariat is required to fill only those cells that do not contain formulas, and cannot be automatically populated.
- The Section 6 "Cash Reconcililation" summarizes the cash outflow and cash balance at the end of the annual period reflected in this report. The CCM Secretariat is required to fill only those cells that do not contain formulas, and cannot be automatically populated.
-Please refer to the Spreadsheet "Definitions" for a detailed description of all the Cost Groupings and the Performance Areas used in this Expenditure report.
-Please refer to the Spreadsheet "Lists" for a complete overview of all the category options you can use to fill this Expenditure report
Version August 2017

## Costed_Workplan_Year2
CCM FUNDING AGREEMENT - COSTED WORK PLAN
Section 1. General Information
CCM Name: |  | CCM Mali
CCM Agreement No: |  | MAL-CFUND-1706
Starting Date: |  | 2016-10-01 | [7 empty] | GRAND TOTAL (Fixed Costs + Activities) = |  |  |  |  | 87657 |  | EUR
Year of Agreement: |  | Year 2
Currency: |  | EUR
Section 2. Fixed costs and HR positions covered by CCM Funding Agreement
2A. Fixed Costs | [13 empty] | 2B. HR positions covered by this agreement
No. | Cost Grouping | Performance Area | Description | Total Year (in USD/EUR) |  | Assumptions / comments | [6 empty] | No. | CCM Secretariat positions | [5 empty] | Assumptions / comments
1 | Human Resources | Alignment | Human Resources (Secretariat staffs) | 35100 |  | EUR 45,368: le salaire calculé sur la base de la grille du PNUD NOC GP et NOB Ch suiv Eval (cf grilleen Annexe). CCM Hub Comment: le niveau de Ressources Humaines doit être en ligne avec le niveau de l'année précedente. On approuve le montant de EUR 35,100 | [7 empty] | Description |  |  | No. of positions financed by other sources | No. of positions financed by GF | Total No. of positions
2 | Communication Material and Publications | Alignment | Overhead cost (itemized fees to manage CCM funding) | 4593 |  | Website maintainance ( 335,38 par mois) , translation ( 568). | [6 empty] | 1 | Executive Secretary |  |  |  | 1 | 1 | Salary for the Senior manager : EUR 1174 salary brut including employee social contributions+ Part patronale 20% INPS + 6,56% AMO
3 | Non-health Equipment | Alignment | Office Equipement | 2900 | [8 empty] | 2 | Oversight Officer |  |  |  | 1 | 1 | Salary for the Monitoring-Evaluation Officer : EUR 1103 Salaire Brut including employee social contributions+ Part patronale 20% INPS + 6,56% AMO
4 | Indirect and Overhead Costs | Alignment | Vehicule maintenance | 1632 |  | Augmentation legère du carburant de 1212 à 1500 | [6 empty] | 3 | [5 empty] | 0
5 | Indirect and Overhead Costs | Alignment | Office rental and supplies | 3968 |  | Phone+Internet connectiity. Ajout de 548 pour les frais de communication du Président et vice président à raison de 274 par personne. | [6 empty] | 4 | [5 empty] | 0
|  |  | Total | 48193 | [13 empty] | 2
Section 3. CCM Activities
Number of Activities
|  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
No. | Cost Grouping | Performance Area | Activities | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total No. Activities | Budget (in USD/EUR) | Assumptions / Comments
1 | Travel-related Costs | Alignment | CCM Plenary / General Assembly meeting | [12 empty] | 8 | 2283 | CCM Meetings: Meeting room + coffee break for 35 participants x EUR 3.8 (EUR 133) + travel costs for 11 people (civil society members ) + for 10 people ( members of Governemnt ) EUR 7.62 x 20 (EUR 152,4). 4 General meetings + 4 Extraordinary meetings. nous devions conduire la Note Concept Paludime en 2018, Pour cela on a besoin d'AG pour valider les demandes de Financement.. | bar: Q1 M2 to Q1 M3; Q2 M5 to Q2 M6; Q3 M8 to Q3 M9; Q4 M11 to Q4 M12
2 | Travel-related Costs | Oversight | Oversight Committee meetings | [12 empty] | 8 | 1397 | Meeting room + coffee break for 27 participants x EUR 3,8 (EUR 103) + travel costs for 10 members * EUR 7,62 (EUR 72,6) Remplacement des mebres venant des regions avec tion des frais de voyage et des perdiems CCM Hub commentaire: merci de bien noter que le per diem est permis seulement pour les membres de la Société Civile! CCM: C'est OK | bar: Q1 M1; Q1 M3 to Q2 M4; Q2 M6 to Q3 M7; Q3 M9 to Q4 M10; Q4 M12
3 | Travel-related Costs | Alignment | Technical Working groups meetings | [12 empty] | 5 | 914 | Meeting room (CCM) + coffee break for 18 participants x EUR 3,05 (EUR 54,90) + travel costs for 15 CCM members * EUR 7,62 (EUR 114,3). CCM Mali: en 2018, nous devions reviser le Reglement Interieur et autres textes reglementaires, exigeant des seances de validation et de compte rendu aux membres | bar: Q1 M1; Q2 M4; Q3 M7; Q4 M10; Q4 M12
4 | Travel-related Costs | Oversight | Site Visits / Monitoring Visits | [12 empty] | 3 | 16922 | Site visits: Rental of three four-wheel drive vehicle for 08 days (EUR 76.22/day) (EUR 76.22x 08 days x 1vehicle) = EUR 609,76+ Accommodation and perdiems for 06 people (EUR 53.36 x 06 people x 08 days) (EUR 2561,28) +Accommodation and perdiems for the driver (EUR 53.36 x02 driver x 08 days) (EUR 853,76) + 100 litres of fuel per visit (100 xEUR 1.01 x2vehicles x 08 days) = EUR 1616 (5640,8 par visite de site) Nous avions reduit la visite de site à 3 visites par an avecla reduction du nombre de person ne et du nombre de jour sur le terrain. CCM Mali: Nous avions tenue compte de la remarque en effet pendant les missions les personnes ressources autres que la socité civile particpent aux visites et recoivent les perdiems sauf les PTFs. CCM Hub: merci de vous conformer au règlement du Fonds Mondial. Per diem pour qui n'est pas membre de la Soc. Civile n'est pas accepté. Pour les autres membres seulement une couverture des coûts est permise. | bar: Q2 M4; Q3 M8; Q4 M11
5 | Travel-related Costs | Alignment | Workshops, Meetings for Funding Request development | [12 empty] | 1 | 183 | Meeting room (CCM) + coffee break for 18 participants x EUR 3,05 (EUR 54,90) + travel costs for 15 CCM members EUR 7,62x 15 (EUR 114.3) | bar: Q3 M7
6 | Travel-related Costs | Constituency Engagement | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | [12 empty] | 5 | 3966 | Ateliers de retro-information à la socité civile à Bamako transport (25*7,25*2) 361+ coffe break ( 3,8*2*25)190 +lunch (7,22*25*2)361 =912. Ségou transport Bko segou 2 membres (30,4)+ ( (25*7,25) 361+ coffe break ( 3,8*25)95 +lunch (7,22*25)180,5+ perdiem 2 nuités (53,3*2*2) 213,2 =699,6. Kayes transport Bko Kayes 2 membres (30,4*2) 60,2+ transport partcipants (25*7,25) 361+ coffe break ( 3,8*25)95 +lunch (7,22*25)180,5+ perdiem 2 nuités (53,3*2*2) 213,2 =730. Sikasso transport Bko Sikasso 2 membres (30,4*2) 60,2+ transport partcipants (25*7,25) 361+ coffe break ( 3,8*25)95 +lunch (7,22*25)180,5+ perdiem 2 nuités (53,3*2*2) 213,2 =730, Mopti: transport Bko-Mopti-Bko 2 membres (30,4*2=60,98)+transport participants (7,25*25=181,25)+coffe break (3,8*30=114)+lunch (7,25*30=217,5)+perdiem (53,3*2*3 nuitées=319,8), soit 893,53, Les per diems pour les membres de la Société Civile sont acceptés. | bar: Q1 M1; Q1 M3; Q2 M6; Q3 M9; Q4 M11
7 | Travel-related Costs | Constituency Engagement | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | [12 empty] | 1 | 424 | Atelier elaboration du plan de travail de la societé civile Meeting room (CCM) + coffee break for 20 participants x EUR 3,8 (EUR 76,) + travel costs for 15 CCM members EUR 7,62x 15 (EUR 114.3) + lunch for 20 participants x 7,22 (144,4 Euros) + Bloc notes GF for 18 participants x 1,1 (20,6 euros) + 2 boites Marqueur x 09 (1,83 euros) + 2 paquets Chemises à rabat 4,6 x 2 (9,15 euros) +stylo paquet de 50 x 6,9 (6,86 euros) + Flip Chart 2 x 4,6 (9,15 euros)+ Rame tirage pour photocopie 2 x 23,3 (46,6 euros) | bar: Q1 M2
8 | Travel-related Costs | Alignment | Workhops, Meetings and Training | [12 empty] | 1 | 785 | Atelier de renforcement du capacité des membres du CCM sur le Code d'ethique Meeting room (WHO ) + coffee break for 56 participants x EUR 3,8 (EUR 212,8) + lunch ( 56*7,22) 404,3 travel costs for 22 CCM members EUR 7,62x 22 ) (EUR 167,64) | bar: Q2 M6
9 | Travel-related Costs | Constituency Engagement | Constituency engagement meetings (specify in comments) | [12 empty] | 1 | 939 | Atelier de renforcement de la soicté civile ( role et responsabilités, mobilisation des ressources, droits humains et Genre) Meeting room (l'atelier s'étale sur 3 jours pour traiter profondement les thèmes) (CCM) + coffee break for 18 participants x EUR 3,8 x 3jrsx (EUR 205,2 + travel costs for 15 CCM membersx3jrsx EUR 7,62= (EUR 326,25), lunch (7,22x3jrsx18 pers= 389,88 Euros)+ Bloc notes GF for 18 participants x 1,1 (17,6 euros) | bar: Q2 M5
10 | Travel-related Costs | Alignment | Workhops, Meetings and Training | [12 empty] | 1 | 5499 | Revision du Manuel et Procedures de gestion. Meeting room (CCM) + coffee break for 54 participants x EUR 3,05 x 2 jours (EUR 329.4) + lunch break (EUR 9,15 X 54 participants x 2 jours = EUR 988.2) + travel costs for 22 people ( EUR 7.62 x 22 x 2 jours =EUR 335,28) + travel cost for consultant (EUR 2'359.76) + Perdiem for consultant EUR 1'486,38 (EUR 495.46 X 3 x1) | bar: Q2 M5
11 | Travel-related Costs | Alignment | Workhops, Meetings and Training | [12 empty] | 1 | 3445 | Atelier d'information du Public ( autorités Publiques , Partenaires, secteur privé ) sur la gestion de la Subvention au Mali. Meeting room (Hotel ) 600 euros + coffee break for 80 participants x EUR 3,8 (EUR 304) + lunch ( 80 *18,2) EUR 1456 travel costs for 30 civil socity members EUR 7,62x 30 ) (EUR 228,6) Média (600 euros), 80 partipants case ( bloc note, stylo, chemise ) 3,2*80 (256 euros) | bar: Q4 M10
12 | Travel-related Costs | Constituency Engagement | Workhops, Meetings and Training | [12 empty] | 1 | 2707 | Il est proposé le partage des réponses des popiulations clés aux trois maladies sous forme d'atelier de documentation, Paratge d'expériences de réponse de réseaux de populatins clés contre la maladie transport 30 personnes de population clés (30x1jrx7,62 euros= 228,9)+ coffee break (35x1jrx3,8 = 133 euros)+ lunch (35x7,25=253,75 euros)+ supports pédagogiques 35x7,62 = 266,7 euros)+ location salle (1x1jrx137,2=137,2 euros)+ kakemono (5x281= 1686 euros), soit au total 2705,25 euros. | bar: Q4 M11
13 | [15 empty] | 0
14 | [15 empty] | 0
15 | [15 empty] | 0
[17 empty] | 39464 | * Has to be detailed if the yearly activity line budgeted is over 10'000 per annum.
Section 4. Co-funding
No. | Cost Grouping | Performance Area | Description of funding support | Q1 M2: Budget (in USD/EUR); Q2 M4: Source of financing; Q3 M8: Comment
1
2
3
4
5
0
Section 5. Special conditions
|  |  | Expected | Q1 M1: Approved; Q1 M3: Variance; Q2 M5: Comments
CCM Secretariat positions (headcount) - Maximum (number of position) |  |  | 2 | Q1 M1: 2; Q1 M3: 0
Civil Society engagement: 15% of the budget - Minimum (Please detail the lines and amounts to be taken into account in the comment section) (in USD/EUR) |  |  | 13148.55 | Q1 M1: 10891.6667; Q1 M3: -2256.8833; Q4 M11: 0.12425
Co-funding - Minimum (in USD/EUR) The amount expected represents the minimum to be co funded for the 3 years agreement. |  |  | 0 | Q1 M3: 0
Version August 2017

## Instrucciones_Informe (hidden)
Informe de gastos de los Acuerdos de financiamiento de los MCP
- El Informe de gastos es un documento que refleja la ejecución anual de las actividades y el uso financiero de los recursos aprobados en el Plan de trabajo costeado. El CCM Hub lo guardará para fines de rendición de cuentas, verificación del ALF y auditorías.
- La Secretaría del MCP debe siempre mantener el registro y la documentación sobre los gastos presentados en este informe.
- El Informe de gastos contiene 6 secciones: 1.Información general 2.Cambios fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP 3. Actividades del MCP 4.Contrapartida 5.Condicciones 6. Reconciliación de Caja
- En general, sólo las celdas amarillas y las celdas grises relativas al presupuesto aprobado pueden rellenarse en formato libre. Algunos desplegables y fórmulas forman parte del documento: solicitamos no modificarlos para obtener un documento estandarizado para todos los MCPs financiados por el Fondo Mundial.
-La Sección 1 "General Information" ("Información general") refleja la información básica sobre el Acuerdo de financiamiento del MCP | GRAND TOTAL (Fixed Costs + Activities) =
- En la parte superior del documento, el cuadro "Grand Total" muestra el importe anual final (Presupuesto) cubierto por el Acuerdo de financiamiento del MCP y el gasto real, tanto en términos absolutos como en porcentaje del presupuesto aprobado. Estas celdas contienen fórmulas: son automáticamente pobladas, y no se pueden llenar libremente.
- La Sección 2 "Fixed costs and HR positions covered by CCM Funding Agreement" ("Costos fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP") incluye cualquier costo recurrente de la Secretaría del MCP. Esta categoría contiene 2 tablas separadas para resumir los costos fijos, asegurándose de que las categorías se agrupan de manera que haya una "Agrupación de Costos" ("Cost Grouping") por línea y los costos relacionados con recursos humanos. Para cada línea, la Secretaría del MCP debe proporcionar tanto el presupuesto anual establecido, según el Plan de trabajo costeado, como el gasto real.
- La Sección 3 "CCM Activities" ("Actividades del MCP") muestra la implementación, durante el año, de las actividades planificadas en el Plan de trabajo costeado correspondiente. La lista de actividades es estándar para todos los MCP, cualquier nombre detallado o específico que pudiera referirse al presupuesto del MCP se puede agregar en la última columna, como un comentario.
- Dentro de la tabla de la Sección 3, la columna "Total Activities approved" ("Total de Actividades aprobadas") debe cuantificar el número de actividades planificadas para el año, según la información contenida en el Plan de trabajo costeado correspondiente. La columna "Budget" ("Presupuesto") muestra el costo total de la línea en la moneda acordada (USD/EUR) para el financiamiento del MCP. Para cada línea, la Secretaría del MCP también debe proporcionar el número real de actividades puestas en práctica, el presupuesto anual total aprobado, según el Plan de trabajo costeado accordado, y el gasto real. | Total Activities approved | Total Activities executed | Budget approved | Expenditure
- Las columnas "Costs Grouping" ("Agrupación de Costos") y "Performance Area" ("Área de Desempeño") responden a los términos aprobados por el Fondo Mundial. | Cost Grouping | Performance Area
- El cuadro de la Sección 4 "Co-funding" ("Contrapartida") es obligatorio sólo si el presupuesto de 3 años es superior a USD 300.000. Sin embargo, se invita a todos los MCP a incluir en el Plan de trabajo costeado actividades cofinanciadas.
- La Sección 5 "Special Conditions" ("Condiciones Especiales") resume el estado de los Condiciones Especiales enumeradas del Acuerdo de financiamiento del MCP. La Secretaría del MCP debe llenar sólo aquellas celdas que no contienen fórmulas, y que no pueden ser rellenadas automáticamente.
- La Sección 6 "Cash Reconcililation" ("Reconciliación de caja") resume las salidas de caja y saldo de caja al final del periodo anual que se refleja en este informe. La Secretaría del MCP debe llenar sólo aquellas celdas que no tienen fórmulas, y que no pueden ser rellenadas automáticamente.
- Consulte la pestaña "Definitions" (únicamente disponible en inglés) para obtener una descripción detallada de todas las agrupaciones de costos y las áreas de desempeño utilizadas en este Informe de gastos.
- Consulte la pestaña "Lists" (únicamente disponible en inglés) para obtener una descripción completa de todas las opciones de categoría que puede utilizar para llenar este Informe de gastos.
Versión Agosto 2017

## Definitions
Instructions
A. General instructions
1 | Which worksheets to complete | The CCM funding application requires the CCM to complete the following worksheets: ► Performance framework ► Detailed budget - Period 1 including detailed assumptions ► Detailed budget - Period 2 including detailed assumptions ► Co-Payment ► CCM funding request form
The following forms will be automatically generated: - Work plan - Summary budget per performance area, per Cost Grouping and per source of fund (SOF)
Additionally the CCM may include other worksheets or attachments to provide additional information to support the detailed budget e.g. to support a costing assumption.
2 | Recommended steps in completing the template | ! CAUTION : PLEASE NOTE THAT THIS TEMPLATE CONTAINS MACROS. You should ensure that you have the right setting: On the Menu Bar, Select “Tools”, then move the cursor over “Macro” and select “Security”. From the options select “Medium” and then select “Ok”. Close the file and re-open it. You will receive a security warning. Select “Enable Macros”. This will enable all the features of the Budget Toolkit to be fully active.
3 | Cell formatting | Below the applicant is taken through an explanation of the intended data to be entered in each column of the template. Note that most cells have fixed formatting which should not be adjusted unless absolutely necessary.
6 | Information sources | If applicants have any technical difficulty in using this template or are unsure about any aspect of it, guidance may be obtained from the Global Fund through sending an e-mail to ccm@theglobalfund.org
B. Specific instructions for data entry, by each column header - Menu
| Column header | Instructions | Possible check? | Comments | Additional information available
| Menu | ►Region, Country, CCM are to be selected from the drop down lists. ►Enter in the name of the recipient organization. The GF Secretariat will enter the Agreement number.
C. Specific instructions for data entry, by each column header - Performance Framework
| Column header | Instructions | Possible check? | Comments | Additional information available
Section A. General information
| Funding start date | ►Enter Day, Month and Year (numeric values) for the intended start of the funding period. Final date will be determined by the Global Fund based on completion of the application review process. |  | The CCM should plan the starting date 2 months after the complete documentaiton has been submitted to the GF Secretariat CCM Team.
| Year 1 and Year 2 | This section gives information on the reporting periods over the funding term, dates when progress updates and disbursement requests (PUDR) are due. Based on a 12 continuous month periods, the cells will be populated automatically. The reporting periods could be aligned with national reporting cycle. For any change in the proposed format, pls submit your request to the CCM Team. | Progress Update and Disbursement request are due one month upon completion of Q3 and Q7 (month 10 and month 22 respectively).
| Section B. Overall goal and objective | Goal and Objectives are broad and overarching statements of long term outcome of the program and should be consistent with the strategy defined by the CCM during the planning exercise. ►Each strategic objective should be in line with the Performance areas defined by the Global Fund. |  |  | Definition Sheet in the Application template and 'Step by step guide to CCM Funding'.
| Section C. Performance Framework | Performance Area ►Select a key Performance Area as defined under Section B above. A drop-down list shows the areas applicable to CCM funding. This field cannot be overwritten.
| Section C. Performance Framework | Selection of Indicator(s): ► Indicator #1 ' % of planned oversight activities completed with documented participation by all CCM constituencies' is compulsory. All CCMs applying for expanded funding should provide base line data and set targets (intended results) for this indicator. ► Subsequent indicators are to be selected from the GF core list, in line with the overall objectives defined in Section B above. The CCM Team recommends that the maximum number of indicators for a two year plan is five. ► On exceptional cases, CCMs can propose to measure an indicator outside the GF core list of indicators. Those indicators will have to be reviewed and approved by the CCM Team before the funding request can be finalized by the CCM and submitted to the GF. ► Indicators should be numbered sequentially in the first column of this section. | Information has to be provided in all cells relating to each indicator. The indicator number cell will turn RED when information is missing. |  | Detailed information about the indicators is included in the 'step by step guide to CCM funding'
| Section C. Performance Framework | Setting baselines ►baselines must be provided for each of the selected indicator with a clear data source, ideally a reference document. If baselines cannot be given at the onset of the program, they should be established. Setting targets ►targets should be cumulative and set according to when the indicators will be measured. Tied to other donors (Y/N) ►Whether the target reflects solely Global Fund financing through the current grant (Tied Yes - activities are funded solely by the current grant) or co-financed (Not tied when targets are not directly tied to GF financing, when GF resources contribute and thus are shared between all donors involved). Baselines include targets ►In this column you should select 'Yes' or 'No' from the drop down list to indicate whether or not baselines are included in each target. In general, the baseline is to be included. | For baselines, supporting documentation will have to be provided for future verification by the LFA.
D. Specific instructions for data entry, by each column header - Detailed budgets Period 1 and Period 2
As noted above, when a line of data is entered in the "Detailed budget - Year 1" the same Reference Number, objective, Performance Area, activity and Cost Grouping will automatically be repeated on the Year 2 detailed budget sheets ("Detailed budget - Year 2"). Note that it does not mean that each activity line has to be completed with cost data (i.e. with unit cost and quantity data) in each year. If there is no budget data for an activity in a year, you should enter zeros. If you have a NEW activity in "Detailed budget - Year 2" you must enter the activity in "Detailed budget - Year 1" (with zero cost in year 1), so that the activity is automatically copied into the following years.
!Caution: Applicants should not add any totals or sub-totals in any worksheet within the template as this will interfere with the logic of the budget summaries.
Applicants will note that the detailed budget worksheets ("Detailed budget - Year 1" and "Detailed budget Year 2" ) are automatically totaled and analyzed into the summary budget worksheet ("Summary budget, by Cost Grouping, Performance Area and source of fund (SOF)"). This involves the use of pivot tables that have been pre-set to analyze the data input. Applicants should not attempt to adjust these tables as this may corrupt their functioning.
| Column header | Instructions | Possible check? | Comments | Additional information available
| Objective Number | This number refers to the objective defined in section B - Overall goals and objectives in the performance framework worksheet and for which a budget activity is to be defined.
| Performance Area | The performance area will be populated automatically based on the information provided in Section B of the performance framework sheet.
| Activity | In the column you should describe clearly and concisely, the planned budget activity. The wording should be consistent with that used in the work plan.
| Directly related indicator | This column has been included to easily show the link between the budget and the Performance Framework. A reference should be entered where the activity matches with a target within the Performance Framework. The number entered should be the indicator number referenced in the Performance Framework. | Cross check from the Performance Framework to see that all directly related budget activities show a reference to the relevant indicator
| Assumptions | This column requires a short description of the detailed assumptions used to arrive at the budget amount and may make cross reference to a detailed document submitted with this request for funding. Budget assumptions should provide sufficient information to be able to determine how unit quantities and unit costs were calculated. | Confirm that the assumptions spelled out comply with the requirement that all key assumptions, including unit costs and quantities should be provided.
| Cost categories | This is a drop down list of 8 defined cost categories. Each budget activity should be associated with a Cost Grouping. For further description of the categories refer to the Definition table. | Check that the allocation follows the Global Fund Cost Grouping descriptions contained in the guidelines. Ensure costs are eligible for GF funding as per the definition and limitations stated in this section of the application form. | CCMFunding_Expanded_Application form, Section on 'Definitions' in Instructions worksheet.
| Measurement unit | This is the unit of measurement to which the unit cost (in the next column) refers. It will depend on the nature of the activity and the complexity of the costing method. Examples may include: monthly salary cost per person, cost per meeting, cost of a site visit, etc. Note that costs such as Human Resources showing a simple multiplication of unit cost by quantity may not be appropriate in the template. Applicants should explain the detailed assumptions of Human Resources costs in the worksheet "detailed assumptions" or refer to a separate document. | Ensure clear and concise information is provided for LFA and GF review of the application. | Ensure the costs are eligible as per the definition table.
| Unit cost | This is the unit cost of the item described in the preceding column in the currency defined in Section A. General information - Performance Framework worksheet. Budget assumptions should provide sufficient information to be able to determine how unit costs were calculated. If the item is costed in a currency other than the proposed currency, the working to convert the unit cost to the defined currency should be shown in the "Detailed assumptions" worksheet. If there is a differential unit cost for the same activity line in the same quarter then a separate row should be added in the budget, and the calculation explained in the "Detailed assumptions worksheet".
| Quantity | This will be the actual quantity for which the cash budget is required. Note: budget assumptions should provide sufficient information to be able to determine how unit quantities were calculated. | Where the activity has a directly related target in the Performance Framework, ensure the budget is consistent with the Performance Framework.
| Total amount | This cell contains a formula which multiplies the Unit cost by the Quantity by quarter in Years 1 and 2. | No specific checks proposed
| Total quantity Period 1 / Total quantity Period 2 | This is a formula which sums the four quarterly quantities to give the annual quantity. | Where the activity has a directly related target in the Performance Framework, ensure the budget is consistent with the Performance Framework. If there are differences, this should be explained in the "Detailed assumptions" worksheet.
| Total amount Period 1 / Total amount Period 2 | This is a formula which sums the four quarterly budget amounts in the proposal currency to give the annual budget. | Ensure the reported amounts are accurate.
E. Other Sources of funding (SOF)
| Column header | Instructions | Possible check? | Comments | Additional information available
CCMs applying for more than USD100,000 per year are required to report in this section the source of funds and amounts mobilized as required under the CCM funding policy.
| Summary funding distribution | Global Fund Amount The cells corresponding to 'GF Funding amount' will be populated automatically based on the information provided in sheets 'detailed budget Year 1' and 'detailed budget Year 2' . | Amounts specified under this section of the report are accurate and supported by clear documentation for future verification. |  | Guidelines for CCM Funding
Source of funds (SOF)1, 2, etc ►For each non GF funding you will specify the funding source and the amount committed for the CCM. ►Under Section 2 of the form (Section 2 Detailed funding information) you will have to specify the percentage of this amount going to ‘Secretariat support Costs’ and the percentage going specifically to support directly CCM performance costs. ►For the amount to support CCM performance costs, you are then required to specify the percentage which is allocated for each performance area (oversight, constituency engagement, alignment, capacity building / gender).
F. CCM funding request form
| Column header | Instructions | Possible check? | Comments | Additional information available
Section A: budget summary
| A1 to A7 | Information in this section will be uploaded with data entered in different parts of the form. | Verify information in this section of the report is accurate and matches information entered in other parts of the form (detailed and summary budgets).
Section B: recipient entity information
| B1 | Name of the recipient entity is populated automatically. ►Sector has to be specified.
| B2 to B5 | ►Complete information has to be entered | Ensure all information is complete and accurate.
Section C: CCM approval
|  | ►Name and title information has to be provided for each CCM Member. The funding application is completed only when it has been signed by all members. Original document is to be submitted to the Global Fund Secretariat. | Ensure all information is complete and accurate.
| Others | Others significant costs which do not fall under the above-defined cost group. Costs under this cost group are to be clearly specified.
Definitions
NOTE: The CCM Secretariat should always keep the track and documentation on the estimation of costs and the variation agains the budget.
| Cost grouping | General Description | Limitations
| Human Resources | Salaries, wages and related costs (pensions, incentives, supplements, top ups, and other employee benefits, etc.) relating to all employees (including field personnel), and employee recruitment costs. Eligible costs under this cost grouping are the salaries of CCM Secretariat staff. | (i) Secretariat staff should not exceed 2 persons. (ii) Scope of work for key personnel is to be submitted to the GF CCM Team for approval. (iii) CCM funding shall not be used to remunerate CCM members. (iv) Salaries must be commensurate with national salary scales.
| Travel-related Costs (includes meetings' expenses) | Workshops, meetings, training publications, training-related travel, including training per-diems. Do not include human resources costs related to training which should be included under the Human Resources category. Constituency consultations for non government constituencies only (e.g. civil society) and processes to promote and improve the quality of stakeholder participation, including travel costs for civil society participation. Eligible costs under this group of activities includes (i) CCM general meeting expenses, travel costs for members to attend CCM meetings, CCM support costs. (ii) Expendable equipment, office supplies, travel, field visits and other costs relating to program planning and administration. Legal, accounting costs, bank charges, etc. | (i) Ideally CCMs should meet no more than on a quarterly basis with a maximum of 6 meetings per year. (ii) Each grant should have at least one field visit per year, but no more than two. Exceptions could be granted if related to low performing grants. (iii) not more than 10 persons attending the field visit. (iv) Non members invited by the CCM should not exceed 20% of the total membership. (v) Do not include CCM Secretariat staff or consultancy fees, as these costs are to be included in the Human Resources and Technical Assistance categories described above. (vi) Constituency meetings should follow a CCM meeting, ideally no more than on a quarterly basis with a maximum of 6 meetings per year. (vii) Constituency meetings should not include more than 20 persons. (viii) CCM Secretariat staff costs or consultancy fees are not included in this category as they are to be included in the Human Resources and Technical Assistance categories described above
| External Professional Services | Costs of all consultants (short or long term) providing technical or management assistance. This includes all costs related to the consultant such as consulting fees, travel and per-diems, field visits and other consultant costs relating to program planning. Technical Assistance may be used for technical or management assistance to support core CCM functions including civil society participation, program oversight and alignment with other national bodies. This includes all costs related to the consultant such as fees, travel and per-diem, field visits and other costs related to program planning and supervision. | (i) CCM funding cannot be used for hiring consultants to write proposals for Global Fund financing. (ii) Terms of reference for consultants hired by the CCM must include a specific clause prohibiting the writing of proposals by the consultant hired.
| Non-health Equipment | This category covers office furniture and equipment (laptop, beamer, digital camera, photocopier, etc). | (i) Vehicle purchase or vehicle long term lease are not eligible costs.
| Communication Material and Publications | Communication materials including printed materials and communication costs associated with core CCM functions (e.g., call for proposals, periodic reports of implementation status, minutes of meetings, website cost, newsletter, translation of key information, printing).
| Indirect and Overhead Costs | Overhead costs such as office rent, utilities, internal communication costs (mail, telephone, internet), insurance, fuel, security, cleaning. Management or overhead fees. | (i) Overhead costs are to be itemized and should not exceed 20% of the overall budget.
| Performance Areas | Definition
| Oversight | Oversight activities as Oversight commitees' meeting, visits and document sharing with CCM members
| Constituency engagement | Communication activities completed by he CCM to engage constituencies government and non -government.
| Alignment | Activities to ensure Global Fund grants that are consistent with impact/outcome indicators in national strategy documents, relevant national bodies and other donors support.
| Capacity Building Gender | Activities to ensure CCM members are trained on them role and training to strenghten CCM representatives role.
| Sustainability and Transition | Activities to engage the CCM is prepared for and is taking into account sustainability and transition problematic in the response to the fight against the diseases as country.

## Sheet5 (hidden)
OrganizationName
CCM Afghanistan
CCM Albania
CCM Algeria
CCM Angola
CCM Armenia
CCM Azerbaijan
CCM Bangladesh
CCM Belarus
CCM Belize
CCM Benin
CCM Bhutan
CCM Bolivia
CCM Bosnia and Herzegovina
CCM Botswana
CCM Bulgaria
CCM Burkina Faso
CCM Burundi
CCM Cambodia
CCM Cameroon
CCM Cape Verde
CCM Central African Republic
CCM Chad
CCM Colombia
CCM Comoros
CCM Congo (Democratic Republic)
CCM Congo (Republic of)
CCM Costa Rica
CCM Cote d'Ivoire
CCM Croatia
CCM Cuba
CCM Djibouti
CCM Dominican Republic
CCM Ecuador
CCM Egypt
CCM El Salvador
CCM Equatorial Guinea
CCM Eritrea
CCM Ethiopia
CCM Fiji
CCM Gabon
CCM Gambia
CCM Georgia
CCM Ghana
CCM Guatemala
CCM Guinea
CCM Guinea-Bissau
CCM Guyana
CCM Haiti
CCM Honduras
CCM India
CCM Indonesia
CCM Iran (Islamic Republic of)
CCM Iraq
CCM Jamaica
CCM Kazakhstan
CCM Kenya
CCM Kosovo
CCM Kyrgyzstan
CCM Lao PDR
CCM Lesotho
CCM Liberia
CCM Macedonia
CCM Madagascar
CCM Malawi
CCM Malaysia
CCM Mali
CCM Mauritania
CCM Mauritius
CCM Moldova
CCM Mongolia
CCM Montenegro
CCM Morocco
CCM Mozambique
CCM Myanmar
CCM Namibia
CCM Nepal
CCM Nicaragua
CCM Niger
CCM Nigeria
CCM Pakistan
CCM Panama
CCM Papua New Guinea
CCM Paraguay
CCM Peru
CCM Philippines
CCM Romania
CCM Rwanda
CCM São Tomé and Príncipe
CCM Senegal
CCM Serbia
CCM Sierra Leone
CCM Solomon Islands
CCM South Africa
CCM South Sudan
CCM Sri Lanka
CCM Sudan
CCM Suriname
CCM Swaziland
CCM Syria
CCM Tajikistan
CCM Tanzania
CCM Thailand
CCM Timor Leste
CCM Togo
CCM Tunisia
CCM Turkmenistan
CCM Uganda
CCM Ukraine
CCM Uzbekistan
CCM Viet Nam
CCM Yemen
CCM Zambia
CCM Zanzibar
CCM Zimbabwe
Non-CCM Coordination Committee for Prevention and Fight with HIV/AIDS
Non-CCM DPR of Korea
Non-CCM Palestine
Non-CCM Somalia
Non-CCM West Bank and Gaza Strip
RCM Abidjan-Lagos Corridor Organisation
RCM Elimination of Malaria in Mesoamerica and Hispaniola Island (EMMIE)
RCM Organisation of Eastern Caribbean States
RCM Pan Caribbean Partnership against HIV/AIDS (PANCAP)
RCM Regional Steering Committee for the Regional Artemisinin Initiative (RAI)
RCM Southern Africa Regional Coordinating Mechanism (SARCM)
RCM Western Pacific
RO African Network for the Care of Children Affected by HIV/AIDS (ANECCA)
RO AIDS and Rights Alliance for Southern Africa and Enda Santé (ARASA-ENDA)
RO Alliance Nationale Contre le Sida (ANCS)
RO Asia Pacific Network of People Living with HIV/AIDS (APN+)
RO Australian Federation of AIDS Organisations (AFAO)
RO Caribbean Vulnerable Communities Coalition (CVC) and El Centro de Orientación e Investigación Integral (COIN)
RO Center for Health Policies and Studies (PAS Center)
RO Central American Network of People with HIV (REDCA+)
RO East Europe and Central Asia Union of PLHIV (ECUO)
RO East, Central and Southern Africa Health Community (ECSA-HC)
RO Elimination 8 (E8)
RO Eurasian Coalition on Male Health (ECOM)
RO Eurasian Harm Reduction Network (EHRN)
RO Handicap International (HI)
RO Humanist Institute for Cooperation with Developing Countries, Southern Africa (HIVOS)
RO Intergovernmental Authority on Development (IGAD)
RO International Community of Women Living with HIV/AIDS (ICW Latina)
RO International HIV/AIDS Alliance (IHAA)
RO International HIV/AIDS Alliance in Ukraine (IHAU)
RO International Organization for Migration (IOM)
RO International Treatment Preparedness Coalition - West Africa (ITPC-WA)
RO Kenya AIDS NGOs Consortium (KANCO)
RO Latin American and Caribbean Network of Transgender People (REDLACTRANS)
RO Lubombo Spatial Development Initiative 2 (LSDI-2)
RO Middle East and North Africa Harm Reduction Association (MENAHRA)
RO Organismo Andino de Salud - Convenio Hipólito Unanue (ORAS CONHU)
RO RedTraSex
RO Regional Oversight Mechanism for Latin America
RO Southern African Development Community Secretariat
RO Youth Leadership, Education, Advocacy and Development (Youth LEAD)
RCM Africa Regional Coordinating Mechanism