United Nations Development Programme

Country: Montenegro

PROJECT DOCUMENT

| Project Title | Catalyzing financial sustainability of the protected area system in Montenegro |
| --- | --- |
| UNDAF Outcome(s)/Indicator(s): (Link to UNDAF outcome., If no UNDAF, leave blank) | By 2011, Public Institutions with the support of Civil Society Organizations (CSO) are better able to ensure good governance, rule of law and equal access to justice and promotion of human rights. |
| Expected Outcome(s)/Indicator(s): (CP outcomes linked to the SRF/MYFF goal and service line) | CPD C. Environmentally responsible economic development |
| Expected Output(s)/Indicator(s): (CP outputs) | CPAP 4.2.4 Improved management of protected areas |
| Implementing partner: (designated institution/Executing agency) | United Nations Development Programme (UNDP) |
| Brief Description The total funding currently available for the planning and administration of the protected area system (PAS) of Montenegro is estimated to be at least 50% below what is required for its effective management. With the incremental expansion of the PAS (in part, as a result of the activities undertaken in a counterpart GEF-funded project, Strengthening the sustainability of the PA system of Montenegro), this funding gap is expected to increase even further. The project will focus outputs and activities at two levels of intervention: (i) the national PA system level, through working with different public institutions and agencies in order to develop and strengthen their capacity to effectively secure and administer funds for the protected area system; and (ii) the level of individual protected areas in northern Montenegro, through working with a range of stakeholder groups to diversify and increase the available funding to, and develop more cost-efficient systems for management and administration of funds for, those protected areas |

Agreed by (Government): Minister for Spatial Planning and Environment

Mr. Branimir Gvozdenovic

NAME						SIGNATURE				Date/Month/Year

Agreed by (UNDP/Executing Entity/Implementing Partner): UN Resident Coordinator &UNDP Resident Representative

Mr. Alexander Avanessov

NAME						SIGNATURE				Date/Month/Year

TABLE OF CONTENTS

PART I: SITUATION ANALYSIS	5

1.1. Context, global significance, environmental, institutional and policy background	5

Environmental context	5

Protected area system	6

Socio-economic context:	8

Institutional context	8

Legislative context	10

1.2	Threats and root-causes	11

1.3	Desired long-term vision and barriers to achieving it	11

1.4	Stakeholder analysis	13

1.5	Baseline analysis	15

PART II: STRATEGY	17

2.1	Project Rationale and Conformity to GEF Policies and Strategic Objectives	17

2.2	Country Ownership: Country Eligibility and Country Drivenness	18

2.3	Design principles and strategic considerations	18

2.4	Project Objective, Outcomes and Outputs/Activities	20

2.5	Financial modality	32

2.6	Indicators, Risks and Assumptions	32

2.7	Cost Effectiveness	34

2.8	Sustainability	35

2.9	Replicability	36

PART III: PROJECT RESULTS FRAMEWORK	37

PART IV:  MANAGEMENT ARRANGEMENTS	43

PART V:  MONITORING FRAMEWORK AND EVALUATION	44

PART VI: LEGAL CONTEXT	48

PART VII: ANNEXES	49

Annex I: Risk Analysis	49

Annex II: Terms of Reference for Key Project Positions	50

Annex III: Stakeholder Involvement Plan	54

Annex IV: METT, Capacity Development and Financial Scorecards	58

SIGNATURE PAGE	59

ACRONYMS

| APR | Annual Project Report |
| --- | --- |
| AWP | Annual Work Plan |
| BD | Biodiversity |
| BCA | Benefit Cost Analysis |
| CBNRM | Community Based Natural Resource Management |
| CBO | Community-Based Organization |
| CO | UNDP Country Office |
| CPAP | Country Programme Action Plan |
| CVM | Contingent Valuation Method |
| EA | Executing Agency |
| EIA | Environmental Impact Assessment |
| EIS | Environmental Information System |
| EPA | Environmental Protection Agency |
| EPF | Environment Protection Fund |
| EU | European Union |
| GDP | Gross Domestic Product |
| GEF | Global Environment Facility |
| GIS | Geographic Information System |
| GTZ | German Technical Cooperation |
| HDI | Human Development Index |
| IA | Implementing Agency |
| IFC | International Finance Corporation |
| IR | (Project) Inception Report |
| IUCN | International Union for the Conservation of Nature |
| IW | Inception Workshop |
| M&E | Monitoring and Evaluation |
| MAFWR | Ministry of Agriculture, Forestry and Water Resources |
| MED | Ministry of Economic Development |
| METT | Management Effectiveness Tracking Tool |
| MPA | Marine Protected Area |
| MSPE | Ministry of Spatial Planning and Environment |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NEX | National Execution |
| NFP | National Forestry Policy |
| NGO | Non-Government Organization |
| NP | National Park |
| NPAFP | National Protected Area Financial Plan |
| NPI | Nature Protection Institute |
| NR | Nature Reserve |
| NSSD | National Strategy for Sustainable Development |
| NTO | National Tourism Organization |
| PA | Protected Area |
| PAs | Protected Areas |
| PAS | Protected Area System |
| PENP | Public Enterprise National Parks |
| PES | Payment for Ecosystem Services |
| PEWG | Park Establishment Working Group |
| PIR | Project Implementation Review |
| PM | Project Manager |
| PMU | Project Management Unit |
| PoWPA | (CBD) Programme of Work on Protected Areas |
| PSC | Project Steering Committee |
| PTR | Project Technical Report |
| RCU | UNDP-GEF Regional Coordination Unit |
| RP | Regional Park |
| SBAA | Standard Basic Assistance Agreement |
| SMP | Strategic Management Plan |
| SME | Small and Medium-sized Enterprises |
| SO | Strategic Objective |
| SPA | Special Protection Areas |
| TBD | To be determined |
| TBWP | Total Budget and Work Plan |
| TCM | Total Cost Method |
| TEV | Total Economic Valuation |
| TOR | Terms of Reference |
| UN | United Nations |
| WWF | Worldwide Fund for Nature |

# PART I: SITUATION ANALYSIS

### 1.1. Context, global significance, environmental, institutional and policy background

#### Environmental context

- Montenegro became the 192nd member of the UN on 28 June 2006. It is a small (13,812km2) mountainous country located in south-eastern Europe and borders Bosnia & Herzegovina to the north-west, Serbia  the north, Kosovo to the north-east, Croatia and the Adriatic Sea to the south-west, and Albania to the south-east.  The maritime zone of Montenegro extends up to 12 nautical miles out to sea and is some 2,500 km2 in extent.

- Montenegro is a mountainous country with a very wide array of ecosystems and habitat types, especially for a country of its size.  The terrain of Montenegro ranges from high mountains along its borders with Serbia, Kosovo and Albania, through a segment of the Karst of the western Balkan Peninsula, to a narrow (2-10 km wide) coastal plain. The coastal plain disappears completely towards the hinterland, where Mount Lovcen and other ranges plunge abruptly into the inlet of the Gulf of Kotor. The coastal region is noted for its seismic activity.  Montenegro's section of the Karst lies generally at elevations of 1000 meters above sea level, although some areas rise to 1,900m such as Mount Orjen (1,894m) the highest massif among the coastal limestone ranges. The lowest part of the central inland area is in the Zeta River valley. The central lowland plain is a flat-floored, elongated depression typical of karstic regions. The underlying geology is predominantly limestone, which dissolves to form sinkholes and underground caves. The high mountains of the northern inland parts of Montenegro include some of the most rugged terrain in Europe, and act as a major watershed for several surrounding countries. They average more than 2000 meters in elevation (e.g. Bobotov Peak in the Durmitor Mountains reaches 2,523 meters). The mountains of Montenegro were the most ice-eroded section of the Balkan Peninsula during the last glacial period. Montenegro also includes the second longest canyon in the world (82km long and up to 1,300m depth), the Tara River canyon.  Due to the sharp changes in relief, the climate changes rapidly from a Mediterranean climate at the coast to a sub-alpine climate on the highest mountains.

- With 3,250 plant species, Montenegro is considered as one of the most floristically diverse areas of the Balkan Peninsula. It has a species-area index for its vascular flora of 0.837, the highest of all European countries (Stevanovic. et al 2000).  Montenegro also forms part of the Mediterranean Basin ‘biodiversity hotspot’, one of 153 centers of globally significant floral diversity. The number of Balkan vascular floral endemics in Montenegro is very high, with 392 taxa (~7% of the total vascular flora) recorded, markedly in the high mountain areas of the country. Of particular global significance are the 46 locally endemic vascular plants, mostly comprising Tertiary relicts. The remaining flora of Montenegro includes around 1,093 species of freshwater algae, approximately 1,500 species of marine algae (300 of which are macro algae) and 589 species of bryophytes. In addition, some 284 species of lichens have been recorded, and some 2000 species of fungi are estimated.

- Terrestrial invertebrates in Montenegro have been poorly studied. The best studied groups include Mollusks (323 species of which 136 land snail species are of international biodiversity significance, most of which are relictual endemics), Oligochaetes (27 species) and Arthropods (~16,000 – 20,000 species). About 295 fish species have been recorded in the waters of Montenegro, of which some 90 species are freshwater and more than 205 marine. There are 56 species of amphibians and reptiles. The coastal region of Montenegro and its hinterland – in particular the Skadar Lake, Lovćen and Prokletije - are considered the most significant centers of biodiversity of reptiles and amphibians on the Balkan Peninsula and in Europe. Of a total of 526 European bird species, 297 (or 57%) can be found regularly in Montenegro, with several additional species (~29 species) registered as occasional visitors. With 204 nesting bird species, Montenegro has a species-area index for nesting birds of 0.557, considerably higher than the figure for the entire Balkans (0.435). Lake Skadar, shared with Albania, is one of the most important wintering sites for waterfowl in Europe. Sixty five species of terrestrial mammals have been recorded within the territory of Montenegro.

#### Protected area system

- The Government of Montenegro adopted the National Strategy for Sustainable Development (NSSD) in 2007. The NSSD promotes the establishment of a national ‘network of protected areas’, and the expansion of this network to ensure that all ‘ecosystems (are represented under a formal) protection regime’ (NSSD 2007). The new Law on Nature Protection (No. 51/08), adopted in 2008, makes provision for six categories of protected areas: Strict/ Special Nature Reserves; National Parks; Regional Parks/ Nature Parks; Natural Monuments; Protected Habitats; and Landscapes with Outstanding Features. In addition to protected areas, the Law also prescribes protection regimes that apply to certain species and to geological and paleontological objects. National Parks are designated and managed in terms of the new Law on National Parks (No. 56 of 2009).

- The national protected area system (PAS) currently covers 133,309 ha, or 9.7% of the territory (see Table 1). The largest portion (103,695ha or ~78%) of the PAS is represented by the 5 national parks – Durmitor, Skadar Lake, Lovćen, Biogradska gora and the recently proclaimed Prokletije - and their constituent nature reserves, some 500ha in extent. The remaining protected areas, comprising a total of 28,964ha (~22% of the PAS), includes: 41 Natural Monuments; four Landscapes with Outstanding Features; and one area protected by Municipal decision (equivalent to the Landscapes with Outstanding Features category).

Table 1: Formal national protected areas of Montenegro

| Protected areas names (by national protection category) | Surface (ha) | Share of the total territory |
| --- | --- | --- |
| National parks | 103,695 | 7.5% |
| Skadarsko jezero | 40,000 |  |
| Lovcen | 6,400 |  |
| Durmitor | 33,895 |  |
| Biogradska gora | 5,400 |  |
| Prokletije | ~18,000 |  |
| Nature reserves | 650 | 0.044% |
| NP Skadar Lake: Manastirska tapija, Panceva oka, Crni zar, Grmozur, Omerova glavica | 420 |  |
| NP Durmitor: Crna Poda | 80 |  |
| Tivat Saltpans | 150 |  |
| Natural Monuments | 13,641.5 | 0.99% |
| Djalovica gorge | 1,600 |  |
| Lipska cave | - |  |
| Magara cave | - |  |
| Globocica cave | - |  |
| Spila cave at Trnov/ Virpazar | - |  |
| Babatusa cave | - |  |
| Novakovica cave at Tomasevo | - |  |
| Duboki do pit at Njegusi | - |  |
| Piva river canyon | 1,700 |  |
| Komarnica river canyon | 2,300 |  |
| Communities of Pinetum mughi montenegrinum at Ljubišnja (1,000 ha), Durmitor (5,200 ha) and Bjelasica (400 ha) | 6,600 |  |
| Communities of Pinus heldraichii in Orjen (300 ha), Lovćen (300 ha) and Rumija (100 ha) | 700 |  |
| Individual dendrological sites: Quercus robur scuteriensis at Curioc near Danilovgrad, Quercus pubescens in Orahovac near Kotor, olive trees at Mirovica, Old Bar and Ivanovići, Budva, etc. | - |  |
| Beaches of the Skadar Lake | (<2) |  |
| Long beach Ulcinj | 600 |  |
| Little beach Ulcinj | 1.5 |  |
| Beach Valdanos | 3 |  |
| Beach Velji pijesak | 0.5 |  |
| Beach Topolica, Bar | 2 |  |
| Beach Sutomore | 4 |  |
| Beach Lucica, Petrovac | 0.9 |  |
| Beach Canj | 3.5 |  |
| Beach Pecin | 1.5 |  |
| Buljarica | 4 |  |
| Beach Petrovac | 1.5 |  |
| Beach Drobni pijesak | 1 |  |
| Beach Sveti Stefan | 4 |  |
| Beach Milocer | 1 |  |
| Becici beach | 5 |  |
| Slovenska plaza, Budva | 4 |  |
| Beach Mogren | 2 |  |
| Jaz | 4 |  |
| Beach Przno | 2 |  |
| Savinska Dubrava in Herceg Novi | 35.46 |  |
| Botanical reserve of laurel and oleander, above Sopot spring near Risan | 40 |  |
| Botanical garden of mountain flora in Kolasin | 0.64 |  |
| Botanical garden of general Kovacevic in Grahovo | 0.93 |  |
| Njegos and July 13 Parks in Cetinje | 7.83 |  |
| Park of the hotel Boka in Herceg Novi | 1.2 |  |
| City park in Tivat | 5.9 |  |
| Park of the Castle at Topolica | 2 |  |
| Landscapes with Outstanding Features | 322.5 | 0.02% |
| Hill Spas, above Budva | 131 |  |
| Semi-island Ratac with Zukotrljica | 30 |  |
| Old Ulcinj island | 2.5 |  |
| Hill Trebjesa, Nikšić | 159 |  |
| Areas protected by municipal decisions (equivalent to the PA category: Landscapes with Outstanding Features) | 15,000 | 1.08% |
| Kotor-Risan Bay, Kotor Municipality | 15,000 |  |
| TOTAL PAs | 133,309 | 9.7% |

- Montenegro also has a number of designated ‘international conservation areas’. These include: one RAMSAR site (Skadar Lake NP); one Biosphere Reserve (Tara River Basin – 182,899ha, including the entire extent of Durmitor NP and Biogradska gora NP); and two World Heritage Sites (WHS) – Durmitor (Durmitor NP with Tara River Canyon – 39,000ha) as a natural WHS and Boka Kotorska (the Kotor-Risan Bay protected by municipal decision) as a natural and cultural WHS. Some of these areas (i.e. those areas falling outside the five national parks) however are not formally recognized as national PAs and/or lack proper protection regimes, financing, and capacitated management structures.

#### Socio-economic context:

In 2003 Montenegro’s total permanent population was 620,145. The country has a Human Development Index (HDI) of 0.834, well above the global average of 0.753 (UNDP Human Development Report, 2009). According to the 2003 census, the Montenegrin population totaled some 620,145 people. Some 13% of these had post-school qualifications (some7.5% had a university education), 48% had a secondary school education while the remaining 39% had either elementary school education (~35%) or no formal education at all (~ 4%). In 2006, primary school enrolment rate was 96.9%. Illiteracy levels in 2003 were estimated at 2.35%. Around 61% of Montenegrin population lives in urban areas, and 98% have access to a water source. Life expectancy at birth is 74 years. During the last few years, infant mortality rates were in the area of 9 – 11 (per 1,000 live births).

In the second half of the current decade, unemployment fell substantially from around 22% in 2004 to 11% in 2008.  Average annual net salary in 2007 was 337 Euros (a large increase compared to, for example, 195 Euros in 2004), and unemployment fell below 12%. Even though there is a lack of continuous data on poverty, the last available indicators for 2005 and 2006 suggest a leveling off of the poverty rate at 11.3%, and a small decrease in inequality measures (e.g. the Gini coefficient fell from 0.259 in 2005 to 0.243 in 2006).

In 2006 and 2007, economic growth was 8.6% and 10.3% of GDP respectively, placing Montenegro among the group of the fastest growing economies in the world. Growth has slowed in the second half of 2008 as a result of negative global economic trends, and in 2009 the economy went into recession with a projected negative growth of 4–5% of GDP until the end of the year. GDP in 2007 was 2.5 billion Euros, and per capita GDP in PPP US$ in 2006 was 9,250.  The economy is oriented toward services (including tourism) - accounting for 72.4% of the GDP in 2007 - while the industry/manufacturing sector is concentrated on a few products, notably aluminium. Among the economic sectors, tourism was one of the main drivers of recent economic growth, with the number of foreign tourists increasing by more than 45 percent in both 2005 and 2006 and by almost 55 percent in 2007.

The administrative set up of the country includes national and local level governments, with local self-government structured into 21 municipalities. The country is currently implementing a wide range of political and economic reforms, and has EU integration as one of its key objectives. In December 2008, Montenegro submitted an application to become a candidate country in the EU accession process.

#### Institutional context

A number of ministries and administrative bodies are responsible for environmental and protected areas management in Montenegro. Responsibilities for the establishment and administration of formal protected areas are split between national and local level administrations, depending on the PA category: strict and special nature reserve, national parks and protected habitats (including protected species) are proclaimed and managed at a national level; while the other categories (regional and nature parks, natural monuments and landscapes with outstanding characteristics) are proclaimed and managed by local government.

The Ministry of Spatial Planning and Environment (MSPE) is the primary Ministry responsible for developing national strategies, policies, laws and standards for environmental protection. The Ministry may also act as a coordinator/ implementing agency for a number of PA projects and initiatives. The Ministry performs administrative supervision over the work of several public institutions responsible for PA planning and management. The Public Enterprise National Parks (PENP) is the only specialized institution tasked with PA management in Montenegro. PENP is responsible for protection and management of the five Montenegrin national parks - Durmitor, Biogradska gora, Skadar Lake, Prokletije and Lovcen. The Enterprise was established in 1993 under the provisions of the Law on National Parks. PENP comprises four administrative units (one for each national park) and a central headquarters in Podgorica. It is governed by a Management Board and a Director (appointed by the Government), and there is a Scientific Committee that advises on particular issues relevant to environmental protection in the national park. The Nature Protection Institute (NPI) is responsible for: the identification of areas and species that need special protection status; proposing nature protection measures and issuing decrees/ resolutions on placing certain natural assets under protection; maintenance of protected areas inventories; and conducting research. The NPI is also designated institution for preparation of feasibility studies for proclamation of new PAs and the lead institution for the biodiversity monitoring programme. The Public Enterprise Morsko dobro is responsible for the planning and management of the public maritime domain, a ‘Special Purpose Area’ covering the narrow coastal belt along the entire seashore of Montenegro (at least 6 meters inshore from the line that the highest waves reach during the time of strongest storm, a surface area of some 60 km2). The newly established Environmental Protection Agency (EPA) is responsible for: environmental permitting and environmental assessment procedures; environmental inspection and enforcement; designing environmental monitoring programmes, collecting and processing monitoring data and maintaining appropriate information system; and communication of environmental information and reporting in accordance with national regulations, EU environmental acquis and multilateral environmental agreements.

The Ministry of Tourism is responsible for developing the policy framework for tourism development. Together with the National Tourist Organization, it is responsible for the implementation of tourism development strategy, promotion of tourism and similar activities.

The key competencies of the Ministry of Agriculture, Forestry and Water Resources (MAFWR) for inter alia: preparation of laws, policies and management plans; agricultural, forestry and water planning; protection of agricultural, forestry and water resources; and the development and maintenance of information systems. The implementation of MAFWR’s mandate is undertaken by Forestry and Water Administrations. The Forest Administration is tasked with: forest management planning; development of inventories; programmes for forest management and use; implementation of afforestation projects; maintenance of forest information systems; protection, prevention and mitigation of negative impacts on forests; and implementation of rehabilitation programmes. According to the new Nature Protection Law, Forest Administration will assume a role in managing protected areas that will be designated within forested zones (except for the forests in national parks which are regulated under the Law on National Parks and managed by PENP).Water Administration is responsible for the implementation of water legislation, including: regulation of watercourses; protection of water from pollution; use of water and water resources; preparation of relevant plans and programmes; calculation of water management fees and charges; and overseeing water use in line with the Government’s programme, organization and management of water management monitoring.

The Ministry of Finance has a central role in planning and executing national budgets. It receives annual budget plans from all the public administration units, balances them according to expected budget revenues and formulates budget proposals which are passed by the Parliament. It supervises the Tax Administration (tasked with collection of fiscal revenues) and Real Estate Administration (keeps data on land and property registers and provides land records).

The competences for proclamation and management of certain categories of nature protected areas (regional/ nature parks, natural monuments, and landscapes with outstanding characteristics) are delegated to local governments. However the extent to which this part of municipal mandates has been fulfilled is almost negligible and linked to just a few examples where local governments have initiated processes that led to proclamation of protected areas. Even in such cases, municipal initiatives have as a rule fallen short of establishing proper management structures and providing adequate resources for PAs.

Some of the key national NGOs that have been active in nature protection area in Montenegro in the past few years include, amongst others, Greenhome, Most, Centre for the Protection of Birds, and Greens of Montenegro. A number of international non-profit and non-governmental organizations such as WWF and REC have also actively contributed to meeting the nature protection objectives and promoting PAs.    The most notable results of the activities undertaken in the past by NGO sector include: raising awareness about values of PAs and threats they are facing; promotion of PAs and of the cross-border cooperation; concrete improvements related to the protection of certain species and habitats; contributions to research and biodiversity information, initiatives for protection of new areas; and improvements in cooperation with local communities.

#### Legislative context

The Law on Environment (Official Gazette of Montenegro No. 48/2008) introduces an integrated approach to environmental management and defines objectives and principles for environmental protection. The Law regulates inter alia: national plans and strategies required under certain multilateral environmental agreements; environmental monitoring and reporting requirements; liability for environmental damage; and environmental financing. In respect of environmental financing, the Law prescribes that the state and local self-government units should provide for environmental protection financing. Financing sources are classified as state budget, local self-government budgets, environmental protection fund, other sources prescribed by special regulations and international sources (international loans, donations and assistance, instruments, programmes and funds of the EU, UN and other international organizations) and foreign investments. Article 60 of the Law stipulates that environmental protection funds can also be secured through private sources (concessions), public-private partnerships and other appropriate models in line with specific regulations. Local self-governments are entitled to levy environmental protection charges. Polluter and user pays principles are endorsed as some of the basic principles of the Law. The Law envisages establishment of an environmental protection fund (revenue sources and disbursement mechanism to be detailed through a specific regulation). Until the fund is established, environmental charges prescribed under previous legislation (Environmental Protection Law 12/96 and respective decree) apply and are paid into the state budget.

The two key pieces of legislation relevant to the planning and administration of PAs in Montenegro are the Nature Protection Law and the Law on National Parks. The Law on Nature Protection (Official Gazette of Montenegro No. 51/08) aims to transpose the key EU legislation in this area, such as Habitats and Birds Directives. The rationale for the adoption of the Law was to introduce an EU-compliant categorization of protected areas, prescribe procedures for designation of protected areas (including a requirement for designation of managers for each category, preparation of management plans etc.) and set a legal basis for establishment of Natura 2000 network. In terms of PA financing, the Law affirms the user pays principle prescribing that users of natural assets are obliged to pay charges for their use and bear costs of rehabilitation of any damaged areas. Article 64 of the Law provides for nature protection funding to be raised from: state and local self-government budgets in line with annual nature protection programmes, plans and projects; charges for the use of protected areas; donations; and other sources in line with relevant legislation. The Law requires that PA management plans contain provisions on financial aspects of their implementation.  Article 68 of the Law specifically defines the basis for levying charges for the use of protected natural assets, and is replicated in the new Law on National Parks. The Law on National Parks (Official Gazette of the RM No 47/91 and 27/94). (Official Gazette of Montenegro 56/09) defines the borders, level of protection, limitations on development, and permitted resource uses of national parks. The Law specifically provides for the PENP to collect fees for the use of national parks, including from inter alia: entrance fees; a range of visitor services; marketing rights; filming and advertising; rentals; fishing; accommodation; and commercial harvesting. The specifications for the level and management of the fees for these uses are, in turn, contained in the gazetted ‘Decisions’ passed by the Board of Directors of the PENP (i.e. Decision 53/06 and Decision 08/07, 73/08).

### 1.2	Threats and root-causes

- The biodiversity of Montenegro is under ongoing pressure from: (i) continued urbanisation, notably along the narrow coastline, across the central lowland plain and around the natural lake systems; (ii) unsustainable levels of tourism development across the entire coastal zone, and more locally around mountain resorts; (iii) illegal construction and development in and around protected areas (PAs); (iv) pollution of the aquatic and marine habitats from untreated wastewater; (v) unsustainable levels of water usage for industrial and household purposes; (vi) illegal harvesting of forest products, fish, game and other natural resources, notably in the northern mountain regions; (vii) unsustainable fishing practices in the marine environment (e.g. use of dynamite); and (viii) the impact of global climate change, especially the effects of hot and dry periods on forest habitats. The most significant cumulative impact of these threats on the biodiversity of Montenegro is: (a) the increased fragmentation of the remaining natural areas in the coastal zone; (b) a reduction in the ecological functioning of many natural areas; (c) a reduction in the effectiveness of natural areas as a buffer against climate change impacts; (d) a reduction in the capacity of the environment to provide key ecosystem services; (e) the ongoing loss of threatened habitats and associated species; and (f) the incremental loss of the economic benefits accruing from biodiversity.

### Desired long-term vision and barriers to achieving it

- The long-term solution sought by the Government of Montenegro is the establishment of a sustainably funded representative system of protected areas, under an effective and adaptive management regime. This solution requires that protected area agencies have adequate capacities to identify and resource cost-effective management efforts across an expanded protected area system. Under this scenario, protected area institutions will have the ability to: (i) secure sufficient, stable and long-term financial resources for protected areas; (ii) allocate these resources in a timely manner and appropriate form to cover the full costs of protected areas; and (iii) ensure that the protected areas are managed effectively and efficiently with respect to conservation and other complementary objectives. To enhance this ability, protected area agencies will also need to: (a) seek closer alignment of their protected area management objectives with local, regional and national socio-economic development priorities; and (ii) improve inter-sectoral co-operation and collaboration to address the increasingly complex conservation and developmental challenges facing protected areas. A number of initiatives are currently underway, including a suite of complementary GEF-funded projects, to achieve this long term solution. These include programs to: improve the representation of the protected area system; strengthen the capacity of PA institutions to administer this expanded system; enhance cooperative governance; and mainstream protected areas into local and regional socio-economic development programmes. A critical gap however is support to the processes for, and institutions involved with, securing and managing funds to administer an expanded PAS. Funding baselines for PA management in Montenegro are currently well below the levels required to ensure that the protected area system properly serves its function as an important tool to protect biodiversity.

- There are three barriers to improving the financial sustainability of an expanded PAS in Montenegro:

(i) Under-developed policy instruments and regulatory framework: While there is a modern national policy setting (National Environment Policy, 2008; National Forestry Policy, 2008), and the associated enabling legislation (Law on Environment, 2008; Law on Nature Protection, 2008; Law on National Parks, 2009), to support the diversification of the funding base for nature protection in Montenegro, this still remains a relatively new area of development for the country. There is an urgent need to now identify the applicability of the different financing instruments under different PA management regimes, and the preparation of specific regulations to facilitate and direct their implementation. A strong business case needs to be developed to motivate an increase in national and local government funding of the protected area estate, notably through investments in infrastructure and facilities that could contribute to improving the long-term financial sustainability of the PAS. Underpinning this business case is a need to better understand the value of the goods and services provided by protected areas so that decisions about economic development are made with the full understanding of the costs and benefits involved. Credible and reliable estimates of economic values of protected areas are needed to support the case for further national and local government investment in protected area establishment and management. The national legislation (primarily the Law on Environment) provides for a number of innovative environmental financing mechanisms, including a set of national and local environmental levies such as air pollution, hazardous waste etc. charges and a national Environmental Protection Fund (EPF). However the policy and regulatory frameworks to ensure their effective implementation remains under-developed, notably the disbursement of income from these potential financing sources to support nature protection efforts. There continues to be a lack of legal clarity in the fiscal and operational responsibilities, for the different categories of PAs, across the responsible national and local public institutions. While the legislation in principle makes provision for public-private/NGO-partnerships in the provision of commercial services in protected areas, the strategic approach to these partnerships and the legal procedures and contractual documentation to underpin partnerships have yet to be developed. There are currently no mechanisms to enable cross-subsidization across the entire PAS, or more equitable distribution of government funding allocations, with the result that PA agencies could increasingly come to direct expansion efforts towards the income-generating ‘honey-pot destinations’ and avoid (or neglect) high biodiversity areas with little or no income-generation potential.

(ii) Insufficient revenue-streams: There is a critical need to increase, diversify and stabilize the financial flows to all categories of protected areas through the implementation of a more diverse portfolio of financing mechanisms. The annual funding gaps for the ‘basic’ and ‘optimal’ management scenario for the current protected area system have been conservatively estimated during the PPG phase at €820,000 and €1.9m respectively. A large proportion of current PA funds (~85%) are directed towards human resource costs and basic maintenance (e.g. path/road maintenance) and operational (e.g. functional enforcement) activities. Due to financial constraints, there remains a limited investment by PA agencies in ‘pure’ biodiversity conservation programmes (e.g. habitat restoration, wildlife management), environmental education initiatives and tourism and visitor infrastructural development. Assuming that protected area expansion efforts are moderately successful in the medium-term (i.e. PAS increases in size to at least 210,000ha by 2012), this funding gap is expected to rise to approximately €2.8m for the basic management scenario and €6m for the optimal management scenario. This may result in further cuts to the range of basic operational management activities that may be funded within the PAS. Indications are that the national and local government budget allocations are, in the light of other more pressing demands on the national fiscus, not likely to increase significantly from their current base level of less than €1m per annum to fill this financing gap. Local government already have limited to no capacity or resources to undertake PA management functions, with the result that PAs under municipal management control will remain virtually unfunded unless these PAs can become more financially self-sustainable in future. Other public institutions (Morsko dobro, Forest Administration, Marine Biology Institute, NPI and NTO) have made little or no provision for PA planning and management costs in the national governments medium-term expenditure framework. The primary source of income for the entire PAS is currently four of the five national parks (€1,071,323), of which only Durmitor NP generated a small surplus in 2008. These parks are rapidly reaching the limits of their income-generation potential using the current user-pays approaches. In some instances (e.g. fees from sand and gravel extraction: €108,785 in 2008) income streams may not even be ecologically sustainable in the medium- to long-term, and the resultant loss will have to absorbed by increasing income revenue from other user fees. The remaining protected areas in the PAS, to date, generate no income from user fees or services and, without significant investment in appropriate infrastructure development; this situation will remain for the immediate future. Without ongoing donor funding to supplement existing government budget allocations, the legal reform, policy development, planning, expansion, research and monitoring support functions for the PAS will continue to remain under-resourced, in the absence of other funding options. Access to donor funding still remains opportunistic, and donor agencies tend to ‘drive’ the priorities for investment.  There is currently limited capacity in the MSPE to secure funding from multilateral development agencies, international conservation organizations and private donors for the PAS in a coordinated and structured way.

(iii) Low cost-effectiveness of business and financial management systems: The determination of annual appropriations from national and local government treasuries for PA management is currently not based on objective criteria linked to the management objectives of the PAS.  At both the protected area system level, as well as for individual protected areas, there is a limited use of business planning processes to optimally use limited financial resource allocations and source additional funds to fill financing gaps. Although PENP prepare medium-term (5-year) management plans for national parks, these are largely premised on a utilitarian business-as-usual management approach, with little innovation adopted in improving revenue streams and improving cost-efficiencies. The links between management plans and budget allocations also remains somewhat tenuous, with the suite of activities undertaken in each park largely determined by the allocation constraints and not by a strategic prioritization process. The concept of business-oriented financial planning and performance based budgeting is still in the early stages of development in the PENP, and the requisite capacities/ skills at both the institutional and parks level are still in need of development. National Park managers are still not fully trained in the application of financial management systems and procedures at the park level. The PENP is still busy developing expertise in the provision of visitor facilities and services, the market-related (or cost recovery) pricing of these and the apportioning of income to improve their quality and administration. Management and business planning processes for PAs under competences of local governments and Morsko dobro are still virtually non-existent. This is further exacerbated by the lack of dedicated staffing capacity, notably in the municipalities, leading to operational inertia in many of the small PAs. With the designation of forest zones of PAs to the Forest Administration, the financial management capacity of staff responsible for these areas may still need to be developed. At the level of the PA system, the cost-effectiveness of the different institutional arrangements for PA planning and management, and the cost-effectiveness of different approaches to PA operations have not been critically assessed.

### Stakeholder analysis

The Ministry of Spatial Planning and Environment (MSPE), Public Enterprise National Parks (PENP) and the Municipalities of Zabljak, Tivat, Podgorica, Andrijevica and Kolascin will be the main public institutions responsible for different aspects of project implementation. They will work in close cooperation with other affected public institutions, including the: Ministry of Agriculture, Forestry and Water Management (MAFWR) –Forestry Administration; Ministry of Finance; and Morsko Dobro. The project will focus stakeholder engagement at two levels of intervention: (i) working with national and local public institutions and agencies in order to strengthen their capacities for business planning, financial management, fund raising, and revenue generation from user pays systems in protected areas; and (ii) working directly with civil society organizations, tourism agencies, natural resource (water) users, recreational (adventure tourism) user groups and individuals to mitigate impacts and optimize benefits of project activities. Table 2 below describes the major categories of stakeholders and their anticipated involvement in the project.

Table 2: Key stakeholders and roles and responsibilities

| Stakeholder | Roles and Responsibilities |
| --- | --- |
| Ministry of Spatial Planning and Environment | MSPE will, primarily through the Deputy Minister and the department for nature protection and environmental assessments, be responsible for the overall coordination of the project. It will also be an important partner in, and primary beneficiary of, project activities. It will be directly involved in the project through: preparation of spatial plans for special purpose areas in northern Montenegro; development of the targeted communications to high level government decision-makers to motivate for improved government investment in the PAS; preparation of the NPAFP; preparation of secondary legislation and complementary tools and mechanisms to facilitate implementation of the NPAFP; fund-raising for the PAS; development of guidelines for cost-effective management of PAS; and involvement in the skills development and training programs for MSPE staff. The MSPE will chair the Project Steering Committee (PSC) |
| Public Enterprise National Parks | PENP is an important partner in, and beneficiary of, the project. It will be involved in the project through: support to the economic valuation processes in national parks; participation in the development of the NPAFP; updating of regulations to support revenue generation mechanisms in national parks; support to the introduction of a PES scheme in Zabljak; planning and implementation of adventure based tourism and recreation services in the national parks of northern Montenegro; introduction of business planning processes in national parks; improvement of the financial management systems and cost-effectiveness of operations in national parks; and involvement in the skills development and training programs for national park staff. The PENP will be a member of the PSC. |
| Ministry of Finance | The Ministry of Finance is an important partner in the project. It will be involved in the project through: participation in the preparation of the NPAFP; participation in development of regulatory instruments to support the implementation of the NPAFP; and providing support to the increase of government funding allocation to the PAS though different public financing mechanisms. The Ministry of Finance may be a member of the PSC. |
| Local Government - Zabljak, Tivat, Podgorica, Andrijevica and Kolascin | The affected local municipalities are important partners in, and beneficiaries of, the project. The Tivat municipality (and Morsko dobro) will participate in: the economic valuation of Tivat Saltpan NR; and the preparation of an integrated management and business plan for the Tivat Saltpan Nature Reserve. The Podgorica, Andijevica and Kolascin municipalities will participate in the nature-based concessioning process planned for Komovi RP. The Zabljak Municipality will lead the feasibility assessment process for the introduction of a watershed protection surcharge for the municipal area. All municipalities will also be involved in the relevant project skills development and training programs. The municipalities will all be members of the PSC. |
| MAFWR - Forestry Administration | Forestry Administration will be actively involved in the project through: participation in the development of the NPAFP; participation in regulatory reform processes required to support the financial sustainability of the PAS; and providing direct support to the nature-based tourism concessioning process in Komovi regional park, notably if the concession includes areas under the management of Forestry Administration. The Forestry Administration/MAFWR may be a member of the PSC. |
| Regional and Local Tourism Organisations | Regional and Tourism organisations are important partners in the development and implementation of project activities focused on improving the tourism and recreational facilities and services in northern Montenegro. They will provide professional and technical support in ensuring the alignment of project investments with regional and local tourism plans, programs and projects to reduce duplication of effort and optimise returns from investment. It is envisaged that a representative of the tourism organisations in northern Montenegro would be represented on the PSC |
| UNDP GIS Project | The UNDP GIS Project is an implementation partner for the project. It will provide database and decision-support system for the project. |
| WWF - Dinaric Arc Eco-region Project/ Mediterranean Programme office | WWF will support the integration and alignment of project activities in the PAs of northern Montenegro with the Dinaric Arc Ecoregion initiatives. |
| National and regional NGOs | Relevant national NGOs such as Greenhome, Greens of Montenegro and Most will be encouraged to take an active role in implementing project activities, notably in the involvement and beneficiation of local communities in Komovi from the concessioning process. National and local NGOs will actively participate in the stakeholder engagement processes for all project activities. A representative from national NGOs will be a member of the PSC. |
| Academic and research Institutes | Relevant national and regional academic and research institutes will contribute to the project in, for example, local scientific surveys and specialist mapping. |
| Representatives of local communities (e.g. residents of Zabljak ) | Inhabitants of the villages or settlements around the PAs of northern Montenegro will be made aware of the project activities and invited to take part in the decision making process. They will be represented in the local working committees and actively involved in the project activities relating to the introduction of a PES scheme in Zabljak. Their cooperation will be sought in implementing project activities including resource protection, alternative income development (e.g. nature-based tourism), awareness raising, etc. |
| National and local press and media | The project will cooperate with national and local press and media on public awareness issues. |
| UNDP-Montenegro | The roles and responsibilities of UNDP-Montenegro will include: Ensuring professional and timely implementation of the activities and delivery of the reports and other outputs identified in the project document; Coordination and supervision of the activities; Assisting and supporting MSPE in organizing coordinating and where necessary hosting all project meetings; Contracting of and contract administration for qualified project team members; Manage and be responsible of all financial administration to realize the targets envisioned in consultation with MSPE; Establishing an effective networking between project stakeholders, specialized international organizations and the donor community. The UNDP will be a member of the Steering Committee |

### Baseline analysis

- The total budget allocation by government for the PAS in Montenegro was roughly estimated at €2.17m and €2.28m per annum in 2008 and 2009 respectively, of which nearly €1.76m (81%) and €1.68m (74%) respectively constituted the total budget of the Public Enterprise National Parks (PENP) (see Table below).

Table 3: Financing of the protected area network in Montenegro (2007-2009)

| Total PAs network budget (in EUR) | 2007 | 2008 | Plan 2009 |
| --- | --- | --- | --- |
| Ministry of T&E (share for PAs) | 86,443 | 158,054 | 323,494 |
| Nature Protection Institute (share for PAs) | 197,138 | 221,112 | 244,038 |
| PENP total budget | 1,523,823 | 1,756,946 | 1,681,100 |
| Other (municipal, Marine Biology Institute, Morsko dobro) | 27,111 | 32,042 | 33,729 |
| Total PAs network budget | 1,834,515 | 2,168,153 | 2,282,361 |

- Table 4 shows the breakdown of the income and expenditure for the PENP over the period 2007-2009. The national budget allocation to PENP accounted for 30% and 41% of income in 2007 and 2008, with the remaining income generated from park-based fees. In 2008, donor funding accounted for an additional €529,000 in income for PENP, most of which (~€349,000) was used for Skadar Lake NP. The main revenue generating instruments for national parks in 2008 included: entrance fees (€322,348); rafting (€169,912); leases (€138,830); fishing licenses and other annual fees (€116,949); sand and gravel extraction (€108,785); tourism services (€39,261); rental of bungalows (€18,060); souvenir sales (€9,883); and natural resource use (€7,972). Excluding donor-funding sources, the average operating cost per ha (including HR costs) for national parks are currently estimated at €20/ha (based on 2008 expenditure).

Table 4: Income and expenditure of the Public Enterprise National Parks (PENP) 2007-2009

| PENP Management Unit/ Funding source | 2007 (actual) | 2008 (actual) | 2009 (planned) |
| --- | --- | --- | --- |
|  | Income (€) | Expenditure (€) | Income (€) | Expenditure (€) | Income (€) | Expenditure (€) |
| Durmitor NP | 538,070 | 564,205 | 426,513 | 412,917 | 293,500 | 404,000 |
| Skadar Lake NP | 343,874 | 299,740 | 448,986 | 478,757 | 344,000 | 430,000 |
| Biogradska gora NP | 133,750 | 214,289 | 101,161 | 206,354 | 68,300 | 187,500 |
| Lovcen NP | 55,629 | 117,291 | 60,286 | 146,053 | 45,300 | 120,000 |
| PENP Support Services | - | 297,694 | - | 487,994 | - | 420,800 |
| National budget allocation | 452,500 | - | 720,000 | - | 930,000 | - |
| TOTAL | 1,496,823 | 1,493,219 | 1,756,946 | 1,732,075 | 1,681,100 | 1,562,300 |

- While the Government of Montenegro continues to implement legislative and policy reform, commit modest financial resources and deploy technical and professional capacity, to support the planning, management and expansion of protected areas, this will remain inadequate to significantly improve the financial sustainability and management effectiveness of the protected area system.

- Under the ‘business-as-usual’ scenario, the total costs of planning and managing the PAS will remain at a level of at least 50% below what is required for their optimal management. With the incremental expansion of the PAS (in part, as a result of the activities undertaken in the counterpart project Strengthening the sustainability of the PA system of Montenegro), this funding gap is expected to increase even further. Despite a strong political commitment to and enabling broad legislative framework for, the financing of protected areas the government will continue to perceive protected areas as a ‘financial drain’ on the national fiscus, and a restrictive and unproductive form of land use. Government allocations to public institutions for PA-related planning and management will thus remain at their current levels, in the absence of a strong business case for increased government investment. Government allocations to PENP, supplemented by own income from national park user fees, will continue to be focused on the five national parks, while other categories of protected areas will receive limited or no government support for reserve operations. Because of escalating financial constraints within the management authorities for the other categories of protected areas, the ecological integrity of these smaller PAs will continue to degrade, and illegal use will continue. Due to a lack of capacity and a range of other priorities in public institutions responsible for PA management, the regulatory framework to support the implementation of a range of the different financing instruments currently provided for in national legislation will largely be developed on an ad hoc basis. A number of innovative mechanisms to increase revenue streams and improve cost effectiveness of operations will remain untested.

- Ongoing research and inventory efforts in and around protected areas will ensure that an important repository of knowledge is maintained on the state of the biodiversity of Montenegro, and the identification of priority areas and species for conservation action. Information management work undertaken by the NPI (US$660,000) will be supplemented by data collected by a forestry inventory (US$785,640), the ongoing development of the national environmental geospatial database (US$400,000), and technical support to data collection efforts to implement NATURA 2000 (US$23,357).

- Institutional and individual capacities will continue to be developed in the MSPE, PENP and the NPI through direct donor agency funding support (WWF, GEF, ADC, Italian Government, and Norwegian Government – US$1,175,000). Donor support will also be deployed to strengthen the planning and operational management systems and capacities of Skadar Lake NP (GEF and GTZ – US$150,000).

- The MSPE will maintain the development processes in the new Prokletije National Park, with ongoing technical support from the NPI (US$17,000) and funding support from donor agencies (US$112,000).  Progress on the establishment processes for the Delta Bojana/Buna River as a protected area (US$400,000) may be protracted until outstanding issues on the proposed boundaries, zoning and institutional arrangements are satisfactorily addressed. Feasibility assessments being undertaken by different donor-funded projects for trans-boundary conservation areas between Montenegro and Albania and Bosnia-Hezegovina (US$160,000) will be constrained by the current capacity and resource constraints of the MSPE and NPI, and the absence of an existing institution to effectively administer and manage the Montenegrin component of a trans-boundary conservation area. The donor funded feasibility assessment of, and management planning processes for, an MPA at Katici islands (US$196,410) will test the efficacy of the establishment of an MPA in Montenegro and identify the legal, institutional and capacity constraints for this category of PA. The spatial planning of the Bjelasica-Komovi region (US$1,000,000) would provide the enabling planning framework for the establishment of the Komovi Regional Park. Tourism development initiatives in the Bjelasica-Komovi region (US$3,143,760) will achieve varying levels of sustainability depending on the institutional support (infrastructure, training, regulatory, policy, etc.) provided by the responsible local public institutions.

- The partner UNDP GEF-funded project  Strengthening the sustainability of the PA system of Montenegro (US$1,000,000) will support: (i) the design and development of a scientifically-based ecological network and protected area system; (ii) the identification and design of a new marine PA for Montenegro; (iii) the establishment of the Komovi Regional Park; (iv) the restructuring and strengthening of protected area institutions; (v) the development of protected area management skills within these institutions; and (v) the support of the development of local SMEs in Komovi Regional Park.

# PART II: STRATEGY

### Project Rationale and Conformity to GEF Policies and Strategic Objectives

- The project is aligned with GEF’s Strategic Objective (SO) 1 of the Biodiversity focal area, ‘Catalyzing Sustainability of Protected Areas Systems’. The project is consistent with Strategic Programme’s (SP) 1 of SO 1; ‘Sustainable financing of PA systems at the national level’.

- The project will contribute to achieve the aims of SP 1 by investing GEF resources in the implementation of a suite of activities that could collectively catalyse a significant improvement in the ability of the Montenegrin PAS to secure sufficient, and more reliable, funds. The project will support the development of a system-level financing plan for the PAS that provides the strategic framework for a range of project interventions at the institutional and site (PA) level. It will improve the knowledge base to support the preparation of this system-level financial planning, and strengthen the enabling legal-regulatory framework to facilitate its implementation. The project will also support the roll-out of business planning processes at the local protected area level by facilitating the development of PA business plans for different categories of PAs. Finally, it will test a diverse range of tools and revenue mechanisms to increase funding streams to PAs and improve the cost-effectiveness of PA management systems.

- The project will contribute to the achievement of GEF’s expected outcomes and main indicators under this priority programming area as follows:

| GEF-4 BD Strategic objective and programmes | Expected outcomes | GEF-4 BD Indicators | Project contribution to indicators |
| --- | --- | --- | --- |
| SO-1: Catalyzing Sustainability of Protected Area Systems | Biodiversity conserved and sustainably used in protected area system | Extent of habitat cover (hectares) by biome type maintained as measured by cover and fragmentation in protected area system Protected area management effectiveness as measured by protected area scorecards that assess site management, financial sustainability and capacity | 165,000 ha of marine, mountain, freshwater, forest, karst and coastal habitats maintained in the protected area system Capacity development scorecard increasing from 37%, 49% and 33% (systemic, institutional and individual capacity) to >57%, 60% and 62% respectively |
| SP-1 Sustainable financing of protected area (PA) systems at the national level | PA systems secure increased revenue and diversification of revenue streams to meet total expenditures required to meet management objectives Reduction in financing gap to meet PA management objectives | Total revenue and diversification in revenue streams | Financial sustainability scorecard improves to a score of >55% from the current level of 26% Total annual budget available for management of PAS increased from a baseline of US$3,946,611 to >US$5,100,000 |

### 2.2	Country Ownership: Country Eligibility and Country Drivenness

- This project is a response to a number of policy documents that frame the government policies and strategies for biodiversity conservation and the establishment and management of protected areas in Montenegro.

- The project responds to recommendations 5.1, 5.2 and 6.6 of the Second Environmental Performance Review of the Republic of Montenegro (2007) and a number of recommendations contained in the National Capacity Self-Assessment Report (2007). The project is consistent with the financing principles of the National Strategy of Sustainable Development of Montenegro (NSSD) and the General Goals 1 and 3. It aligns directly with the following measures of the NSSD: (i) diversification of the tourism offer, and subsequent increase in revenue opportunities, in the northern region; (ii) establishing an efficient system for the management of protected areas; (iii) strengthening the human resource capacity for the protection of biodiversity; and (iv) strengthening regulatory and market instruments for environmental protection. The project complements the sustainable financing and nature-based tourism development objectives contained in the National Biodiversity Strategy and Action Plan (NBSAP, 2009). The project aligns with a number of priority activities identified in the National Report on Status, Problems and Preservation of Marine and Coastal Diversity in Montenegro (2004), the National Forestry Policy of Montenegro (2008) and the National Integrated Coastal Zone Management Strategy (2008).

- The project is assisting the country in the implementation of the CBD Programme of Work on Protected Areas (PoWPA), notably Goal 3.2 (capacities) and Goal 3.4 (financial sustainability).

### 2.3	Design principles and strategic considerations

- The administrative boundary of the project is the entire network of marine and terrestrial protected areas. Thematically, the project will deal with strengthening the capacity to: a) prepare system-wide and site level financial plans; b) improve the enabling policy and legal framework; c) increase funding streams; and; c) improve cost-effectiveness of management systems. The project will focus outputs and activities at two levels of intervention: (i) the national PA system level, through working with different public institutions and agencies in order to develop and strengthen their capacity to effectively secure and administer funds for the protected area system; and (ii) the level of individual protected areas in northern Montenegro (see map below), through working with a range of stakeholder groups to diversify and increase the available funding to, and develop more cost-efficient systems for management and administration of funds for, those protected areas.

- Under the alternative scenario promoted by the project, Montenegro will have by 2013: (i) a  national strategic planning framework for the sustainable financing of the protected area system; (ii) an enabling legal-regulatory framework for PA financing mechanisms; (iii) an increase in funding for the PAS from government grant allocations and environmental levies; (iv) completed business planning processes in two protected areas (v) an increase in donor funding and loans for the PAS;  (vi) a demonstrable improvement in the cost-effectiveness of the financial, business and operational systems of PAs; and (vii) an increase in revenue from a range of user pay mechanisms across four PAs in northern Montenegro.

- The increment of the project in terms of global environmental benefits is represented by an expected increase in: overall PA institutional capacity (from an average capacity assessment scorecard baseline of 40% to >51%); and financial sustainability of the PAS (from financial sustainability scorecard baseline of 26% to >40%). In the long-term (by 2015 and beyond) threats such as unsustainable tourism development; illegal construction; drainage and pollution of wetlands; unsustainable water usage; and illegal harvesting of forest products, fish, game and other natural resources, will be contained at the level of the entire expanded PA system of the country, covering 165,000 ha.

- The project will be implemented as a complementary partner project with the GEF-funded UNDP project ‘Strengthening the sustainability of the PA system of Montenegro’. Project resources, capacity and knowledge will be pooled wherever possible to achieve economies of scale.

- The project will liaise with the counterpart project managers of: (a) Development of a Mediterranean Marine and Coastal Protected Areas (MPAs) Network through the boosting of Mediterranean MPAs creation and management in areas within national jurisdiction of third countries project being implemented by RAC/SPA as part of UNEP’s Mediterranean Action Plan; and (b) GEF funded UNEP-World Bank project Strategic Partnership for the Mediterranean Sea Large Marine Ecosystem – Regional Component: Implementation of agreed actions for the protection of the environmental resources of the Mediterranean Sea and its coastal areas to explore opportunities to share resources and lessons learnt in the marine protected area domain.

- The project will participate in bilateral and multilateral working groups to exchange lessons learnt between complementary PA establishment projects currently underway, including: (a) Delta Bojana River/Buna River as part of the World Bank Montenegro Sustainable Development Project; (b) a cross-border protected area between Bosnia-Herzgovina and Montenegro in the region of Maglic-Bioc-Volujak as part of the UNEP/ENVSEC Enhancing Transboundary Biodiversity Management in South East Europe project; (c) the ADA-GTZ-SNV Prokletije / Bjeshkët e Namuna Cross-border Mountain Range Development Programme; and (d) the preparation of a Management Plan for the Pilot Marine Protected Area of Katic Island, currently being undertaken by DFS Engineering as part of the Italian Ministry of Environment, Land and Sea support for implementation of the NSSD.

- The project will seek representation on technical working groups established by the WWF’s Mediterranean Programme Office’s Dinaric Arc Initiative (sub-project Preservation of the biodiversity of southwest Balkan: protection of nature and areas in cross-border area Durmitor-Tara River-Prokletije) to ensure the alignment with project activities implemented in northern Montenegro.

- The project will participate in the spatial planning processes for the Komovi region being led by the Ministry for Economic Development. The project will align the project’s nature-based tourism development activities planned for Komovi Regional Park with the Master Plan for Sustainable Tourism Development and Bjelasica and Komovi Region undertaken by DFS Engineering as part of the Italian Ministry of Environment, Land and Sea support for implementation of the NSSD. It will also seek representation on steering committees established to oversee: (a) sustainable tourism and regional development initiatives being implemented in the five municipalities around Komovi, as part of the Austrian-Montenegrin Partnership Project, funded by the Austrian Development Cooperation; and (b) sustainable land use and natural resource management activities implemented in the mountain ecosystems of northern Montenegro by the World Bank GEF-funded project Montenegro Institutional Development and Agriculture Strengthening.

- The project manager will liaise closely with counterpart project managers of: (i) the WWF Dinaric Arc Ecoregion project, (ii) the GEF-funded World Bank project Lake Skadar-Shkoder Integrated Ecosystem Management Project; (iii) GTZ in the institutional and individual capacity building support to the protected area agencies; (iv) the GEF-funded World Bank project Montenegro Sustainable Tourism Development Project and (iv) the Functional Analysis of the Forestry Administration project financed by Lux-Development to avoid duplication of effort, and identify opportunities for collaboration.

### Project Objective, Outcomes and Outputs/Activities

- To address the above barriers, the project has the objective of improving the financial sustainability of Montenegro’s protected area system. The project has three components – along with their associated outcomes, outputs and activities - which will contribute towards achieving the project objective. These are: Component 1 Enabling legal and policy environment for improved financial sustainability; Component 2 Securing revenue streams for the protected area system; and Component 3 Development of institutional and individual capacity of protected area institutions to raise PA management cost-effectiveness.

Component 1 Enabling legal and policy environment for improved financial sustainability

Output 1.1:  An economic valuation of the PAS supports the case for sustained public investment in protected area establishment and management

This output will seek to develop a rough estimate of the lower limit of the total economic value (TEV) of the protected area system. Because of a paucity of reliable financial data on the ecosystem goods and services for many of the protected areas in Montenegro, the project has adopted the approach of implementing detailed valuation studies for five protected areas representing a range of different use values (i.e. direct-use and indirect use) across the PAS. During the PPG phase an initial assessment of the importance of the primary values of four existing protected areas (Durmitor National Park, Biogradska gora National Park, Skadar Lake National Park and Tivat Saltpan Nature Reserve) and one protected area currently under establishment (Komovi Regional Park), was undertaken. Based on this initial assessment, the values to be determined during the full project for each of these five protected areas, and the most appropriate methods that could be adopted for each value, were identified. These are summarized in the table below (refer to the original technical report, Improving the financial sustainability of the protected area system of the Republic of Montenegro, for a more detailed description).

Table 5: Summary of the proposed methodologies for TEV studies

| Values | Methods | Approach |
| --- | --- | --- |
| Durmitor National Park |
| Recreation Value: hiking, biking, rafting, skiing, sports fishing, accommodation and food services | Market prices Travel Cost Method (TCM) Contingent Valuation Method (CVM) Expert Opinion | Collection of secondary data Interviews with tourists, tour operators, guides, etc. |
| Extractive Value: production of useful plant species for human use and enjoyment including NTFP, timber for household needs | Market prices Shadow prices | Collection of secondary data Interviews – see Serbia Forestry study |
| Habitat for important animal species | CVM Expert opinion | Interviews with general population Interviews with experts |
| Hydrological Services: Water collection, storage, and purification | Market prices Damage avoided | Collection of secondary data, interviews with scientists and engineers |
| Biodiversity | CVM | Interviews with general population, tourists, experts |
| Potential pharmaceutical values | Expert opinion | Interviews with experts |
| Biogradska gora NP |
| Habitat for important species | CVM | Interviews with experts, tourists, general population |
| Recreation | Market Price TCM | Secondary data |
| Watershed Protection / flood protection / erosion control | Damage cost avoided Change in productivity | Secondary data Interviews with experts Research |
| Carbon storage | Shadow price | Secondary data including forestry inventory data |
| Komovi |
| Wood extraction | Market price Shadow price (local fuel wood) | Secondary data Interviews with local population |
| Habitat for important plant (and fungus) species | Market prices Shadow prices CVM | Secondary data Interviews with local population, experts, tourists |
| Habitat for important animal species | CVM Expert opinion | Interviews with local population, experts, tourists |
| Recreation | Market price TCM | Interviews with tourists, tour operators, service providers, guides |
| Watershed Protection / flood protection / erosion control | Damage cost avoided Change in productivity | Secondary data Interviews with experts Research |
| Carbon storage | Shadow price | Secondary data |
| Skadar Lake NP |
| Commercial Fishing | Market price | Secondary data Interviews with fisherman, buyers, local population |
| Habitat for important bird species (and other wildlife) | Donor funding Expert opinion CVM | Secondary data Interviews with donors, experts, tourists, tour operators, guides, other stakeholder groups |
| Recreation (including sports fishing) | Market price TCM | Secondary data Interviews with tourists |
| Watershed purification and storage | Damage cost avoided Change in productivity | Secondary data Interviews with experts Research |
| Cultural Value | CVM | Interviews with tourists, general population |
| Tivat Saltpan |
| Fish Breeding Habitat | Expert opinion Market pricing | Interviews with experts Secondary data |
| Recreation | TCM | Interviews with tourists, tour operators |
| Important Bird habitat | Expert opinion CVM | Interviews with experts, tourists, general population |

Once the valuations have been completed for these five sites, a per hectare value to determine the lower limit of the TEV of the entire protected area system will be determined and extrapolated (with strong consideration of the severe limitations of extrapolation) to the entire PAS. Using the lower limit TEV for the PAS, the project will then develop and implement a communications strategy that demonstrates to key decision-makers the benefits and costs of adequately investing in the management and expansion of the PAS.

The activities under this output are specifically directed at:

- Validating the primary economic values of each of the five targeted protected areas identified during the preparatory phase;

- Designing, testing and implementing valuation studies for each economic value within each of the protected areas to determine a monetary quantification of the ecosystem products and services in each PA;

- Collating and extrapolating the results of these valuation studies to the entire protected area system;

- Preparing a Benefit-Cost Analysis (BCA) that assesses the public benefits and costs of establishing and managing protected areas as an economically viable form of land use;

- Formulating a focused communication and marketing strategy, targeted at high-level government decision-makers, that presents a succinct overview of the contribution of the PAS to the socio-economic well-being of Montenegro and its citizens;

- Developing the requisite briefing media for, and implementing the communication program to, targeted government decision-makers; and

- Documenting the lessons learnt and detailing the methodologies used in economic valuations.

Work under this output will be done under the guidance of a small reference group comprising management staff of the five targeted PAs, MSPE and the Project Manager. This may be supplemented by representatives from different PA institutions (including MSPE, PENP, Morsko dobro, Forest Administration and affected Municipalities) as required. The Project Manager will contract an academic program or institute to design and implement all the valuation studies, extrapolate the results of the valuation studies to the wider PAS and prepare the benefit-cost analysis. It is envisaged that staff from the PA institutions may participate in selected valuation studies to ensure continuity in future repeat valuation exercises. The Project Manager will contract a marketing and communications specialist - with specific expertise in financial media and communications – to design and implement the focused marketing and communications program. The MSPE will oversee and direct the work of the marketing and communications specialist. Information from this output will, in turn, support the preparation of the National Protected Area Financial Plan (see Output 1.2).

Output 1.2: A National Protected Area Financial Plan (NPAFP) is adopted

Based on the preliminary financial assessments undertaken during the preparatory phase, work under this output will focus on preparing a Financial Plan that is based on the realistic needs of the PAS, and the adoption of viable and diversified financial mechanisms to fund it. This business-oriented Financial Plan will be organized around three key aspects of the financial planning process: a) a detailed financial analysis that identifies funding needs and gaps, b) a pre-selection and analysis of different financial mechanisms, and an understanding of the legislative and regulatory framework for their implementation, and c) a formulation of the Financial Plan to guide the implementation of a sustainable financing strategy for the PAS.

The results of the valuation studies and benefit-cost analysis undertaken in Output 1.2 will be used to guide and direct the development of this financial plan. The lessons learnt in the implementation of Outputs 2.1 – 2.3 will also be integrated into the Financial Plan, wherever practicable. The outcomes of this assessment will, in turn, direct the implementation of Outputs 3.1 - 3.3.

The specific activities to be undertaken will include:

- Accurately updating the current financial baseline prepared for the PAS during the PPG, including analyzing the protected area costs, reviewing different income sources and identifying specific cost-reduction opportunities;

- Using financial planning tools (e.g. scenario logic) to: a) qualify and quantify the projected financial needs for the PAS under different management scenarios; and b) determine the ‘financial gap’ between the current financial scenario and the optimal (or desired) scenario;

- Assessing the functionality of the financial management system of the protected area institutions, including accounting (income and expenditure), salaries and benefits, classification of expenses (standardization), cash flow, transparency (availability of and access to information), and auditing (internal and external);

- Selecting the most appropriate financial mechanisms to ensure the diversification of financing sources for the PAS. The focus of this activity is on ensuring the maintenance, and increase in income, from conventional financial sources (governments, donors, and trust funds), as well as developing innovative alternatives (e.g. payments for environmental services, market mechanisms, etc.) to supplement the current income streams;

- Defining the legal and institutional framework that is required to mobilize financial resources, adopt business management principles, establish innovative financial mechanisms, and ensure the autonomy of financial management based on principles of modern governance;

- Identifying opportunities for cost-saving to achieve economies of scale, eliminate duplication and improve service delivery;

- Using a ‘market-based approach’, preparing a ‘National Protected Area Financial Plan’ (NPAFP) that establishes lines of strategic action to mobilize financial resources and build financial capacity to support a system of protected areas in Montenegro. The financial plan would include: a) a summary of financial needs and gaps (identified in point (ii) above); b) the investment priorities; c) a market analysis; d) financial mechanisms; e) economic impacts; f) a detailed implementation programme (detailed activities, staffing requirements and budget); and g) the means of measuring progress; and

- Documenting lessons learnt in the design and development of the NPAFP.

A national working group representing all the public agencies and institutions responsible for the planning, administration and monitoring of the PAS will be constituted to oversee the design and development of the NPAFP. This working group will be supplemented by the requisite expertise from the Ministry of Finance and NGO’s. The working group will, based on regional and global best practice, define the format and content of the NPAFP. The technical work in developing the Financial Plan will be undertaken by an international financial planning service provider. They will be required to work in close collaboration with the relevant departments and public institutions of the affected Ministries and Local Governments.  The NPAFP will be reviewed by the national working group and approved by the Project Steering Committee. Once approved, the NPAFP will be annexed to the National Biodiversity Strategy and Action Plan. The regulatory reform recommendations contained in the Financial Plan will specifically guide the implementation of Output 1.3.

Output 1.3: A suite of regulatory instruments are in place to support implementation of the NPAFP

Work under this output is focused on supporting the implementation of the recommended actions for regulatory and policy reform that are to be identified in the NPAFP (see Output 1.2). The NPAPF will thus direct the prioritized activities to be supported under this output. During the preparatory phase of the project however, a review of the enabling policy and legislation was undertaken to develop an initial idea of the strengths and weaknesses of the legal-regulatory framework for PA financing, and identify potential areas for project support.  It was evident from this review that, although the national policies and legislation do establish a modern and favorable policy and legislative context for the financing of the PAS, the secondary legislation and complementary tools and mechanisms to facilitate their in situ implementation remains poorly developed. A number of recommendations for the development of regulatory instruments, that could assist the operationalization of national policies and legislation, were thus preliminarily identified. These included the following:

- Development of regulations (or by-laws) that prescribe the rules, procedures and administration  for each of the different funding mechanisms provided for in national legislation and/or recommended by the NPAFP;

- Contribute to the preparation of enabling legislation that would provide for the establishment and administration of the Environmental Protection Fund (EPF);

- Contribute to the development of administrative procedures or provisions for earmarking disbursement of income from the EPF and/or local (municipal) environmental levies to support the planning and management of protected areas;

- Development of an incentives framework to retain skilled and competent protected area planning and management staff in the conservation sector;

- Evaluation, and strengthening, of the regulatory framework for PPP tourism concession agreements;

- Development of formal procurement procedures and contractual templates for the outsourcing of PA planning and operational functions; and

- Assessment of legal options for the integration of biodiversity offsets (that are linked to protected areas) into formal EIA decision-making and approval processes for large-scale development with significant environmental impact.

The national working group constituted to oversee the design and development of the NPAFP (see Output 1.2 above) will also coordinate the implementation of the activities under this output. It is envisaged that a national legal firm, with considerable experience in Montenegrin environmental law, be appointed on a retainer contract to the project to provide ongoing support to legal specialists employed within (or contracted to) the relevant national and local government institutions. They will report formally to the Project Manager but, depending on the nature of the support provided, the legal firm will work directly with the staff of the affected institution/s in preparing the necessary legal opinions, draft regulations, draft by-laws, contractual templates or formal procedures.

Component 2 Secure revenue-streams for the protected area system

Work undertaken in this component will seek to develop, implement and assess a suite of funding sources that could: (a) diversify the revenue streams for individual protected areas (see Outputs 2.1 and 2.2); and (b) improve the income-generation potential of existing user fees in PAs in northern Montenegro (see Output 2.3).

Output 2.1: A payment for ecosystem services (PES) scheme is piloted in the Durmitor World Heritage Site and National Park

The topography of the Durmitor World Heritage Site and National Park (see Map 2), situated in the northwest of Montenegro, is characterized by a 1500m plateau which is incised by the deep canyon valleys of the Tara, Draga, Komarnica and Susica rivers, and from which high mountain peaks rise up to 2525m. The Park thus serves as a watershed for the Municipality of Zabljak (resident population of 4,521) which obtains its entire supply of potable water from the park and surrounds. The town of Zabljak (resident population = 1,956) receives its water supply from springs around ‘Crvena greda’ and the wells of ‘Mlinski potok’. Beside the resident population the town also has 5 hotels, three motels, numerous private lodging facilities and a small ski resort with the capacity to host an additional 2,000 visitors. The Public Water Company (PWC) supplies water to 57% of the town users (at €0.26/m3 for households and €0.84/m3 for businesses) through gravitational pipelines from ‘Crvena greda’, while the remainder of the population collect water from local wells or ponds. The ski resort gets its water from the ‘Sopot’ spring, but does not have a purchasing relationship with the PWC. The total annual consumption value of the water supply to the town of Zabljak is roughly estimated at €81,136.

This output is designed to test the feasibility of capturing a revenue stream for an ecosystem service - clean water - provided by the park to a very specific group of beneficiaries – the town of Zabljak. Establishing this fiduciary relationship also has the potential to enhance the perceived value of the park with local residents and businesses, and may encourage a more responsible relationship between the park and its neighbouring communities. This pilot, if successful, could then provide an example of what could be possible elsewhere in Montenegro where ecosystem services are neither recognized by the marketplace nor by many decision-makers, and are thus undervalued and their management underfunded.

The activities for this output are then specifically directed at:

- Reviewing regional and global practice in equivalent local PES schemes and documenting best practice and lessons learnt;

- Establishing a working group - comprising representatives of the Municipality of Zabljak, Durmitor NP, PWC, residents and business (including hotels and the ski resort) - to discuss the modalities of contributing to park management costs for assuring the ongoing supply of clean water to the town of Zabljak;

- Accurately determining the current annual consumption value of water supply to Zabljak;

- Securing an in principle agreement from all stakeholders to review and decide on mechanisms for a payment to the park for protection of the watershed;

- Undertaking a detailed cost-benefit analysis of alternative payment (pricing of charges, administration of the charges, disbursement of the income) mechanisms for watershed protection (e.g. PWC and/or ski resort agrees to pay the park a fixed annually agreed fee; PWC agrees to pay the park a fixed percentage of its income from water supply to Zabljak; an additional watershed protection surcharge  is added onto the current household and business water charges, and administered by the PWC; a cubic meter surcharge is levied on the ski resort);

- Securing an agreement on the preferred payment mechanism;

- Developing the administrative procedures for the efficient collection and disbursement of income for watershed protection;

- Designing and implementing an extensive communications and awareness campaign in Zabljak about the administrative arrangements to be put in place to collect money to pay for watershed protection;

- Preparing, as required, municipal by-laws that would ensure legal enforcement of the preferred payment mechanism;

- Advertising the effective date, and administrative arrangements, for the implementation of the watershed protection surcharge; and

- Reviewing the efficacy of the implementation arrangements and documenting the lessons learnt.

Work under this output will be done under the overall guidance of the local working group (see point (ii) above) that will be constituted to represent the interests of all affected stakeholders in the town of Zabljak. The Project Manager will appoint an independent service provider (public consultation specialist) to constitute, organise, host, facilitate, mediate and record the activities of this working group. The public consultation specialist will also facilitate bilateral or multilateral meetings between parties to address any specific financial or technical issues or resolve any conflicts that may arise from time to time. The outcomes of these meetings shall, unless otherwise agreed, be made publicly available. The public consultation specialist shall also support the municipality, national park and PWC in implementing an effective joint communication and awareness campaign and in documenting the lessons learnt for wider dissemination. A financial specialist in the water sector will be contracted by the Project Manager to provide technical support to the local working group and will work in close collaboration with the public consultation specialist. They will specifically be tasked to: (i) review regional and national best practice in equivalent PES schemes; (ii) determine the current annual consumption value of water supply to Zabljak; (iii) define alternative payment mechanisms for watershed protection; (iii) undertake a cost-benefit analysis of each of these mechanisms; (iv) develop the administrative procedures for the collection and disbursement of income from a watershed protection surcharge; and (v) providing the technical inputs into the preparation of the requisite municipal by-laws. The Zabljak Municipality and the PWC shall, with support from the project, provide the lead in developing the most appropriate administrative and regulatory framework for implementation of the watershed protection surcharges. If required, the legal firm contracted under Output 1.3 may provide legal support services as and where required.

Output 2.2: A nature-based tourism concessioning process is piloted in Komovi Regional Park

Abutting the Albanian border, the mountainous region of Komovi is located in the south-eastern corner of the Tara River Basin Biosphere Reserve). An area of at least 21,000 ha in this region has been targeted for the establishment of the first Regional Park in Montenegro (see Map 2). The recently approved GEF Medium-Sized Project ‘Strengthening the sustainability of the PA system of Montenegro’ will support the establishment of the Komovi Regional Park. GEF and co-financing resources have been leveraged to, inter alia,: (i) undertake a feasibility assessment for the park; (ii) implement stakeholder consultation and negotiation processes; (iii) proclaim the regional park; (iv) demarcate the park boundaries; (v) appoint a management authority; (vi) upgrade basic park infrastructure; (vii) establish a co-management structure for the park; (viii) and establish a green business support program for SMEs.

Work under this output is designed to improve the financial sustainability of the regional park – once established - by piloting a nature-based tourism concessioning process that could allow a private commercial operator to construct and operate tourism facilities within the proclaimed regional park on the basis of a medium to long-term contract (~15-20 years on a ‘build-operate-transfer’ agreement), in return for payment of concession fees to the designated park management authority. If successful, this means of generating income would then enable the managing authority for the regional park to focus its resources and capacity on the core business of managing biodiversity. The provisions contained in the Law on Concessions (Official Gazette of Montenegro, No. 8/09) will provide the regulatory guide in the identification of the concession opportunity; procurement process; selection of a preferred bidder; concession period; negotiated legal agreement; concession management; and concessioning fee to be concluded in this output.

Work under this output will include the following elements:

- Global review – this will include an analysis of national, regional and international best practice in PA concessioning processes, and lessons learnt. Concessioning operating manuals, contractual templates for concessions, bidding memoranda and social and environmental guidelines would be collated to support and guide the concessioning process for the park.

- Identification of the concession opportunity - this will include the selection of the concession opportunity, mapping the concession area and establishing the scale and carrying capacities for the concession.

- Design of the concessioning process – this will include performing a legal review, designing the contract, developing the environmental guidelines, determining how to approach the social and empowerment issues, and modelling the operations to establish financial viability and minimum rentals.

- Inviting an expression of interest – this would involve the issuing of an Information Memorandum to potential investors providing basic details of the concession opportunity, its location and size, and a synopsis of how the process would be run. Interested investors will be requested to provide basic bidder information. This prequalification phase would ensure that the companies that emerge from the prequalification process all have the financial strength and proven experience in nature-based tourism development and management.

- Due-diligence and ground-truthing – this will involve giving all the prequalified bidders the opportunity to ascertain all the information they need to present informed and competitive bids, including physical facilities and ecological information; and to ensure that such access to information is equal for all prequalified bidders. The concession contract is finalised during this phase so that bidders have full knowledge of the contract before bidding.

- Bidding memorandum - the bidding memorandum will describe in detail the manner in which the actual bidding process is to be conducted, including what information is required, the opening of bids, how the technical components are to be evaluated, how the financial bids will be evaluated, the procedure for the announcement of winning bidders, closure of the concession contract, requirements in terms of the bid and development bond, payment of execution fees and the timetable;

- Appointment of the preferred bidder, contractual negotiation and contract management; and

- Documenting of lessons learnt, and collating tools developed, for further replication.

The Park Establishment Working Group (constituted under the counterpart medium-sized GEF project to oversee the regional park establishment process) will guide the initial planning stages of the concessioning process until the management authority for the park is formally designated. Thereafter the designated regional park management authority will take overall responsibility for implementing the concessioning process, finalising the contract and administering the concession agreement. The Project Manager will contract an international transaction adviser to provide technical support to the concessioning process, including: (i) best practice reviews; (ii) identification of concession opportunity; (iii) modelling economic feasibility of concession opportunity; (iv) preparing all legal and procedural documentation; (v) preparing information materials and responding to informational requests; (vi) overseeing compliance with selection criteria; (vii) due diligence of prequalified companies; (viii) contractual negotiations; and (ix) documentation of lessons learnt, best practice, templates and opportunities for replication. The Project Manager may also appoint the national nature-based tourism specialist contracted under Output 2.3 to work with the RTO Bjelasica and Komovi and the three affected local municipalities (Andrijevica, Kolasin and Podgorica) to preliminarily identify, assess and select the most appropriate concessioning opportunity in the Komovi RP.

Output 2.3: The income from user fees for adventure-based tourism in the protected areas of northern Montenegro is improved

During project preparation, adventure tourism was identified as one of the most promising means to generate additional revenue streams for the protected areas of northern Montenegro. Work under this output is directed at testing the feasibility of increasing park revenues by improving and strengthening the development, administration and promotion of adventure tourism services in Biogradska gora and Durmitor National Parks (when park management capacity is developed in the newly proclaimed Prokletije NP and the proposed Komovi RP, these areas will also be included under this output). Table 6 below provides an overview of the different adventure tourism services on offer in the protected areas of northern Montenegro, and the options for improvement and mechanisms for additional revenue capture.

Table 6: Menu of options to improve the revenue streams from adventure tourism in the PAs of northern Montenegro

| Adventure tourism service | Opportunities for improvement of adventure tourism services | Options for revenue capture |
| --- | --- | --- |
| Rafting, canoeing and kayaking | Improve facilities (e.g. launch sites) for rafting, canoeing and kayaking Evaluate rafting fee structure Rental of canoes and kayaks | Increased entrance fees Increased rafting fees Rental fees |
| Biking | Develop new, and maintain existing, biking trail network Prepare and distribute maps of biking trails Improve facilities Rentals of bikes | Increased (summer) entrance fees Bike rentals |
| Hiking | Develop new, and maintain existing trail network Prepare and distribute maps of hiking trails Multi-day trails | Increased entrance fees Hiking trail fees |
| Rock climbing | Formalize and map climbing areas Provide first aid and emergency services Prepare and distribute maps of climbing routes | Increased entrance fees Climbing fees |
| Caving | Identify caves that can be developed for recreational and scientific use and those that should be closed to visitors Develop visitor facilities and services in high volume use caves | Increased entrance fees Selected cave visit fees |
| Sport (fly) fishing | Promote sport fishing Rent fishing equipment Designate sport fishing areas Host fishing competitions | Increased entrance fees Fishing permits Competition fees Fishing equipment rental fees |
| Skiing and snowboarding | Improve licensing agreements with ski companies Improve facilities and services for cross-country skiers and snowboarders Rental of skiing and snowboarding equipment | Increase entrance fees License fees Rental fees |
| Accommodation for adventure tourism users | Establish multiple day hiking/cross-country skiing trails with overnight huts Improve tent camping sites Establish camper van sites | Camping and camper van fees Overnight hut fees Multiple day trail fees |
| Food outlets | Development of new food outlets/restaurants | Sales income |

Activities in this output will be specifically directed at:

- Preparing an overarching ‘adventure-based recreation and tourism strategy’ for the protected areas of northern Montenegro. This may include: a) needs analyses; b) feasibility assessments of different adventure products; c) identification of strategic priorities for adventure tourism development; d) defining the spatial distribution of adventure tourism products; and e) development of a framework plan of action;

- Supporting the establishment and implementation of market-based user fees for adventure tourism products. This would include: determining the willingness to pay; evaluating existing pricing structures; assessing expected revenue generation from increases in fees; developing fee collection methods; developing compliance systems; and monitoring the income from (and costs of) providing and maintaining the adventure tourism product;

- Assessing the conservation, management and use options for a number of caves (e.g. Jama u Malom Lomnom dolu, Jamski sistem u Obrucinama, Malo Lomno, Vjetrena brda and Ledena Pecina). This would include preparing a detailed management and business plan for a cave that could be considered for development as a nature-based tourism destination;

- Preparing and implementing an infrastructural and services development plan to support boating (commercial rafting, canoeing and kayaking) operations in the parks and improve revenues. This may include the: development of facilities at boat launch sites and exit points; commercial rental of boats and equipment; provision of emergency safety equipment and services; etc;

- Improving the network of cross-country skiing, hiking, biking and horse riding trails This may include the: development of minimum trail standards (environmental, construction, maintenance, etc.); assessment of the ‘state of trails’ in the NPs; upgrading of the trails as required (e.g. improving the drainage system, re-surfacing, re-alignment, step or bridge construction/repair, soil rehabilitation/ restoration, etc.) to meet minimum trail standards; development and installation of signage for trails; upgrading/construction of overnight huts; and developing mechanisms to address areas of potential user conflict;

- Formalising the park-approved sport climbing routes. This would include: identification of existing climbing routes; assessing the environmental impacts on these climbing routes; defining the ‘footprint’ of park-approved climbing routes, and guidelines for their use; identifying access routes to approved climbing routes; rehabilitating climbing routes that are not approved (e.g. removal of bolts, rehabilitation of informal paths, etc); and development and installation of park signage;

- Preparing information brochures, maps, signage and branding of all national park-approved tourism products and services;

- Developing working forums with the different adventure tourism user groups to facilitate collaboration and cooperation in the ongoing development of adventure tourism facilities and services; and

- Recording lessons learnt in implementation, and collation of planning tools and materials developed.

The Project Manager will, in close collaboration with PENP, contract an international nature-based tourism specialist to develop an ‘adventure tourism strategy’ for the protected areas of northern Montenegro. The tourism specialist will also provide technical and advisory support to the PA institutions in: the development of its fee structures (and their administration) for the adventure tourism products provided by PA’s; business planning processes for cave tourism development; identification of the infrastructure and services needed to support boat-based recreational and commercial use; recreational planning associated with skiing, biking, hiking and horse trails; and planning of climbing routes. The PA management will be directly responsible for the in situ development and maintenance of all infrastructure and services associated with the adventure tourism products. They will also be responsible for establishing and maintaining collaborative working forums with the recreational user groups and commercial operators. A tourism marketing agency will be contracted by the Project Manager to support PA institutions in designing, developing and producing adventure tourism maps and other promotional and marketing media.

Component 3 Developing institutional and individual capacity of PA institutions to raise cost-effectiveness of PA management

Output 3.1: Business planning processes are introduced to different categories of PAs

Work under this output will focus on supporting business planning processes in one national park (Biogradska Gora) and one nature reserve (Tivat Saltpan Nature Reserve). These PAs will serve as test sites for the future replication of business planning processes across other national parks (managed by PENP) and regional parks/nature reserves/natural monuments (managed by local municipalities). The product of the business planning processes undertaken under this output is the development of a business plan that will describe the financial opportunities offered by the park/reserve, provide recommendations on those opportunities that are most cost-effective and viable, and outline a strategy for pursuing them.

The process of development of the business plans for Biogradska gora National Park and Tivat Saltpan Nature Reserve will include:

- Preparing a management plan for Tivat Saltpan Nature Reserve;

- Reviewing the management plan for Biogradska gora, and updating as necessary;

- A review of the financial baseline of the park/reserve, and the financial needs of the park/reserve under different operational management scenarios.

- An overview of the “goods and services” that the park/reserve provides and the markets and competition that may exist for those goods and services now and in the future;

- A detailed assessment of the costs of pursuing the most viable sources of revenue for the park/reserve;

- A detailed assessment of the assumed benefits and income from those revenue streams, along with an assessment of risk;

- An assessment of the legal and political framework as it relates to pursing those revenue streams (e.g. whether tourism revenues will be ‘ring-fenced or whether they must be submitted to the local/central government budget, whether the protected area has the legal authority to sell biodiversity or other ecosystem service credits);

- A medium-term projection of the anticipated annual national/local government grant allocation to the park/reserve;

- An assessment of potential income from existing Montenegrin environmental financing mechanisms (e.g. environmental levies) and a medium-term projection of income from these sources;

- An assessment of opportunities to reduce park/reserve planning, administration and management costs (e.g. outsourcing of functions; concessioning visitor facilities and services; improving fee collection mechanisms; deployment of staff and equipment; leasing of large infrastructure and equipment; introducing more efficient financial systems, etc.);

- Detailed strategies, next steps, activities and investments required to capitalize on the most viable opportunities. This may also include a short-term fundraising strategy to raise the needed capital to pursue a particular strategy; and

- Documenting lessons learnt, preparing a generic PA business plan template and describing a set of standard business planning procedures.

The Project Manager will appoint an international business planning consultancy to provide professional and technical support to the park management of Biogradska gora NP and the Municipality of Tivat in preparing and updating their park/reserve management and business plans. The business planning consultancy will take overall responsibility for drafting the respective business plans. The park/reserve management authority will constitute a local stakeholder reference group to make structured inputs into the different stages of the business planning process. At each stage of the business planning process, the business planning consultancy will be responsible for hosting a business planning training and information sharing session for PENP staff from other national parks (in the case of Biogradska gora NP) and local government staff responsible for management of regional parks/nature reserves/natural monuments in other regions of Montenegro (in the case of Tivat Saltpan NR). The business planning consultancy shall also document lessons learnt from these test sites and, based on the lessons learnt, prepare a generic PA business plan template and describe a set of standard business planning procedures for integration into the NPAFP.

Output 3.2: The fund-raising capacity of PA institutions is improved

Work under this output will be focused on developing the capacity of the PA institutions to develop and implement a fund-raising strategy that could supplement current investments in the planning and management of the PAS. Targeted sources of funding under this output would include accessing grants and loans for PA development from: multilateral development agencies; regional development banks; bilateral aid agencies; international conservation organizations; and private donors (including individual donors, foundations and corporations). It will also facilitate the strengthening of partnerships with the private and NGO sector in the implantation of donor-funded projects.

The activities under this output are specifically directed at:

- Fund-raising and project management training for at least 10 targeted staff from different PA institutions. Training courses would include: knowledge of donor/lender profiles; loan/donor application procedures; project design; donor/bank agency liaison; project budgeting; project monitoring and loan repayments mechanisms;

- Developing a fund-raising strategy for the PAS. This could include inter alia: a) profiling potential donors and banks; b) identification and prioritization of partnership opportunities with potential donors or banks; c) strategic approaches to fund-raising; d) strategic approaches to maintaining funder relationships; d) exit strategies for funded projects; f) institutional capacity needs; g) information management; and h) monitoring and evaluation of funding strategies and approaches;

- Developing cost-efficient procedures for the management and administration of donor funds and/or loans;

- Developing marketing and communication materials for key projects targeted for donor funding or loans;

- Preparing, on a prioritized basis, detailed project proposals to potential donors and/or banks;

- Build, develop and formalise working relationship with NGOs, volunteers and academic institutions to support fund-raising efforts, and implement donor-funded projects;

- Establishing and maintaining a consolidated information database on prospective donors and banks, and funded projects; and

- Documenting lessons learnt, profiling training and skills development completed and collating fund-raising materials developed.

The Project Manager will, in close collaboration with the MSPE, appoint a specialist fund-raiser/project developer on an18 month retainer contract. The contractor shall be placed within the MSPE offices. This contracted individual will then support the development of the strategic framework, tools and mechanisms for fund-raising across the PAS. The fund-raiser/project developer will also focus on improving the skills base of a core of selected staff from different PA institutions in order to build the institutional sustainability of fund-raising efforts. The skills development, facilitated by the contractor, will include short-course training, mentoring, experiential training and regional study trips. The MSPE shall provide logistical support to the appointed contractor and will, in cooperation with the PA institutions, identify the staff who will receive skills development support.

Output 3.3: A business support ‘help desk’ assists in improving the cost-effectiveness of PA institutions

Work under this output will involve the establishment of a help desk function to provide ongoing technical and professional support in improving the efficiencies of the financial, business and operational functions of the PAS. It is envisaged that the specific recommendations for implementing these cost-effectiveness measures will be developed and described in more detail in the plan of action contained in the NPAFP (see Output 1.2). It is anticipated that activities under this output would then be programmed to follow on directly after adoption of the NPAFP.

Based on the preliminary assessment undertaken during the preparatory phase, it is envisaged that this ‘help desk’ may include the following support activities:

- Facilitating the implementation of recommendations for the improvement of existing financial management systems for PAs;

- Strengthening internal financial controls;

- Ensuring compliance with national financial management systems, accounting guidelines and standards and auditing requirements;

- Strengthening financial information flows to individual PAs;

- Providing advocacy support in motivating for an incremental increase of national budget allocations for the PAS

- Providing technical support in setting market-related pricing of PA products

- Providing support in developing more efficient user fee collection mechanisms;

- Facilitating the review of the organisational structure of, and staffing deployment in, PENP to improve efficiencies;

- Facilitate the implementation of incentives mechanisms for PA staff and ‘profitable’ PAs (i.e. those generating a surplus);

- Assisting outsourcing, concessioning, leasing and co-management processes that could improve cost-effectiveness of PA operations;

- Training and mentoring of key staff of PA institutions; and

- Documenting lessons learnt and collating information on institutional support provided.

Work under this output would be guided by the national working group constituted to oversee the design and development of the NPAFP (see Output 1.2). The international financial planning service provider contracted to prepare the NPAFP will be tasked by the Project Manager with the establishment and staffing of this ‘help desk’ facility. They will be required to work in close collaboration with the relevant departments and public institutions of the affected Ministries and Local Governments. It is foreseen that PA departments and institutions use the ‘help desk’ facility as a mechanism to improve staff skills. PA institutions will thus designate appropriate staff to work with, and be trained by, the contracted service provider.

### Financial modality

- The project activities are focused on knowledge management, regulatory reform, institutional capacity building and the in situ testing of financial planning technologies and systems. The project objective will thus be achieved primarily through the provision of technical assistance. No loan or revolving fund mechanisms are considered appropriate, and therefore grant-type funding is considered adequate to enable successful delivery of project outcomes.

### Indicators, Risks and Assumptions

The project indicators are detailed in the Strategic Results Framework which is attached in Section II of this Project Document. Project risks and risk mitigation measures are described in table 7 below.

Table 7: Risks facing the project and the risk mitigation strategy

| Risk | Rating | Mitigation Measures |
| --- | --- | --- |
| Government is slow in allocating sufficient funds to finance an expanded PAS, resulting in increasing pressures on the PA institutions to ‘exploit’ protected areas to offset costs of management | Moderate | The project will specifically seek to quantify the public good benefits, intrinsic values and non-use values of the PAS. On the basis of this valuation, the project will then prepare communications media to present the benefits and values of the PAS to key decision-makers in government. The project will then seek to negotiate an increase in government financial allocations to administer the expanded PAS. The project will also test financing mechanisms and cost-effective management approaches that could, over the long-term, incrementally reduce the ongoing dependency of the PAS on substantial annual government grant allocations. |
| Resistance to increasing (or introducing new) entrance fees, recreational user fees and PES surcharges. These conflicts cannot be timeously addressed and resolved. | Moderate | The project will: 1. Strengthen the capacity in PA institutions to: identify the equitable ‘market rate’ for PA products and services; evaluate consumer ‘willingness to pay’ (WTP); and measure the elasticity in demand 2. Facilitate the establishment of cooperative forums with different user groups to (amongst others): discuss any new fees and surcharges proposed; and comment on recommendations for increases to existing fees and surcharges. 3. Improve and diversify the facilities and services offered by the affected PAs in order to justify any increase in existing fees, or introduction of new fees 4. Strengthen the capacity of PA’s to improve the effectiveness of their fee collection methods 5. Identify mechanisms for the introduction of discounted rates for selected user groups (e.g. school groups, local communities, volunteers) to facilitate access to PA products and services |
| Local government (municipalities), Morsko dobro and Forest Administration do not fully participate in project activities | Moderate | The project will collaborate closely with the GEF-funded project ‘Strengthening the sustainability of the protected area system of Montenegro’ in: (i) ensuring the formal designation of management authority for the different categories of PAs (excluding national parks), as required by the new Law on Nature Protection; (ii) defining the anticipated human resource capacity needs (staffing, skills, competence levels, knowledge) of local government/ Morsko dobro and Forest Administration and the requisite resources, training and development requirements needed to address these capacity gaps; and (iii) contributing to the implementation of focused training programs for the responsible staff. The project will ensure that these institutions are properly consulted and adequately represented in the relevant working forums and the Project Steering Committee. The project will collaborate directly with, and strengthen the capacities of, the Municipality of Tivat (Tivat Saltpan Nature Reserve), the Andrijevica, Kolasin and Podgorica Municipalities (Komovi Regional Park) and the Forest Administration unit in Komovi. Lessons learnt will be documented for replication. |
| Income from environmental levies is not made available for use by PA institutions for conservation purposes | Low | The project will contribute to strengthening the regulatory framework for the Environmental Protection Fund (EPF). It will specifically help to develop administrative procedures for earmarking disbursement of income from the EPF, in close collaboration with the Ministry of Finance and the MESP. It will also support negotiations to ‘ring-fence’ income (on a pro rata basis) from other national and local (municipal) environmental levies to support the ongoing planning and management of protected areas. |
| Legal conflicts delay nature-based tourism concessioning processes in Komovi | Low | The project will conform to the legal framework of the Law on Concessions (Official Gazette of Montenegro, No. 8/09) in piloting the concessioning process in Komovi. |

### Cost Effectiveness

- The project will seek to achieve a catalytic investment in securing the long-term financial sustainability of the national protected area system. Costs incurred in project implementation will focus only on those additional actions required to provide key incremental assistance to the government in undertaking strategically critical reforms to improving the financial viability of the PAS. To accomplish this, the project will seek to complement and build upon the extensive baseline activities already underway in the sector, and the existing capacities of national and local government institutions, international agencies and NGO’s. Wherever possible, the project will use the competencies and logistical skills within the mandated national institutions to implement project activities. Where applicable, project resources will also be deployed to strengthen and expand existing PA funding initiatives and programmes to avoid duplication of effort. Increased co-financing commitments will continue to be targeted by the project during the implementation phase. Project implementation arrangements will be merged with those of the counterpart GEF-funded project ‘Strengthening the sustainability of the protected area system of Montenegro’ to reduce duplication of effort and reduce overhead and operating costs.

- The project is considered cost-effective for the following primary reasons:

- A comparatively small investment by the project in the valuation of the goods and services provided by protected areas will improve PA decision-making, and enable better communication of protected area benefits to communities, governments and donors. It is envisaged that the analysis of the economic benefits of the PAS could convince the government, communities and the private sector of the importance of increasing its investment in protected areas.

- A modest expenditure in the preparation of a medium-term national financial plan for the PAS will result in a national strategic framework that will guide and direct the future mobilisation of financial resources, and the development of financial capacities, to fund the administration of an expanded system of PAs in Montenegro.

- Project funding for the piloting of a PES scheme in Zabljak could, if succesfully implemented, directly yield an annual income to Durmitor NP of €5-10,000 per annum. The real value of the GEF investment may however be more fully realised if the payment for water services could be replicated for other catchment areas located (in part, or in whole) within PAs. The return on investment is then conservatively estimated at €100,000 -200,000 per annum.

- A relatively small project investment in supporting the piloting of a nature-based concession in Komovi Regional Park is expected to generate a financial return to park management of at least €20m over a 25-year concession (no adjustment for inflation) for re-investment in conservation management activities. Assuming a Build-Operate-Transfer concession agreement, the park will also take full ownership of the commercial venture (including capital assets) at the end of the concession agreement term. The lessons learnt in the concessioning process in Komovi will then provide the knowledge framework for PAs administered by local government to release and develop similar concession opportunities in other PAs as a means of generting income for their conservation management.

- Project investments in improving the adventure-based tourism enterprises in the PAs of northern Montenegro is expected to allow the affected PA institutions to increase current fee structures, and introduce new fees where relevant, for the provision of these facilities and services. Project resources will also be used to coordinate the marketing of the different adventure tourism products and facilitate collaboration in revenure capture mechanisms thus contributing to economies of scale. It is anticipated that adventure-based recreation and tourism in northern Montenegro would, over time, become the primary revenue generator for PAs in the region.

- Project support in improving the fund-raising capacity of the PA institutions is expected to yield a three-fold increase in the income raised per annum from different donor and grant funding sources for the PAS (from a baseline of ~€530,000 in 2008).

- Modest project investments in the introduction of business planning tools at the local PA level and the establishment of a central ‘help-desk’ function is expected to improve the cost-effectiveness of PA institutions by: (a) strengthening internal financial controls and financial systems; (b) ensuring effective flows of financial information; (c) optimising product-pricing; and (d) introducing incentive mechanisms for PAs and PA staff to improve income streams and reduce costs.

- The overall project is expected to generate significant new revenues to the PAS. Taken together, the GEF investment in Components 1, 2 and 3 of approximately US$ 1 million - disbursed over three years - is projected to generate additional revenue streams of at least US$2 million per year after completion of the project. The project’s cost effectiveness therefore, is based on substantial returns from increased central transfers and revenue generated through new financial mechanisms, optimized operational costs and new financial management capacity established in the Montenegrin PAS. Alternative approaches could include financing large-scale investment in PA infrastructure and equipment, through loans of the World Bank or EBRD. That scenario would presumably also achieve a similarly lasting effect in terms of PA financial health, but with much larger initial investment required and with the additional burden on the Government to repay loans during the uneasy times of the global financial crisis. The per-dollar value of achievements of the loan-based scenarios would therefore considerably exceed those of the proposed project.

### Sustainability

- The project has been carefully designed to optimize prospects for improving the sustainability of the protected area network in the following areas:

- Financial and institutional sustainability is an integral part of project design. The project will develop the systemic capacity of protected area institutions to more effectively secure and administer funds for protected area management. It will do this by: (i) developing a national strategic planning framework for the sustainable financing of the protected area system (Output 1.2); and (ii) strengthening the legal-regulatory framework to support the implementation of this strategic planning framework (Output 1.3). The project will also develop the institutional and individual capacity of two protected areas (Tivat Saltpan Nature Reserve and Biogradska Gora National Park) and protected area institutions by facilitating the adoption of modern business and financial management techniques in sourcing funding and improving cost-effectiveness. It will do this by: (i) introducing the business planning processes to protected areas administered by PENP and Local Government respectively (Output 3.1); (ii) developing and communicating a cost-benefit  argument for increasing annual government funding to the PAS (Output 1.1);  (iii)  strengthening the fund-raising skills and expertise in the MSPE (Output 3.2); and (ii) establishing a help desk to support PA institutions to improve the cost-effectiveness of their financial, business and operational systems (Output 3.3).  Finally the project will also provide support to individual protected areas in northern Montenegro to diversify and sustain a range of user pay mechanisms - payment for ecological services (Output 2.1), tourism concessions (Output 2.2) and adventure tourism product development (Output 2.3). If successfully implemented, these user-pay systems will contribute to diversifying and improving the long-term revenue streams for protected area management in the northern mountainous region of Montenegro. They will also provide lessons and tools for replication and scaling up in other protected areas across the country. It is thus envisaged that the GEF investment will catalyze a significant long-term improvement in the financial sustainability of the PAS of Montenegro.

- Environmental sustainability will be directly enhanced by the project through increasing the financial resources available for conservation. These funds will, in part, be used by PA institutions to implement mitigation measures to reduce the threats to the native biodiversity contained within the protected area system. Environmental sustainability will also be indirectly promoted in the project through a quantification of the contribution that the establishment and management of a representative protected area system makes (or could make) to the socio-economic well-being of Montenegro (Output 1.1). Project activities will seek to demonstrate that a number of protected areas could, over time, become an economically viable form of use and actively contribute to local economic development, particularly in rural areas (Output 1.2). The ‘mainstreaming’ of protected areas and an incremental reduction on the dependence of protected areas on the fiscus will provide a powerful rationale for overcoming a government reticence to invest in, and increase the extent of, the protected area estate in order to effectively protect threatened ecosystems, habitats and species.

- Social sustainability will be enhanced through the implementation of a number of individual stakeholder engagement processes developed for each of the project activities. Robust stakeholder engagement plans for the respective project activities will be prepared to ensure direct stakeholder involvement in all aspects of business and financial planning, and in the implementation of revenue generation mechanisms, at both the national (PAS) and local (individual PAs) levels. These stakeholder engagement plans will also make strong provision for conflict management with different categories of user groups. The project will further identify approaches to, and mechanisms for, the direct involvement of the private sector, local user groups and NGOs in revenue generation, notably though partnerships, co-management and co-operative governance. By example, the feasibility of concessioning nature-based tourism enterprises to the private sector in return for payment of concession fees will be tested (Output 2.2). The project will invest in improving the quality of adventure tourism services to park visitors (Output 2.3) and raise income from donors and financiers for capital investments in park user facilities and services (Output 3.2).

### 2.9	Replicability

- Replication will be achieved in the project through the direct replication of selected project elements and practices and methods, as well as the scaling up of experiences.

- The project will support the Government of Montenegro in: (i) developing a long-term sustainable financing plan for the terrestrial and marine PAS; (ii) adopting business planning processes in PAs; and (iii) strengthening the enabling legal-regulatory framework and institutional capacity for implementation of the financing plan. GEF funding will then be used to test the efficacy of a suite of different financing mechanisms (advocacy for improved government budget allocation, fund-raising from donors and financiers, PES, tourism concessioning, adventure-based tourism product development) and cost-effective management approaches as a means towards increasing, diversifying and stabilizing financial flows to the PAS. It is envisaged that the lessons learnt from the implementation of these mechanisms and approaches will be used by the project to then guide the replication and/or scaling up across the PAS. Each project output will include the documentation of lessons learnt from implementation of activities under the output, and a collation of the tools and templates (and any other materials) developed during implementation. The Project Manager will use the knowledge management system, developed under the current GEF Medium-Sized Project ‘Strengthening the sustainability of the PA system of Montenegro’, to ensure the collation of all the experiences and information. This knowledge database will then be made accessible to different PA stakeholder groups in order to support better decision-making processes. Information contained in the knowledge management system will also be used for the iterative refinement and updating of the NPAFP and PA business plans.

- By year 3, it is anticipated that all the protected areas in northern Montenegro will be implementing business planning processes that are geared to strengthening their financial sustainability.

# PART III: PROJECT RESULTS FRAMEWORK

This project will contribute to achieving the following Country Programme Outcome as defined in CPAP or CPD: By 2011, Public Institutions with the support of Civil Society Organizations (CSO) are better able to ensure good governance, rule of law and equal access to justice and promotion of human rights.

Country Programme Outcome Indicators: Environmentally responsible economic development

Primary applicable Key Environment and Sustainable Development Key Result Area (same as that on the cover page, circle one): Improved management of protected areas

Applicable GEF Strategic Objective and Program: SO: Catalyze Sustainability of Protected Area Systems; SP: Sustainable finance of protected area systems at the national level

Applicable GEF Expected Outcomes: Biodiversity conserved and sustainably used in protected area systems; Strategic Programme: PA systems secure increased revenue and diversification of revenue streams to meet total expenditures required to meet management objectives; Reduction in financing gap to meet PA management objectives

Applicable GEF Outcome Indicators: Total revenue and diversification in revenue streams

| Project Strategy and purpose | Objectively verifiable indicators |
| --- | --- |
|  | Indicator | Baseline | Target by EOP | Sources of verification | Assumptions and risks |
| Project Objective: To improve the financial sustainability of Montenegro’s protected area system | Financial sustainability scorecard for national system of protected areas | PAS project target: 45% | >55% | Annual review of Financial Sustainability Scorecard | Assumptions: The government commits to actively supporting implementation of the enabling legislation for the PAS Existing staff skills and competencies are retained in the PA institutions Current revenue streams to the PAS are maintained and reinvested back into PA management Risks: Government fails to allocate sufficient funds to finance the management of an expanded PAS Local government, Morsko dobro and Forest Administration do not fully participate in project activities |
|  | Capacity development indicator score for protected area system | PAS project targets: Systemic: 47% Institutional: 56% Individual: 57% | Systemic: 57% Institutional: 60% Individual: 62% | Annual review of Capacity Development Indicator Scorecard |  |
|  | Total budget (including operational, HR and capital budget) (US$) for protected area management | Current: US$3,946,611 PAS Project target: US$5,060,000 | This project target: >6.5m | Annual financial report of the MSPE |  |
| Outcome 1: Enabling legal and policy environment for improved PA financial sustainability | Outputs: An economic valuation of the PAS support the case for sustained public investment in protected area establishment and management A National Protected Area Financial Plan (NPAFP) is adopted A suite of regulatory instruments are in place to support implementation of the NPAFP |
|  | Decision-making on government budget allocation is based on economic valuation | No | Yes | Annual financial report of the MSPE | Assumptions: Data to derive the economic valuations of the five selected PAs is readily available The NPAFP is adopted as an integral part of the NBSAP There is political support for the establishment of the EPF Regulations are an appropriate legal vehicle to support the operationalization of financing mechanisms provided for in national legislation Risks: Income from environmental levies is not earmarked for use by PAs |
|  | National PA Financing plan operational | - | Yes | Annual financial report of the MSPE |  |
|  | Number of enabling regulations that support implementation of financial mechanisms provided for in legislation | 3 | >6 | Regulations adopted by national and/or local government |  |
| Outcome 2: Securing revenue streams for the PA system | Outputs: 2.1 A payment for ecological services scheme is piloted in the Durmitor World Heritage Site 2.2 A nature-based tourism concessioning process is piloted in Komovi Regional Park 2.3 The income from user fees for adventure-based tourism in the protected areas of northern Montenegro is improved |
|  | Total annual central government budget allocation (US$) per annum for PA management | US$1,627,109 | >US$2,400,000 | Annual financial report of the MSPE | Assumptions: The establishment processes for Komovi Regional Park are successfully concluded Prospective bidders express an interest in a concession opportunity for Komovi RP Zabljak Municipality sustain support for the introduction of a water levy Recreational and nature-based adventure tourism products will be developed without compromising the ecological integrity of the protected areas Risks: Resistance to increasing, or introducing, entrance fees, recreational user fees and PES surcharges Income from environmental levies is not earmarked for use by PAs Legal conflicts delay nature-based tourism concessioning processes |
|  | Total local government budget allocation (US$) per annum for PA management | ~US$40,000 | >US$200,000 | Annual financial reports of affected municipalities |  |
|  | Earmarked income (US$) for PA management per annum sourced from different environmental levies and surcharges | US$0 | >US$100,000 | Annual financial reports of environmental funds |  |
|  | Income (US$) to PENP per annum from a PES scheme for water | US$0 | >US$11,250 | Annual financial report of the PENP |  |
|  | Number of nature-based concessions in PAs administered by local government | 0 | 1 | Legal concession agreements |  |
|  | Income (US$) from recreation and nature-based tourism activities in the four PA’s (Durmitor NP, Biogradska Gora NP, Komovi RP and Prokletije NP) in northern Montenegro | US$677,964 | >US$1,200,000 | Annual financial report of PENP and the Komovi RP management authority |  |
| Outcome 3: Development of institutional and individual capacity of PA institutions to raise PA management cost-effectiveness | Outputs: 3.1 Business planning processes are introduced to different categories of PAs 3.2 The fund raising capacity of the MSPE is improved 3.3 A business support ‘help desk’ assists in improving the cost effectiveness of PA institutions |
|  | Number of protected areas with business plans that enables the implementation of the approved management plan | 1 | 4 (comprising two national parks, one regional park and one nature reserve) | Approved PA management plans and business plans | Assumptions: PA institutions adopt a business planning approach in the planning of protected areas MSPE provide political, technical and logistical support to the project-funded fund-raiser/project developer Protected area institutions designate staff to undergo mentoring, training and skills development A range of donor institutions remain invested in Montenegro Risks: Local government, Morsko dobro and Forest Administration do not fully participate in project activities |
|  | Annual financial support (US$) for the planning and management of PAs from donor funding sources or loans | US$795,000 | US2,200,000 | Annual financial report of PA institutions |  |
|  | Ratio of human resource to operational costs | ~80:20 | 60:40 | Annual financial report of PA institutions |  |
|  | Average % improvement per annum of PA staff salaries | 0 | >10% | Annual HR reports of PA institutions |  |

TOTAL BUDGET AND WORKPLAN

| Award Title: | PIMS 4279 Montenegro PAS |
| --- | --- |
| Award ID: | [to be added when the budget is entered into Atlas] |
| Business Unit: | MNE10 |
| Project Title: | PIMS 4279BD MSP: Catalyzing financial sustainability of the protected area system in Montenegro |
| Implementing Partner (Executing Agency) | UNDP (Ministry of Spatial Planning and Environment) |
| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 2010/11 (USD) | Amount Year 2 2011/12 (USD) | Amount Year 3 2012/13 (USD) | Total (USD) | Budget note |
| COMPONENT 1: Enabling legal and policy environment for improved PA financial sustainability | Ministry of Spatial Planning and Environment (MSPE) | 62000 | GEF | 71200 | International Consultants | 0 | 8,000 | 0 | 8,000 | 1 |
|  |  |  |  | 71300 | Local Consultants | 57,000 | 24,000 | 12,000 | 93,000 | 2 |
|  |  |  |  | 71600 | Travel | 2,000 | 3,000 | 1,000 | 6,000 | 3 |
|  |  |  |  | 72100 | Contractual services - companies | 18,000 | 51,000 | 0 | 69,000 | 4 |
|  |  |  |  | 74100 | Professional services | 4,000 | 5,000 | 3,000 | 12,000 | 5 |
|  |  |  |  | 74200 | Audio visual and printing costs | 2,000 | 4,000 | 2,000 | 8,000 | 6 |
|  |  |  |  | 74500 | Miscellaneous | 1,000 | 2,000 | 1,000 | 4,000 | 7 |
|  |  |  |  | Total Outcome 1 | 84,000 | 97,000 | 19,000 | 200,000 |  |
| COMPONENT 2: Securing revenue streams for the PA system | MSPE | 62000 | GEF | 71200 | International Consultants | 15,000 | 66,000 | 28,000 | 109,000 | 8 |
|  |  |  |  | 71300 | Local Consultants | 9,000 | 39,000 | 27,000 | 75,000 | 9 |
|  |  |  |  | 71600 | Travel | 4,000 | 5,000 | 3,000 | 12,000 | 10 |
|  |  |  |  | 72200 | Equipment and furniture | 8,000 | 16,000 | 14,000 | 38,000 | 11 |
|  |  |  |  | 72300 | Materials and goods | 16,000 | 34,000 | 14,000 | 64,000 | 12 |
|  |  |  |  | 74100 | Professional services | 25,000 | 52,000 | 22,000 | 99,000 | 13 |
|  |  |  |  | 74200 | Audio visual and printing costs | 4,000 | 8,000 | 15,000 | 27,000 | 14 |
|  |  |  |  | 74500 | Miscellaneous | 3,000 | 2,000 | 1,000 | 6,000 | 15 |
|  |  |  |  | Total Outcome 2 | 84,000 | 222,000 | 124,000 | 430,000 |  |
| COMPONENT 3: Development of institutional and individual capacity of PA institutions to raise PA management cost-effectiveness | MSPE | 62000 | GEF | 71200 | International Consultants | 0 | 6,000 | 6,000 | 12,000 | 16 |
|  |  |  |  | 71300 | Local Consultants | 25,000 | 40,000 | 10,000 | 75,000 | 17 |
|  |  |  |  | 71400 | Contract services - individuals | 10,000 | 35,000 | 10,000 | 55,000 | 18 |
|  |  |  |  | 71600 | Travel | 2,000 | 8,000 | 4,000 | 14,000 | 19 |
|  |  |  |  | 72100 | Contractual services - companies | 20,000 | 35,000 | 5,000 | 60,000 | 20 |
|  |  |  |  | 72800 | Information and Technology Equipment | 5,000 | 1,000 | 1,000 | 7,000 | 21 |
|  |  |  |  | 74500 | Miscellaneous | 1,000 | 1,000 | 0 | 2,000 | 22 |
|  |  |  |  | Total Outcome 3 | 63,000 | 126,000 | 36,000 | 225,000 |  |
| PROJECT MANAGEMENT | MSPE | 62000 | GEF | 71300 | Local Consultants | 30,000 | 30,000 | 30,000 | 90,000 | 23 |
|  |  |  |  | 72800 | Information and technology equipment | 5,000 | 0 | 0 | 5,000 | 24 |
|  |  |  |  | Total Project Management | 35,000 | 30,000 | 30,000 | 95,000 |  |
| TOTAL | 266,000 | 475,000 | 209,000 | 950,000 |  |

Budget notes:

- Pro rata costs of contractual appointment of monitoring and evaluation expert for mid-term and final evaluation.

- Costs of contractual appointment of: economic valuation consultancy service; marketing and communications service provider; and legal advisory service. Pro rata costs of contractual appointment of monitoring and evaluation review consultant, auditor and evaluation expert.

- In country travel costs for project stakeholder institutions to attend local reference group meetings (economic valuations) and national working group meetings (preparation of national protected area financial plan). Pro rata in-country travel costs associated with mid-term and end of project evaluation. In-country travel costs estimated at US$0.35/km.

- Costs of contractual appointment of financial planning service provider.

- Service level agreements with the MSPE (and its PEs) to recover pro rata costs associated with data support services (economic valuation of targeted PAs/ financial baseline data), advocacy support (communication of economic benefits of PAS) and  legal services (development of regulatory instruments).

- Costs associated with producing various communication media and resource materials (e.g. presentations, ‘road shows’, information brochures, fact sheets) in support of focused advocacy activities.

- Logistical costs associated with organizing reference group meetings (economic valuations) and national working group meetings (preparation of national protected area financial plan) -venue, catering, facilitation, printing, translation, etc.

- Costs of contractual appointment of: financial specialist (PES – water supply); transaction adviser (nature-based tourism concessions); and nature-based adventure recreation and tourism planning specialist.  Pro rata costs of contractual appointment of monitoring and evaluation expert for mid-term and final evaluation.

- Costs of contractual appointment of: public consultation specialist; legal adviser; nature-based adventure tourism specialist; and tourism marketing agency. Pro rata costs of contractual appointment of monitoring and evaluation experts for mid-term and final evaluation.

- In country travel costs for project stakeholder institutions to attend local and regional working group meetings (Zabljak PES working group, Komovi RP establishment working group/liaison forum and adventure recreation/tourism collaborative forums for PAs of northern Montenegro). Pro rata flight (Bratislava-Podgorica return) and in-country travel costs associated with mid-term and end of project evaluation. In-country travel costs estimated at US$0.35/km.

- Co-financing of the design, production and installation of informational and directional signage associated with adventure-based recreational and tourism services in the PAs of northern Montenegro. Co-financing the procurement of emergency and safety equipment for mountain rescue services in Durmitor NP, Biogradska Gora NP, Prokletije NP and Komovi RP. This may include acquisition of the following emergency and safety equipment to support park-approved adventure tourism services (boat-based activities, trail-based services, caving services and mountain climbing activities): radio and telephone communications; protective wear; portable stretchers; medical equipment and supplies; rope rescue and rigging systems; headlamps; helmets; casualty bags; breathing apparatus; and lifejackets.

- Co-financing the procurement of materials and goods needed to develop, improve and upgrade the adventure tourism facilities and infrastructure (i.e. upgrading entry and pay points, improving boat launch sites and exit points, trails construction and maintenance, upgrading of overnight huts, rehabilitation of degraded areas)  in Durmitor NP, Biogradska Gora NP, Prokletije NP and Komovi RP.  Materials and goods to be acquired may include: geo-textiles, concrete; stone; paint, wood, poles, stones, booms, gates, gravel, fencing, climbing bolts, reinforcing rods, gabions, etc.

- Service level agreements with Zabljak Municipality, the Komovi RP management authority and PENP to recover the pro rata costs associated with: development and implementation of a PES water surcharge in Zabljak; nature-based tourism concessioning process in Komovi RP; the development and maintenance of park infrastructure and services associated with adventure tourism; and the provision of outsourced specialist staff training, as needed.

- Costs associated with the preparation and printing of adventure-tourism maps and other promotional materials (website information, brochures, CDs, etc.) for the PAs of northern Montenegro. Costs associated with the printing of bid documentation for the Komovi Regional Park concession. Costs associated with advertising the intent of the Zabljak Municipality, the PWC and Durmitor NP to introduce a water surcharge in Zabljak.

- Logistical costs associated with organizing local and regional working group meetings (see note 10 above) - venue, catering, facilitation, printing, translation, etc.

- Pro rata costs of contractual appointment of monitoring and evaluation expert for mid-term and final evaluation.

- Costs of contractual appointment of the business and management planning consultant.

- Service level employment agreement for the dedicated fund raiser/project developer

- In country travel costs for project stakeholder institutions to attend local working group meetings (local stakeholder reference groups for business planning in Tivat Saltpan NR and Biogradska Gora NP). Local and regional (Balkan region) travel costs for fund-raiser/project developer. Pro rata flight (Bratislava-Podgorica return) and in-country travel costs associated with mid-term and end of project evaluation. In-country travel costs estimated at US$0.35/km.

- Costs of contractual appointment of financial planning service provider.

- Acquisition of 1 Laptop (1@US$2000), software licenses (1@US$800), portable hard drive (1@US$200), printer (1@US$300), data projector (1@US$800) and mobile phone contracts (1@US$2000) and other peripherals and incidentals (@US900) for the fund-raiser/project developer.

- Logistical costs associated with organizing local working group meetings (see note 19 above) - venue, catering, facilitation, printing, translation, etc.

- Full costs of contractual appointment of Project Manager, and 65% of the costs of the contractual appointment of the Project Assistant (35% of costs of PA to be co-financed by UNDP CO).

- Acquisition of 2 Laptop (2@US$2,000), 1 portable hard drive (1@US$200) and 1 printer (1@US$300)

| Summary of Funds: |  |  |  |  | Year 1 | Year 2 | Year 3 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | GEF | 266,000 | 475,000 | 209,000 | 950,000 |
|  |  |  |  | Ministry of Spatial Planning and Environment | 2,225,000 | 3,475,000 | 1,225,000 | 6,925,000 |
|  |  |  |  | German Technical Cooperation (GTZ) | 110,000 | 150,000 | 40,000 | 300,000 |
|  |  |  |  | UNDP CO Montenegro | 18,000 | 12,000 | 10,000 | 40,000 |
|  |  |  |  | TOTAL | 2,619,000 | 4,112,000 | 1,484,000 | 8,215,000 |

# PART IV:  MANAGEMENT ARRANGEMENTS

The project will be implemented over a period of three years.  UNDP will be responsible for the implementation of the project.  The project will be directly executed (DEX), in line with the Standard Basic Assistance Agreement (SBAA, 2006) and the Country Programme Action Plan 2007-2011 (CPAP, 2007) signed between the UNDP and the Government of Montenegro.

The UNDP, in close cooperation with Ministry of Spatial Planning and Environment (MSPE), will take overall responsibility for the project implementation, and the timely and verifiable attainment of project objectives and outcomes.  The GEF Operational Focal point will represent MSPE at the Project Steering Committee (PSC), while a MSPE high level official who has been nominated as an UNDP Focal Point will provide the government oversight and guidance to the project implementation.  The MSPE UNDP Focal Point will not be paid from the project funds, but will represent a Government in-kind contribution to the Project.

Working closely with the MSPE, the UNDP Country Office (CO) will also be responsible for: (i) providing financial and audit services to the project; (ii) recruitment of project staff and contracting of consultants and service providers; (iii) overseeing financial expenditures against project budgets approved by PSC; (iv) appointment of independent financial auditors and evaluators; and (iv) ensuring that all activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures. A UNDP staff member will be assigned with the responsibility for the day-to-day management and control over project finances.

The Project Steering Committee (PSC) constituted by the counterpart GEF-funded ‘Strengthening the sustainability of the protected area system of Montenegro’ will also serve as this project’s coordination and decision-making body.  It will meet according the necessity, but not less than once in 6 months, to review project progress, approve project work plans and approve major project deliverables. The PSC is responsible for ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project document. The PSC’s role will include: (i) overseeing project implementation; (ii) approving all project work plans and budgets, at the proposal of the Project Manager (PM), for submission to UNDP Regional Center in Bratislava and GEF Unit in New York; (iii) approving any major changes in project plans or programs; (iv) providing technical input and advice; (v) approving major project deliverables; (vi) ensuring commitment of resources to support project implementation; (vii) arbitrating any conflicts within the project and/or negotiating solutions between the project and any parties beyond the scope of the project; and (ix) overall project evaluation. The PSC may include in its composition representation of the following stakeholders: MSPE (Dept. Nature Protection, NPI, PENP, Morsko dobro and EPA); Ministry of Agriculture, Forestry and Water Resources (Forest Administration); Ministry of Finance; Real Estate Administration; Local Municipalities (Andrijevica, Kolasin, Tivat and Podgoricar) and civil society (e.g. REC, Green Home, Greens of Montenegro, MOST, WWF).

The day-to-day administration of the project will be carried out by a Project Manager (PM) and Project Assistant (PA), located within UNDP office. The project staff will be recruited using standard UNDP recruitment procedures. The PM will, with the support of the PA, manage the implementation of all project activities, including:  preparation/updates of project work and budget plans, record keeping, accounting and reporting; drafting of terms of reference, technical specifications and other documents as necessary; identification, proposal of project consultants to be approved by the PSC, coordination and supervision of consultants and suppliers; organization of duty travel, seminars, public outreach activities and other project events; and maintaining working contacts with project partners at the central and local levels. The Project Manager will liaise and work closely with all partner institutions to link the project with complementary national programs and initiatives. The PM is accountable primarily to UNDP and the MSPE, and then to PSC for the quality, timeliness and effectiveness of the activities carried out, as well as for the use of funds.

The PM will produce Annual Work and Budget Plans (AWP&ABP) to be approved by the PSC at the beginning of each year. These plans will provide the basis for allocating resources to planned activities. Once the PSC approves the Annual Work Plan this will be sent to the UNDP Regional Technical Advisor for Biodiversity at UNDP Regional Centre for Europe and Commonwealth of Independent States in Bratislava for revision and approval. Once the Annual Working Plan and Budget is approved by the Regional Centre it will be sent to the UNDP/GEF Unit in New York for final approval and release of the funding. The PM will further produce quarterly operational reports and Annual Progress Reports (APR) to the PSC, or any other reports at the request of the PSC.  Like in the case for the Annual Work Plan these reports are sent for approval and clearance to the UNDP Regional Centre in Bratislava.  These reports will summarize the progress made by the project versus the expected results, explain any significant variances, detail the necessary adjustments and be the main reporting mechanism for monitoring project activities. The PM will be technically supported by contracted national and international service providers, by other public institutions, by contracted NGO’s and by other linked donor funded project units. Recruitment of all specialist services for the project will be done by the PM, in consultation with the UNDP and MSPE.

Audit Clause

The Government will provide the Resident Representative with certified periodic financial statements, and with an annual audit of the financial statements relating to the status of UNDP (including GEF) funds according to the established procedures set out in the Programming and Finance manuals. The Audit will be conducted by the legally recognized auditor of the Government, or by a commercial auditor engaged by the Government.

Use of intellectual property rights

In order to accord proper acknowledgement to GEF for providing funding, a GEF  logo should appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF. The UNDP logo should be more prominent -- and separated from the GEF logo if possible, as UN visibility is important for security purposes.

# PART V:  MONITORING FRAMEWORK AND EVALUATION

Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures and will be provided by the project team and the UNDP Country Office (UNDP-CO) with support from UNDP/GEF.  The Project logframe (Project Results Framework) in Annex A provides performance and impact indicators for project implementation along with their corresponding means of verification. These will form the basis on which the project's Monitoring and Evaluation system will be built. The following sections outline the principle components of the Monitoring and Evaluation Plan and indicative cost estimates related to M&E activities. The project's Monitoring and Evaluation Plan will be presented and finalized at the Project's Inception Report following a collective fine-tuning of indicators, means of verification, and the full definition of project staff M&E responsibilities.

The project will be monitored through the following M& E activities.

Project start:

A Project Inception Workshop will be held within the first 2 months of project start with those with assigned roles in the project organization structure, UNDP country office and where appropriate/feasible regional technical policy and programme advisors as well as other stakeholders.  The Inception Workshop is crucial to building ownership for the project results and to plan the first year annual work plan.

The Inception Workshop should address a number of key issues including:

- Assist all partners to fully understand and take ownership of the project.  Detail the roles, support services and complementary responsibilities of UNDP CO and RCU staff vis à vis the project team.  Discuss the roles, functions, and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for project staff will be discussed again as needed.

- Based on the project results framework and the relevant GEF Tracking Tool if appropriate, finalize the first annual work plan.  Review and agree on the indicators, targets and their means of verification, and recheck assumptions and risks.

- Provide a detailed overview of reporting, monitoring and evaluation (M&E) requirements.  The Monitoring and Evaluation work plan and budget should be agreed and scheduled.

- Discuss financial reporting procedures and obligations, and arrangements for annual audit.

- Plan and schedule Project Board meetings.  Roles and responsibilities of all project organisation structures should be clarified and meetings planned.  The first Project Board meeting should be held within the first 12 months following the inception workshop.

An Inception Workshop report is a key reference document and must be prepared and shared with participants to formalize various agreements and plans decided during the meeting.

Quarterly:

- Progress made shall be monitored in the UNDP Enhanced Results Based Managment Platform.

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc...  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

Annually:

Annual Project Review/Project Implementation Reports (APR/PIR):  This key report is prepared to monitor progress made since project start and in particular for the previous reporting period (30 June to 1 July).  The APR/PIR combines both UNDP and GEF reporting requirements.

The APR/PIR includes, but is not limited to, reporting on the following:

- Progress made toward project objective and project outcomes - each with indicators, baseline data and end-of-project targets (cumulative)

- Project outputs delivered per project outcome (annual).

- Lesson learned/good practice.

- AWP and other expenditure reports

- Risk and adaptive management

- ATLAS QPR

- Portfolio level indicators (i.e. GEF focal area tracking tools) are used by most focal areas on an annual basis as well.

Periodic Monitoring through site visits:

UNDP CO and the UNDP RCU will conduct visits to project sites based on the agreed schedule in the project's Inception Report/Annual Work Plan to assess first hand project progress.  Other members of the Project Board may also join these visits.  A Field Visit Report/BTOR will be prepared by the CO and UNDP RCU and will be circulated no less than one month after the visit to the project team and Project Board members.

Mid-term of project cycle:

The project will undergo an independent Mid-Term Evaluation at the mid-point of project implementation (insert date).  The Mid-Term Evaluation will determine progress being made toward the achievement of outcomes and will identify course correction if needed.  It will focus on the effectiveness, efficiency and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation and management.  Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.  The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document.  The Terms of Reference for this Mid-term evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF.  The management response and the evaluation will be uploaded to UNDP corporate systems, in particular the UNDP Evaluation Office Evaluation Resource Center (ERC).

The relevant GEF Focal Area Tracking Tools will also be completed during the mid-term evaluation cycle.

End of Project:

An independent Final Evaluation will take place three months prior to the final Project Board meeting and will be undertaken in accordance with UNDP and GEF guidance.  The final evaluation will focus on the delivery of the project’s results as initially planned (and as corrected after the mid-term evaluation, if any such correction took place).  The final evaluation will look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental benefits/goals. The Terms of Reference for this evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF.

The Terminal Evaluation should also provide recommendations for follow-up activities and requires a management response which should be uploaded to PIMS and to the UNDP Evaluation Office Evaluation Resource Center (ERC).

The relevant GEF Focal Area Tracking Tools will also be completed during the final evaluation.

During the last three months, the project team will prepare the Project Terminal Report. This comprehensive report will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results.

Learning and knowledge sharing:

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

The M& E budget is provided in the table below.

| Type of M&E activity | Responsible Parties | Budget US$ | Time frame |
| --- | --- | --- | --- |
| Inception Workshop (IW) | Project Manager MSPE, UNDP, UNDP GEF | 5,000 | Within first two months of project start up |
| Inception Report | Project Team PSC, UNDP CO | None | Immediately following IW |
| Measurement of Means of Verification for Project Purpose Indicators | Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members | To be finalized in Inception Phase and Workshop. Cost to be covered by targeted survey funds. | Start, mid and end of project |
| Measurement of Means of Verification for Project Progress and Performance (measured on an annual basis) | Oversight by Project GEF Technical Advisor and Project Manager Measurements by regional field officers and local IAs | TBD as part of the Annual Work Plan's preparation. Cost to be covered by field survey budget. | Annually prior to APR/PIR and to the definition of annual work plans |
| APR and PIR | Project Team PSC UNDP-GEF | None | Annually |
| TPR | Government Counterparts UNDP CO, Project team UNDP-GEF RCU | None | Every year, upon receipt of APR |
| Steering Committee Meetings | Project Manager | None | Following IW and annually thereafter. |
| Technical and periodic status reports | Project team Hired consultants as needed | 6,000 | TBD by Project team and UNDP-CO |
| Mid-term External Evaluation | Project team PSC UNDP-GEF RCU External Consultants (evaluation team) | 24,000 | At the mid-point of project implementation. |
| Final External Evaluation | Project team, PSC, UNDP-GEF RCU External Consultants (evaluation team) | 30,000 | At the end of project implementation |
| Terminal Report | Project team PSC External Consultant | None | At least one month before the end of the project |
| Audit | UNDP-CO Project team | 5,000 | Yearly |
| Visits to field sites (UNDP staff travel costs to be charged to IA fees) | UNDP-CO, UNDP-GEF RCU Government representatives | None | Yearly average one visit per year |
| TOTAL indicative COST Excluding project and UNDP staff time costs | 70,000 |  |

# PART VI: LEGAL CONTEXT

This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement between the Government of Montenegro and the United Nations Development Programme, signed by the parties on the 15th of December 2006. The host country implementing agency shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement. The UNDP Resident Representative in Montenegro is authorized to effect in writing the following types of revision to this Project Document, provided that he/she has verified the agreement thereto by the UNDP-GEF Unit and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objective, outcomes, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document

# PART VII: ANNEXES

## Annex I: Risk Analysis

| Risk | Rating | Mitigation Measures |
| --- | --- | --- |
| Government is slow in allocating sufficient funds to finance an expanded PAS, resulting in increasing pressures on the PA institutions to ‘exploit’ protected areas to offset costs of management | Moderate | The project will specifically seek to quantify the public good benefits, intrinsic values and non-use values of the PAS. On the basis of this valuation, the project will then prepare communications media to present the benefits and values of the PAS to key decision-makers in government. The project will then seek to negotiate an increase in government financial allocations to administer the expanded PAS. The project will also test financing mechanisms and cost-effective management approaches that could, over the long-term, incrementally reduce the ongoing dependency of the PAS on substantial annual government grant allocations. |
| Resistance to increasing (or introducing new) entrance fees, recreational user fees and PES surcharges. These conflicts cannot be timeously addressed and resolved. | Moderate | The project will: 1. Strengthen the capacity in PA institutions to: identify the equitable ‘market rate’ for PA products and services; evaluate consumer ‘willingness to pay’ (WTP); and measure the elasticity in demand 2. Facilitate the establishment of cooperative forums with different user groups to (amongst others): discuss any new fees and surcharges proposed; and comment on recommendations for increases to existing fees and surcharges. 3. Improve and diversify the facilities and services offered by the affected PAs in order to justify any increase in existing fees, or introduction of new fees 4. Strengthen the capacity of PA’s to improve the effectiveness of their fee collection methods 5. Identify mechanisms for the introduction of discounted rates for selected user groups (e.g. school groups, local communities, volunteers) to facilitate access to PA products and services |
| Local government (municipalities), Morsko dobro and Forest Administration do not fully participate in project activities | Moderate | The project will collaborate closely with the GEF-funded project ‘Strengthening the sustainability of the protected area system of Montenegro’ in: (i) ensuring the formal designation of management authority for the different categories of PAs (excluding national parks), as required by the new Law on Nature Protection; (ii) defining the anticipated human resource capacity needs (staffing, skills, competence levels, knowledge) of local government/ Morsko dobro and Forest Administration and the requisite resources, training and development requirements needed to address these capacity gaps; and (iii) contributing to the implementation of focused training programs for the responsible staff. The project will ensure that these institutions are properly consulted and adequately represented in the relevant working forums and the Project Steering Committee. The project will collaborate directly with, and strengthen the capacities of, the Municipality of Tivat (Tivat Saltpan Nature Reserve), the Andrijevica, Kolasin and Podgorica Municipalities (Komovi Regional Park) and the Forest Administration unit in Komovi. Lessons learnt will be documented for replication. |
| Income from environmental levies is not made available for use by PA institutions for conservation purposes | Low | The project will contribute to strengthening the regulatory framework for the Environmental Protection Fund (EPF). It will specifically help to develop administrative procedures for earmarking disbursement of income from the EPF, in close collaboration with the Ministry of Finance and the MESP. It will also support negotiations to ‘ring-fence’ income (on a pro rata basis) from other national and local (municipal) environmental levies to support the ongoing planning and management of protected areas. |
| Legal conflicts delay nature-based tourism concessioning processes in Komovi | Low | The project will conform to the legal framework of the Law on Concessions (Official Gazette of Montenegro, No. 8/09) in piloting the concessioning process in Komovi. |

## Annex II: Terms of Reference for Key Project Positions

| Position Titles | $/person week | Estimated person weeks | Tasks to be performed |
| --- | --- | --- | --- |
| For Project Management |
| Local |
| Project Manager | 500 | 120 | Deliver results and manage funds in line with the work plan approved by PSC; Analyze and evaluate results regularly to ensure that the project is meeting the target beneficiaries’ needs, and communicating them to all PSC members; Record and resolve project issues occurring during implementation; Discuss and deal with local and national authorities on matters pertaining to activities described in the project document; Ensure timely preparation and submission of yearly/quarterly project work plans and reports; Lead the recruitment process of the necessary experts in the areas identified in the project document in accordance with UNDP rules and regulations; Collect, register and maintain information on project activities by reviewing reports and through firsthand sources; and Advise all project counterparts on applicable administrative procedures and ensure their proper implementation. |
| Project Assistant | 400 | 75 | Collect, register and maintain all information on project activities; Contribute to the preparation and implementation of progress reports; Monitor project activities, budgets and financial expenditures; Advise all project counterparts on applicable administrative procedures and ensure their proper implementation; Maintain project correspondence and communication; Support the preparations of project work-plans and operational and financial planning processes; Assist in procurement and recruitment processes; Assist in the preparation of payment requests for operational expenses, salaries, insurance, etc. against project budgets and work plans; Follow-up on timely disbursements by UNDP CO; Receive, screen and distribute correspondence and attach necessary background information; Prepare routine correspondence and memoranda for signature; Assist in logistical organization of meetings, training and workshops; Prepare agendas and arrange field visits, appointments and meetings both internal and external related to the project activities and write minutes from the meetings; Maintain project filing system; Maintain records over project equipment inventory; and Perform other duties as required. |
| For Technical Assistance |
| Local |
| Economic valuation consultancy service | 1,000 | 50 | Output 1.1– validating the primary economic values of each of the five targeted protected areas identified during the preparatory phase; designing, testing and implementing valuation studies for each economic value within each of the five protected areas to determine a monetary quantification of the ecosystem products and services in each PA; collating and extrapolating the results of these five valuation studies to the entire protected area system; preparing a Benefit-Cost Analysis (BCA) that assesses the public benefits and costs of establishing and managing protected areas as an economically viable form of land use; and documenting the lessons learnt and detailing the methodologies used in economic valuations. |
| Communications service consultant | 1,000 | 10 | Output 1.1 – preparing a focused communication strategy that describes the public benefits, and costs, of establishing and managing protected areas in Montenegro, and presents an argument for an increased public investment in the PAS; developing the requisite briefing media for, and implementing the communication program to, targeted government decision-makers |
| Legal adviser | 1,000 | 40 | Output 1.3 – contributing to the reform of PA regulations (specifically relating to the funding, and financial management, of PAs). This may include providing technical support to the local and national government institutions in: development of regulations (or by-laws) that prescribe the rules, procedures and administration for each of the different funding mechanisms provided for in national legislation and/or recommended by the NPAFP; preparation of enabling legislation that would provide for the establishment and administration of the Environmental Protection Fund (EPF); development of administrative procedures or provisions for earmarking disbursement of income from the EPF and/or local (municipal) environmental levies to support the planning and management of protected areas; development of an incentives framework to retain skilled and competent protected area planning and management staff in the conservation sector; evaluation, and strengthening, of the regulatory framework for PPP tourism concession agreements; development of formal procurement procedures and contractual templates for the outsourcing of PA planning and operational functions; and assessment of legal options for the integration of biodiversity offsets (that are linked to protected areas) into formal EIA decision-making and approval processes for large-scale development with significant environmental impact. Output 2.1 – providing legal support services to Durmitor NP and Zabljak Municipality in the levying of a watershed protection surcharge on water supply in Zabljak |
| Public consultation specialist | 1,000 | 14 | Output 2.1 - constituting, organising, hosting, facilitating, mediating and recording the activities of a working group to discuss the levying of a watershed protection surcharge on water supply in Zabljak; facilitating bilateral or multilateral meetings between parties represented in the working group to address any specific financial or technical issues or resolve any conflicts that may arise from time to time; making publicly available the outcomes of any consultation meetings (unless otherwise agreed with the affected parties); supporting the Zabljak municipality, Durmitor national park and Public Water Company in implementing an effective joint communication and awareness campaign; and documenting the lessons learnt in consultation processes |
| Nature-based tourism advisor | 1,000 | 12 | Output 2.2 – supporting the identification of alternative options for a tourism concession opportunity in Komovi RP; supporting the objective assessment of each tourism concession option; supporting the selection of a preferred option; and supporting the preparation of a detailed description of the concession opportunity |
| Tourism marketing agency | 1,000 | 25 | Output 2.3 – providing support to the PENP, other PA management agencies and Local/Regional Tourism Organizations’ in the design, development and production of adventure tourism maps and other promotional and marketing media for adventure-based recreation and tourism in the PAs of northern Montenegro |
| Fund raiser/ project developer | 1,000 | 107 | Output 3.2 – developing fund-raising and project management skills of at least 10 targeted staff from different PA institutions; developing a fund-raising strategy for the PAS; developing cost-efficient procedures for the management and administration of donor funds and/or loans; developing marketing and communication materials for key projects targeted for donor funding or loans; preparing on a prioritized basis, detailed project proposals to potential donors and/or banks; build, develop and formalise working relationship with NGOs, volunteers and academic institutions to support fund-raising efforts, and implement donor-funded projects; establishing and maintaining a consolidated information database on prospective donors and banks, and funded projects; and documenting lessons learnt, profiling training and skills development completed and collating fund-raising materials developed. |
| Monitoring and evaluation review consultant | 1,000 | 20 | Participate in drafting mid-term and final evaluation report/s; Local liaison with project team, government and UNDP during project evaluation; Liaison with the counterpart international monitoring and evaluation expert; Participate in discussions to realign the project time-table/log frame at the mid-term stage |
| Evaluation expert | 1,000 | 10 | The standard UNDP/GEF project evaluation TOR will be used. This will include: participating, alongside the international consultants, in the mid-term and final evaluation of the project, in order to assess the project progress, achievement of results and impacts; developing draft evaluation report and discuss it with the project team, government and UNDP; and as necessary, participating in discussions to realign the project time-table/logframe at the mid-term stage |
| Auditor | 1,000 | 10 | Med-term and final independent audit of project expenditure as per UNDP/GEF standard ToR |
| International |
| Financial planning company | 3000 | 30 | Output 1.2 – accurately updating the current financial baseline prepared for the PAS during the PPG, including analyzing the protected area costs, reviewing different income sources and identifying specific cost-reduction opportunities; using financial planning tools (e.g. scenario logic) to qualify and quantify the projected financial needs for the PAS under different management scenarios and determine the ‘financial gap’ between the current financial scenario and the optimal (or desired) scenario; assessing the functionality of the financial management system of the protected area institutions, including accounting (income and expenditure), salaries and benefits, classification of expenses (standardization), cash flow, transparency (availability of and access to information), and auditing (internal and external); selecting the most appropriate financial mechanisms to ensure the diversification of financing sources for the PAS; defining the legal and institutional framework that is required to mobilize financial resources, adopt business management principles, establish innovative financial mechanisms, and ensure the autonomy of financial management based on principles of modern governance; identifying opportunities for cost-saving to achieve economies of scale, eliminate duplication and improve service delivery; using a ‘market-based approach’, preparing a ‘National Protected Area Financial Plan’ (NPAFP) that establishes lines of strategic action to mobilize financial resources and build financial capacity to support a system of protected areas in Montenegro; and documenting lessons learnt in the design and development of the NPAFP. Output 3.3 – Staffing a ‘help desk’ facility for PA institutions that will inter alia support these institutions in: the implementation of recommendations for the improvement of existing financial management systems for PAs; strengthening internal financial controls; ensuring compliance with national financial management systems, accounting guidelines and standards and auditing requirements; strengthening financial information flows to individual PAs; setting market-related pricing of PA products; developing more efficient user fee collection mechanisms; reviewing the organisational structure of, and staffing deployment in, PENP to improve efficiencies; implementation of incentives mechanisms for PA staff and ‘profitable’ PAs (i.e. those generating a surplus); outsourcing, concessioning, leasing and co-management processes that could improve cost-effectiveness of PA operations; and training and mentoring of key staff. They will also document lessons learnt and collate information on institutional support provided. |
| Financial specialist (PES – water supply) | 3000 | 8 | Output 2.1 –reviewing regional and national best practice in equivalent PES schemes; determining the current annual consumption value of water supply to Zabljak; defining alternative payment mechanisms for watershed protection in Zabljak; undertaking a cost-benefit analysis of each of these mechanisms; developing the administrative procedures for the collection and disbursement of income from a watershed protection surcharge in Zabljak; and providing the technical inputs into the preparation of the requisite Zabljak municipal by-laws. |
| Transaction adviser (concessioning) | 3000 | 14 | Output 2.2 – undertaking best practice reviews in PA concessioning in regional parks; identification of concession opportunity for Komovi RP; modelling economic feasibility of concession opportunity in Komovi RP; preparing all legal and procedural documentation for concessioning process in Komovi RP; preparing information materials and responding to informational requests from prospective bidders for concession in Komovi RP; overseeing compliance with selection criteria for concession opportunity; due diligence of prequalified companies for concession opportunity; contractual negotiations with preferred bidder; and documentation of lessons learnt, best practice, templates and opportunities for replication in other regional parks |
| Nature-based adventure recreation and tourism planning specialist | 3000 | 8 | Output 2.3 – developing an ‘adventure tourism strategy’ for the protected areas of northern Montenegro. Also providing technical and advisory support to the PA institutions in: the development of its fee structures (and their administration) for the adventure tourism products provided by PA’s of northern Montenegro; business planning processes for cave tourism development in northern Montenegro; identification of the infrastructure and services needed to support boat-based recreational and commercial use in the PAs of northern Montenegro; recreational planning associated with skiing, biking, hiking and horse trails in the PAs of northern Montenegro; and planning of climbing routes in the PAs of northern Montenegro. |
| Business and management planning consultant (protected areas) | 3000 | 20 | Output 3.1 - preparing a management plan for Tivat Saltpan Nature Reserve (‘reserve’); reviewing the management plan for Biogradska gora National Park (‘park’), and updating as necessary; reviewing the financial baseline of the park/reserve, and the financial needs of the park/reserve under different operational management scenarios; determining the “goods and services” that the park/reserve provides and the markets and competition that may exist for those goods and services now and in the future; Assessing the costs of pursuing the most viable sources of revenue for the park/reserve; assessing the assumed benefits and income from those revenue streams, along with an assessment of risk; assessing the legal and political framework as it relates to pursing those revenue streams; preparing a medium-term projection of the anticipated annual national/local government grant allocation to the park/reserve; assessing potential income from existing environmental financing mechanisms and a medium-term projection of income from these sources; assessing opportunities to reduce park/reserve planning, administration and management costs; developing detailed strategies, next steps, activities and investments required to capitalize on the most viable opportunities; documenting lessons learnt; and preparing a generic PA business plan template and describing a set of standard business planning procedures. |
| Evaluation experts for mid-term and final evaluation | 3000 | 6 | The standard UNDP/GEF project evaluation TOR will be used. This will include: leading the mid-term and the final evaluations; working with the local evaluation consultant in order to assess the project progress, achievement of results and impacts; developing draft evaluation report and discuss it with the project team, government and UNDP; and as necessary, participating in discussions to extract lessons for UNDP and GEF |
| Justification for Travel, if any: Travel to Montenegro for country/site visits |

.

## Annex III: Stakeholder Involvement Plan

1. Stakeholder identification

During the project preparation stage, a stakeholder analysis was undertaken in order to identify key stakeholders, assess their interests in the project and define their roles and responsibilities in project implementation. Table 1 describes the major categories of stakeholders identified, and the level of involvement envisaged in the project.

Table 1: Key stakeholders and roles and responsibilities

| Stakeholder | Roles and Responsibilities |
| --- | --- |
| Ministry of Spatial Planning and Environment | MSPE will, primarily through the Deputy Minister and the department for nature protection and environmental assessments, be responsible for the overall coordination of the project. It will also be an important partner in, and primary beneficiary of, project activities. It will be directly involved in the project through: preparation of spatial plans for special purpose areas in northern Montenegro; development of the targeted communications to high level government decision-makers to motivate for improved government investment in the PAS; preparation of the NPAFP; preparation of secondary legislation and complementary tools and mechanisms to facilitate implementation of the NPAFP; fund-raising for the PAS; development of guidelines for cost-effective management of PAS; and involvement in the skills development and training programs for MSPE staff. The MSPE will chair the Project Steering Committee (PSC) |
| Public Enterprise National Parks | PENP is an important partner in, and beneficiary of, the project. It will be involved in the project through: support to the economic valuation processes in national parks; participation in the development of the NPAFP; updating of regulations to support revenue generation mechanisms in national parks; support to the introduction of a PES scheme in Zabljak; planning and implementation of adventure based tourism and recreation services in the national parks of northern Montenegro; introduction of business planning processes in national parks; improvement of the financial management systems and cost-effectiveness of operations in national parks; and involvement in the skills development and training programs for national park staff. The PENP will be a member of the PSC. |
| Ministry of Finance | The Ministry of Finance is an important partner in the project. It will be involved in the project through: participation in the preparation of the NPAFP; participation in development of regulatory instruments to support the implementation of the NPAFP; and providing support to the increase of government funding allocation to the PAS though different public financing mechanisms. The Ministry of Finance may be a member of the PSC. |
| Local Government - Zabljak, Tivat, Podgorica, Andrijevica and Kolascin | The affected local municipalities are important partners in, and beneficiaries of, the project. The Tivat municipality (and Morsko dobro) will participate in: the economic valuation of Tivat Saltpan NR; and the preparation of an integrated management and business plan for the Tivat Saltpan Nature Reserve. The Podgorica, Andijevica and Kolascin municipalities will participate in the nature-based concessioning process planned for Komovi RP. The Zabljak Municipality will lead the feasibility assessment process for the introduction of a watershed protection surcharge for the municipal area. All municipalities will also be involved in the relevant project skills development and training programs. The municipalities will all be members of the PSC. |
| MAFWR - Forestry Administration | Forestry Administration will be actively involved in the project through: participation in the development of the NPAFP; participation in regulatory reform processes required to support the financial sustainability of the PAS; and providing direct support to the nature-based tourism concessioning process in Komovi regional park, notably if the concession includes areas under the management of Forestry Administration. The Forestry Administration/MAFWR may be a member of the PSC. |
| Regional and Local Tourism Organisations | Regional and Tourism organisations are important partners in the development and implementation of project activities focused on improving the tourism and recreational facilities and services in northern Montenegro. They will provide professional and technical support in ensuring the alignment of project investments with regional and local tourism plans, programs and projects to reduce duplication of effort and optimise returns from investment. It is envisaged that a representative of the tourism organisations in northern Montenegro would be represented on the PSC |
| UNDP GIS Project | The UNDP GIS Project is an implementation partner for the project. It will provide database and decision-support system for the project. |
| WWF - Dinaric Arc Eco-region Project/ Mediterranean Programme office | WWF will support the integration and alignment of project activities in the PAs of northern Montenegro with the Dinaric Arc Ecoregion initiatives. |
| National and regional NGOs | Relevant national NGOs such as Greenhome, Greens of Montenegro and Most will be encouraged to take an active role in implementing project activities, notably in the involvement and beneficiation of local communities in Komovi from the concessioning process. National and local NGOs will actively participate in the stakeholder engagement processes for all project activities. A representative from national NGOs will be a member of the PSC. |
| Academic and research Institutes | Relevant national and regional academic and research institutes will contribute to the project in, for example, local scientific surveys and specialist mapping. |
| Representatives of local communities (e.g. residents of Zabljak ) | Inhabitants of the villages or settlements around the PAs of northern Montenegro will be made aware of the project activities and invited to take part in the decision making process. They will be represented in the local working committees and actively involved in the project activities relating to the introduction of a PES scheme in Zabljak. Their cooperation will be sought in implementing project activities including resource protection, alternative income development (e.g. nature-based tourism), awareness raising, etc. |
| National and local press and media | The project will cooperate with national and local press and media on public awareness issues. |
| UNDP-Montenegro | The roles and responsibilities of UNDP-Montenegro will include: Ensuring professional and timely implementation of the activities and delivery of the reports and other outputs identified in the project document; Coordination and supervision of the activities; Assisting and supporting MSPE in organizing coordinating and where necessary hosting all project meetings; Contracting of and contract administration for qualified project team members; Manage and be responsible of all financial administration to realize the targets envisioned in consultation with MSPE; Establishing an effective networking between project stakeholders, specialized international organizations and the donor community. The UNDP will be a member of the Steering Committee |

The Ministry of Spatial Planning and Environment (MSPE), Public Enterprise National Parks (PENP) and the Municipalities of Zabljak, Tivat, Podgorica, Andrijevica and Kolascin will be the main public institutions responsible for different aspects of project implementation. They will work in close cooperation with other affected public institutions, including the: Ministry of Agriculture, Forestry and Water Resources (MAFWR) –Forestry Administration; Ministry of Finance; and Morsko Dobro.

2. Information dissemination, consultation, and similar activities that took place during the PPG

Throughout the project’s development, very close contact was maintained with all stakeholders at the national and local levels. All affected national and local government institutions were directly involved in project development, as were public administrations, research and academic institutions and NGO’s. Numerous consultations occurred with all of the above stakeholders to discuss different aspects of project design. These consultations included: bilateral discussions; site visits to pilot sites; consolidated workshops and electronic communications. The preliminary project activities were presented to a range of stakeholders for initial review and discussions, and based on comments received, a final draft of the full project brief was presented to a consolidated stakeholder workshop for in principle approval and endorsement.

3. Approach to stakeholder participation

The projects approach to stakeholder involvement and participation is premised on the principles outlined in Table 2 below.

Table 2: Stakeholder participation principles

| Principle | Stakeholder participation will: |
| --- | --- |
| Value Adding | be an essential means of adding value to the project |
| Inclusivity | include all relevant stakeholders |
| Accessibility and Access | be accessible and promote access to the process |
| Transparency | be based on transparency and fair access to information; main provisions of the project’s plans and results will be published in local mass-media |
| Fairness | ensure that all stakeholders are treated in a fair and unbiased way |
| Accountability | be based on a commitment to accountability by all stakeholders |
| Constructive | Seek to manage conflict and promote the public interest |
| Redressing | Seek to redress inequity and injustice |
| Capacitating | Seek to develop the capacity of all stakeholders |
| Needs Based | be based on the needs of all stakeholders |
| Flexible | be flexibly designed and implemented |
| Rational and Coordinated | be rationally planned and coordinated, and not be ad hoc |
| Excellence | be subject to ongoing reflection and improvement |

The project will focus stakeholder engagement at two levels of intervention: (i) working with national and local public institutions and agencies in order to strengthen their capacities for business planning, financial management, fund raising, and revenue generation from user pays systems in protected areas; and (ii) working directly with civil society organizations, tourism agencies, natural resource (water) users, recreational (adventure tourism) user groups and individuals to mitigate impacts and optimize benefits of project activities.

4. Stakeholder involvement plan

The project’s design incorporates several features to ensure ongoing and effective stakeholder participation in the project’s implementation. The mechanisms to facilitate involvement and active participation of different stakeholder in project implementation will comprise a number of different components:

1. Project inception workshop

The project will be launched by a multi-stakeholder workshop. This workshop will provide an opportunity to provide all stakeholders with the most updated information on the project, the work plan, and will establish a basis for further consultation as the project’s implementation commences.

2. Constitution of Project Steering Committee

A Project Steering Committee’s constituency will be constituted to ensure broad representation of all key interests throughout the project’s implementation. The representation, and broad terms of reference, of the PSC are described in the Management Arrangements in Part IV of the Project Document.

3. Establishment of the Project Management Unit

The Project Management Unit will take direct operational responsibility for facilitating stakeholder involvement and ensuring increased local ownership of the project and its results. The PMU will be located in Podgorica to ensure coordination among key stakeholder organizations at the national level during the project period.

4. Establishment of local working groups

At the activity level, local or specialist working groups (i.e. economic valuation reference groups for target PAs; NPAFP working group; Zabljak PES working group; Komovi Park establishment working group; adventure tourism user work forums; park planning reference groups for Tivat Saltpan NR and Biogradska Gora NP) will be established, as required, to facilitate the active participation of affected institutions, organisations and individuals in the implementation of the respective project activities. Different stakeholder groups may take the lead in each of the working groups, depending on their respective mandates.

5. Project communications

The project will develop, implement and maintain a communications strategy to ensure that all stakeholders are informed on an ongoing basis about: the project’s objectives; the projects activities; overall project progress; and the opportunities for involvement in various aspects of the project’s implementation.

6. Involvement of local stakeholders in project implementation

A number of project activities have specifically been designed to directly involve local stakeholders in the implementation of these activities. These include: facilitating opportunities for the involvement of the private sector in the establishment and use of Komovi RP; testing the introduction of a water surcharge in Zabljak as a means of communicating one of the tangible values of PAs (in this instance, the supply of potable water) to adjacent communities; and facilitating involvement of different adventure tourism and recreation user groups in the improvement and development of adventure tourism services in the northern region of Montenegro.

7. Formalising cooperative governance structures

The project will actively seek to formalise cooperative governance structures at the level of the individual protected areas to ensure the ongoing participation of local stakeholders in the integrated management and business planning of Biogradska Gora NP and Tivat Saltpan NR.

8. Capacity building

All project activities are strategically very focused on building the capacity – at systemic, institutional and individual level – of the key national stakeholder groups to ensure sustainability of initial project investments. The project will also seek to build the capacity of organizations operating at the community level to enable them to actively participate in both the negotiation and implementation of management agreements.

## Annex IV: METT, Capacity Development and Financial Scorecards

The scorecards are attached as separate files.

# SIGNATURE PAGE

Country: Montenegro

| UNDAF Outcome(s)/Indicator(s): (Link to UNDAF outcome., If no UNDAF, leave blank) | By 2011, Public Institutions with the support of Civil Society Organizations (CSO) are better able to ensure good governance, rule of law and equal access to justice and promotion of human rights. |
| --- | --- |
| Expected Outcome(s)/Indicator (s): (CP outcomes linked to the SRF/MYFF goal and service line) | CPD C. Environmentally responsible economic development |
| Expected Output(s)/Indicator(s): (CP outputs) | CPAP 4.2.4 Improved management of protected areas |
| Implementing partner: (designated institution/Executing agency) | United Nations Development Programme (UNDP) |

Agreed by (Government):

_____________________________________                   	  _________________

Mr.Branimir Gvozdenovic, Minister for Spatial Planning and Environment              Date/Month/Year

Agreed by (UNDP):

_____________________________________                                           ________________

Mr. Alexander Avanessov, UN Resident Coordinator &UNDP RR                              Date/Month/Year

# Footnotes

Except for Tivat Saltpans, all current nature reserves are located within the boundaries of two national parks - Skadar Lake and Durmitor – and are administered as an integral part of each NP.

These categories of protected areas are still designated in terms of the previous Law on Nature Protection (No. 36/77 and 2/82).

Estimated at 630,000 in 2007 (NSSD, 2007)

Montenegrin administration is organized at two levels: national level and local level, the latter referring to 21 municipalities (self-government units).

The same revenue generating mechanisms apply to any other PA that is/ will be proclaimed. Article 68 provides for legal or physical persons (as users) to pay the following charges to PA managers: entrance fees; fees for services extended to visitors (such as use of guides, visitors centres, parking, camping); fees for the use of park’s name and logo; bird watching; filming of advertising materials, commercial and other movies; rafting and renting of boats; sports fishing; fees for catering, commercial, accommodation and infrastructure objects (restaurants, bungalows, temporary objects, advertising, electrical network sub-stations, use of land for sports and other events); or any other activities that are in line with the law.

The contribution to the indicators for SO-1 will be delivered by the counterpart project Strengthening the sustainability of the PA system of Montenegro

Although the spatial focus of the project is the individual PAs of northern Montenegro, some Outputs (Output 1.1 and Output 3.1) will also support activities in Tivat Saltpan Nature Reserve (coastal region) and Skadar Lake National Park (central region).

Criteria for the identification of methodologies include: i) using best available practices; ii) comparability with other economic valuation studies conducted in the Balkans or in similar ecosystems; iii) ease of extrapolation of results to the entire PAS; iv) focus on use, and to a lesser extent, non-use values; and v) cost-effectiveness.

Because various valuation techniques only determine the marginal value of a product or service, broader extrapolation of results is limited.

The approach to the preparation of NPAFP will broadly follow the guidelines contained in ‘Business-oriented financial planning for national systems of protected areas’ (Flores, Rivero et al, 2008)

Primarily in terms of Article 68 (especially paragraph 2) of the Law on Nature Protection and Article 20, paragraph 4 of the Law on National Parks.

This may include experiences associated with the leasing of commercial tourism operations in parks to private operators: e.g. restaurants and other facilities at Durmitor and Biogradska Gora.

During the first twelve months, the concessionaire will be held to a Bid and Development Bond which will be designed to ensure that the concessionaire actually goes ahead with its proposals. If the concessionaire fails to implement the project within a specified period, it forfeits the bond.

The International Finance Corporation (IFC), the private sector arm of the World Bank, may be approached to act as a financing partner institution and lead transaction advisor. Montenegro became a member of the IFC in 2007 and currently has 3 advisory projects in Montenegro.

During project implementation a more through feasibility analysis of different revenue options will be undertaken and more accurate return rates determined

No adjustment for CPI

No adjustment for CPI

Contractual value for national and international consultants/companies will include all regular expenses and disbursements incurred in implementing the respective ToRs

The explicit procurement requirements for equipment will be determined during the preparation of the overarching Adventure tourism and recreation strategy for the protected areas of northern Montenegro

The detailed requirements for the improvement of adventure tourism facilities and infrastructure in the respective parks will be developed during the preparation of the  Adventure tourism and recreation strategy for the protected areas of northern Montenegro

All hardware, software and communications equipment procured by the project will be transferred to the MSPE at project completion for dedicated use in fund-raising/project development activities.

All co-financing (cash and in-kind) that is not passing through UNDP.

SBAA, Article II Form Of Assistance, article 3  (http://www.undp.org.me/about/SBAA.pdf)

CPAP, Part VI, article 6.3(http://www.undp.org.me/about/CPAP%20signed%20Sep%202008.pdf)

The approach to the preparation of NPAFP will broadly follow the guidelines contained in ‘Business-oriented financial planning for national systems of protected areas’ (Flores, Rivero et al, 2008)

# Text boxes

Total budget:		 US$	8,215,000

Allocated resources (cash):

- GEF		US$  	950,000

- UNDP 		US$       40,000

- Government		US$	1.450.000

In kind contributions:

- Government		US$	5.475.000

- GTZ		US$ 	300,000

Programme Period: 2007-2011

Project Title: Catalyzing financial sustainability of the protected area system in Montenegro.

Atlas Award ID:        00059194

Atlas project ID:        00073967

PIMS:                         4279

Start date:                  June 2010

End Date:                   May 2013

LPAC Meeting Date: 29.01.2010.

Execution modality:    DEX

Total budget:		 US$	8,215,000

Allocated resources (cash):

- GEF		US$  	950,000

- UNDP 		US$       40,000

- Government		US$	1.450.000

In kind contributions:

- Government		US$	5.475.000

- GTZ		US$ 	300,000

Programme Period:	2007-2011

Energy, Environment and Sustainable Development Programme

Project Title: Catalyzing financial sustainability of the protected area system in Montenegro.

Atlas Award ID:                          00059194

Atlas project ID:                          00073967

PIMS:                                           4279

Start date:                                    June 2010

End Date:                                     May 2013

LPAC Meeting Date:                   29.01.2010

Management Arrangements:      DEX