Private Sector Development Monthly Meeting

| ACTION POINT TRACKING MATRIX 9th January 2013 Action Point Tracker: Cinzia Tecce |
| --- |
| AGENDA | ACTION POINT | RESPONSIBLE PERSON (S) | DEADLINE/TIMELINE | COMMENT | STATUS AS OF 9 JANUARY 2013 |
| SQAM Project Implementation | AWP (Jan-Dec 2013) | Cinzia/Timothy | January | MBS has provided initial feedback | AWP being drafted Delays caused by overdue consensus on Inter-Agency Agreement with UNIDO |
|  | UNIDO/UNDP IIA | Cinzia | December | Awaiting feedback from UNIDO | Several exchanges with UNIDO, at Senior Management level, on Project Management Arrangements IIA revised, based on clear allocation of responsibilities, and shared with UNIDO on December 17th Awaiting feedback from UNIDO |
|  | Selection of Metrology Design Expert | Cinzia | September | The pre-condition set by UNIDO on the release of the expert is to have the IIA signed | TORs prepared and approved by MBS Expert identified and cleared by MBS UNIDO will release expert only after signing IIA |
| PSD Project Funding and Formulation | LPAC Meeting | Cinzia | December | Awaiting meeting with ST and final comments by stakeholders prior to signing minutes and Prodoc | LPAC Meeting organized on December 18th 2012 Minutes and revised Prodoc shared with all stakeholder for final input to the document (deadline for submission of final comments is set for Monday January 14th 2013) |
|  | Meeting with Ministry of Finance | Agnes | ASAP | RR a.i to meet ST on phasing in of PSD Project and phasing out of FIMA | Agnes to arrange for Meeting with ST by week two of January (the meeting arranged for December 21st 2012 did not occur) Agnes to arrange for the TPR date with MoF in which FIMA Terminal Report will be presented and PSD Project and AWP presented |
|  | AWP 2013 | Cinzia/Timothy | ASAP | - | AWP 2013 being drafted |
|  | DFID Financing Agreement | Cinzia | January | Draft Global Corporate Agreement and Guidelines in place and received from Partnership Bureau | Preliminary Discussions held with DFID on Financing Agreement Agreement being drafted For the Project, disbursements will occur every semester in line with the opening of the MICF Funding windows |
| FIMA | Closure of FIMA | Bill/Agnes | ASAP | UNDP to re-position itself towards Microfinance | FIMA will close for the time being on the UNDP part and will be re-conceptualized |
|  | Pending issues on FIMA | Agnes | ASAP | - | Agnes to provide update on Pending FIMA issues |
| EIF | UNDP to support formulation of 1 NES project under the EIF Tier-2 Window | Cinzia | ASAP | Concept Note finalized and approved by EIF Geneva | The PSD Specialist and the EIF team have worked on a concept note to be submitted to EIF Tier-2 funding Window The Concept Note on Anchor Farms within the NES Priority Clusters has been approved Ministry in phase of recruitment of consultants for formulation |
|  | UNDP Geneva EIF Tier-1 Training | Cinzia | January | TORs prepared by UNDP Geneva for Mission to Malawi funded entirely by EIF | UNDP Geneva is on Mission in Malawi to deliver a 3-day training on Trade Mainstreaming under EIF Tier-1 Window Debriefing Session with team scheduled for Thursday 10th 2013 |
| NES | Launch of NES | Cinzia/Timothy/Augustine | December | - | NES Launched successfully MoIT requires additional printed copies of the NES |
| GSB Closure | Organize Final SC for GSB | Timothy | ASAP | - | To arrange for closure of GSB To arrange for Final GSB SCM |
|  | Micro-Loan Foundation Payment of Annual Management Fees | Cinzia | ASAP | - | Under GSB 2012 AWP there was an allocation of 9,000 (Management fee for Micro-Loan Foundation up to April 2013) which has not been paid |