## Goal Level
JSP - Monitoring and Evaluation Plan - GOAL LEVEL
GOAL. Support the doubling of exports and economic diversification by 2019 through better policy consistency and coordination in implementation
Indicator | ID No. | Targets (year) | Data Source/ Means of Verification | Method of Data Collection | Baseline | Frequency of data collection
Total exports (nominal and real value in USD) | G.1 | Double (2018) | NSO (cross-check WB) | Review of official report by NSO | Average total export 2010-2013 | Annual
Diversification indices of merchandise exports | G.2 | Not identified. | http://unctadstat.unctad.org | Download data from UNCTAD website | Average index for 2010-2013 | Annual
Actions required to compile the table
Indicators are suggested in the JSP but not specified. |  | Targets are clearly identified for G.1, but not for G.2 in the GSP. For the latter a benchmark country or regional grouping could be considered instead (e.g. higher than average for SADC). It is suggested to also add related MDGS indicators. | Identify the origin of data. E.g. National Statistic office annual report. For qualitative indicators identify means of verification (e.g. experts' review). | Be precise on how to collect the information (e.g. NSO website on day/month). Include contact details of information provider. | Identify a baseline. E.g. Average applied tariffs for the years 2010-2012 compared to average applied tariffs in 2013-2018. For quantitative indicators identify baseline year (e.g. average 2010-2012), more generic descriptions are acceptable for qualitative indicators. | Identify frequency of data collection. Suggestion for outcome indicators is annually and end of implementation (2018)

## Outcome Level
JSP - Monitoring and Evaluation Plan - OUTCOME LEVEL
PILLAR 1: MARKET ACCESS AND MARKET DEVELOPMENT
OUTCOME X. Increased production through more efficient farming and higher yields and more irrigated oil seed produce. Increased quality of produce. Increased exports due to increased ease of exporting as regulations are more transparent
Indicator | ID No. | Targets (year) | Data Source/ Means of Verification | Method of Data Collection | Baseline | Frequency of data collection
X.X.X.
X.X.X.
Actions required to compile the table
Indicators are not formulated in the JSP. If an outcome formulation is unclear or contains multiple results, specify and simplify. Do not use indicators that are not clearly formulated. The revised M&E should be approved by the SWG. It is suggested to add for each outcome a sustainability indicator to measure social and environmental outcomes. |  | Clearly identified targets are needed. For each target completion date should be put in brackets. If you cannot identify clear targets, consider reformulating or eliminating the indicator. | Identify the origin of data. E.g. National Statistic office annual report. For qualitative indicators identify means of verification (e.g. experts' review). | Be precise on how to collect the information (e.g. NSO website on day/month). Include contact details of information provider. | Identify a baseline. E.g. Average applied tariffs for the years 2010-2012 compared to average applied tariffs in 2013-2018. For quantitative indicators identify baseline year (e.g. average 2010-2013), more generic descriptions are acceptable for qualitative indicators. | Identify frequency of data collection. Suggestion for outcome indicators is annually and end of implementation (2018)

## Output Level
JSP - Monitoring and Evaluation Plan - OUTPUT LEVEL
PILLAR 1: MARKET ACCESS AND MARKET DEVELOPMENT
OUTCOME X. Increased production through more efficient farming and higher yields and more irrigated oil seed produce. Increased quality of produce. Increased exports due to increased ease of exporting as regulations are more transparent
Indicator | Action No. | Targets (year) | Data Source/ Means of Verification | Method of Data Collection | Baseline | Frequency of data collection
X.X.X
X.X.X
X.X.X
Actions required to compile the table
Indicators are not formulated in the JSP. If an output formulation is unclear or contains multiple results, specify and simplify. Do not use indicators that are not clearly formulated. The revised M&E should be approved by the SWG. |  | For output indicators clearly identified targets are needed. For each target completion date should be put in brackets. If there is no target and/or no target could be established, consider eliminating the indicator. If the indicators will be revised after a project formulation indicate a tentative date for revision. | Identify the origin of data. For qualitative indicators identify means of verification (e.g. experts' review on the quality of the study produced on niche products). | Be precise on how to collect the information. Include contact details of information provider. | Identify a baseline. For quantitative indicators identify baseline year (e.g. average 2010-2012), more generic descriptions are acceptable for qualitative indicators. | Identify frequency of data collection. Suggestion for output indicators is quarterly.