# 2019 Annual Work Plan: Global Environmental Facility- Least Developed Countries Fund

# Climate Proofing Local Development Gains in Urban and Rural areas of Machinga and Mangochi Districts

Country: Malawi

UNDAF and CPD Outcome 1.3: Targeted population in selected districts benefit from effective management of environment; natural resources; climate change and disaster risk by 2020.

Expected CPD Output: National policies, local and national institutions effectively support equitable and sustainable economic growth and food security by 2019

UNDAF Output(s):

  - Environment, natural resources, climate change, and disaster risk management mainstreamed in policies, development plans and programmes at national level and implemented in 14 disaster-prone districts

  - Data and knowledge on the impact of climate change, environmental and natural resources degradation and natural disaster collected and made accessible to decision makers in Government, Private Sector and Civil Society

  - Targeted population in selected districts benefit from effective management of environment, natural resources, climate change and disaster risk by 2019

Project Outcomes:	1: The impact of ecosystems degradation in aggravating vulnerability to climate change risks and reducing resilience of development gains understood and integrated into key decision-making processes at the local, sub-national and national levels.

2: Skills and operational capacity of District, EPA and TA level technical officers to support implementation, maintenance and monitoring of the activities under component 1 and to mainstream climate risks into all local development process (skills, legislation, information)

3: Public and domestic water harvesting, storage and distribution reduces climate change driven flooding and regulates availability of water throughout the year in flood & drought hotspots

4: Rehabilitation of badly degraded forests, protection of riverbanks, lake shores and urban infrastructure

5. Productivity of agriculture supported by adoption of climate smart agriculture practices

Executing Entity / Implementing Partner: UNDP /Ministry of Natural Resources, Energy and Environment

Implementing Entity / Responsible Partners: MoFEP, MOAWD, MOLHUD, MOLGRD, DICE, LUANAR, University of Malawi, Mangochi and Machinga District Councils.

IRRF Indicators (Output 1.4):

1.4.2.A.1.1 	Extent to which implementation of comprehensive measures- plans, strategies, policies, programmes and budgets- to achieve low-emission and climate-resilient development objectives had improved (Milestone: 2018: 4)

Corresponding activities in Annual Work-Plan: 1.2.3; 2.1.1; 2.1.2; 2.1.3; 2.1.4; 2.1.8

Brief Description Inadequate mainstreaming of climate change considerations into Malawi national programmes exposes to increase risk the development gains from over US$300 million investments in agricultural input subsidy, decentralization, irrigation expansion, and disaster risk reduction. While healthy ecosystems can provide a cost-effective means of adaptation to climate change, the country’s natural ecosystems continue to be threatened by over-exploitation and inappropriate /weak management and technical capacity; while limited knowledge and inadequate financing reduces the effectiveness of resource users and government’s efforts to “climate proof’ development programmes at local, district and national levels. Malawi has a high risk of climatic and hydrological hazards which include floods, dry spells affecting the country, almost yearly. This is particularly challenging for rural populations who depend largely on natural resources, ecosystem services and smallholder rain-fed farming to feed their families and support their livelihoods. Because of the country’s vulnerability to climate change impacts, responding to such high risks of climate change requires innovative approaches that focus on community-driven participatory planning, the implementation and promotion of sustainable technologies, policies and livelihood strategies, and a consistent focus on putting locally-driven needs first. The goal of the project is to secure the development and food security gains from the baseline programs by empowering communities to integrate climate risk considerations in the development policies, plans, projects and actions. The project is providing knowledge, tools, capacities and methodologies for the adoption of an ecosystems and community-based approach to adaptation, which is more effective in enabling climate vulnerable people to plan for and adapt to the impacts of climate change; benefiting over 458,371 in 91,674 households. Knoweldge is being generated and used to formulate comprehensive community based adaptation plans. Ecological and physical infrastructure measures for water management are being adopted to regulate baseflow and reduce risk of climate change driven floods while mitigating against droughts. In addition, climate smart agriculture and safe post-harvest management technologies and practices are supported to lead to enhanced production, reduction in grain loss and thus increased food security. 2019 is the final year of project implementation mostly focusing on close-out / exit strategy arrangements to ensure sustainability of project interventions. Actual implementation of planned project activities at community-level commenced in November 2015 with to support to Mangochi and Machinga districts councils to deepen their knowledge of climate change adaptation, integration in planning and budgeting processes; increasing community ownership of climate change adaptation process through capacity strengthening of community-based institutions; demonstration and promotion of innovative livelihoods and value chains in agro and non-agro enterprises; demonstration of integrated ecosystem-based approaches to water harvesting and usage; building horizontal and vertical knowledge management structures to effectively share best practices with other districts and at national level.

SIGNATURE PAGE

Agreed by Lead Coordinating/Implementing Partner

Ministry of Natural Resources Energy and Mining –

Date:

Lilongwe, Malawi

Approved by UNDP Agency

United Nations Development Program (UNDP)

Date:

Lilongwe, Malawi

| Output | Planned Activities | Indicators | Target | Time frame |  | Planned Budget |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 | Responsible party | Sources of funds | Budget Description | Amount (USD) |
| Outcome 2: Skills and operational capacity of District, EPA and TA level technical officers to support implementation, maintenance and monitoring of the activities under component 1 and to mainstream climate risks into all local development process (skills, legislation, information) |
| Output 2.1: Operational capacity of the extension service boosted to enable communities to mainstream climate risk considerations into the implementation of baseline programs: AWP Indicator 2.1: Community structures fully participating in project management &vulnerability monitoring Baseline: 0 2019 Target: 70% of community structures taking full ownership, monitor and report CCA project progress to full council | Activity 2.1: Enhance community skills in CCA project management and ownership 2.1.1. Build capacity of local governance structures (ADCs, VDCs) & its sub-committees (VCPCs, ACPCS, VNRMCs, youth groups and other community institutions to boost extension service delivery 2.1.2. Develop an MoU for project handover to the communities. 2.1.3. Expose students and youth in CCA through attachment & internships 2.1.4. Organize district-based project open days to showcase CCA innovations piloted & successful in the project. | # of committees supported with membership by gender # of MoUs developed and adopted # of students by gender No. of technologies showcased | 12 1 4 5 | X X | X X X X | X X X |  | M&E, EDO | GEF/LDCF | 71600 Travel 72300 Matl&Gds 72500 Supp 75700 TR/WKSP 72300 Matl&Gds | 2,000.00 2,000.00 3,600.00 28,300.00 15,600.00 51,500.00 |
| Output 2.2: Local and national development policies influenced by the project supported pilots to strengthen policies and policy enforcement for climate considerations Output Indicator Gender disaggregated data collected using the participatory learning, monitoring system and reported via project reports, publications 0n strategy development and PIR Output Indicator # of plans, programs and reports with gender segregated information | 2.2.1. Support district councils to mainstream CC into the annual planning and implementation cycle 2.2.2. Conduct gender analysis in all hotspots and mainstream gender into the sustainability plan 2.2.3. Capacitate the district gender technical working group | # of plans mainstreamed with CC information # of exit strategies mainstreaming gender in place No. of staff trained by gender | 1 20 | X | X |  |  | Gender Officer | GEF/LDCF | 71600 Travel 72300 Matl&Gds 72500 Sup 75700 TR/WKSP | 2,200.00 1,300.00 1,200.00 20,900.00 25,600.00 |
| Output 2.3: Enhance monitoring, evaluation and learning AWP Indicator 2.3a: Best practices documented & shared with other projects and districts Baseline: 0 2019 Target: 75% of best practices and success stories under the project shared with other projects/districts AWP Indicator 2.3b: Joint M&E visits and number of key meetings 2019 Target: 4 joint M&E visits; 2 Steering meetings, 4DEC, Full Council Meetings | Activity 2.3: Enhance project monitoring, and dissemination of best practices piloted under the project and success stories. 2.3.1. Generate a catalogue of best practices and success stories under the project 2.3.2. Conduct technical review meetings, joint M&E visits, Steering Committee Meetings, Coordination Meetings, DEC, DESC, full council meetings 2.3.3. Conduct an end-line impact survey 2.3.4. Conduct end of project evaluation | # of Innovations piloted & successful # of meetings, minutes and key resolutions agreed, adopted and implemented Report Evaluation Report | 1 12 1 1 | X X | X X | X X X | X X | UNDP/EAD M&E- Machinga and Mangochi |  | 75700 TR/WKSP 72300 Matl&Gds 72500 Supplies 75700 TR/WKSP 72300 Matl&Gds 71300 Lcl cnslts 71200 Intl. Cnslt | 21,400.00 ,700.00 11,500.00 10,000.00 10,000.00 60,000.00 50,000.00 163,600.00 |
|  | District Project Coordinator |  |  | X | X | X | X | DPC | GEF/LDCF | 61300 Sal. Costs | 45,000.00 |

|  | Sub Total Outcome 2 : $285,700.00 |
| --- | --- |

|  | Outcome 3: Public and domestic water harvesting, storage and distribution reduces climate change driven flooding and regulates availability of water throughout the year in flood & drought hotspots |
| --- | --- |
| Output 3.1: Construction of mini dams, water ponds, retention ridges, and water diversion structures: AWP Indicator 3.1: Number of Physical infrastructures constructed to ensure sustainable water supplies Baseline: 0 2019 Targets: 3 ponds and hatcheries operational | Activity 3.1: Consolidate capacity building efforts in fish farming committees in improved Integrated Agriculture Aquaculture (IAA) technologies. 3.1.1. stock fish ponds and hatcheries and build capacity of farmers in fish feed formulation 3.1.2 Finalize and launch the Climate Smart Aquaculture handbook | # of committees capacitated with membership segregated by gender segregated by gender | 9 3 | X X | X X | X X | X X | Water, Fisheries & Irrigation Depts | GEF/LDCF | 71600 Travel 72300 Matl&Gds 72500 Supplies 75700 TR/WKSP 72300 Matl&Gds | 2,000.00 700.00 1,700.00 7,200.00 15,000.00 26,600.00 |
| Output 3.2 Construction of physical structures and institutions to support infrastructure and expansion of water harvesting from dwellings: AWP indicator 3.2: Homes properly using above ground tanks Baseline: 0 2019 target: 100HHs with proper skills in managing above ground water tanks Disaster management instruments updated with climate risk information | Activity 3.2.1: Monitor utilization of above ground tanks & build capacity in operation and maintenance | # of beneficiaries capacitated by gender # of monitoring visits | 150 4 | X | X |  |  | Water, Irrigation & Crops | GEF/LDCF | 71600 Travel 72300 Matl&Gds 72500 Supplies | 1,500.00 1,700.00 3,100.00 6,300.00 |
|  | Activity 3.2.2: Update disaster contingency plans | # of plans updated | 2 | X | X |  |  | Disaster Dept | GEF/LDCF | 71600 Travel 72300 Matl&Gds 72500 Supplies 75700 TR/WKSP 72300 Matl&Gds | 2,600.00 700.00 2,500.00 10,100.00 10,000.00 25,900.00 |
|  | District Project Coordinator |  |  | X | X | X | X | DPC | GEF/LDCF | 71400 Sal. Costs | 45,000.00 |
|  | Sub Total Outcome 3: $ 103,800.00 |
|  | Outcome 4: Rehabilitation of badly degraded forests, protection of riverbanks, lake shores and urban infrastructure |
| Output 4.1: Degraded watersheds (forest ecosystems) rehabilitated, river banks and lake shore protected from direct siltation AWP Target: Hectares of forests under improved management Baseline: 0 2019 target: 9 Village Forest Areas with forest mgt plans | Activity 4.1: Support conservation of forest biodiversity and ecosystem services. 4.1.1 Develop forest management plans for Village Forest Areas and woodlots 4.1.2. Promote dialogue between upstream and downstream users to enhance catchment management for sustainability of irrigation schemes 4.1.3. Promote forest cover in the newly constructed irrigation schemes and fish ponds | # of LFOs with mgt plans # of MoUs developed Area under forest cover | 19 6 25ha | X X | X X X | X |  | EAD & Forestry Dept | GEF/LDCF | 75700 TR/WKSP 72300 Matl&Gds 75700 TR/WKSP 72500 Supp 72300 Matl&Gds | 11,400.00 2,900.00 5,500.00 5,100.00 25,000.00 49,900.00 |
| Output 4.2: provision of improved and sustainable supplies of energy, including adoption of sustainable charcoal AWP Indicator 4.2: Institutions using alternate and improved energy Baseline 0 2019 Target: 1 public institution using renewable energy technologies | Activity 4.2.1Complete and commission biogas plant at Machinga District Hospital 4.2.2. Strengthen the capacity of production groups (energy saving technologies) on quality improvement and marketing | # of biogas plants operational # of groups capacitated by gender inclusion | 1 5 | X | X |  |  | Department of Energy | GEF/LDCF | 72 300 Matl&Gds 72500 Supplies 72300 Matl&Gds 71300 Lcl cnslts | 200.00 500.00 26,700.00 14,000.00 41,400.00 |
| Output 4.3: Diversification of household food basket and incomes via expansion of aquaculture and NTFP reduce pressure on the forests, river and lake fisheries AWP Indicator: Business Mgt skills in cooperative societies improved Baseline: 0 2019 target: At least 70% of members in cooperative societies able to improve quality of products 1 District Enterprise Development plan developed | 4.3.1. Promote Value Addition in all the sectors and market linkages (Fisheries, irrigation, Agriculture, forestry, Trade, etc.) 4.3.2. Strengthen the cooperatives management. 4.3.4 Support the Development of an enterprise development training manual 4.3.5. Process tittle deed and utilities (power & water) connection for oil factory | # of market linkages developed # of cooperatives reached with membership by gender # of manuals developed # of tittle deeds | 4 4 1 1 | X X | X X X X | X X X |  | TRADE | GEF | 72300 Matl&Gds 75700 TR/WKSP 72500 Supplies 71600 Travel 72300 Matl&Gds | 2,200.00 16,100.00 700.00 3,500.00 20,000.00 42,500.00 |
|  | 4.3.5. Linking VSLA groups to COMSIP Cooperative Union | # of VSLs linked with membership by gender | 16 | X | X | X | X | Community Development | GEF/LDCF | 72500 Supp 72300 Matl&Gds 71600 Travel 75700 TR/WKSP | 1,000.00 2,000.00 4,000.00 5,000.00 12,000.00 |
|  | Finance and Admin Assistant (2) |  |  | X | X | X | X | UNDP | GEF/LDCF | 74100 Sal. Costs | 30,000.00 |
| Subtotal Outcome 4: $175,800.00 |
| Outcome 5: Productivity of agriculture supported by adoption of climate smart systems and measures |
|  | 5.1.1 Upscale CSA technologies in newly irrigated schemes and their catchments | # of hectares under soil & water conservation # of demos mounted & participation by gender | 40 25 | X | X | X | X | EAD & Ministry of Agriculture (DADO) | GEF/LDCF | 71600 Travel 72300- Fuel 72300Matl&Gds | 2,900.00 5,400.00 35,300.00 43,600.00 |
| 2018 target: 60% women incorporated in community committees and participating actively in the project | 5.1.4 Monitor progress of Farmer Field Schools & farm business schools | # of FFS & FBS fully operational | 30 | X | X | X | X | EAD &Ministry of Agriculture (DADO) | GEF/LDCF | 71600 Travel 72300Matl&Gd 72500 Supplies | 3,300.00 600.00 4,400.00 8,300.00 |
| 2018 TARGET: 60 ha area of land under climate smart small holder irrigation | 5.2 Enhance Irrigation Schemes Utilization through 5.2.1 Finalizing remaining scheme structures in newly constructed irrigation schemes 5.2.2 Development and capacity building of WUAs for proper scheme operation | # of irrigation schemes completed # of WUAs developed & trained | 3 5 7 | X | X X | X X | X | Department of Irrigation | GEF/LDCF | 72500- Supplies 72300-Matl&Gd 75700 TR/WKSP 72300Matl&Gds 75700 TR/WKSP 71300 Lcl cnslts | 2,500.00 3,000.00 11,600.00 56,100.00 3,000.00 15,000.00 91,200.00 |
| Sub Total Outcome 5: $ 143,100.00 |
| Outcome 6: Project Management |
|  | 6.2. Communication |  |  | X | X | X | X | Mangochi & Machinga District Council | GEF/LDCF | 72500- Supplies | 8,000.00 |
|  | 6.3. Procurement of assorted stationery |  |  | X | X | X | X | Mangochi & Machinga District Council | GEF/LDCF | 72500- Supplies | 4,500.00 |
|  | 6.4 Office Supplies |  |  | X | X | X |  | Mangochi & Machinga District Council | GEF/LDCF | 72500- Supplies | 2,500.00 |
|  | 6.5. Motor vehicle maintenance & insurance |  |  | X | X | X |  | Mangochi & Machinga District Council | GEF/LDCF |  | 8,000.00 |
|  | 6.6. Vehicle Fuel-Local running |  |  | X | X | X |  | Mangochi & Machinga District Council | GEF/LDCF | 72300-Matl&Gd | 8,000.00 |
|  | 6.7. Bank Charges |  |  | X | X | X |  | Mangochi & Machinga District Council | GEF/LDCF | 74500 MiscEXP | 600.00 |
|  | Sub Total Outcome 6: $ 31,600.00 |
|  | GRAND TOTAL: $ 740,000.00 |

# The Annual Work Plan (AWP) Monitoring Tool							Year 2019

# CP Component______________________

Implementing Partner:  Ministry of Natural Resources, Energy and Mining

| EXPECTED OUTPUTS AND INDICATORS INCLUDING ANNUAL TARGETS | PLANNED ACTIVITIES List all activities involving M&E to be undertaken during the year towards stated CP outputs | EXPENDITURES List actual expenditures against activities completed | RESULTS OF ACTIVITIES For each activity, state the results of each activity | PROGRESS TOWARDS ACHIEVING CP OUTPUTS Using data on annual indicator targets, state progress towards achieving the CP outputs. Where relevant, comment on factors that facilitated and /or constrained achievement of results including: Whether risks and assumptions as identified in the CP M&E Framework materialised or whether new risks emerged Internal factors such as timing of inputs and activities, quality of products and services, coordination and / or other management issues |
| --- | --- | --- | --- | --- |
| Output 2.1: Operational capacity of the extension service boosted to enable communities to mainstream climate risk considerations into the implementation of baseline programs: AWP Indicator 2.1: Community structures fully participating in project management &vulnerability monitoring Baseline: 0 2019 Target: 90% of community structures taking full ownership, monitor and report CCA project progress to full council | Activity 2.1: Enhance community skills in CCA project management and ownership |  |  |  |
| Output 2.2: Local and national development policies influenced by the project supported pilots to strengthen policies and policy enforcement for climate considerations Output Indicator Gender disaggregated data collected using the participatory learning, monitoring system and reported via project reports, publications 0n strategy development and PIR Output Indicator # of plans, programs and reports with gender segregated information | 2.2.1. Conduct gender analysis in all hotspots and mainstream gender into the sustainability plan 2.2.2. Capacitate the district gender technical working group |  |  |  |
| Output 2.3: Enhance monitoring, evaluation and learning AWP Indicator 2.3a: Best practices documented & shared with other projects and districts Baseline: 0 2019 Target: 75% of best practices and success stories under the project shared with other projects/districts AWP Indicator 2.3b: Joint M&E visits and number of key meetings 2019 Target: 4 joint M&E visits; 2 Steering meetings, 4DEC, Full Council Meetings | Activity 2.3: Enhance project monitoring, and dissemination of best practices piloted under the project and success stories. |  |  |  |

| Output 3.1: Construction of mini dams, water ponds, retention ridges, and water diversion structures: AWP Indicator 3.1: Number of Physical infrastructures constructed to ensure sustainable water supplies Baseline: 0 2019 Targets: 3 ponds and hatcheries operational | Activity 3.1: Consolidate capacity building efforts in fish farming committees in improved Integrated Agriculture Aquaculture (IAA) technologies. |  |  |  |
| --- | --- | --- | --- | --- |
| Output 3.2 Construction of physical structures and institutions to support infrastructure and expansion of water harvesting from dwellings: AWP indicator 3.2: Homes properly using above ground tanks Baseline: 0 2019 target: 100HHs with proper skills in managing above ground water tanks Disaster management instruments updated with climate risk information | Activity 3.2.1: Monitor utilization of above ground tanks & build capacity in operation and maintenance Activity 3.2.2: Update disaster contingency plans |  |  |  |
| Output 4.1: Degraded watersheds (forest ecosystems) rehabilitated, river banks and lake shore protected from direct siltation AWP Target: Hectares of forests under improved management Baseline: 0 2019 target: 9 Village Forest Areas with forest mgt plans | Activity 4.1: Support conservation of forest biodiversity and ecosystem services. |  |  |  |
| Output 4.2: provision of improved and sustainable supplies of energy, including adoption of sustainable charcoal AWP Indicator 4.2: Institutions using alternate and improved energy Baseline 0 2019 Target: 1 public institution using renewable energy technologies | Activity 4.2.1Complete and commission biogas plant at Machinga District Hospital 4.2.2. Strengthen the capacity of production groups (energy saving technologies) on quality improvement and marketing |  |  |  |
| Output 4.3: Diversification of household food basket and incomes via expansion of aquaculture and NTFP reduce pressure on the forests, river and lake fisheries AWP Indicator: Business Mgt skills in cooperative societies improved Baseline: 0 2019 target: At least 70% of members in cooperative societies able to improve quality of products 1 District Enterprise Development plan developed | 4.3.1. Promote Value Addition in all the sectors and market linkages (Fisheries, irrigation, Agriculture, forestry, Trade, etc.) 4.3.2. Strengthen the cooperatives management |  |  |  |
| Output 5.1: Adoption of climate smart farming practices including water use efficiency in small scale irrigation systems improved. AWP Target 5.1: Hectares on which climate smart farming is practiced Baseline: 0 2018 Target: 40ha of land under CSA 60ha area of land under climate smart small holder irrigation | 5.1.1 Upscale CSA technologies in newly irrigated schemes and their catchments 5.2 Enhance Irrigation Schemes Utilization through 5.2.1 Finalizing remaining scheme structures in newly constructed irrigation schemes 5.2.2 Development and capacity building of WUAs for proper scheme operation |  |  |  |

|  | ANNUAL PROCUREMENT PLAN 2019 |
| --- | --- |
| PROJECT TITLE: |  | Climate Proofing Development Gains in Rural and Urban areas of Machinga and Mangochi Districts |
| PROJECT ID: |  | 00080319 |
| ANNUAL PLAN PERIOD: |  | 1st January to 31st December, 2019 |
| REQUESTER: |  | Ministry of Natural Resources, Energy and Mining (Environmental Affairs Department) |
| Description of Procurement Items | Quantity |  | COA | Estimated Price | Currency | Available Budget in USD | Method of Procurement | Timeline for Procurement | Implementing partner focal point | Responsible UNDP Prog. Analyst |
| Description of goods, services or works to be procured | No. | UNIT OF MEASURE | FUND/ DONOR | OUTPUT | ACTIVITY | ACCOUNT | USD | MK or USD | USD | Government Procurement or UNDP Support Service or other | Expected Delivery Date |  |  |
| 2.3.3. Conduct an end-line impact survey | 1 | Number of studies | 10003 | 90060 | 1 | 71300 | 20,000 |  | USD | UNDP Procurement | 30th October 2019 | Shamiso Najira | Ben/ Sothini |
| 2.3.4. Conduct end of project evaluation | 1 | Number of studies | 10003 | 90060 | 1 | 71300 | 50,000 |  | USD | UNDP Procurement | 31st December 2019 | Shamiso Najira | Ben/ Sothini |
| 3.1.1. stock fish ponds and hatcheries and build capacity of farmers in fish feed formulation | 54,000 | No. of fingerlings | 10003 | 90060 | 9 | 72300 | 15000 |  | USD | Govt Procurement | 1st April 2019 | Shamiso Najira | Ben/ Sothini |
| Activity 4.1: Support conservation of forest biodiversity and ecosystem services. |  | Tree nursery inputs and cement | 10003 | 90060 |  | 72300 | 25,000 |  | USD | Govt Procurement | 1st April, 2018 | Shamiso Najira | Ben/ Sothini |
| Activity 4.2.1Complete and commission biogas plant at Machinga District Hospital | 1 | No of contractors Accessories/goods for biogas plant | 10003 | 90060 |  | 71300 72300 | 14,000 26,700 |  | USD | Government Procurement | 30th June 2019 | Shamiso Najira | Ben/ Sothini |
| 5.2.1 Finalizing remaining scheme structures in newly constructed irrigation schemes | 3 | Local contractors Cements, reinforcement wires/bars | 10003 | 90060 |  | 71300 72300 | 15,000 56,100 |  | USD | Govt Procurement | 1st July 2019 | Shamiso Najira | Ben/ Sothini |
|  | Note: |
|  | IP shall request UNDP Country Office to provide project support services by specifying “UNDP Support Service” under “Method of Procurement.” |
|  | If any changes to be made on the procurement plan for UNDP Support Services, such as descriptions, specifications and quantity of the procured items, IP shall notify the changes by writing to UNDP Country Office. |
|  | The procurement of goods and services and the recruitment of project personnel conducted through UNDP Support Service method, the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures. |
|  | The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office. |
|  | Where UNDP/Gov Procurement is noted, a decision is yet to be made between UNDP and Gov on who will handle the recruitment for that study |

RISK LOG

| Project Title: Climate Proofing Development Gains | Project ID: 00080319 | Date: 1st January to 31st December, 2019 |
| --- | --- | --- |

| Type | Description | Impact (I) & Probability | Countermeasures/Mgt response | Responsible Party | Status Q1 | Status Q2 | Status Q3 | Status Q4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Political | Political commitment and will to prioritize climate change | Shot-term issues may be prioritized over attention to the medium to longer-term climate change issues; e.g priority mostly given to political activities such as farm input subsidy program over climate change issues I= 4 P=3 | Continued advocacy and awareness raising at all levels will be made to ensure that there is commitment to mainstreaming climate change into sector policies, plans and budgets. | EAD, UNDP |  |  |  |  |
| Operational | Weak capacities of the DAESS and other departments at the district level | There are weak capacities in various departments due to vacant posts e.g EDO which is a critical post in the project. I=4 P=3 | The project will link with various development actors, consultants to build capacities of the counterpart departments in relevant fields required in the project | EAD, UNDP |  |  |  |  |
|  | High illiteracy levels among the community members in the hotspots | High illiteracy levels among community members in the hotspots which may affect rate of adoption of innovations bought about by the project I=5 P=3 | The project will train management committees and farmers involved in various interventions to ensure that they understand the tasks at hand, the project will also disseminate project lessons via workshops, television and radio programmes in local languages to ensure that they reach a larger audience. Exposure visits will also promote the spirit of seeing is believing | EAD, UNDP |  |  |  |  |
|  | New employees allocated to the project sites | New employees allocated to the project sites not trained in the quality process and procedures adopted by the organization I=4 P=2 | The project will link with government sectors to maintain staff in the project sites I=5 P=2 | EAD, UNDP |  |  |  |  |
| Natural | Climate shocks [floods and droughts] occur during the project implementation phase | Disasters may affect/change attention of government and the community from the project I=3 P=2 | UNDP will link with other UN Agencies to provide support to districts through relief projects so that the attention from climate change program is not diverted. | EAD, UNDP |  |  |  |  |
| Economic | Inflation: increase in prices and fall in the purchasing value of money | Inflation may negatively affect the project budget I=5 P=3 | Services should be booked in advance and materials should be purchased in bulky | EAD, UNDP |  |  |  |  |
| Supplier | Inadequate capability of supplier | Provision of fake equipment for public works activities for infrastructures i.e (irrigation) I=3 P=1 | Technical expertise should inspect all the supplies during goods delivery | EAD, UNDP |  |  |  |  |

# Text boxes

Total Estimated Budget for 2019: US$740,000.00

Of which:

GEF/LDCF US$ US$740,000.00

TOTAL:     US$ US$740,000.00

Programme Period:		5 years

Atlas Award ID:		80319

Project ID:			90060

PIMS #				4508

Start date:		             July 2014

End Date			June 2019

Management Arrangements	NEX

PAC Meeting Date		28 August 2014