## Setup and Share
Namibia Accelerator Lab 100 Day Action plan Draft (002)
Areas | Activity | Objective | Key Outcome | Action needed | Est Date | Status | Win status | Risks/Interventions
Set UP | Space SET UP | Create an innovative and co-working space for the team to work. | One open plan co-working space | Get authorization | 31.10.2019 | Done | Orange - Medium
|  | Plan Layout/Design |  | `-Layout of office space Paint (SDGs), furniture, lamps, i.e. |  | In progress
|  | Acquire Communication Utilities |  | Projector, software SPSS, Atlas TI (data analysis tool), cell phones 4G devices, MTC Contracts |  | In progress
| Introduce team | RR to introduce the Acc Lab Namibia team to the global network. | One introductory vid/poster | Conceptualization of Team introduction | 24 - 25/9/19 | Done (alka to send the meeting) | Green- quick
|  |  | One set of Professional pics of acc lab team | Professional photos |  | Pending
| 100-day action plan | Develop a draft road map for the first 100 days | Draft of first 100 days with input from all team members, for submission to ACC LAB HQ for feedback | Create draft 1 and share for input s | 2019-09-25 | Done | Green- quick
|  |  |  | Present draft to RR and DRR |  | Done
| Mandatory Courses 1-8 | To Complete all 8-mandatory course | Complete all 8 courses | 1 course (Be safe ) completed | November/December 2019. *Yrika to complete by Feb 2020 | In progress | Orange - Medium
|  |  |  | 7 more courses to be completed |  | In progress
| Group Email Set up | For use for external stakeholders when sharing and receiving communications. | 1 group email set up for acc lab communications | To create an email address for Yrika. | 2019-09-12 | In progress | Green- quick
|  |  | 3 individual emails created for Acc Lab team members including communications | Add Margretha for communications to the group email | Done. | Done
| UNCDF Kammy | To receive input from Kammy and UNCDF colleagues on 100 day plan | - Commentary on 100-day plan from UNCDF | Send draft to Kammy for inputs | 2019-09-26 | In progress | Orange - Medium
| Boot Camp | Share our journey up until now | Final 100-day plan | Attend final Acc Lab boot camp Quito Ecuador | 7 - 12 October 2019 | Done | Green Quick
|  | Receive guidance from the facilitators on way forward |  |  |  | Done
Share | Global SDG WEEK - 20 September – 7th October 2019. | Use social media and public engagement to share information on SDG’s | For public to have a better understanding of the sdg’s and to be introduced to local solutions | Develop content and engagement plan and share content according to the plan |  | Done | Green- quick ( the intention was to run SDG week for 2 weeks consecutively however only 1 week was done)
|  | Highlight local projects and efforts that address SDG’s. | Get a picture of where Namibia stands with regards to different goals |  |  | Done
|  | Include the call for action for SDG Song |  |  |  | Not done | Requires revision and further planning. Hijacking and being roped into other actions.
| SDG Song | Advocacy | songs aimed at primary school age students | Send out call for song submission (via social media) aimed at primary school children |  | Not started | Blue- No Action yet
|  | Teaching tool for primary school children to learn about the SDG’S | Prize for winner – trip to NADEET to take part in their educational program | Choose winner and announce winner in Free Rangers Comic |  | Not started
| Cartoon – kayec – Namibian and UN (OTHER STAKEHOLDERS TO INVOLVE) | Advocacy | Cartoon – kayec – Namibian and UNDP (OTHER STAKEHOLDERS TO INVOLVE? | Set Up Agreement on way forward | Check in with Nathan and Communiction team | Not started | Orange- Medium
|  | Communication tool to inform the public about topics that cover the SDG’s |  | Connect with Illustrator to conceptualize next issue
| Launch Magazine Layout | two page layout on Acc Lab & UNDP projects | Advocacy and information sharing on Acc Lab & UNDP | content to be created and printed to the newspaper layout | ? | Not started | Orange - Medium
| SDG HUB Online Platform | The Acc Lab virtual platform to interact and hold discussions about the SDG goals. Upload 100 day action plan initiatives to the SDG Hub | Online community adding to SDG (Namibian Context) knowledge base |  |  | Started and in progress | Green- Quick
One virtual space for Acclab
| GRB WORKSHOP- 4 | Training of civil servants GRB to be included in budgets across the board. | 20 Civil servants trained on GRB | Plan content |  |  | Requires revision and further planning. Hijacking and being roped into other actions.
|  | Involve ONF , CSI |  | Contract consultant to facilitate workshop
| Blogpost | Sharing knowledge of Acclab projects, research etc. | - One blogpost a month | - Blog post 1 – Electric car launch |  |  | Green- quick
- Blog post 2 – Ecosystem Mapping of local solutions (Sense making workshop)
EXPERIMENT | Meeting with MR. Mendelsohn - Smart cities – urban design project of CBD – River walk project | - Possibility to partner up for Riverwalk project (new location – preferably vulnerable community) | - High quality access to non-motorized transport | - Official Collaboration set up |  |  | Orange- Medium
|  | - Green wall along river walk | - Safer river bed | - Decide on new location
Thriving economic activity in the river walk
| Finish Embassy meeting | Setup bilateral meeting to provide further support | -
| NCRST – Fembio project | Capacitate the business/business owner so they can have their products displayed/sold in retail spaces | - Identify what needs to be done to get products in local shops (own shelf) |  |  |  | Blue- No Action Yet
- Provide solution to barcoding issue (collaborate with partners such as MITSD )
| Meeting with Mr. Linke B – Bicycle Ambulance | - Possibility to partner up for Bicycle ambulance in Outapi | - Community equipped with transport method (sustainable and eco friendly ) suitable for their context |  | 2019-09-17 |  | Orange- Medium
|  | - Get the town council and local authority involved | - Patients meet their required level of nourishment
- SUNCYCLE- Local solution for renewable energy transportation. E-bikes for rural areas
- Collaborate with MOHSS (connect to Hep E)
- Collaborate with Min of Poverty – Food bank connected to Clinic.
- Have a garden next to clinic that’s supervised. Use this food to makeup food parcels for community effected by HIV/AIDS
- (Future possibility – Dr prescribe meds alongside with a food parcel)
| Meeting with Ms. Akwenye One Economy Foundation | - Possibility to partner up for capacity building for 2nd economy businesses | - Capacitated 2nd Economy business that can operate in the 1st “ economy” |  | 2019-09-18
- Collaborate with one of the universities to
- CSI and Empretec
- Include private sector
| Shack dwellers | -Knowledge exchange |  |  |  |  | Blue-No Action Yet
-Address Urban migration ?
- How can they make use of renewable materials ? (eg sustainable portable houses
-(look into bi-laws that stop temporary structures)
| CLIMATE PROJECT- ONYIKA - GIZ and NNF held a workshop to sensitize onyik community to climate change | - Learn about Systems circle method for community engagement. | Better knowledge on how to use Systems mapping. | Attend workshop | 2019-09-14 |  | Green-Quick Win
| Onyika Project – | - Solution observation
Used a new tool called system circle to gather information from the community - good example of how
| Sitali – mushroom | - project aimed at giving those who have been effected by HIV/AIDS an income and provide food to the community. Her project needs help to get it going again |  |  |  |  | Blue-No Action Yet
- Plan for growth ?
- Have a garden next to clinic so patients can get food there
- WFP – train in aquaponics (or Aqua Greens train women in Zambezi region on aquaponics)
- Can we connect project to AMTA ?
- What can UNICEF (children focus), Who (ARV’S and nutrition ) and UNAIDS
| Finnish Call for Proposal – Madam Jholarina LGBTQ advocate | - Capacitate Trans woman in the south in the areas of entrepreneurship | - Capacitated Trans woman in the south |  |  |  | Orange- Medium
|  | - Include CSI and Empretec | - Decent work for Trans women
| MOU Signing with NUST | Establishing official partnership for collaboration with the University. | One Signed MOU |  | 2019-09-27 |  | Green Quick
Engagement with 15 ? students from 3 universities
| Lizelle Food in a bag | - Grassroot Solution within vulnerable community |  |  |  |  | Blue- No Action Yet
| SHOULD I KEEP THIS IN ? | - how to get it off the ground ?
| My thoughts are that this can go under eco system mapping to identify where we can place this in the long run | Idea moving forward- drop off warehouse – (organize items – N$10 shelf and people can shop )
-
| Development Bank of Namibia – Innovation Award 2019 – link up ? judge ? | - Could partner up to be panel in judging their innovation award and offer collaboration of some sort |  |  |  |  | Blue- No Action Yet
| SHOULD I KEEP THIS IN ? Yes we need to link this to the CSI project | - Stakeholder ?
-

## Experiment
Sense Making workshop (make use of system circle methodology ) | Ecosystem Mapping of local problems | - Gain better understanding of local problems and direction on how to address them | - Plan workshop and invite stakeholders | End October – Beginning November | Orange - Medium
Involve UNICEF, UNAM, IUM and NUST and NPC
BCLME
Climate Change Action