REQUEST FOR  enabling activity

Proposal for Funding Under the

part i:  project IDentifiers

| Project Title: | Nigeria's First Biennial Update Report |
| --- | --- |
| Country(ies): | Nigeria | GEF Project ID: |  |
| GEF Agency(ies): |  | GEF Agency Project ID: | 5480 |
| Other Executing Partner(s): | Federal Ministry of Environment | Submission Date: | 11 September 2014 |
| GEF Focal Area (s): |  | Project Duration (Months) | 18 |
| Type of Report: |  | Expected Report Submission to Convention | June 2015 |

- Project Framework*

| Project Objective: To assist Nigeria in the preparation of its First Biennial Update Report for the fulfillment of the obligations under the United Nations Framework Convention on Climate Change (UNFCCC) |
| --- |
| Project Component | Project Outcomes | Project Outputs | (in $) |
|  |  |  | GEF Project Financing | Confirmed Co-financing |
| Information on national circumstances and institutional arrangements | National circumstances reviewed and updated; and institutional arrangements relevant to the preparation of NCs identified and characterized. | General analyses of the country’s physical, social, economic and demographic characteristics, including an update of the main socio-economic indicators that affect GHG emissions, mitigation, actions in the country and its vulnerability to and impact of climate change. Description of institutional arrangements relevant to the preparation of the BUR and NC Development of a document on the contemporary situation of climate change in Nigeria | 10,000 | 2,000 |
| National inventory of GHG | National GHG Inventory for 2011, using 2006 IPCC methodologies. | Activity data collected and objectively validated for 2011 in critical sectors of the inventory. 2011 Land Cover map prepared for GHG estimates in the LULUCF sector National emission factors developed or improved for key sectors and where data available. Inventory report for the year 2011 prepared and published | 110,000 | 69,250 |
| Mitigation actions | National mitigation actions: emission and mitigation scenarios, NAMAs and other mitigation actions. | Emission scenarios including Business As Usual and different growth trends until 2030 provided. Mitigation scenarios including the implementation of NAMAs and other actions until 2030 developed and assessed. Reports of NAMAs and other actions prepared and assessed for policy recommendation. | 80,000 | 72,250 |
| Constraints and gaps and related financial, technical and capacity needs | Completed report on identification and assessment of constraints and gaps related to financial, technical and capacity needs. | Assessment of technical, financial and capacity needs for mitigation. Evaluation of financial needs and constraints to adopting climate change measures and strategies. Information updated on financial resources, technology transfer, capacity building and technical support received from the GEF, developed country parties and multilateral organizations for activities related to climate change | 10,000 | 5,500 |
| Monitoring, Reporting and Verification (MRV) | A completed report on domestic MRV actions in the country | Domestic MRV Implementation Report prepared | 40,000 | 51,500 |
| Education and Public awareness | Education and Public awareness | Organization of workshops/ seminars and training sessions to build capacity at various levels and assisting local governments in integrating CC in their planning. Educational materials for decision makers and key public and private sector stakeholders at all levels of governance prepared and disseminated through various media. Web page of the Department of Climate Change, Federal Ministry of Environment improved. | 42,000 | 6,000 |
| Publication of Nigeria’s First Biennial Update Report | Nigeria’s First Biennial Update Report to the UNFCCC published | First Biennial Update Report disseminated to the national stakeholders, decision makers and the civil society; First Biennial Update Report published and submitted to the UNFCCC | 18,000 | 2,000 |
| Monitoring and evaluation | M&E plan developed and implemented | Progress report (finanical and technical) prepared and submitted | 10,000 | 4,500 |
| Subtotal | 320,000 | 213,000 |
| Project Management Cost (including Direct Project Services cost 5,000) | 32,000 | 269,250 |
| Total Project Cost | 352,000 | 482,250 |

*   List the $ by project components.  Please attach a detailed project budget table that supports all the project components in this table.

- Source of Co-financing for the Project by Name and by Type

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
|  | National Meteorological Agency |  | 382,250 |
|  | UNDP Country Office |  | 100,000 |
| Total Co-financing |  |  | 482,250 |

- GEF Financing  Resources Requested by Agency,  Country and Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Programming of Funds | (in $) |
| --- | --- | --- | --- | --- |
|  |  |  |  | GEF Project Financing (a) | Agency Fee a)/ (b)2 | Total c=a+b |
|  |  | Nigeria |  | 352,000 | 33,440 | 385,440 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources | 352,000 | 33,440 | 385,440 |

a) Refer to the Fee Policy for GEF Partner Agencies

part ii:  Enabling Activity JustiFication

| A. Enabling Activity Background and Context (Provide brief information about projects implemented since a country became party to the convention and results achieved): | Nigeria ratified the United Nations Framework Convention on Climate Change (UNFCCC) in 1994; and the Kyoto Protocol in 1997. The Federal Ministry of Environment (FME) is the implementing entity for UNFCCC through Department of Climate Change (DCC) which acts as the focal point to the Convention and facilitates the participation of both the public and private sectors in the UNFCCC and the Kyoto Protocol mechanism. The DCC coordinated the preparation of the First and Second National Communications, including the greenhouse gas inventories, as well as studies on vulnerability, impact and adaptation to climate change, technology transfer, education, and public awareness, with the aid of resources from International Organisation. The country is in the process of preparing its first Biennial Update Report (BUR) and the third National Communication. In these regards, it is seeking assistance from the Global Environment Facility (GEF) with the United Nations Development Program (UNDP) as the implementing agency. Nigeria's First National Communication was submitted to the Conference of the Parties in 2003, the Second National Communication in January 2014. As a result of the new international context, based on decisions taken during the Conferences of the Parties (COP) 16 and 17, Nigeria’s First Biennial Update Report is proposing outcomes that would enable it respond to emerging obligations under the UNFCCC such as NAMAs, MRV and national inventory reports, among others. |
| --- | --- |
|  | Nigeria is also implementing its National Action Programme (NAP) alignment enabling activity under the United Nations Convention to Combat Desertification (UNCCD). In recognition of the need to climate-proof the country’s environment, Nigeria prepared a National Adaptation Strategy and Plan of Action (NASPA) in 2011 and a National Policy on Climate Change and Response Strategy (NPCC-RS) which was approved by the Federal executive Council in September 2012. The country has an Inter Ministerial Committee on Climate Change, which meets on a regular basis to take important decisions on the progress of the country’s climate change efforts. It has also served as an entry point for mainstreaming climate change considerations into various government line ministries’ policies and plans. The inter-ministerial committee includes representatives from relevant ministries and agencies such as the Ministries of Agriculture and Rural Development; Water Resources; Foreign Affairs; and Health, the National Emergency Management Agency and the National Planning Commission. The country also recognizes the critical importance of climate change in national development planning. The Federal Government’s current economic growth plan, Nigeria Vision 20:2020, Economic Transformation Blueprint, recognizes a changing climate as a threat to sustainable growth in the next decade. It sees climate change as a critical challenge globally and, in Nigeria, as a potential driver of “damaging and irrecoverable effects on infrastructure, food production and water supplies, in addition to precipitating natural resource conflicts.” This recognition is an important first step towards a climate change adaptation strategy and action plan. In addition, the country recognizes the advocacy role of civil society organizations (CSOs) and the importance of research in advancing knowledge about climate change through collaboration with academic and research institutions. To this end, it has a network of researchers and works with a number of CSOs in mainstreaming knowledge-based climate change information into national development. In the new national and international climate change mitigation and adaptation framework, and to fulfill the new obligations arisen from COP 16 and 17 in Cancun and Durban respectively relating to the submission of national communications and Biennial Update Reports, support from the Global Environment Facility is needed for the continuous development and consolidation of the existing technical and institutional capacity and to continue the efforts of mainstreaming climate change into national policies, plans and programmes. This First Biennial Update Report, which is to be submitted by June 2015 will provide an update of the country’s most recently submitted national communication i.e. the Second National Communication. |
| B. Enabling Activity Goals, Objectives, and Activities (The proposal should briefly justify and describe the project framework. Identify also key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable. Describe also how the gender dimensions are considered in project design and implementation): | The long term objective of the project is to strengthen the technical capacity of Nigeria in the development of actions that allow the mainstreaming of climate change into national and sectoral development goals by continuing the institutional and technical capacity strengthening process. The immediate objective of the project is to assist Nigeria in the preparation and submission of its First Biennial Update Report to the Conference of the Parties to the UNFCCC for the fulfillment of its obligations to the Convention under Dec. 1/CP. 16 par. 60 and Dec 2/CP. 17 par. 41 and Annex III. The project’s expected outcomes are: Update of the national circumstances and institutional arrangements relevant to the preparation of the biennial report and the national communications. Evaluation of the National GHG Inventory with 2011 as the baseline year, using 2006 IPCC methodologies. Description of the country’s mitigation actions including emission scenarios, mitigation scenarios, NAMAs and other mitigation actions Assessment of the technology, financial and capacity needs for mitigation. Support to the process of establishing domestic Measurement, Reporting and Verification arrangements. Further strengthening Education and Public awareness on climate change issues Publication and submission of the First Biennial Update Report according to the guidelines contained in Annex III of Dec.2/CP. 17 The Project outcomes will be achieved through a suite of outputs and activities, which are in line with the GEF’s climate change mitigation objective CCM-3 under GEF-6: Foster Enabling Conditions to Mainstream Mitigation Concerns into Sustainable Development Strategies – Programme 5: Integrate findings of Convention obligations and enabling activities into national planning processes and mitigation targets. General analyses of the country’s physical, social, economic and demographic characteristics including an update of the main socio-economic indicators that affect emissions, mitigation, actions in the country and its vulnerability to and impact of climate change.. Description of institutional arrangements relevant to the preparation of the BUR and NC A document of contemporary situation containing relevant information with respect to climate change. Activity data collected for 2011 in critical sectors of the inventory. 2011 Land Cover map National emission factors improved for key sectors Inventory report published Emission scenarios including business as usual and different growth trends until 2030. Mitigation scenarios including the implementation of NAMAS and other actions until 2030. |
|  | NAMAs description and other mitigation actions report. Update of climate scenarios for the country, using IPCC models. Proposal for gender sensitive climate change adaptation and mitigation measures in priority sectors and regions. Technology, financial and capacity needs for mitigation assessed. Financial needs and constraints in order to adopt climate change measures and strategies evaluated Information updated on financial resources, technology transfer, capacity building and technical support received from the GEF, developed country parties and multilateral organizations for activities related Climate change Description of the strategic actions on MRV carried out in the country Workshops and training sessions organized to create capacity in public, scientific and technological institutions, educational and civil society institutions; and specially for assisting local governments in integrating CC in their planning. Educational materials aimed at the general public, teachers, elementary and secondary students, academics and local governments. Web page improved. First Biennial Update Report disseminated to the national stakeholders, decision makers and the civil society First Biennial Update Report published and submitted to the UNFCCC The Department of Climate Change (DCC) has been responsible for coordinating the First and Second National Communications to the Conference of the Parties of the UNFCCC, a number of greenhouse gas emission inventories and adaptation projects. These efforts have contributed to the institutional strengthening process, making DCC competent for the application of the Convention at the national level. In all projects, DCC has ensured the participation of the different relevant stakeholders including academia, private companies, government institutions and civil society. The integration of the different sectors strengthens the institutional and technical capacity of the different stakeholders and institutions. Thus, the influence of the development process in climate change studies has not been limited to a reduced group of experts and decision makers from the governmental institution, where lies the responsibility for the fulfillment of the national obligations to the Convention. The Federal Ministry of Environment, through DCC, would continue to undertake these leadership and coordination roles for the development of those actions required under the Convention, including the mainstreaming of climate change issues into national development actions for the achievement of results to be reported and communicated through the National Communications and Biennial Update Reports. The stakeholders involved in the project comprise different institutions and organizations, with different roles and participation. As earlier indicated, the Federal Ministry of Environment, through the Department of Climate Change, will act as the Implementing Partner and will be in charge of the project coordination. Relevant Ministries, such as the Ministries of Agriculture and Rural Development, Water Resources, Transport, Civil Aviation, Health, Finance and Trade and Investment, as well as the Energy Commission of Nigeria will play key roles in the elaboration of the National GHG Inventories, as they provide critical data for the estimation of the respective sectoral emissions. |
|  | In the development of the mitigation actions, an important role will be played by the Universities particularly the Centre for Climate Change and Fresh Water Resources (Federal University of Technology, Minna) and other research institutions, in particular regarding assumptions related to sector specific mitigation plans and in updating the baseline scenarios, based on the newest available data, as well as for the NAMAs identification and preparation for its inclusion in the National Registry and its submission to the UNFCCC. The Department of Climate Change will coordinate capacity building activities for identification, preparation and implementation of mitigation actions for GHG emissions in key economic sectors. The Inter-ministerial Committee on Climate Change will continue to play an important role as a consultation committee, as it includes representatives from the Federal Ministry of Environment (FME), Ministry of Foreign Affairs, Ministry of Finance, Ministry of Petroleum Resources, Nigeria National Petroleum Corporation, Ministry of Transport, Ministry of Health, Ministry of Agriculture and Rural Development, Ministry of Water Resources, National Planning Commission , Ministry of Science, Technology, the academia and Civil Society. Climate change is a phenomenon that affects the entire population, however, children, the elderly, the physically challenged and women are groups that are most affected. Understanding how the different social roles, economic status of men, women and physical well-being of other vulnerable groups are affected differently by climate change will improve actions taken to (adapt to and) mitigate climate change. Consequently, organizations representing these vulnerable groups such as the Ministry of Women Affairs will be incorporated into the project, not only as beneﬁciaries but also in the decision-making process on climate change related activities to ensure inclusive, and gender-sensitive climate change strategies and plans are being identified and implemented. |
| C. Describe the Enabling Activity and Institutional Framework for Project Implementation (discuss the work intended to be undertaken and the output expected from each activity as outlined in Table A ). | Institutional framework On behalf of the Government, the Ministry of Environment (FME), through the Department of Climate Change (DCC), will act as the Implementing Partner. The DCC will be the executing and operational unit that will coordinate and implement the project activities for the preparation of the Biennial Update Report. In this regard, it will play the same role it did in the past for the preparation of the previous two National Communications. The Government of Nigeria will provide support to the project through a number of initiatives, including the Low Emission Capacity Building Programme. This will include provision of technical experts, office space and equipment, and Conference and meeting space. It will also provide support to the coordinator (Project Manager) of the project. Additional co-financing will be available from UNDP, which will be the GEF Implementing Agency for the project. It will also provide administrative support and budgetary and financial monitoring for the execution of project activities. It will further offer technical back-stopping to the project through its international climate change advisor. |
|  | Activities for Project implementation (i) National circumstances A synthesis of the national development priorities, objectives and circumstances on the basis of climate change will be provided through an analysis of the National Development Plans and other relevant national and state level development report. This outcome will also take into consideration all new studies, projects and research developed since the preparation of the Second National Communication. It will include aspects such as geography, demography, gender, natural resources, climate and education, social and cultural aspects, as well as macroeconomic parameters, employment, income and services gender considerations including the vulnerable groups in the society. The characterization of the specific sectors such as agriculture, forestry, soils, ecosystems and biodiversity, water resources, fisheries, coastal resources, energy, waste, tourism, transport and health will also be addressed. The probable effect of the national circumstances described on Nigeria’s ability to mitigate climate change will be specifically assessed. Also as part of this outcome, the information on the institutional arrangements relevant to the preparation of the national communications and the biennial update reports will be updated. (ii) GHG National Inventories Nigeria has developed two national inventories of greenhouse gases with reference years 1990, and 2000. As part of this project, the 2011 Inventory will be developed using the 2006 IPCC Guidelines. Moreover, the national emission factors for the agriculture, forestry and other land use sectors will be used. These emission factors will be made available to the BUR team and used for the 2011 GHG inventory. The 2011 National Inventory will include the estimation of the net emissions involving direct greenhouse gases: carbon dioxide (CO2), methane (CH4), nitrous oxide (N2O), hydrofluorocarbons (HFC), perfluorocarbons (PFC) and sulfur hexafluoride (SF6). Furthermore, it will include the estimation of the indirect emissions of greenhouse gases (ozone precursors) such as nitrogen oxide (NOx), sulfur dioxide (SO2), carbon monoxide (CO) and non-methane volatile organic compounds (NMVOCs). The sectors of the national activity to be considered will include Energy, Industrial Processes and Product Use, Agriculture, Forestry and other Land use and Land cover change as well as Waste. The inventory to be prepared in the framework of this First Biennial Update Report, as in the previous inventories, will be under the responsibility and coordination of the Department of Climate Change. The main activities to be undertaken for this component are: Renewing and strengthening Institutional arrangements with other institutions/Ministries for specific sectors. Data collection/ interaction with data providers (for 2011 inventory) and other key stakeholders. |
|  | Preparation of working sheets and summary tables, uncertainty estimation and management. Analysis of Result. Publication of 2011 Inventory report. (iii) Mitigation actions Identifying the low-cost options for reducing the carbon intensity of the economy and designing effective interventions is crucial to attaining the national goal of low carbon, climate resilient, pro-growth and sustainable development With the goal of implementing national appropriate mitigation actions in the context of sustainable development and national development priorities, Nigeria will establish a number of sectoral NAMAs in order to identify existing or potential national actions and its submission to the UNFCCC. As part of the activities under this BUR, a report will be put together containing a description of the national arrangements to enable the implementation of NAMAs. An important activity of this project will be the collection of data on mitigation actions or groups of actions being developed in the country and their analysis to provide a description in the BUR that includes name, nature of the action, coverage, quantitative goals, progress indicators, associated methodologies and assumptions, objectives, steps taken or envisaged to achieve the action, progress of implementation and results achieved. Data on participation in international carbon market mechanisms will be collected and reported on. The mitigation analysis proposed will build on the results obtained in previous and current studies and projects. In particular, baseline and mitigation scenarios until 2030 for abatement of GHG emissions will be further developed. (iv) Support for financial and technical Capacity needs for mitigation received A study of financial, technological and capacity needs and constraints of institutions responsible for activities related to climate change mitigation will be conducted through a number of activities including, but not limited to: Evaluating the financial needs and constraints to adopting climate change measures and strategies for effective national mitigation response. Updating information on financial resources, technology transfer, capacity building and technical support received from the GEF, developed country parties and multilateral organizations for activities related to climate change. Evaluation of capacity needs through the collection, synthesis and analysis of existing information, individual interviews or group discussions, site visits, among others. (v) Monitoring, Reporting and Verification An integral assessment will be conducted regarding the different options and possibilities for the domestic MRV according to the guidelines to be developed, considering national circumstances and capabilities, as well as taking into account the different nature of the mitigation actions. Furthermore, a report will be prepared describing the progress of implementation of such institutional arrangements. |
|  | (vi) Education and public awareness Seven National awareness campaigns (one per each of the six geo-political zones and one national) targeting relevant stakeholders in the public, scientific and technological institutions, educational and civil society organizations institutions will be organized. This will also help in assisting governments at all levels to integrate Climate Change considerations in their planning. Basic climate change IEC materials aimed at the general public, teachers, elementary and secondary students, academics and local governments will be prepared, and disseminated using the mass media including dedicated web pages. (vii) Compilation, Publication and Submission of the First Biennial Update Report The First Biennial Update Report document will be compiled according to the guidelines contained in Annex II of Dec. 2. CP 17 and it will be submitted to the Conference of the Parties in the United Nations Framework Convention on Climate Change according to the requirements and formats established by the UNFCCC Secretariat. Furthermore, the Biennial Update Report will be disseminated to identified relevant national stakeholders, including decision makers, researchers, private sector operators and representatives of the civil society. |
| D. Describe, if possible, the expected cost-effectiveness of the project: | This enabling activity will not produce GHG emission reductions directly but will contribute to better understanding and improved capacity for implementation of Nigeria’s climate change policy. |
| E. describe the budgeted M&E Plan: | The project monitoring and evaluation will be carried out according to UNDP programming policies and procedures. Project start A Project inception meeting will be held within the first two months of project start with those with assigned roles in the project organization structure, UNDP country office and other relevant stakeholders. Quarterly The Project Coordinator shall report progress made in the quarterly reports to be monitored in UNDP ATLAS and the UNDP New Enhanced Results Based Management Platforms. Bi-annual progress: Status Survey Questionnaires to indicate progress and identify bottlenecks as well as technical support needs will be carried out twice a year. Annually Annual Report: The Project Coordinator with the collaboration of the project team will prepare an annual report which will be submitted to the national coordination body and the UNDP offices in the country and at HQ. This report could be jointly reviewed during the fourth quarter of the year by the National Implementing Partner and UNDP, with the purpose of analyzing the progress into the results achievement, its relation with the expected effects, as well as the review of the Annual Work Plan for the next year. End of Project During the last three months, the Project Coordinator with the collaboration of the project team will prepare the Project Terminal Report, to be submitted and reviewed by the national coordination institution and UNDP. Audit on Project will follow UNDP Financial Regulations and Rules and applicable Audit policies. |
| F. Explain the Deviations from typical Cost Ranges (where applicable): | N/A |

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the Operational Focal Point endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Yomi Johnson Ladapo | Director/GEF operational Focal point | Ministry of Environment | 09/05/2014 |

B. Convention Participation

| Convention | Date of Ratification/ Accession (mm/dd/yyyy) | National Focal Point |
| --- | --- | --- |
| UNCBD |  |  |
| UNFCCC | 08/30/1994 | Dr. Adejuwon Samuel |
| UNCCD |  |  |
| Stockholm Convention |  |  |
|  | Date Signed (mm/dd/yyyy) | National Focal Point | Date of Notification under Article 7 to the Minamata Convention Secretariat |
| Minamata Convention |  |  |  |

C.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Climate Change Enabling Activity approval in GEF 6. |
| --- |
| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| Adriana Dinu, Executive Coordinator and Director, a.i UNDP-GEF. |  | 09/11/2014 | Maude Veyret-Picot, Technical Specialist, UNDP (Green-LECRDs) | +1 212 906 6196 | maude.veyret-picot@undp.org |

Annex: ENVIRONMENTAL AND SOCIAL SCREENING SUMMARY

Name of Proposed Project:     Nigeria's First Biennial Update Report

A. Environmental and Social Screening Outcome

☒Category 1. No further action is needed

☐Category 2.  Further review and management is needed.  There are possible environmental and social benefits, impacts, and/or risks associated with the project (or specific project component), but these are predominantly indirect or very long-term and so extremely difficult or impossible to directly identify and assess.

☐Category 3. Further review and management is needed, and it is possible to identify these with a reasonable degree of certainty. If Category 3, select one or more of the following sub-categories:

☐Category 3a: Impacts and risks are limited in scale and can be identified with a reasonable degree of certainty and can often be handled through application of standard best practice, but require some minimal or targeted further review and assessment to identify and evaluate whether there is a need for a full environmental and social assessment (in which case the project would move to Category 3b).  See Section 3 of the Review and Management Guidance.

☐Category 3b: Impacts and risks may well be significant, and so full environmental and social assessment is required. In these cases, a scoping exercise will need to be conducted to identify the level and approach of assessment that is most appropriate.  See Section 3 of Review and Management Guidance.

B. Environmental and Social Issues (for projects requiring further environmental and social review and management)

NOT REQUIRED

C. Next Steps (for projects requiring further environmental and social review and management):

NOT REQUIRED

D. Sign Off

___________________________________

Project Manager: maude.veyret-picot

Signed Date: 2014-09-09

# Footnotes

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submission.

Co-financing for enabling activity is encouraged but not required.

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources. For EAs within the ceiling, PMC could be up to 10% of the Subtotal GEF Project Financing.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF