| UNITED NATIONS DEVELOPMENT PROGRAMME NIGERIA COUNTRY OFFICE | ONE PAGE MISSION REPORT SUMMARY Dates: 19 – 23June 2017 |
| --- | --- |
| Name: Anthony Omata Josephine Edwards | Unit: M&E and PFT units | Extension No. | Travel Authorization Number: |
| Approved Mission Itinerary Abuja – Niger Niger – Abuja Abuja – Gombe Gombe - Abuja | Mission Title UNDP/BOI Solar Energy Project Phase I; Visit to sites in Niger and Gombe states. |
| Participants Ruseh Oghenekaro (BOI) Anthony Omata(UNDP) Josephine Edwards(UNDP) |
| Background The UNDP/BOI field visit was to validate the procurement and instalment of solar equipment communities in Niger and Gombe states as below; State: Niger Date of mission: 19 – 20 June 2017 Project Sites: (i)Swasun community, Katcha LGA, (ii) Mantutu community, Katcha LGA State: Gombe Date of mission: 21 – 23 June 2017 Project Sites: (i)Kolako community, Balanga LGA, (ii) Ayaba community, Billiri LGA These communities at present are not connected to the national grid and depends mainly on fuelwood for energy use. Findings Niger State All items were available on site for both communities except for the items below; Solar panels – These are been imported and should be available mid-July based on information from supplier. Power House Construction - This will be completed in mid-July. Thunder Arrestor – This will be provided when the power house in constructed. Completion date for both sites in Niger state is 2nd week of August Gombe State Equipment arrived at Gombe site on the day of verification. All items were available for both communities except for the items below; Solar panels – These are been imported and should be available mid-July based on information from supplier. Power House Construction - This will be completed in early August. Thunder Arrestor – This will be provided when the power house in constructed Completion date for site in Gombe is (Kolaku community-ending of August and Ayaba community- mid September) Next Steps/Actions UNDP project team to follow up very closely with BOI to ensure solar panels are delivered as scheduled. UNDP to also ensure field visits are scheduled against timelines to ensure installation is completed as agreed. Pictures Cross-section of some equipment at Niger state site Verification in progress by UNDP, BOI and supplier at Niger state site Waiting patiently…! Some young members of the community waiting for batteries to be dismantled from shipment casing at Niger state site Some young members of the community waiting for batteries to be dismantled from shipment casing at Niger state site Off-loading some equipment at Gombe state site Some equipment at a district head’s house for safe keeping before installation Off-loading some equipment at Gombe state site This is how the finished solar power house will look like. This is an initial pilot executed by Niger State government and BOI. |