Strengthening the Capacity of

National Human Rights Commission Project

Donors: Finland, Switzerland, Denmark, UK, UNDP and OHCHR

# Implementing Partners: NHRC, UNDP and OHCHR Nepal

CA			            Constituent Assembly

CDO			Chief District Officer

CERD			Convention on the Elimination of Racial Discrimination

CPA			Comprehensive Peace Agreement

CSO			Civil Society Organisation

DDC			District Development Committee

DNA			Deoxyribonucleic Acid

ESCR			Economic, Social and Cultural Rights

FOPHUR			Forum for Protection of Human Rights

GoN			Government of Nepal

HIV/AID                         	 Human Immunodeficiency Virus/ Acquired Immune Deficiency Syndrome

HRBA			Human Rights Based Approach

HRC			Human Rights Council

ICC			International Coordinating Committee

ICCPR			International Covenant on Civil and Political Rights

ICRC			International Committee of the Red Cross

IDPs			Internally Displaced Persons

INSEC			Informal Sector Service Centre

INGO			International Non-Governmental Organization

IT			            Information Technology

NDC			National Dalits’ Commission

NGOs			Non-Governmental Organizations

NHRC			National Human Rights Commission

NHRIs			National Human Rights Institutions

NWC			National Women’s Commission

OHCHR		            Office of the High Commissioner for Human Rights

OSRT			Office of the Special Rapporteur on Trafficking

PIU                                    Project Implementation Unit

PMO			Prime Minister Office

PSA			Public Service Annuncement

QUARA			Quality Assurance and Review Advisor

SCNHRC                          Strengthening the Capacity of National Human Rights Commission

SDC			Swiss Agency for Development and Cooperation

SLC			School Leaving Certificate

ToT			Training of Trainers

UPR			Universal Periodic Review

UK 			United Kingdom

UNDP			United Nations Development Programme

VDC			Village Development Committee

Project Information

Full Title: Strengthening the Capacity of National Human Rights Commission Project

Award ID: 00049651

Expected Output:

1) NHRC capacity strengthened in promoting and monitoring investigation, documentation and reporting of human rights violations.

2) Selected laws reviewed and amendments recommended in order to comply with international treaties as a part of fulfilling treaty obligations.

Implementing Partner: National Human Rights Commission, UNDP and OHCHR Nepal

Project Duration: August 2009 - December 2012

Total Budget:			USD 2,300,380

Allocated Resources:

UNDP: 			          	USD 200,000

Denmark: 			            USD 393,700

UK: 			            USD 331,675

Finland: 			            USD 602,410

SDC: 				USD 475,737

OHCHR parallel funding: 	USD 300,380

Executive Summary

This is the fourth progress report of the project to the donors and presents the annual progress from January to December 2011. The Executive Summary of this report is followed by the Background, Project Summary, Annual Progress, Financial Implementation, Priorities for Coming quarters and Conclusion.

With the project entering its last year, it is time to analyse the progress and setbacks of the project.  The project began in early 2010 while the National Human Rights Commission (NHRC) was faced with critical concerns such as the enactment of the NHRC Bill, staffing issues, and low level of implementation of the NHRC’s recommendations.  Some other areas of concerns raised by various international communities were NHRC’s cooperation and collaboration with OHCHR and civil society organisations, maintaining NHRC’s "A" status conferred by the ICC Accreditation Committee.  In this situation, the project has had a substantial role in addressing the gaps and challenges of NHRC during its brief period.  The project maintained a strategic and realistic vision by balancing both immediate and long-term needs of the Commission. The balance and coordination maintained by the project with NHRC Commission and staff, OHCHR, civil society and the international community has been essential to the project’s success.  Some notable achievements include the increased level of implementation of NHRC’s recommendations, and the introduction of innovative concepts such as the Human Rights Based Approach (HRBA) Manual and its related training conducted in different parts of the country as a preventive measure for human rights protection.

Monitoring and Investigation

This year a total of 84 cases were monitored and investigated out of which 66 cases were related to torture, extrajudicial killing, and disappearance, and 18 human rights treaty based monitoring in the areas of health, education, senior citizens, prisoner’s rights, and consumer rights in various parts of the country. The Commission forwarded 148 recommendations during this reporting period to the Government of Nepal for necessary action such as providing compensation and reparation to the victims, and prosecution of the perpetrators.  The second phase of the exhumation mission was conducted at the suspected burial site of the five persons disappeared and killed in Godar Village Development Committee (VDC) in Dhanusa district during the armed conflict period.   A comprehensive report on exhumation has been prepared for follow-up by the appropriate authorities.  As a result of continuous effort, the government released and handed over compensation of NRs 1.5 million to the family members of the victims after continued follow-up on the cases.

Institutional Strengthening of NHRC

After efforts of continued pressure and lobbying, the long pending National Human Rights Commission Act was finally enacted on 20 January 2012.  Despite some reservations on the new Act, its absence had been causing a serious impediment to everyday administration and effective implementation of its constitutional mandate.  The project played an active role in the passage of the NHRC Bill through concerted effort with civil society, UN agencies, and international community.  A series of lobby and advocacy programmes and publications targeted at the passage of Bills have contributed to the enactment of the National Human Rights Commission Act, 2011.

The project has provided a range of tools for better delivering NHRC’s services of human rights protection and promotion.  For instance the Exhumation Guidelines and Complaint Handling guidelines produced after a series of consultation are aimed at enhancing the Commission’s monitoring and investigation capacity. Some highly innovative concepts such as the Human Rights Audit Guideline, HRBA training Manual, and Economic, Social and Cultural Rights (ESCR) Indicators User Guide will be instrumental in expanding NHRC’s current scope of work and venturing in the areas of ESCR. Similarly the project has provided infrastructural support for development of Human Rights Resource Centre in the Central and Regional Offices, NHRC’s website redesigning, high-power internet facility, and computers.  In terms of capacity building, the project has supported for Training of Trainers on HRBA to Development for 25 NHRC staff in collaboration with OHCHR,  and provided Appreciative Inquiry Training for 43 staff that was effective in revitalizing staff morale and garnering commitment.

The project has had a vital role in linking NHRC with the donors, civil society organisations, international community, and UN agencies, as human rights is an area of concern for all.  NHRC has reinforced its major constitutional mandate of working jointly with civil society organisations by collaborating for advocacy on crucial issues such as impunity, transitional justice issues, human rights situation, rights of senior citizen, child, women and other marginalised groups.

The project provided the technical services and facilitated the entire process of the new Strategic Plan (2011-13) formulation that commenced from the end of 2010.  Due to deep understanding of the intricacies and complexity of NHRC, the project could provide substantial input to the Plan.  The final Strategic Plan (2011-2013) of NHRC sets out priories for addressing critical issues such as ending impunity and discrimination; monitoring of ESC Rights, and institutional development.

Treaty Monitoring and Legal Assistance and Advice

The project continued its support to NHRC for monitoring the fulfilment of international human rights treaty obligations of the Government of Nepal.  Three state reports namely the 3rd periodic report on the Economic Social & Cultural Rights, the 3rd, 4th & 5th Periodic Report on the Child Rights Convention, and the ILO  Convention, 169 Report were reviewed from a human rights perspective and consulted with a broad range of stakeholders.  Likewise, three Bills namely the Penal Code, Criminal Procedure, and Sentencing Bill, have also been reviewed in line with internatinal human rights instruments and the recommendations have been submitted to the Government of Nepal.  The project also facilitated the review of the current Annual Plan, Policies and Budget of  the Government of Nepal from a human rights perspectives and organised an interaction program with concerned experts, government agencies, and civil society organizations. The programs came up with valuable recommendations as well as encouraging response from  the participants that suggested to organise follow-up program in the future.  Likewise the project supported the Universal Periodic Review (UPR) report prepation process to monitor the UPR recommendations.

Training and Education on Human Rights

Building capacity of government and non-governmental organisations by imparting specific knowledge and skills on HRBA has been an important step towards institutionalising human rights in the overall cycle of development plan and programs.  To that end 227 government officials and civil society organisations have been trained on HRBA to Development in different parts of the country.  The training has generated positive response and motivation in the issues of human rights while developing skills to analyse their work from a human-rights perspective. The HRBA training will also be instrumental in creating a valuable link with the monitoring of the National Human Rights Action Plan and the ESCR of people.  A total of 591 human rights defenders were trained on basic human rights as well as on specific human rights issues in different parts of the country. The training has developed capacity of human rights defenders, and also resulted in formation of network and collaboration among NHRC and human rights organizations. A Training Curriculum for Human Rights Defenders, as well as said before, a training manual on human rights based approach to development has been prepared.

The second batch of ten interns completed the six-month long Human Rights Internship Program and gained a wide range of skills for human rights protection and promotion.  Till date 20 aspiring youths have been groomed as human rights professionals.  The recruitment process of the new third batch is underway.

Human Rights Advocacy

NHRC, civil society, OHCHR and international organisations  made concerted efforts to build pressure on the government for implementation of NHRC recommendations. An interaction program on “The Role of Stakeholders in Ending Impunity in Nepal” was effective in garnering commitment from key authorities such as the Prime Minister to address the issues of impunity and implementation of NHRC’s recommendations.  Similarly, the project facilitated advocacy programs on a wide range of thematic issues—such as caste discrimination, torture, disappeared victims, rights of disabled persons, rights of senior citizens, women’s rights, and rights to movement—with a  a series of promotional activities including human rights day, exhibition of the human rights publications,  discussion programs, football match and blood donation program.  Held in different parts of the country, these events were effective in presenting the overall situation and challenges on different themes of human rights, identifying the possible way forward, and garnering commitment and support from concerned stakeholders.

As last year, the project supported the NHRC to produce 16 publications (see Annex 3 for details) on different human rights issues.  The diverse nature of publications such as training manuals, guidelines, human rights situation monitoring reports, thematic human rights reports, and newsletters have contributed to keeping the public informed as well as enhanced NHRC’s capacity for human rights protection.  Some landmark publications such as the Ujuri upar Aayog ka Sifarisharu (Recommendations on the Complaints Received) a book that documents the total cases of complaints received by NHRC pertaining to the armed conflict, , the status of implementation of recommendations, and analysis -- has been an important advocacy tool for NHRC and the human rights community.  Building on the previous year’s successes, the project also maintained its support for the preparation of the National Status Report on Trafficking in Persons.

To raise popular awareness on human rights and put pressure on the concerned stakeholders, the weekly radio program on human rights Sachetana continues to be broadcast through Radio Sagarmatha and its eleven network radio stations across Nepal. An independent evaluation of the radio program concluded that the radio program has been effective in raising awareness on general human rights and the functions of NHRC among the public.

Conclusion

Despite some internal and external challenges, the project has strengthened NHRC in many areas.  The enhanced level of implementation of NHRC’s recommendations mainly in terms of compensation to the victims of human rights violations, enactment of the NHRC Act, and development of innovative tools for human rights work such as the Consumer Rights Guidelines, Human Rights Audit Guidelines, and HRBA training manual are some significant project outcomes.  Similarly, the strengthening of NHRC’s capacity for investigation and monitoring of human rights violations, capacity development for NHRC staff and human rights defenders, and advisory role to the Government of Nepal on state report and draft Bills have been crucial for effective delivery of NHRC’s constitutional mandate.  Finding an appropriate and timely means of addressing critical matters such as the management of staff within NHRC, the state of impunity in the country, implementation of NHRC’s recommendations for taking action against the perpetrators of human rights violations, and the drafting of the Constitution within the extended timeframe will be decisive for an improved human rights culture in the country.  A strong commitment, collective advocacy, and sincere efforts from NHRC and other actors such as the Government of Nepal, civil society, and international community will be inevitable for realising the broader goals of NHRC for the protection and promotion of human rights.

- Background

The National Human Rights Commission of Nepal (NHRC) was established on 26 May 2000, under the Human Rights Commission Act of 1997.  The Interim Constitution of Nepal, 2007, elevated NHRC as a constitutional body and broadened its mandate relating to the protection, promotion and respect of human rights. The Comprehensive Peace Accord (CPA) has entrusted NHRC with responsibilities to monitor the compliance of the human rights provisions of that accord.  Article 132 of the Interim Constitution of Nepal vests primary responsibility in the Commission to protect and promote the human rights in Nepal.  In order to implement the constitutional mandate, NHRC is empowered to conduct inquires and investigations on its own and upon complaint filed at NHRC office, to take decisions on cases and recommend to the Government of Nepal, compensation to the victims and punishment to the perpetrators. In addition to reviewing national laws to determine consistency with obligations undertaken under international human rights conventions ratified by Nepal, the Commission has also been mandated to recommend appropriate amendments and effective implementation and to work jointly with civil society especially human rights organizations on human rights advocacy, education, training, and awareness campaigns on human rights. Newly enacted National Human Rights Commission Act 2012 also added more mandates such as monitoring of human rights related activities of international human rights organizations, rescue and interim relief to the victims of human rights violations.

The Strategic Plan of NHRC was designed with the objective of implementing the constitutional mandates.  In this context, UNDP, OHCHR and NHRC developed the Strengthening the Capacity of National Human Rights Commission (SCNHRC) Project with the major goal of supporting NHRC to implement its Strategic Plan for strengthening its capacity for protection, promotion and respect of human rights.

- Project Summary and Objectives

The SCNHRC Project covers the following areas of strategic focus based on the functions, duties and powers of the National Human Rights Commission, as set out in the Interim Constitution of Nepal 2007 and the Strategic Plan of NHRC.

  - Formulation of strategies and human rights audit plan to ensure the respect of human rights by state actors;

  - Monitoring of Human Rights obligations and strengthening the internal HR treaty monitoring mechanism;

  - Ensuring a Human Rights Friendly Constitution;

  - Promotion and protection of civil, political, socio-economic and cultural rights;

  - Enhancing NHRC’s capacity to collaborate with civil society mainly human rights NGOs and;

  - Review of the discriminatory laws in line with international human rights standards.

- Annual Progress

The annual progress is presented on the basis of the six major results set out in the 2011 Annual Work Plan of the project.  The details of the progress are provided from Annex 1 to 4.

Activity Result 1: Formulation of Strategies and Human Rights Audit and Compliance Plan

- A comprehensive resource manual on HRBA has been prepared and published.  The resource manual covers the basic concept of HRBA, and ways of integrating human rights in the development cycle.  The overall aim of this venture is to integrate human rights in development plans and programs of the government.  The manual is an important tool for NHRC in view of its constitutional mandate of monitoring the implementation of ESCR as well as the National Human Rights Action Plan.

- This year a total of 227 government officials and civil society organisations have been trained on HRBA conducted in different parts of the country.  The participants of training  comprised of concerned government organizations such as District Development Committee, District Health Offices, District Education Office and District Administrative Office.  Building capacity of government as well as non-governmental organisations on HRBA is an  important step towards mainstreaming  human rights in the overall cycle of development plan and programs.  The training has generated motivation to address human rights issues, while developing skills to enable actors in both government and civil society to analyse their work from a human-rights perspective.  Follow up mechanisms will be crucial to get significant result in the long-term.

A Trainer of Trainers on HRBA was organised from 18 to 21 December for 30 participants from NHRC and government organisations to produce trainers for training.  The lead trainer of the ToT was from OHCHR, Geneva.

- The first draft of the Comprehensive Human Rights Audit Guideline has been prepared.  The Guideline is an innovative concept for providing a tool for monitoring  economic, social and cultural rights.  The Guideline sets out indicators and guidelines to audit the compliance of state and private organizations to fulfill its human rights obligations.  After consultation with wider stakeholders, the Guideline will be piloted next year.  The Guideline is an innovative tool developed with the objective of strengthening the NHRC’s capacity to work for human rights protection in a preventive way.  During the process of finalizing the Guideline some project sites were visited to test the Guideline.  The Melamchi Drinking Water Project in Sindupalchowk and the industrial areas in Butwal, Rupandehi were visited for that purpose in October and November.

Activity Result 2: Strengthening NHRC's Capacity for Monitoring of HR Treaty Obligations

- The project supported the deployment of a total of 18 HR treaty monitoring missions in different thematic areas such as right to education, rights of people living with HIV/AIDS, prisoner’s rights, right to health, child rights, senior citizens rights, right to education and consumer rights. (see Annex 2)  The missions have been followed by consultation with concerned stakeholders and recommendations to the Government of Nepal to take necessary action in each theme. As follow up to the treaty monitoring, a three days’ training workshop on Right to Food was organised in Dadeldhura.   A total of 45 participants comprising of government officials from the District Food Corporation, Chief District Office, and civil society organizations were trained.

- The project facilitated the UPR review process, starting with the UPR report preparation in 2010.  A high-level delegation comprising of NHRC, NWC and NDC participated during Nepal’s review in the UPR mechanisms in Geneva on 27 January 2011.  During the program, the delegation also participated in the side-events and lobbied the concerned state representatives to raise pertinent human rights issues of Nepal.  A total of 135 recommendations were made during the review at UPR mechanism.  On the basis of the UPR working group report and outcome of the January review, the project organised a series of meetings with NHRC, OHCHR and other NHRIs to lobby the Government of Nepal for adoption of the recommendations that were to be further considered by June 2011 and related rejected recommendations.

- OHCHR and NHRC also jointly prepared a UPR Road-Map: a concrete and systematic framework for implementing the UPR recommendations. The Road Map lists the concrete actions to be taken by each State actor of Nepal, including the Prime Minister Office (PMO), the Legislature -Parliament and relevant Ministries to fulfil the UPR recommendations. The UPR Road Map also lists actions that other agencies, such as civil society organizations (CSOs) and United Nations agencies, should take to support the Government. The Road Map was jointly submitted by OHCHR and NHRC to the OPM on April 2011.

- Subsequently, the Commissioner from NHRC participated during the adoption of the final UPR outcome document in Geneva during the Plenary of HRC held in 7 June 2011.  During the Plenary Session OHCHR provided information and technical advice to NHRC.   The Commissioner presented the overall human rights situation of Nepal and advocated with the GoN to accept the UPR recomemndations that the Government had rejected or kept under consideration.  The Government  of Nepal agreed to accept 12 more  recommendations.

- The project extended support for the development of a plan to implement the UPR recommendations of the final UPR outcome document.  In 2012, a series of programmes will focus on: advocacy and lobbying;  awareness raising on issues emerging from the UPR recommendations at both regional and national level; and, development of promotional materials.

- A comprehensive Human Rights Defender’s Training Curriculum has been prepared after a series of consultation meetings with NHRC staff.  OHCHR and experts including the Quality Analysis Review Advisor (QUARA) provided their inputs on the curriculum.  The curriculum includes Basic Concept of HR, Evolution of HR, National and International Mechanisms of HR, Overview of ICESCR and ICCPR, History of HR in Nepal, Fundamental Rights, Roles & Responsibilities of HR Defenders, and Investigation Monitoring and HR Dialogue.  A standard curriculum like this will serve as an important tool for building the professional capacity and ethics of NHRC staff, HR organisations, and HR defenders.

- Consultations were organised among NHRC senior officials and representatives from the Nepal Police, OHCHR and the project, to conceptualise a human rights related training manual for the Nepal Police. Topics of the training manual have been provisionally identified.  Similarly, a Human Rights Reporting Training Manual is being prepared in consultation with NHRC, human rights defenders, senior journalists and OHCHR.  The resource material will be a valuable tool particularly for journalists reporting on human rights issues.

- The project supported the development of the overall concept and terms of reference for the position of Special Rapporteur on ESCR, CERD, child rights, women’s rights and human rights defenders.  The position of the Special Rapporteur is being integrated in the institutional structure of NHRC with the major objectives of strengthening the capacity of NHRC through advisory role for the preparation of thematic status reports, advisory role to the Commissioners on the concerned themes, and building necessary capacity and skills of NHRC staff on these themes.  The recruitment process of the Rapporteurs is underway.

Activity Result 3: Incorporating Human Rights in the Constitution

- The project has been providing inputs to the Constitutional Assembly (CA) for a human rights friendly constitution. Since the constitution making process has been stalled, a TV jingle on the theme of Constitution has been broadcast for raising awareness among the general public on the need to complete work on the final constitution.

Activity Result 4: Strengthening NHRC's Capacity to act for the Promotion and Protection of Civil and Political, and Economic, Social and Cultural Rights

- Three policy guidelines i.e. the Complaint Handling Guidelines, Exhumation Guidelines, and Consumer Rights Monitoring Guidelines developed.  These guidelines will be crucial for strengthening the institutional capacity of NHRC by enabling it to carry out its responsibilities in a more effective and systematic way.  Consultation meetings were held with concerned stakeholders for all the policies and guidelines.  (see Annex 4 for details).  The Consumer Rights Monitoring Guideine has been prepared in the light of prevailing violations of consumer rights, inadequate consumer protection laws and weak implementation of existing ones and serves as a tool for those working for the the rights of consumers such as NHRC, human rights activists, government staff and consumer rights activists.  The policies and guidelines have been used during monitoring msisions, for instance the Consumer Rights Monitoring Guideline was used during the monitoring mission related to consumer rights protection in Dhading district.

- A comprehensive report on exhumation has been prepared for publication.  A high-level exhumation mission at the suspected burial site of five persons disappeared and presumed to be killed during the armed conflict period was carried out in September 2010.  In February 2011, a second phase of the high-level exhumation mission was conducted at the suspected burial site of the five persons disappeared and killed in Godar VDC in Dhanusa during the armed conflict period.  The first mission had recovered remains of four bodies from the site while the second mission successfully recovered the fifth body.  A comprehensive report on exhumation has been prepared for follow-up by the appropriate authorities. The NHRC’s role in dealing with these emblematic cases from the armed conflict period is crucial in terms of providing justice to the victims, prosecuting the perpetrators, and supporting the impending transitional justice system.  As a result of continuous effort, the government released compensation of Rs 1.5 million to the family members of the five victims on the basis of NHRC’s recommendation.

- The project has supported a total of 216 monitoring and investigation missions to date in different parts of the country.  In 2011, a total of 66 monitoring and investigation missions have been conducted in different themes such as extrajudicial killing, torture, internally displaced persons, women’s right etc.(see Annex 1 for details).

- NHRC’s capacity in advocacy on impunity related issues has also been strengthened through development of joint strategies between NHRC and OHCHR. NHRC and OHCHR jointly published a legal opinion paper on “Remedies and Rights Revoked: Case withdrawals for serious crimes in Nepal” in August.

- NHRC, civil society, OHCHR and international organisations have been making concerted efforts to build pressure on the Government of Nepal for implementation of NHRC’s recommendations. An interaction program on “The Role of Stakeholders in Ending Impunity in Nepal” was organized on 13 January 2011 in coordination with the Forum for Protection of Human Rights, one of the pioneer human rights organisations of Nepal.  Three thematic papers were presented on the role of various stakeholders for ending impunity by the Office of the Prime Minister, NHRC and Civil Society. The papers focused on the overall situation of impunity, its challenges, non-implementation of NHRC recommendations, and withdrawal of criminal prosecutions.  The program saw the participation of the Prime Minister of Nepal, the Ministery of Home Affairs, Government Secretaries, Chairperson of FOPHUR, Head of OHCHR, CA members, Former NHRC Members, representatives of the Attorney General’s Office, security officials, civil soceity members, and representatives of political parties.

In response to the program, the Prime Minister directed the concerned ministries to imlement NHRC’s recommendations and prepare its implementation status.  The PM appreciated NHRC’s role in the protection of human rights and expressed strong commitment to follow-up on the implementation of NHRC recommendations.  Subsequently, the Office of the Prime Minister prepared a status report on the implementation status of NHRC recommendations.  The report has given some encouraging figures in terms of the implementaton  of NHRC recommendations in 2011 compared to implementation figures of NHRC recommendations in 2010.  The implementation status of the total of 465 recommendations was as follows:

Table 3: Implementation status of NHRC’s recommendations

| Level of Implenmentation | Implementation status as per NHRC’s record up to 2010 (365 recos) | Implementation status as per PM Office report, as of May 2011 (465 recos) |
| --- | --- | --- |
| Fully Implemented | 8% | 28% |
| Partially Implemented | 32% | 55% |
| Non-Implemented | 60% | 17% |

- The Indicators for Monitoring ESCR in Nepal - A User's Guide has been published.  It was prepared by the Working Group on ESCR Indicators comprising NHRC, OHCHR, CSOs and the Government of Nepal. The Guide provides a set of structure, process and outcome indicators on the rights to adequate food, housing, health, education and work in the context of Nepal. The indicators will be a useful tool for monitoring ESCR in Nepal and strengthening NHRC’s capacity to deal with violations related to economic, social and cultural rights. Orientation programs on the Guide have been planned for other Government and Civil Society Organizations.  Two workshops on the Indicators of Economic Social and Cultural Rights were organized by the Biratnagar Regional Office in November that had active participation of 65 concerned stakeholders in the region. (see Annex 4 for details)

- The weekly radio program on human rights Sachetana continues to be broadcast through Radio Sagarmatha in Kathmandu and its eleven network radio stations across Nepal. Following the completion of its one year contract in March 2011, an independent evaluation of the radio program was conducted from 6-30 March 2011.  The evaluation was based on the objectives of the program which included – raising awareness among the general public of NHRC's mandate; reinforcing the implementation of NHRC recommendation, and contributing  to a human rights friendly society.  The evaluation concluded that the radio program had largely achieved its objectives and made some encouraging findings.  The radio program was found to have raised awaress of general human rights and role/functions of NHRC and in some instances enabled individuals to avail themselves of the complaints procedures provided the NHRC.   It was also found that the program had served to increase collaboration between media and NHRC for promotion of human rights.

- NHRC has the constitutional mandate of making people aware of their human rights. In line with that, NHRC has been producing promotional and education material for concerned stakeholders.  In this context, Public Service Announcements (PSA) on human rights issues such as women’s rights (gender based discrimination), child rights (corporal punishment), rights against torture, rights of persons with disability, and NHRC’s functions have been produced for broadcast through various radio channels.  The six PSAs were produced through wider consultations with NHRC staff on the theme, content and style of presentation.

- NHRC has the mandate of monitoring the human rights component of the Comprehensive Peace Accord (CPA).  The CPA’s 5-year status report has been prepared, covering human rights violations committed by both parties of the signatories of the CPA .

- The National Status Report on Trafficking in Persons especially on Women and Children 2009- 2010 was formally launched by the Prime Minister of Nepal during the 63rd International Human Rights Day on 10 December.  The national report is one of the major outputs of Office of the Special Rappartuer againt Trafficking of NHRC.  A reference group comprising UN agencies, INGOs, NGOs, and Ministry of Labour, Ministry of Home Affairs and Ministry of Foreign Affairs institutions provided input to the report. OHCHR faciliated OSRT’s contact with the UN Special Rapporteur for the purpose of the report.  The report is divided into seven chapters covering the situation of trafficking in persons, international trafficking and migration in entertainment industry, foreign labour migration and trafficking.  It also addresses Monitoring of Anti-Trafficking Policies, Programs, and Activities, Law Enforcement Status and Judicial Responses to Trafficking and Responses of National, Regional and International Communities in combating trafficking in persons. The report will be instrumental for those working to combat trafficking in persons and for the researchers and academics. A series of consultations were organised in several dates for consultation on the report (see Annex 4 for details).

- Every year, NHRC celebrates human rights days to better understand and generate awareness of emerging human rights issues.  The human rights days marked are as follows:

- The Convention on the Elimination of All Forms of Racial Discrimination (CERD) Day was marked on 21 March 2011 in coordination with the National Coalition Against Racial Discrimination.  The programme was organized to advocate for inclusion of rights of Indigenous Peoples and other minority groups  in the forthcoming constitution.

- The 14th International Day Against Torture was held on 26 June in Kathmandu and Biratnagar.  During the event, NHRC presented a paper on the situation of torture victims in Nepal; some torture victims shared their bitter experience and its impact on their lives. The Attorney General, Secretary of PMO, OHCHR, representative of political parties, civil society representatives and the Commissioners addressed the issue.

- The Government of Nepal declared as the Anti-Untouchability Day.  To mark the fifth year of this declaration, an interaction program was organised in coordination with National Dalit's Academy on 4 June 2011.  A paper was prepared containing an analysis of the Caste-based Discrimination and Untouchability (Offences and Punishment) Act, passed by the Legislature-Parliament in March 2011, on the situation of caste based discrimination in Nepal.  Two human rights experts made comments on the paper.  The Minister for Local Development, CA members, NHRC, National Women Commission, National Dalit's Commission, security agencies, civil society, and media participated in the programme.  Similarly, the day was also marked at the regional level in Biratnagar.  Strong recommendations were made to the GoN and concerned parties for the effective implementation of the Caste-based Discrimination and Untouchability (Offences and Punishment) Act.  NHRC’s coordination with civil society for dealing with the issue of untouchability and caste based discrimination was commended in the program.  Similarly a discussion program on the situation of racial discrimination and untouchability was held in Biratnagar on 6 November.  Interaction on Law against Untouchability was organized in Ilam and Taplejung by the Regional Office of NHRC, Biratnagar Office on 25 and 29 December that had total of 65 participants. There interactions were highly effective in terms of generating awareness on newly enacted laws against discriminations.

- An interaction program was organised during the International Day of Enforced Disappearances on 30 August to raise the concerns of those disappeared people during the armed conflict period.  NHRC made a presentation of the current data of disappeared people and activities carried out by the Commission in its relation.  The program had participation of concerned government organisations, civil society organisations, and families of the victims.

- A three-day program comprising an interaction and street rally was held during the International Day for Persons with Disabilities from 2 to 4 December.  The program focused on the issues of persons with disability and reviewed relevant laws in line with the Convention on the Rights of Persons with Disability.  A 30-minute documentary has also been prepared with a view of raising awareness on the issues of persons with disabilities.

- A series of events were organised nation-wide to mark the International Human Rights Day on 10 December.  Events included street rally, interaction programs focusing on different human rights issues, exhibition, blood donation program, and football match. (see Annex 4 for details)

- NHRC in coordination with the Nepalese Law Student’s Association, NHRC and other human rights organisations including OHCHR organised a program on Advancing Justiciability of Economic, Social and Cultural Rights from 11-13 April 2011.  The conference discussed a broad range of issues in the light of ICESCR such as its overview, role of judiciary, quasi judiciary, law professionals, constitutional protection, transitional justice, review of NHRIs mandates, national and international protection mechanisms, and approaches and tools to deal with ESCR violations.  The conference comprised Chief Justice, Secretary of the Office of the Prime Minister, Commissioner of NHRC, Attorney General, CA members, Member of National Planning Commission, and participants from civil soceity, I/NGOs, Nepal Bar, UN agencies, and law schools.  The program was highly effective in sensitising on the ICESCR and its importance in the present context of Nepal.  NHRC’s role in the protection and promotion of ICESCR was presented during the programme.

- During the 16-day national campaign on violence against women, an interaction program entitled “Role of Media for Promotion and Protection of Human Rights in Women” was organised jointly with Sanchrika Samuha on 4 December.  The program was highly effective in raising awareness of women’s rights issues, and possible means of addressing them.  The event was attended by key stakeholders including the Minister of Women, Children and Social Welfare, media, NGOs, legal professionals and victims of gender-based violence. Similarly, several interaction programmes on issues of women rights relating to the rights of Kamlaris,  freedom to movement and role of stakeholders in protection of women’s rights have been held in Kailali and kanchanpur (see annex 4 for details)

- The project supported NHRC to prepare and publish different types of policy recommendations such as NHRC’s recommendation relating to the transitional justice system in Nepal.

Activity Result 5: Strengthening NHRC's Capacity and enhancing the Collaboration with Civil Society and Human Rights NGOs

- An interaction programme analysing the government’s annual budget from a human rights perspective was held on 24 July, 2011.  The NHRC produced a comprehensive paper analysing the annual budget on the basis of groups and sectors such as women, children, disabled, marginalised groups, and areas such as agriculture, education, employment etc.  The programme was highly appreciated by the participants as an innovative initiative  considered instrumental for ensuring that human rights are addressed in national plans and policies.  The representatives of the National Planning Commission were of the view that such an exercise of analysing the National Plan from a human rights perspective would also enable the National Planning Commission to come up with new indicators and more effective means of addressing human rights at the national level.  Similarly, there were many suggestions to hold a series of follow up activities and form mechanisms on the basis of the program.  Participants included representatives from the NHRC, National Planning Commission, Ministry of Planning, Ministry of Finance and civil society organisations.  The report of the session was sent to the Government of Nepal.

- A series of interaction programmes were held in different parts of the country with active participations of the Commissioners.  Briefing meetings on the local security and human rights situation were organised with security and administrative officials in Ilam, Dhankuta, Pokhara and Dhangadi. Concerned regional administrators, regional police chief and army chief participated in the briefing meeting. The NHRC’s Chairperson and Commissioner headed the meeting.   Similar meeting were organised with human rights defenders during the same time  (see annex for details).

- As in previous years, the project facilitated NHRC’s participation in the "24th Annual meeting of the International Coordination Committee of National Institutions for the Promotion and Protection of Human Rights (ICC)" held in Geneva from 16 to 19 May 2011.  On the basis of NHRC status reports, communication between NHRC and ICC, and recommendations from concerned organisations and individuals, the ICC Sub Committee on Accreditation (SCA) decided to retain the NHRC’s “A” status.

- The new NHRC Strategic Plan (2011-2013) has been prepared. The Plan has incorporated seven strategic objectives of NHRC for the coming three years- such as ending impunity, institutional development, monitoring and investigation of violations of human rights, monitoring the compliance of international human rights instruments, monitoring and justiciability of economic, social and cultural rights, protection and promotion of group rights, transitional justice and human rights friendly constitution. The project facilitated the entire process of the Strategic Plan formulation.  A series of consultation meetings were held at the regional level in Pokhara, Dhangadi, Nepalgunj, Biratnagar, and Janakpur and then at the national level in Kathmandu. (see annex 4 for details)  The consultation had active participation of NHRC staff, Government organisations, security agencies, civil society, academia, political parties and professional organisations.

- The NHRC Annual Planning Meeting held from 21-23 August incorporated the Strategic Objectives and prepared the Annual Work Plan of NHRC and the Annual Work Plan (2011-2012) for the  Project.  The planning meeting decided to review the Annual Work Plans every four months, based on which the first meeting was held from 15-16 December. Commissioners, secretary, head of the department from headquarters, and all the regional and sub-regional offices participated in the meeting.

- NHRC and OHCHR jointly reviewed the NHRC Bill 2009 registered at the Legislative Parliament. NHRC and OHCHR produced a technical position paper analysing the Bill in line with Paris Principles and the related independence and autonomy of NHRC.  The project published the “NHRC-OHCHR Observation on NHRC Bill 2009: Open dialogue on draft legislation series 2” to support  advocacy with Members of Parliament on the enactment of the NHRC Bill.

- An interaction program in coordination with a Joint Forum, a network of Human Rights NGOs, was organised to lobby the CA members for the passage of the Bill.  The CA members, including the Chairperson of the CA, accepted that the independence and autonomy of the NHRC would be incorporated in the Bill. Concerned CA members agreed to call a meeting with NHRC senior management on the Bill to disucss contentious issues.  During the program, the Secretary of the NHRC presented a paper on the status of the Bill, and the necessary changes to be made for ensuring autonomy and independence of NHRC.  After the presentation, the participants gave their comments on the NHRC Bill.  The discussion was facilitated by the former Speaker of the House and the Coordinater of the Sub-Committee of the Legislature-Parliament.  OHCHR Chief of Asia Pacific Section (Geneva) who was at the program, stressed the need for timely enactment of the Bill in conformity with the Paris Principles.  Towards the end of the program, the Coordinator of the Sub-Committee of the Legislature-Parliament called a meeting with NHRC for a final disucssion on the Bill.  The event was attended by the Chairperson of the House, CA members, government officials, Nepal Police-HR Cell, Nepal Army-HR cell, lawyers, representatives of political parties, human rights activists, OHCHR, civil society, media and NHRC staff.  It was highly influential and effective in terms of advocating for the passage of NHRC Bill and garnering support from the Speaker and concerned CA members.

- To raise awareness on human rights issues among the general public, the NHRC is establishing Human Rights Resource Centres in its central and regional offices.  The procurement process for infrastructural support is underway.  The major input for the resource centres will include training for librarians, premises renovation, books, bookcases, printers, scanners, photocopier, and furniture.  A total of 36 computers have been handed over to NHRC for the use of the resource centre and other purposes.  NHRC was also provided with Mailer Daemon Server and Anti-virus software to strengthen the IT system.

- During this year, a total of 591 (see Annex 4 for details) human rights defenders have been trained on the basic concept of human rights and specific areas such as Human Rights & Journalism, Rights of Indigenous Peoples and Women, Forensic Investigation Procedures in various parts of the country. Banke, Taplejung, Dhanusa, Surkhet, Banke, Dhanusa, Kaski, Kathmandu, Rupandehi, Kanchanpur, Dang, Dadeldhura, Kailali, Bhojpur, Dolkha.  These training programme developed capacity of the human rights defenders in the field of human rights documentation and also resulted in formation of a network among NHRC and human rights defenders in different parts of the country.

- The second batch of ten interns have completed the six-month long Human Rights Internship Program and gained a wide range of skills for human rights protection and promotion.  To date, 20 aspiring youths have been groomed as human rights professionals.  The Human Rights Internship Program has been a highly successful activity, especially considering its relatively low cost.  Witnessing the growth of fresh interns into promising professionals has been a valuable experience.  The recruitment process for the third batch is underway.  An experience sharing program was organised for the interns on 29 December at NHRC.

- NHRC has the constitutional mandate to coordinate with civil society.  A summary report entitled Civil Society Coordination with NHRC - 2011 was published and disseminated.  The report gives a brief account of the programs carried out by NHRC in coordination with civil society and OHCHR in 2011.

- The project supported a discussion programme with civil society on the report related to human rights violations in Ramechhap during the conflict period.  The report was prepared jointly by NHRC, national level human rights organizations and OHCHR.  The programme was conducted on 6 February.

- A report entitled “A Baseline Study on Reported Cases related to Abuse or Human Rights Violation of elderly people related cases in Nepali media” was lauched on 26 August.  Interaction programs on the rights of senior citizens were organised in Pokhara and Birgunj.  The program focused on the roles of concerned stakeholders on the rights of senior citizens, social security issues, legal challenges, protection mechanisms etc.

- An interaction program on "Freedom of Movement: Fundamental Human Rights" was held on 15 May.  It had a total of 147 participants comprising ministers from the Ministry of Tourism and Civil Aviation, and representatives from Federation of Nepalese Chambers of Commerce and Industry, Nepal Chambers of Commerce,  political parties, civil society, and OHCHR.  A paper analysing the bandhas (strikes) organised in the last three years and its impact on human rights, particularly on the freedoms to movement of general people was presented.  Toward the end of the interaction program, the participants urged the political parties and interest groups to stop using bandhas as a loose means of protest and to respect the rights of the general public.

- 11 issues of the monthly Human Rights Bulletin have been published in 2011.  The  bulletin produced in English gives a major highlight of the activties of NHRC and is a widely disseminated publication.

Activity Result 6: Selected Laws reviewed and recommended for new Legislation as required by International Treaty Obligations

- The project supported the NHRC to review the State report on the ILO Convention 169, 3rd periodic report of the Economic Social & Cultural Rights, and 3rd, 4th & 5th Periodic Report on the Child Rights Convention.  Based on the review, comprehensive reports on the implementation status of the Conventions were prepared. After consultation with concerned stakeholders on the reports, recommendations were made to the Government of Nepal.

- Likewise, the Penal Code, the Criminal Procedure Code and Sentencing Bill, currently tabled in the Legislature-Parliament, were reviewed in line with international human rights instruments.  A consultation meeting was organised on the report with  representatives from OHCHR, I/NGO staff, human rights activists, civil soceity organisations, lawyers, Nepal Police, Armed Police, and NHRC staff. Suggestions and comments were then submitted to the GoN.

- Priorities for coming quarters

Some of the priorities for the coming quarters are as follows:

- Conduct a series of training on HRBA for Government and NHRC officials.

- Continue advocacy and consultation programs on Human Rights Audit Guideline.

- Establish and strengthen the Human Rights Resource Centres.

- Publish reports such as the five years monitoring report on comprehensive peace accord (CPA), National Report on the status report of trafficking in persons, and compilation report on exhumation.

- Preparation of UPR recommendation monitoring report.

- Review of the laws and implementation of human rights treaty obligations.

- Continue support for monitoring and investigation of human rights violations.

- Conduct research on transitional justice and trends of withdrawal of serious human rights related cases.

- Conduct research on the economic, social and cultural rights situation based on the indicators prepared.

- Financial Implementation

Conclusion

The project’s support has been crucial to enable NHRC to carry out its core function of monitoring and investigation, advocacy, dialogue and advice to the GoN on human rights issues.  A wide range of activities have been carried out and successfully completed in the areas of investigation and monitoring, exhumation, coordination with civil society and the international community, human rights training, advocacy, and publications.  NHRC’s venture in areas such as its facilitation of  the UPR process and collaborative efforts for ending impunity have contributed to NHRC commitment for human rights protection and promotion. During this year, the second phase exhumation mission recovered the human remains of the fifth missing person in Godar, Janakpur and successfully completed the exhumation mission. Likewise, the restored “A” status of NHRC by ICC SCA has affirmed the credibility and independence of NHRC and motivated the institution to carry out its roles more effectively.

The project has made a significant contribution to strengthen NHRC’s capacity for monitoring and investigating cases of human rights violations, widen the scope of work of NHRC in the sector of economic, social and cultural rights through development of innovative concepts such as the training manual on HRBA, ESCR indicators, and HRBA training targeted for government staff working in the sectors of health, education, and supply. Similarly, the project continued to conduct joint advocacy programmes on different themes in coordination with human rights organizations in across Nepal.

The new the NHRC Strategic Plan (2011-2013) has been finalised.  It has a strong emphasis on different aspects of human rights such as ending the culture of impunity by increasing state accountability for human rights, strengthening institutional capacity of NHRC with a strong focus on staffing, investigation and monitoring of human rights violations, fulfilment and compliance with international treaty obligation, the respect, protection and fulfilment of CESCR, transitional justice, and support for the development of human rights friendly constitution.

Nevertheless, there are still numerous challenges that need to be carefully addressed by NHRC in the coming days.  Finding appropriate and timely means of addressing critical matters such as the management of staff within NHRC, the state of impunity, implementation of NHRC’s recommendations for taking action against the perpetrators of human rights violations, and the  Constitution making process within the extended timeframe will be decisive for an improved human rights culture in the country.  A strong commitment, collective advocacy, and sincere efforts from NHRC and other actors such as the Government of Nepal, civil society, and international community will be inevitable for realising the broader goals of NHRC.

***

| Annex 1 |
| --- |
| Monitoring and Investigation (January-June 2011) for SCNHRC |
| SN | NHRC Office | Theme | No of Cases |
| 1 | Pokhara Office | Extra-judicial killing | 3 |
| 2 | Pokhara Office | Internally Displaced | 3 |
| 3 | Pokhara Office | Domestic Violence | 1 |
| 4 | Dhangadi Office | Torture | 5 |
| 5 | Kathmandu Office | Extrajudicial Killing | 5 |
| 6 | Kathmandu Office | Demonstration/Bandh called by Chettri society | 1 |
| 7 | Kathmandu Office | Demonstration/Bandh called by UCPM | 5 |
| 8 | Butwal office | Torture | 1 |
| 9 | Butwal office | Extrajudicial Killing | 1 |
| 10 | Butwal office | Internally Displaced | 1 |
| 11 | Butwal office | Child rights/ conflict victim | 1 |
| 12 | Butwal office | Threat | 1 |
| 13 | Butwal office | Right to property | 1 |
| 14 | Dhanusa office | Disappearance and Extrajudicial killing | 1 |
| 15 | Khotang Office | Disappearance | 1 |
| 16 | Khotang Office | Extrajudicial killing | 1 |
|  |  | Total | 32 |
| Monitoring and Investigation (July-December 2011) for SCNHRC |
| 1 | Kathmandu Office | Extrajudicial killing | 1 |
| 2 | Kathmandu Office | Extrajudicial killing | 1 |
| 3 | Kathmandu Office | Torture | 1 |
| 4 | Kathmandu Office | Demonstration Monitoring | 1 |
| 5 | Kathmandu Office | Illegal detention | 1 |
| 6 | Kathmandu Office | Demonstration Monitoring (Bandh) | 1 |
| 7 | Kathmandu Office | HR situation monitoring | 1 |
| 8 | Kathmandu Office | Women's Rights | 1 |
| 9 | Kathmandu Office | Torture | 1 |
| 10 | Kathmandu Office | Torture and extrajudicial killing | 1 |
| 11 | Janakpur Office | Torture | 1 |
| 12 | Janakpur Office | Extrajudicial Killing | 1 |
| 13 | Janakpur Office | Administration of Justice | 7 |
| 14 | Janakpur Office | Administration of Justice | 3 |
| 15 | Pokhara Office | Torture | 2 |
| 16 | Pokhara Office | Disappearances | 1 |
| 17 | Pokhara Office | Administration of Justice | 1 |
| 18 | Pokhara Office | Extrajudicial Killing | 1 |
| 19 | Pokhara Office | Disappearances | 2 |
| 20 | Nepalgunj Office | Extrajudicial Killing | 2 |
| 21 | Nepalgunj Office | Torture | 1 |
| 22 | Nepalgunj Office | Torture | 2 |
|  |  | Total | 34 |

|  |  | Annex 2 |  |
| --- | --- | --- | --- |
| Treaty Monitoring Missions (January-June 2011) for SCNHRC |
| SN | Date/NHRC Office | Theme | No of missions |
| 1 | Pokhara Office | Monitoring Mission-Old Age home Monitoring based on the Rights of Senior Citizens | 1 |
| 2 | Dhangadi Office | HIV/AIDS | 2 |
| 3 | Butwal Office | Child Rights | 1 |
| 4 | Butwal Office | Prisoner's Rights | 2 |
| 5 | Butwal Office | Right to Health | 1 |
| 6 | Butwal Office | Right to Education | 1 |
| 7 | Kathmandu Office | Free and fair environment during SLC examination [Child Rights] | 1 |
| 8 | Kathmandu Office | Detention Centre Monitoring | 1 |
| 9 | Khotang Office | Human Rights Situation Monitoring | 1 |
|  |  | Total | 11 |
| Treaty Monitoring Missions (July-December 2011) for SCNHRC |
| SN | Date/NHRC Office | Theme | No of missions |
| 1 | Kathmandu Office | Consumer Rights Monitoring in Dhading | 1 |
| 2 | Dhangadi Office | Monitoring of Human Rights Situation | 3 |
| 3 | Pokhara Office | Detention Centre Monitoring | 1 |
| 4 | Pokhara Office | Human Rights Situation Monitoring | 1 |
| 5 | Nepalgunj Office | Security and HR situation | 1 |
|  |  | Total | 7 |

Annex 3

| SN | Publications in 2011 for SCNHRC |
| --- | --- |
| 1 | Human Rights Bulletin (monthly issues from Jan to Dec) |
| 2 | NHRC Nepal and OHCHR Nepal observations on the NHRC Bill 2009 |
| 3 | Nagarik Samaj Sanga Aayog ko Sahakrya - Sanchipta Pratibedan 2067 (Civil Society Coordination with NHRC -Summary Report 2011) |
| 4 | Rastriya Manab Adhikar ek Jhalak (NHRC -a glance) |
| 5 | Karagar tatha Hirasat Anugaman Marganirdeshika 2067 2nd edition (Prison and Detention Monitoring Guideline) |
| 6 | Manabadhikar Sambandhi Sankramankalin Nyaaka Sambandha ma Rastriya Manabadhikar Aayog ko Nirnaya (NHRC's Decisions related to transitional Justice) |
| 7 | Remedies and Rights Revoked - Case Withdrawal for Serious Crimes in Nepal |
| 8 | Upabhokta ko Manab Adhikar Sanrakshan tatha Sambardhanka Lagi Anugaman Marga Nirdeshika 2068 (Consumer Rights Monitoring Guideline) |
| 9 | Baseline Study on Reported Cases of Elder Abuse in Nepali Press(July 2008- July 2010) |
| 10 | Indicators for Monitoring ESCR in Nepal - A User's Guide |
| 11 | Information Booklet |
| 12 | HRBA To Development -Resource Manual |
| 14 | Barishk Pratibedan - Sar Sanchipta Chhapai (67-68)/ (Summary Annual Report) |
| 15 | Trafficking in Persons, Especially on Women and Children in Nepal -National Report (2009-2010) |
| 16 | Trafficking in Persons, Especially on Women and Children in Nepal -National Report (summary in English) |

Annex 4

| List of Major Project Activities for 2011 |
| --- |
| S.N | Date | Name of Activity | Venue/place | Total Partici-pants | M | F |
| 1 | 06 Jan | Interaction program on consumer rights monitoring guideline | NHRC hall | 111 | 61 | 16 |
| 2 | 13 Jan | Role of Stakeholders for Ending Impunity in Nepal | NHRC hall | 165 | 109 | 65 |
| 3 | 23-27 Jan | Geneva visit for UPR process | Geneva | 4 | 3 | 1 |
| 4 | 24 Jan | Strategic planning consultation meeting -Dhangadhi | Dhangadhi | 66 | 53 | 13 |
| 5 | 24 Jan | Consultation regarding Janakpur Exhumation Mission | NHRC meeting room | 14 | 13 | 1 |
| 6 | Jan -March I quarter | Backlog cases (Decision of the Commission on 110 cases) | Kathmandu | 2 | NA | NA |
| 7 | 21 Jan | Interaction on Consumer Rights Monitoring Guideline | Dhangadhi | 46 | 36 | 10 |
| 8 | 28 Jan | Meeting on Human Rights Audit Guideline | NHRC hall | 9 | 7 | 2 |
| 9 | 06 Feb | Interaction program on the documentation of Human Rights violation during conflict period at Ramechap | Ramechap | 79 | 71 | 8 |
| 10 | 07 Feb | Interaction program on ILO 169 Convention relating to Indigenous and Tribal people | NHRC hall | 53 | 34 | 19 |
| 11 | 09 Feb | Donors' meeting | NHRC hall | 34 | 20 | 14 |
| 12 | 27 Feb | Consultation meeting for Consumer Rights Monitoring Guideline | Biratnagar |  | 20 | 1 |
| 13 | N/A | UPR Translation | NA |  |  |  |
| 14 | 11-18 Feb | Godar Exhumation Mission (II Phase) | Godar VDC, Dhanusha | 12 |  |  |
| 15 | 20-21 Feb | Half yearly Review meeting of NHRC FY 2067/2068 | View Bhrikuti, Lalitpur | 36 | 29 | 7 |
| 16 | 22 Feb | Planning Meeting with Regional and SROs | NHRC Office |  |  |  |
| 17 | 23 Feb | Meeting with OSRT Department on National OSRT Report | SCNHRC |  |  |  |
| 18 | 24 Feb | Consultation meeting organized by OSRT | NHRC hall |  |  |  |
| 19 | 04 March | Consultation on HR Training Curriculum and manual development for Nepal Police | SCNHRC hall |  | 7 | 5 |
| 20 | 05 March | Consultation for NHRC's new Strategic Plan | Biratnagar | 74 | 60 | 14 |
| 21 | 14 March | Sharing on the Independent Evaluation of radio program Sachetana | NHRC Hall | 15 | 9 | 6 |
| 22 | 21 March | CERD Day Marked in coordination with National Coalition Against Racial Discrimination | NA |  |  |  |
| 23 | 28-30 March | Basic human rights training for HR Defenders | Charikot, Dolkha | 32 | 19 | 13 |
| 24 | 30 March | UPR Review meeting | NHRC hall | 10 | 7 | 3 |
| 25 | 04 April | Discussion on DNA Test process on Godar exhumation | NHRC hall |  |  |  |
| 26 | 04 April | First PEB meeting | NHRC hall | 8 | 6 | 2 |
| 27 | 17 April | Sharing on Radio program evaluation | NHRC hall | 9 |  |  |
| 28 | 20 April | Interaction program on NHRC Bill 2068 | Everest Hotel | 147 | 120 | 27 |
| 29 | 21 April | Consultation for NHRC's new Strategic Plan | Sita palace hotel Janakpur | 73 | 75 | 8 |
| 30 | 25 April | Meeting on Consumer Rights Monitoring Guideline | NHRC Hall | 9 | 5 | 4 |
| 31 | 22 April | Interaction on Human Rights Issues | Janakpur | 60 |  |  |
| 32 | 11-13April | Advancing justiciability of economic, social and cultural rights | Bode Bhaktapur , Nepal | 131 | 55 | 76 |
| 33 | 16-19May | 24th Annual meeting of the International Coordination Committee of National Institutions for the Promotion and Protection of Human Rights (ICC) | Geneva , Switzerland |  |  |  |
| 34 | 05 May | Discussion on Human Rights Audit Guideline | NHRC Office |  |  |  |
| 35 | 06 May | Consultation on the report on review of Criminal Code, Criminal Procedure Code and Sentencing Bill | NHRC hall | 62 | 42 | 22 |
| 36 | 17-18 May | Basic human rights training for HR Defender | Baitadi | 32 |  |  |
| 37 | 12 May | Consultation for NHRC's new Strategic Plan | World Trade Centre, Tripureswor | 68 | 56 | 12 |
| 38 | 15 May | Freedom of Movement: Fundamental Human Rights, Interaction Program | NHRC | 147 | 122 | 25 |
| 39 | 20 May | Consultation for NHRC's new Strategic Plan | NHRC | 5 | 4 | 1 |
| 40 | 27- 29 May | Appreciative Inquiry Training | Park Village | 43 | 27 | 16 |
| 41 | 31 May | Interview for HR Internship | NHRC | 4 | 3 | 2 |
| 42 | 25 May | Interaction Program on the Rights of Senior Citizens | Pokhara |  |  |  |
| 43 | 24-25 May | Basic human rights training for HR Defender | Kailali | 34 |  |  |
| 44 | 16-30 June | Broadcast period of the TV Jingle on Constitution | NA | NA | NA | NA |
| 45 | 25 May | Workshop on the Role of Concerned Stakeholders on the Rights of Senior Citizens/ Pokhara | Pokhara | 60 |  |  |
| 46 | 26 Jun | 14th International Day Against Torture | NHRC | 192 | 146 | 46 |
| 47 | 26 Jun | Interaction Program during the Torture Victim's Support Day | Biratnagar | 45 |  |  |
| 48 | 30 Jun | Project Executive Board Meeting | NHRC | 7 | 5 | 2 |
| 49 | 04 Jun | Interaction Program on Rights Against Untouchability | Hotel Himalaya, Kupandole | 91 | 73 | 18 |
| 50 | 04 Jun | Training on HR & Journalism | Nepalgunj | 38 | 0 | 38 |
| 51 | 05 -10 Jun | Participation in the 17th Session of Universal Periodic Review | Geneva | 1 | NA | NA |
| 52 | 06 Jun | Third Advisory Committee Meeting | NHRC | 17 | 13 | 4 |
| 53 | 14 Jun | Workshop on Rights of Senior Citizens | Parsa | 80 | 60 | 20 |
| 54 | 19 Jun | Consultation on production of radio jingle on HR themes | Kathmandu | 19 | 14 | 5 |
| 55 | 09 -11 Jun | Orientation for second batch of interns | NHRC | 10 | 2 | 8 |
| 56 | 29-30 Jun | Human Rights Training for HRD | Bhojpur | 22 |  |  |
| 57 | 03-04 Jul | Consultation on the situation of Trafficking of women and children | Biratnagar | 51 | 21 | 30 |
| 58 | 13 Jul | Interaction on the Role of concerned stakeholders for protection of women's right | Kailali | 43 | 23 | 20 |
| 59 | 18-19 Jul | Consultation for the preparation of National Report on the situation of Trafficking of women and children | Butwal | 39 | 15 | 24 |
| 60 | 15-16 Jul | Training on Basic human rights for HR Defender, Dhangadi RO | Kanchanpur | 32 | 16 | 16 |
| 61 | 19-20 Jul | Training on Basic human rights for HR Defender, Dhangadi RO | Dadeldhura | 28 |  |  |
| 62 | 21 Jul | Consultation on the 3rd periodic report of GoN on ICESCR | NHRC | 45 | 28 | 17 |
| 63 | 21 Jul | Interaction on Consumer Rights Monitoring Guideline | Dhangadi | 46 |  |  |
| 64 | 24 Jul | Consultation with media persons for developing HR reporting guideline for journalists | NHRC | 13 | 13 | 0 |
| 65 | 26 Jul | Discussion on Godar Exhumation Mission Report | NHRC | 16 | 14 | 2 |
| 66 | 26 Jul | Analysis of the annual budget, plan and program of Govt. of Nepal from a human rights perspective - An Interaction Program | Everest Hotel, Baneshor | 147 | 120 | 27 |
| 67 | 27 Jul | Interaction in relation to investigation and monitoring | Dang | 70 |  |  |
| 68 | 28 Jul | Orientation on HR friendly journalism | Dang | 35 |  |  |
| 69 | 01-02 Aug | Training /workshop on Forensic investigation procedures | Butwal | 31 | 26 | 5 |
| 70 | 03-05 Aug | Training on HRBA to Development | Lumle, Pokhara | 25 | 23 | 2 |
| 71 | 04-05 Aug | Training for HRD on Rights of Indigenous People & Women | NHRC | 39 | 20 | 19 |
| 72 | 05-06 Aug | Consultation for NHRC's new Strategic Plan | Godavari Village Godavari | 11 | 10 | 1 |
| 73 | 07 Aug | Consultation for NHRC's new Strategic Plan | NHRC | 10 | 9 | 1 |
| 74 | 10 Aug | Talk Program on Contemporary Issues of International Humanitarian Law and its relation to Human Rights | NHRC | 72 | 48 | 24 |
| 75 | 15-16 Aug | Training on Basic Human Rights for HR Defender | Pokhara | 35 | 22 | 13 |
| 76 | 17 Aug | Donors' meeting (Sharing by QUARA) | NHRC | 14 | 7 |  |
| 77 | 18 20 Aug | NHRC Annual Planning and Review Meeting | Hotel Dhulikhel Lodge, Dhulikhel | 44 | 33 | 11 |
| 78 | 21 23 Aug | NHRC Annual Planning and Review Meeting | NHRC Office | N/A |  |  |
| 79 | 26 Aug | Book Launch of the book "Baseline study on Reported cases of elder abuse in nepali press(July 2008- July 2010)" | NHRC | 73 | 50 | 23 |
| 80 | 30 Aug | Interaction Program on International Day of Disappeared | NHRC | 191 | 140 | 51 |
| 81 | 05 Sep | Consumer Rights Monitoring Guideline- Launch Program | NHRC | 89 | 63 | 26 |
| 82 | 09 Sep | Training on Basic Human Rights for HR Defender | Surkhet | 30 |  |  |
| 83 | 07– 09 Sep | Training on HRBA to Development (Biratnagar RO) | Jhapa | 47 | 40 | 7 |
| 84 | 10 Sep | Interaction on HR situation and security | Surkhet | 40 |  |  |
| 85 | 12-14 Sep | Training on HRBA to Development (Biratnagar RO) | Dhankuta | 48 | 40 | 8 |
| 86 | 12 Sep | Interaction with Security and Administration on HR situation | Dhankuta | 12 | 12 |  |
| 87 | 13 Sep | Interaction on the analysis of human rights situation | Dhankuta | 36 | 31 | 5 |
| 88 | 15 Sep | NHRC's new Website demo meeting | NHRC | 28 | 23 | 5 |
| 89 | 18 Sep | UPR Follow-up Meeting | NHRC | 7 | 5 | 2 |
| 90 | 25-27 Sep | Training on HRBA to Development | Baglung | 34 | 2 | 32 |
| 91 | 19-21 Sep | Training on Rights to Food | Dhadelhura | 45 |  |  |
| 92 | 22 Sep | Interaction Program on Human Rights Situation of Mahakali Zone | Dhangadi | 70 |  |  |
| 93 | 21 Sep | Interaction Program on Rights of Senior Citizens,Dhangadhi RO | Kanchanpur | 68 |  |  |
| 94 | 25 Sep | Interaction on Rights of Kamlaris | Dhangadi | 91 |  |  |
| 95 | 29 Sep | Project Executive Board Meeting | NHRC | 7 | 5 | 2 |
|  | 29-1 Sept/Oct | Training on Basic Human Rights for HR Defender | Dhanusa | 33 | 27 | 6 |
| 96 | 15-17 Oct | Training on HRBA to Development, Dhangadi RO | Dhangadhi | 40 | 34 | 6 |
| 97 | 15 Oct | Interaction on Women's Right | Kanchanpur | 28 |  |  |
| 98 | 18-20 Oct | Training on HRBA to Development, Dhangadi RO | Kanchanpur | 33 | 27 | 6 |
| 99 | 22 - 24 Oct | Training for HR Defenders (covering 5 districts) | Surkhet | 42 |  |  |
| 100 | 31 Oct | Field Visit to Melamchi Drinking Water Project for preparation of HR Audit Guideline | Sindupalchowk | 4 |  |  |
| 101 | 03- 04 Nov | Workshop on the Indicators of Economic Social and Cultural Rights | Biratnagar | 35 |  |  |
| 102 | 06 Nov | Discussion Program on the Situation of Racial Discrimination & Untouchability | Biratnagar | 65 |  |  |
| 103 | 06 Nov | Consultation on NHRC website design | NHRC | 16 |  |  |
| 104 | 09 Nov | Meeting at the Prime Minister's Office regarding UPR follow up and implementation of NHRC recommendations | PMO's Office | 4 |  |  |
| 105106 | 23 Nov | Training on Basic Human Rights for HR Defender | Banke | 30 |  |  |
| 107 | 27 Nov | Discussion on Criminal Justice System & Human Rights Violations | Biratnagar | 35 |  |  |
| 108 | 08-10 Nov | Field Visit to Butwal Office (visit to industrial area for preparation of HR audit guideline) |  |  |  |  |
| 109 | 14 Nov - 5 Dec | Constitutional related Jingle broadcasting | Kantipur Television | NA | NA | NA |
| 110 | 22 Nov | Discussion on draft exhumation guideline | NHRC | 43 | 15 | 18 |
| 111 | 24 Nov | Interaction Program on Blood-Service Charge & Rights of Consumers | Biratnagar | 22 |  |  |
| 112 | 25-26 Nov | Interaction on HR situation and security | Banke | 58 |  |  |
| 113 | 27-28 Nov | Workshop on the Indicators of Economic Social and Cultural Rights | Biratnagar | 30 |  |  |
| 114 | 28 Nov | Interaction Program on the Draft Report on Convention of the Rights of Children | NHRC | 76 | 52 | 24 |
| 115 | 04 Dec | Workshop on Role of Media for Promotion & Protection of Human Rights of Women | Everest Hotel | 111 | 59 | 52 |
| 116 | 02-04 Dec | Interaction Program during the International Day of Rights of Person's with Disability | Kathmandu | 65 |  |  |
| 117 | 02-04 Dec | Rally during the International Day of Rights of Person's with Disability | Kathmandu | N/A |  |  |
| 118 | 10 Dec | 63rd Human Rights Day Celebration | NHRC | 400 |  |  |
| 119 | 04-06 Dec | Football Match during the Occasion of Human Rights Day | Jawalakhel Football Ground | N/A |  |  |
| 120 | 08 Dec | Blood Donation Program on the Occasion of Human Rights Day |  | 47 |  |  |
| 121 | 10 Dec | 63th Human Rights Day Celebration | Nepalgunj | 100 |  |  |
| 122 | 15-16 Dec | NHRC Review Meeting | Pokhara |  |  |  |
| 123 | 16 Dec | Current Situation of Impunity and Human Rights | Pokhara | 90 |  |  |
| 124 | 18 Dec | Discussion on Proposed HRC Bill | NHRC | 33 | 28 | 5 |
| 125 | 18-21 Dec | ToT on HRBA to Development | Godavari Village | 30 | 24 | 6 |
| 126 | 22 Dec | Project Executive Board Meeting | NHRC | 8 | 5 | 3 |
| 127 | 29 Dec | Experience Sharing Program with Interns | NHRC | 16 | 9 | 7 |
| 128 | 22 - 24 Dec | Human Rights Training Program for Youth, Biratnagar RO | Taplejung | 30 |  |  |
| 129 | 25 Dec | Interaction on Law Against Untouchability, Biratnagar RO | Taplejung | 35 |  |  |
| 130 | 26-27 Dec | Training for Journalists on HR Reporting | Dhanusa | 20 | 14 | 6 |
| 131 | 27-29 Dec | Training on Basic Human Rights for HR Defender (covering 8 districts) | Banke | 50 |  |  |
| 132 | 29 Dec | Interaction on Law Against Untouchability, Biratnagar RO | Illam | 30 |  |  |
| 133 | Dec | Documentary on the NHRC- Nepalgunj Regional Office |  | N/A |  |  |
| 134 | Dec | Documentary on the Rights of Persons with Disability |  | N/A |  |  |

# Footnotes

Review of NHRC at ICC SCA took place on 26 May 2011.