## Overall Progress
Project ID | 61318 | Project Title | Reducing Risks and Vulnerability from Glacial Lake Outburst Floods (GLOF) in Northern Pakistan
Quarter (1st, 2nd..) | 2nd Quarter 2015
Prepared by (Project M&E) | Fahad Bashir Bangash
Reviewed by (Project Manager) | Khalil Ahmed
Approved by (Program Officer)
Project Quality Rating
Project Output Statements | Quarter Progress Status On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Progress Assessment/Remarks | Challenges | Follow-up Actions & Due-by | Responsibility | Lesson Learnt
1. Develop Policy Recommendations and Guidelines to address GLOF risks in Northern Pakistan. | Achieved | Policy and Guidelines Developed, shared with Relevant Line Departments/Stakeholders | Lack of knowledge and interest from stakeholders |  | MoCC
2. Indicators and criteria for GLOF vulnerability developed and systematically applied to enable priority allocation of risk reduction efforts and investments. | Achieved | Developed Indicatiors and Criteria for GLOF Vulnerability | lack of knowledge and skills |  | MoCC
3. Systematic engagement of the project with global and regional research networks and centers working on GLOF issues. | Achieved |  |  |  | MoCC
4. Risk and hazard maps for mountain valleys with the highest GLOF risk and exposure of lives, livelihoodsand infrastructure. | On-Track | Risks and Hazard Maps developed and will be printed after approval | lack of expertise and technical equipments |  | MoCC/GLOF
5. Preparedness actions for vulnerable communities conducted to reduce risks from GLOF events. | On-Track | Action Plans Developed and Shared with all Stakeholders for approval | Lack of knowledge and mobilization of community especially females |  | MoCC/GLOF
6. A community based system for GLOF risk monitoring & early warning in priority communities. | On-Track | CB-EWS is enabled and training to community and line departments conducted | Installation of EWS in Remote areas |  | MoCC/GLOF
7. Targeted GLOF risk reduction measures such as check dams, spill-ways, slope stabilization or controlled drainage established in Bagrot and Drongagh valleys. | On-Track | Mitigation and Risk Reduction Structures completed with few minor work is left | Unusual weather pattrens, lack of experience and knowledge of community. |  | MoCC/GLOF
8. Technical knowledge and project lessons documented for use in future initiatives. | On-Track | Work in Progress on Technical Knowledge and Lessons Documented |  |  | MoCC/GLOF
9. Project experiences disseminated to policy makers and disaster management planners in Pakistan and the wider HKH region. | On-Track | Experience sharing and information dissemination is done |  |  | MoCC/GLOF
Overall Project Progress | On-Track | Satisfactory |  |  |  | Satisfactory
Project Financial Review
Fund Source | Budget ($) | Expenditure ($) | Delivery (%)
Core/TRAC 1 | 57877 | 60808 | 105%
Core/TRAC 2/3 (BCPR) | 0 | 0 | 0%
Donor ______________ | 362500 | 345438 | 93%
Donor ______________ | 0 | 0 | 0%
Total | 420377 | 406246 | 97%
[1] Rate each output’s and the overall project’s progress as Satisfactory, Partially Satisfactory or Inadequate based on the latest QPR and own assessment based on meetings with the project staff and stakeholders.

## QPR 1 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | RESULTS QUARTER 1 | [6 empty] | RESOURCES QUARTER 1
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q2 | AWP Budget ($) | Expenditure ($) | % Delivery
Completed, Ongoing, Delayed, Cancelled
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity
1.1.2. Activity
1.1.3. Activity
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL

## Quarter Progress Tracking Table
| EXPECTED OUTPUTS | Quarter Progress - On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Status Explanation (Please be specific and concise) | PLANNED ACTIVITIES (as per AWP)
[5 empty] | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter | Preceding Quarter Follow-up
[10 empty] | Action(s) | Status Explanation
Project Output 1 : Risk and hazard maps for mountain valleys with the highest GLOF risk and exposure of lives, livelihoodsand infrastructure.
| Indicator 4.1: Hazard Maps of the Bagrot, Bindogol and Gollain valleys are improved and finalised Baseline 4.1: No comprehensive risk and vulnerability maps for mountain valleys with highest GLOF risks available Target 4.1: By the end of project, all GLOF risk areas in Pakistan are covered by remote sensing information •By the end of project, GLOF specific simulation models for at least 2 GLOF prone mountain valleys are developed •By end of the project, at least 2 GLOF-prone mountain valleys are analysed by a detailed hazard zonation and vulnerability assessment | On-Track | Consultant has been hired and the development of maps in progress | Activity Result4.1.1
|  |  |  | 4.1.1. Hiring of an Individual Consultant | Lack of availability of local technical expertise | Continued Regular meetings with Consultant | GLOF Team / PMD |  | Organizational / Operational | 1 | Final and Printable Version to be submitted for both valleys
4.1.2. Printing of the final maps
| Indicator 4.2: Simulation modelling for Bagrot, Bindogol and Gollain conducted Baseline 4.2:No comprehensive risk and vulnerability maps for mountain valleys with highest GLOF risks available Target 4.2:By the end of project, all GLOF risk areas in Pakistan are covered by remote sensing information •By the end of project, GLOF specific simulation models for at least 2 GLOF prone mountain valleys are developed •By end of the project, at least 2 GLOF-prone mountain valleys are analysed by a detailed hazard zonation and vulnerability assessment | On-Track | 4.2.1. On-going simulation modelling for three GLOF sites will be completed | Activity Result 4.2.1
GLOF Team / PMD
[9 empty] | Organizational/Operational | 1 | Final and Printable Version to be submitted for both valleys
Project Output 5: Preparedness actions for vulnerable communities conducted to reduce risks from GLOF events.
| Indicator 5.1: Awareness of the vulnerable communities raised on GLOF and other CC issues Baseline 5.1:Limited awareness by vulnerable communities in the Gilgit-Baltistan and Chitral valleys on GLOF risks and risk reduction measures Target 5.1:By the end of the project, at least 90% of households in the target area are aware of the functionality of the GLOF EWS and able to respond to warning signals •By the end of the project, at least 2 full-scale GLOF early warning drills have been conducted, involving all households in the target communities | On-Track | Awareness Session and refresher session conducted to keep community aware if GLOF Threats and risk measures | Activity Result 5.1.1
|  |  |  | 5.1.1.Regular meetings with vulnerable communities | No Female Staff Member to sensitized Female community member | Continued Awareness and refresher sessions | GLOF Team |  | Strategic | 1 | As it’s a continuous activity,To be finalized in Next quarter
|  |  |  | 5.1.2. Awareness workshops for the stakeholders and target communities |  |  | GLOF Team
| Indicator 2.2: Baseline 2.2: Target 2.2: |  |  | 2.2.1. Activity | [5 empty] | 0
|  |  |  | 2.2.2. Activity | [5 empty] | 0
|  |  |  | 2.2.3. Activity | [5 empty] | 0
Project Output 3
| Indicator 3.1: Baseline 3.1: Target 3.1: |  |  | 3.1.1. Activity | [5 empty] | 0
|  |  |  | 3.1.2. Activity | [5 empty] | 0
|  |  |  | 3.1.3. Activity | [5 empty] | 0
| Indicator 3.2: Baseline 3.2: Target 3.2: |  |  | 3.2.1. Activity | [5 empty] | 0
|  |  |  | 3.2.2. Activity | [5 empty] | 0
|  |  |  | 3.2.3. Activity | [5 empty] | 0
Project Output 4
| Indicator 4.1: Baseline 4.1: Target 4.1: |  |  | 4.1.1. Activity | [5 empty] | 0
|  |  |  | 4.1.2. Activity | [5 empty] | 0
|  |  |  | 4.1.3. Activity | [5 empty] | 0
| Indicator 4.2: Baseline 4.2: Target 4.3: |  |  | 4.2.1. Activity | [5 empty] | 0
|  |  |  | 4.2.2. Activity | [5 empty] | 0
|  |  |  | 4.2.3. Activity | [5 empty] | 0
| 5.2. Activity Result: Village Hazard Watch Groups (VHWGs) are strengthened | On-Track | VHWGs are strengthened | 5.2.1. Meetings and dialogues with Village hazard Watch Griups (VHWGs) | 1. Intra and inter village conflicts . 2. Procedural delays in release of funds | Continued Meetings and Dailogue | GLOF Team / CBDRMC |  | Strategic | 1 | Continuous activity, will run till end
5.2.2 Exposure visits for VHWGs to other valleys
| 5.3. Activity Result: Valley DRM Committees are strengthened | On-Track | Meetings and Trainings of DRMC Members conducted | 5.3.1 Meetings with DRM Committees | Again limited time and limited budgetary allocations | Continued Meetings and Dailogue |  |  | Strategic | 1
5.3.2 Training of DRMC members in leadership and governance
5.3.3 Exposure visits for DRMCs
| 5.4. Activity Result: Mass awareness on GLOF issues through Media | On-Track | Mass awareness campaign is done | 5.4.1. Mass awareness campaigns through electronic and print media, briefings, workshops and reporting |  | Continued Mass awareness campaigns |  |  | Strategic
| 5.5 Activity Result: Strengthening of valley based DRM Funds | On-Track | Half Contribution done | 5.5.1 .Contribution to existing DRM Funds of Bagrot and Bindogol | limited community skills for procurement s |  |  |  | Strategic | 1 | Contribution done
|  |  | Gollain DRM Fund established | 5.5.2. Establishment of new DRM Fund at Gollain
| 5.6 Activity Results: Strengthening of the CBDRCs | On-Track | CBDRC's strengthened | 5.6.1 .Strengthening of existing CBDRCs of Bagrot and Bindogol |  |  |  |  | Strategic | 1 | CBDRMC Strengthened
5.6.2. Strengthening of the CBDRC at Gollain
| 5.7 Activity Result: Capacity building and facilitation of disabled and elders on GLOF RR | On-Track | MoU signed with Bindogol and Bagrote Community for disabled and Elderly on GLOF Risk Reduction | 5.7.1. Meetings, dialogues and capacity building of the disabled and elderly of Bagrot and Bindogol on GLOF Risk Reduction |  |  |  |  | Strategic | 1
Project Output 6: A community based system for GLOF risk monitoring & early warning in priority communities.
Activity Result 6.1.1
| 6.1. Activity Result: Early Warning System established/strengthened Baseline 6.1:No GLOF early warning system for Bagrot and Drongagh valleys in place •Vulnerable households are not able to receive and react to GLOF early warning messages Target 6.1:-By the end of the project, 90% of households in each target valley are able to receive and respond to GLOF early warning signals and take the appropriate actions following the warning. •By the end of the project , at least 2 CBOs are trained in the operation and maintenance of the EWS and ensure its continued functionality •A special watch group for each GLOF prone valley will be formed to establish a new or to strengthen an existing Early Warning System | Completed |  | 6.1.1. Early warning system in Bagrot and Bindogol to be completed and operational (on-going with PMD under first LOA)) |  |  | GLOF Team/PMD |  | Organizational / Operational | 1 | EWS Strengthened and Established
| 6.2. Activity Result: Early Warning System (EWS) established in new GLOF site at Chitral (on-going with PMD under the 2nd LOA) | Completed | EWS Installation at Gollain Valley is done | 6.2.1. Installation of equipment |  |  | GLOF Team/PMD
|  |  |  | 6.2.2. SOPs developed for operation and maintenance of the EWS |  |  |  |  | Organizational/Operational/Strategic
| 6.3. Activity Result: Communities trained in evacuation during GLOF | Completed | Communities Trained in Evacuation during GLOF | 6.3.1. Mock drills are demonstrated in both of the pilot sites in Bagrot, Bindogol and Golain |  | Regular Mock Drills are conducted | GLOF Team / CBDRMC |  |  | 1 | Continuous activity, will run till end
| 6.4 Activity Result: Strengthening of the relevant line departments | Completed | Line Department Strengthened | 6.4.1. Local Met office strengthening in GLOF monitoring | [5 empty] | 1 | Strengthened
| 6.5. Activity Result: Training of Govt. Official in GLOF Early Warning | Completed | Govt. Officials trained in GLOF Early Warning | 6.5.1. Govt. officials of relevant departments trained in GLOF early warnings, evacuation and use of communication equipment |  | Refresher Courses for Officials of Department | GLOF Team / PMD / CBDRMC |  |  | 1 | Govt. Officials Trained in GLOF EWS
Project Output 7: Targeted GLOF risk reduction measures such as check dams, spill-ways, slope stabilization or controlled drainage established in Bagrot and Drongagh valleys
Activity Result 7.1.1
| 7.1 Activity Result: Climate change adaptation structures are constructed as GLOF RR measures Baseline 7: No risk reduction measures for GLOF in place in the target sites Target 7:-By the end of the project, concrete engineering measures are in place to reduce the impact of GLOF events on vulnerable communities in each target valley (as appropriate: effective drainage systems, check dams, mini dams, ponds, spill ways, slope stabilization, tree plantation, controlled drainage) | On-Track | Adaptation Structures are almost completed, just final touching left at Bagrote | 7.1.1. On-going projects initiated during 2014 to be completed |  | Continuous Monitoring of the civil work to keep up the pace and timely completion | GLOF Team / CBDRMC |  | Operational/Organizational/Environmental | 1 | Mostly Structures are completed and few are in Final stages of Completion, will be completed in Next Quarters. Delays caused due to Prolonged Winters in Mountainuous Regions
| 7.2 Activity Result: GLOF RR measures are initiated and completed | ON-Track | RR Measures (Safe Access Routes) are initiated and completed | 7.2.1. New GLOF RR measures such as check dams, protection walls, diversion spurs, bridges, irrigation channels, CBDRC and safe access routes to be initiated in Bagrot, Bindogol and Golain valleys | Limited skills of community members to manage financial matters | Continuous Monitoring of the civil work to keep up the pace, effective implementation and timely completion | GLOF Team / CBDRMC | In GB and Chitral for these activities prior rainfall or snow fall is required to initiate and test the activities. had to wait for the rains to come. Activity was delayed. But on Dry Plantation , water is effecting negatively and unknown weather pattrens causes problem in timely completion of activity
| 7.3 Activity Result: Bioengineering structures for slope stabilisation are implemented | ON-Track | Bio-Engineering Structure are completed | 7.3.1. Bioengineering structures such as soft gabion walls, slope plantations etc. to be initiated and completed in Bagrot ,Bindogol and Golain valleys | Limited Knowledge of community members in Bio-engineering
| 7.4 Activity Result: Technical Assistance for Bioengineering activities required | completed | Technical assistance provided | 7.4.1. Hiring of the technical services for implementation of bio-engineering structures
| 7.5 Activity Result: Implementation of IWMPs | Completed | Plantation and Seeds swoing done | 7.5.1. Implementation of activities planned in the IWMPs of Bagrot and Bindogol
Project Output 8: Technical knowledge and project lessons documented for use in future initiatives.
Activity Result 8.1.1
| 8.1 Activity Result: Case Studies on best practices and lessons learned developed Baseline 8: - Inadequate technical papers capturing project knowledge available •Inaccessibility to maps, reports, remote imagery and case studies Target 8:-•By the end of the project, all technical decisions and lessons are captured in dedicated reports •By the end of the project, a GLOF risk reduction manual is available and disseminated both nationally and internationally •By year 2 of the project, a project website is established and linked to the GLOF risk database developed under Outcome 1 | On-Track | Consultant Hired for Developing documenting Best Practices | 8.1.1. Reports and case studies conducted to document best practices and lessons learned from the Pakistan GLOF Project |  |  | GLOF Team
8.1.2. Technical assistance to be hired for the task
| 8.2 Activity Result: A PC-1 (project proposal on govt’s format) is developed for replication and scaling up of project activities | On-Track | PC-1 is forwarded to MoCC for replication and scaling up of a project | 8.2.1. Meetings and workshops with govt. officials and other stakeholders | Lack of Govt. Interest |  | GLOF Team / MoCC | Lack of Government Interest in proceeding with PC-1
8.2.2. Hiring of and individual expert to undertake the task of developing the PC-1
| 8.3 Activity Result: Project’s Exit Strategy Developed | On-Track | Consultant hired for Developing Exit Strategy | 8.3.1 . Hiring of Individual Consultant to develop the exit strategy of the project |  |  | GLOF Team / MoCC
| 8.4 Activity Result: Terminal Evaluation Conducted and Reported | On-Track | Concept Note for conducted Terminal Evaluation is forwarded to UNDP | 8.4.1. Hiring of an Individual Consultant to conduct the evaluation |  |  | GLOF Team / UNDP / MoCC
Project Output 9: Project experiences disseminated to policy makers and disaster management planners in Pakistan and the wider HKH region.
Activity Result 7.1.1
| 9.1 Activity Result: Knowledge generated through the Pakistan GLOF Project disseminated to all stakeholders Baseline 9: - •No systematic knowledge transfer on GLOF risks from Pakistan to other countries Target 9: -By the end of the project, at least 1 international exchange visit between GLOF risk reduction projects has taken place •By the end of the project, DRM planning authorities of at least 3 GLOF-prone districts in Pakistan visit the target sites with a view on replication of the project approach in other vulnerable sites •By the end of the project, at least 2 project dissemination workshops have been conducted in Pakistan, with attendance by stakeholders from all GLOF-prone districts | On-Track | Information Dissemination Workshops conducted at Gilgit and Chitral. Islamabad and other provinces are due by next quarter | 9.1.1 .Seven Knowledge sharing workshops in; Bagrot, Gilgit, Skardu, Bindogol, Chitral, Peshawar and Islamabad will be organised |  |  | GLOF Team / MoCC
| 9.2 Activity Result: Dissemination of the project knowledge and experiences on GLOF to HKH region and for wider global outreach | On-Track | Knowledge and experience sharing visit is conducted to ALPs region | 9.2.1. A GLOF International conference in Islamabad will be organised |  |  | GLOF Team / MoCC / UNDP
| 9.3 Activity Result:Exposure Visits of DRM Planning Authorities from other districts | On-Track | Exposure visit of DRM Planning Authority to other districts is conducted | 9.3.1 .Three exposure visits for DRM Authorities from other GLOF prone districts to Bindogol and Bagrot |  |  | GLOF Team / MoCC
| 9.4 Activity Result: Exposure and advocacy visits for CCD staff to GB and Chitral | On-Track | One exposure and experience sharing visits on GLOF issues for the staff of Climate Change Division to Chitral and Gilgit-Baltistan is done and one will be organised in next quarter | 9.4.1. Two exposure and experience sharing visits on GLOF issues for the staff of Climate Change Division to Chitral and Gilgit-Baltistan will be organised |  |  | GLOD Team / MoCC

## field monitoring (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | QUARTERLY RESULTS
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Preceding Quarter Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter
|  |  | On Track/Achieved (0-49%), Require Monitoring/Not Achieved, Require Urgent Management Attention |  | Action(s) | Status Explanation
Indicator 1.1: Baseline 1.1: Target 1.1: Quarter 1 Target (%): | Project Output 1
Activity Result 1.1.1
| Activity 1.1.1 a |  |  |  | 0
| Activity 1.1.1 b |  |  |  | 0
| Activity 1.1.1 c |  |  |  | 0
Activity Result 1.1.2
| Activity 1.1.2 a |  |  |  | 0
| Activity 1.1.2 b |  |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: Quarter 1 Target (%): | Activity Result 1.2.1
Activity 1.2.1 a
Activity 1.2.1 b
Activity 1.2.1 c
Indicator 2.1: Baseline 2.1: Target 2.1: Quarter 1 Target (%): | Project Output 2
Activity Result 2.1.1
Activity 2.1.1 a
Activity 2.1.1 b
Activity 2.1.1 c
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  |  | 0
| 2.2.2. Activity |  |  |  | 0
| 2.2.3. Activity |  |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  |  | 0
| 3.1.2. Activity |  |  |  | 0
| 3.1.3. Activity |  |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  |  | 0
| 3.2.2. Activity |  |  |  | 0
| 3.2.3. Activity |  |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  |  | 0
| 4.1.2. Activity |  |  |  | 0
| 4.1.3. Activity |  |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  |  | 0
| 4.2.2. Activity |  |  |  | 0
| 4.2.3. Activity |  |  |  | 0

## QPR 3 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | RESULTS QUARTER 3 | [8 empty] | RESOURCES QUARTER 3
|  | Activity Status | Brief Status Explanation (Please be specific and concise) | Q2 Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q4 | AWP Budget ($) | Expenditure ($) | % Delivery
|  | Completed, Ongoing, Delayed, Cancelled |  | Action(s) | Status Explanation
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity |  |  | 0
| 1.1.2. Activity |  |  | 0
| 1.1.3. Activity |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity |  |  | 0
Baseline 1.2: | 1.2.2. Activity |  |  | 0
Target 1.2: | 1.2.3. Activity |  |  | 0
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity |  |  | 0
| 2.1.2. Activity |  |  | 0
| 2.1.3. Activity |  |  | 0
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  | 0
| 2.2.2. Activity |  |  | 0
| 2.2.3. Activity |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  | 0
| 3.1.2. Activity |  |  | 0
| 3.1.3. Activity |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  | 0
| 3.2.2. Activity |  |  | 0
| 3.2.3. Activity |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  | 0
| 4.1.2. Activity |  |  | 0
| 4.1.3. Activity |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  | 0
| 4.2.2. Activity |  |  | 0
| 4.2.3. Activity |  |  | 0
TOTAL

## Risks
Types of Risks
Environmental | Financial | Organizational | Political | Operational | Regulatory | Strategic | Other
Natural Disasters: storms, flooding, earthquakes | EXTERNAL economic factors: interest rates, exchange rate fluctuation, inflation | Institutional Arrangements | Corruption | Complex Design (size: larger/multi-country project; technical complexity; innovativeness, multiple funding sources) | New unexpected regulations, policies | Partnerships failing to deliver | Other risks that do not fit in an of the other categories
Pollution incidents | INTERNAL: | Institutional/ Execution Capacity | Government Commitment | Project Management | Critical policies or legislation fails to pass or progress in the legislative process | Strategic Vision, Planning and Communication | Might refer to socioeconomic factors such as: population pressures; encroachment – illegal invasions; poaching/illegal hunting or fishing
Social and Cultural | Co-financing difficulties | Implementation arrangements | Political Will | Human Error/Incompetence |  | Leadership and Management
Security/Safety | Use of financing mechanisms | Country Office Capacity (specific elements limiting CO capacity) | Political Instability | Infrastructure Failure |  | Programme Alignment
Economic | Funding (Financial Resources) | Governance | Change in Government | Safety being compromised |  | Competition
| Reserve Adequacy | Culture, Code of Conduct and Ethics | Armed Conflict and Instability | Poor monitoring and evaluation |  | Stakeholder Relations
| Currency | Accountability and Compensation | Adverse Public opinion/media intervention | Delivery |  | Reputation
| Receivables | Succession Planning and Talent Management |  | Programme Management |  | UN Coordination
| Accounting/Financial Reporting | Human resources Processes and Procedures |  | Process Efficiency |  | UN Reform
| Budget Allocation and Management |  |  | Internal Controls
| Cash Management/Reconciliation |  |  | Internal and External Fraud
| Pricing/Cost Recovery |  |  | Compliance and Legal
Procurement
Technology
Physical Assets

## Monthly Progress (hidden)
On Track/Achieved | 76-100%
Require Monitoring/Not Achieved | 50-75%
Require Urgent Management Attention | 0-49%
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) |  |  |  | RESULTS QUARTER 1
Activity Status Month 1/2/3
[5 empty] | Progress (Completed/OnTrack (76%-100%), Require Monitoring/Delayed/off track (50-75%), Cancelled (0-49%) | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise)
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | Activity Result 1.1.1
| Quarter 1: 20% | Quarter 2: 50% | Quarter 3: 80% | Quarter 4: 100%
| Activity: 1.1.1 a Activity: 1.1.1 b | Activity: 1.1.1 a Activity: 1.1.1 c | Activity: 1.1.1 c Activity: 1.1.1 d | Activity: 1.1.1 c Activity: 1.1.1 d Activity: 1.1.1 e
Activity Result 1.1.2
| Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 c | Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 d
Activity Result 1.1.3
| Activity: 1.1.3 a Activity: 1.1.3 b | Activity: 1.1.3 c Activity: 1.1.3 d | Activity: 1.1.3 e Activity: 1.1.3 f | Activity: 1.1.3 e Activity: 1.1.3 f
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL