## Overall Progress
Project ID | PAK/02/G61 (00056550)
Quarter (1st, 2nd..) | 2nd Qtr, 2015
Prepared by (Project M&E) | Syed Azmat Hussain Shah, Office Secretary
Reviewed by (Project Manager)
Approved by (Program Officer)
Project Quality Rating
Project Output Statements | Quarter Progress Status On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Progress Assessment/Remarks | Challenges | Follow-up Actions & Due-by | Responsibility | Lesson Learnt
Output 1: Promoting public (manufacturers and consumers) awareness of the environmental effects of the emissions of controlled substances and other substances that deplete the ozone layer. | on track | LUMS Conference was attended and special session on ozone layer protection was organized from 10-12 April, 2015. Disseminated awareness material among students from different schools, colleges and universities to raise awareness about protection of ozone layer | N/A | 2nd Qtr | Ozone Cell | Awareness at grass root level is vital for the protection of ozone layer
Output 2: | on track | Quota issued to the eligible importers of HCFCs on 14th April, 2015 by taking all the stakeholders onboard | Prevention of illegal trade and implementation of effective control measure | 2nd Qtr | Ozone Cell | For smooth Implementation of quota system all the stakeholders must be involved
Implementation of quota system for limiting the imports of HCFCs is in place and communicated to the institutions for implementation.
Output 3: Effective compliance of ODS phase-out as per the Montreal Protocol | on track | ii) 2nd Consultative meeting on HFC amendment was held under the chair of JS (IC) / NPD (ozone cell) at Ministry of Climate Change on 15th April, 2015 for HCFC alternatives | N/A | 2nd Qtr | Ozone Cell | Regular interaction with all the stakeholders is very important to effective compliance of ODS Phase out
iii) JS (IC) / NPD (Ozone Cell) attended 35th OEWG from 19-26 April, 2015 at Bangkok and the ODS phase-out issues were finalized for the MOP
|  | iv) JS (IC) / NPD (Ozone Cell) attended Intersessional Consultative Meeting on HFC Amendment from 10-12 June, 2015 at Bangkok. Financial and Technical issues related to North American Proposed HFCs Amendmen were discussed. | N/A
Output 4: To remain compliance of ODS phase-out as per the Montreal Protocol | on track | i. Meetings / Workshop to develop a strategy to phase out Methyl Bromide and search for suitable alternatives | N/A | 3rd Qtr |  | N/A
Output 5 : Data collection of ODS used in Pakistan (types and quantities) in 2014 is done as per the requirements of Montreal Protocol | on track | i. Collected import data of HCFC from FBR /PRAL / Importers. ii. Collected data before the stipulated date by the Montreal Protocol and analyzed data provided by all stakeholders according to allocated quota. iii. Prepared and submitted Country Report and Article 7 Data report on time to the secretariat of Montreal Protocol. | Compliance with Pakistan's allowable HCFCs limit | 2nd Qtr | Ozone Cell | Reliable and accurate data from concerned government department is very necessary for accurate and timely reporting of the ODSs
Overall Project Progress | Satisfactory
Project Financial Review
Fund Source | Budget ($) | Expenditure ($) | Delivery (%)
Core/TRAC 1 | 0 | 0 | 0%
Core/TRAC 2/3 (BCPR) | 0 | 0 | 0%
Donor _____MLFS___ | 112233 | 23775.33 | 0%
Donor ______________ | 0 | 0 | 0%
Total | 0 | 0 | 0%
[1] Rate each output’s and the overall project’s progress as Satisfactory, Partially Satisfactory or Inadequate based on the latest QPR and own assessment based on meetings with the project staff and stakeholders.

## QPR 1 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | RESULTS QUARTER 1 | [6 empty] | RESOURCES QUARTER 1
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q2 | AWP Budget ($) | Expenditure ($) | % Delivery
Completed, Ongoing, Delayed, Cancelled
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity
1.1.2. Activity
1.1.3. Activity
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL

## Quarter Progress Tracking Table
EXPECTED OUTPUTS | Quarter Progress - On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Status Explanation (Please be specific and concise) | PLANNED ACTIVITIES (as per AWP)
|  |  |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter | Preceding Quarter Follow-up
[9 empty] | Action(s) | Status Explanation
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | Delayed | Technical Workshop for Manufacturers | Activity 1.1.1 | NPM was not appointed | 4th Quarter | NPM/Staff | Non availability of regular NPM leads towards the delay in carrying out approved AWPs activities | Hiring of New NPM
Indicator 1.2: Baseline 1.1: Target 1.1: | Achieved | One seminar on benefits of using ozone friendly appliances for consumers | Activity 1.1.2 | Delay of payment to vendors due to non availability of project account signatories | N/A | NPM/OS | Such events are essential to make the relevant stakeholders aware about the ozone friendly appliances and technologies | N/A
Indicator 1.3: Baseline 1.1: Target 1.1: | On track | Printing and publication of technical literature and its dissemination to industry and other stakeholders. | Activity 1.1.3 | Delay of payment to vendors due to non availability of project account signatories | N/A | NPM/OS | Awareness raising through print media plays a vital role in sensitizing the issue | Hiring of New NPM
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | Delayed | Training Programmes for Customs/Technicians | Activity 2.1.1 | NPM was not appointed | 3rd & 4th Quarter | NPM/Staff | Properly staffed unit is essential to carry out approved AWP activities | Hiring of New NPM
Indicator 2.1: Baseline 2.1: Target 2.1: | On track | Control of Illegal Import | Activity 2.1.1 a | Non availability of online quota system | Monitoring of HCFC Import data on monthly basis | NPM/OS | Monitoring of HCFC imports on monthly basis reduces the risk of illegal import as everybody know that propoer check and balance system is in place and any illegal import will be seized. | N.A
Indicator 2.2: Baseline 2.1: Target 2.1: | Completed | HCFC quota Allocation 2015 | Activity 2.1.2 | Non availability of online quota system | Monitoring of HCFC Import data on monthly basis | NPM/OS | Monitoring of HCFC imports on monthly basis is an handy tool. It enables ozone cell to implement the HCFC quota system effectively.
Indicator 2.2: Baseline 2.2: Target 2.2: |  |  | 2.2.1. Activity | [5 empty] | 0
|  |  | 2.2.2. Activity | [5 empty] | 0
|  |  | 2.2.3. Activity | [5 empty] | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: |  |  | 3.1.1. Activity | [5 empty] | 0
|  |  | 3.1.2. Activity | [5 empty] | 0
|  |  | 3.1.3. Activity | [5 empty] | 0
Indicator 3.2: Baseline 3.2: Target 3.2: |  |  | 3.2.1. Activity | [5 empty] | 0
|  |  | 3.2.2. Activity | [5 empty] | 0
|  |  | 3.2.3. Activity | [5 empty] | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: |  |  | 4.1.1. Activity | [5 empty] | 0
|  |  | 4.1.2. Activity | [5 empty] | 0
|  |  | 4.1.3. Activity | [5 empty] | 0
Indicator 4.2: Baseline 4.2: Target 4.3: |  |  | 4.2.1. Activity | [5 empty] | 0
|  |  | 4.2.2. Activity | [5 empty] | 0
|  |  | 4.2.3. Activity | [5 empty] | 0
Indicator 2.3: Baseline 2.1: Target 2.1: | On track | Preparation of stage II of HPMP | Activity 2.1.3 | NPM was not appointed | 4th Quarter | NPM |  | Hiring of New NPM
Project Output 5
Indicator 5.1: Baseline 5.1: Target 5.1: | Achieved | Collection of import data of HCFC from FBR /PRAL / Importers. | Activity 5.1 | Illegal Import, Proper recording of import data | N/A | NPM/OS | Analysis of import data on monthly basis make NOU able to submit the country report well in time. | N/A
Indicator 5.2: Baseline 5.1: Target 5.1: | Achieved | Collection of data before the stipulated date by the Montreal Protocol and analysis of data provided by all stakeholders according to allocated quota. | Activity 5.2 | Illegal Import, Proper recording of import data | N/A | NPM/OS
Indicator 5.2: Baseline 5.1: Target 5.1: | Achieved | Preparation and submission of Country Report and Article 7 Data report on time to the secretariat of Montreal Protocol. | Activity 5.3 | Illegal Import, Proper recording of import data | N/A | NPM/OS

## field monitoring (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | QUARTERLY RESULTS
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Preceding Quarter Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter
|  |  | On Track/Achieved (0-49%), Require Monitoring/Not Achieved, Require Urgent Management Attention |  | Action(s) | Status Explanation
Indicator 1.1: Baseline 1.1: Target 1.1: Quarter 1 Target (%): | Project Output 1
Activity Result 1.1.1
| Activity 1.1.1 a |  |  |  | 0
| Activity 1.1.1 b |  |  |  | 0
| Activity 1.1.1 c |  |  |  | 0
Activity Result 1.1.2
| Activity 1.1.2 a |  |  |  | 0
| Activity 1.1.2 b |  |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: Quarter 1 Target (%): | Activity Result 1.2.1
Activity 1.2.1 a
Activity 1.2.1 b
Activity 1.2.1 c
Indicator 2.1: Baseline 2.1: Target 2.1: Quarter 1 Target (%): | Project Output 2
Activity Result 2.1.1
Activity 2.1.1 a
Activity 2.1.1 b
Activity 2.1.1 c
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  |  | 0
| 2.2.2. Activity |  |  |  | 0
| 2.2.3. Activity |  |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  |  | 0
| 3.1.2. Activity |  |  |  | 0
| 3.1.3. Activity |  |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  |  | 0
| 3.2.2. Activity |  |  |  | 0
| 3.2.3. Activity |  |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  |  | 0
| 4.1.2. Activity |  |  |  | 0
| 4.1.3. Activity |  |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  |  | 0
| 4.2.2. Activity |  |  |  | 0
| 4.2.3. Activity |  |  |  | 0

## QPR 3 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | RESULTS QUARTER 3 | [8 empty] | RESOURCES QUARTER 3
|  | Activity Status | Brief Status Explanation (Please be specific and concise) | Q2 Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q4 | AWP Budget ($) | Expenditure ($) | % Delivery
|  | Completed, Ongoing, Delayed, Cancelled |  | Action(s) | Status Explanation
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity |  |  | 0
| 1.1.2. Activity |  |  | 0
| 1.1.3. Activity |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity |  |  | 0
Baseline 1.2: | 1.2.2. Activity |  |  | 0
Target 1.2: | 1.2.3. Activity |  |  | 0
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity |  |  | 0
| 2.1.2. Activity |  |  | 0
| 2.1.3. Activity |  |  | 0
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  | 0
| 2.2.2. Activity |  |  | 0
| 2.2.3. Activity |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  | 0
| 3.1.2. Activity |  |  | 0
| 3.1.3. Activity |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  | 0
| 3.2.2. Activity |  |  | 0
| 3.2.3. Activity |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  | 0
| 4.1.2. Activity |  |  | 0
| 4.1.3. Activity |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  | 0
| 4.2.2. Activity |  |  | 0
| 4.2.3. Activity |  |  | 0
TOTAL

## Risks
Types of Risks
Environmental | Financial | Organizational | Political | Operational | Regulatory | Strategic | Other
Effect of Climate Changes | Funds Disbursement | Non Availability of regular NPM | Change in Government | Delivery
Ozone Depletion | Bank Account signatories | Human resources Processes and Procedures |  | Procurement
| Financial Delivery |  |  | Technology
| Delay of payments to vendors |  |  | Physical Assets

## Monthly Progress (hidden)
On Track/Achieved | 76-100%
Require Monitoring/Not Achieved | 50-75%
Require Urgent Management Attention | 0-49%
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) |  |  |  | RESULTS QUARTER 1
Activity Status Month 1/2/3
[5 empty] | Progress (Completed/OnTrack (76%-100%), Require Monitoring/Delayed/off track (50-75%), Cancelled (0-49%) | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise)
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | Activity Result 1.1.1
| Quarter 1: 20% | Quarter 2: 50% | Quarter 3: 80% | Quarter 4: 100%
| Activity: 1.1.1 a Activity: 1.1.1 b | Activity: 1.1.1 a Activity: 1.1.1 c | Activity: 1.1.1 c Activity: 1.1.1 d | Activity: 1.1.1 c Activity: 1.1.1 d Activity: 1.1.1 e
Activity Result 1.1.2
| Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 c | Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 d
Activity Result 1.1.3
| Activity: 1.1.3 a Activity: 1.1.3 b | Activity: 1.1.3 c Activity: 1.1.3 d | Activity: 1.1.3 e Activity: 1.1.3 f | Activity: 1.1.3 e Activity: 1.1.3 f
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL