## Sheet1
DRM Project Procurement Plan 2019
Outputs | Planned Activities | Procurement Details | Dates | Estmated Budget (USD) | Comments
Output 1: Disaster preparedness and response mehanisms enhaced disaster EWS procedures strenthened | Development of NDRRF Action Plan | National Consultation Workshop | 22 April - 03 May | 750 | $250/workshop
|  | 4 Regional Consultations Workshops | 6 May - 17 May | 3050 | $762.50/region
|  | Travel Cost for airline tickets/DSA/vehicle Hire | 6 May - 17 May | 10000 | $2,500/province
|  | Recruitment of International Consultant | 25 March - 29 March | 19200 | TOR finalized. In the process of recruting the IC
| Support NDC develop NDRRF Monitoring & Reporting Tool | 2 National Workshops | 20 May - 24 May | 500 | $250/workshop
| Training on NDRFF/Sendai Monitor | 1 Training Sendai/NDRRF monitor | 01 April - 05 April | 250 | Draft training TOR developed
|  | 1 Training on Media | 08 April - 09 April | 250
|  | 1 Training on Gender in DRR | 2019-04-10 | 250
| Finalize and publish DRM Capacity Assement and Capacity Development Plans | Printing | 22 April - 26 April | 2500
| Support NDC in developing resourcing plan | 1 National Workshop | 11 April - 12 April | 250
| Finalize Disaster Loss Database covering 5 provinces | 2 National trainings | 29 April - 3 May | 500 | $250/workshop
| Handover of ICT equipment and launching of NDC Loss database | Launching | 2019-05-31 | 500
| Project Cost | Communication Cost | February - June | 450 | Ongoing
| Project Cost | Office Supplies | February - June | 450 | Ongoing
| Project Assistants (Support Staff) | Local Consultants | Jan - June | 16272 | Funds committed in Janaury for 3 ICs.
|  |  | March - June | 2136.94 | Funds to be committed by 15 March
| Project Travel Expenses | Travel Cost for airline tickets/DSA/vehicle Hire | March - June | 7264 | To be utilzed between the said months
Output 2: Disaster Risk Mangement Integrated into Development plans and budget | Review, finalize and publish Multi Hazard Risk Assessment results of the Provines | Printing | 27 May - 31 May | 4850
| Provincial Consultations on NDRRF & development of implementation plans for provinces | 3 Provincial Workshops | 6 May - 17 May | 6000 | $2000/province
|  | Travel Cost for airline tickets/DSA/vehicle Hire | 6 May - 17 May | 4500 | $1500/province
| Support Provinces and Districts with mainstreaming DRR into provincial and districts into provincial development plans | 1 National Workshop | 3 June - 7 June | 350
| Project Travel Expenses | Travel Cost for airline tickets/DSA/vehicle Hire | March - June | 1602
| Project Cost | Communication | February - June | 450
| Project Cost | Office Supplies | February - June | 450
Output 3: Preparedness and planning mechanisms and tools to manage disaster recovery processes at National and sub-national levels strengthened | Project Cost | Communication Costs | March - June | 450 | Ongoing
| Project Cost | Office Supplies | March - June | 450 | Ongoing
| Recovery Framework | Printing | 22 April - 26 April | 3550
| Recovery Framework | Workshop | 6 May - 17 May | 400
Output 4: Readiness of DMT Members and the NDC to prepare and respond to disasters enhanced | Enhanced Disaster Needs Assessment and Analysis Capacity of PNG (ACAPS | 1 National Training | 15 April - 19 April | 500
|  | 2 Trainings at Provincial Level | 15 April - 19 April | 5000 | $2500/province
|  | Travel Cost for airline tickets/DSA/vehicle Hire |  | 2500
|  | Recruitment of International Consultant | 25 March - 29 March | 39276 | TOR finalized. In the process of recruiting the IC
| Support PNG with Initiatives on enagaing private sector for DRM | I workshop | 10 June - 13 June | 750
| Project Assistants (Support Staff) | Local Consultant | Jan - June | 4006 | Funds committed in January
| Project Cost | Communication Costs | March - June | 450 | Ongoing
| Project Cost | Office Supplies | March - June | 450 | Ongoing