United Nations Development Programme (UNDP)

Region: Latin American and the Caribbean (LAC)

Caribbean Risk Management Initiative Phase 2 (CRMI II) Project Document

2014 Substantive Revision

| Project Title: | Caribbean Risk Management Initiative, Phase 2 |
| --- | --- |
| Expected RPD Outcome(s): | Regional Programme Outcome 4. Countries are able to reduce the likelihood of conflict and lower the risk of natural disasters, including from climate change |
| Expected RPD Output(s): | Programme Outputs as stated in the RBLAC RPD: Output 4.3. Effective institutional, legislative and policy frameworks in place to enhance the implementation of disaster and climate risk management measures at national and sub-national levels (SP output 5.2) |
| Executing Entity: | UNDP Regional Center, Panama |
| Implementing Agencies: | UNDP, CDEMA, UWI, CARICOM (CCCCC), GREDES |

| Regional Programme Period: 2008 – 2013; 2014-2017 Key Result Area (Strategic Plan) SP Outcome 5 Atlas Award ID: 00060722 Start date: 15th March 2011 End Date: 31th December 2014 PAC Meeting Date: August 26 – December 4, 2010 Management Arrangements Direct Execution | INPUTS Budget 2011-2014 Total resources required 1,386,420 Total allocated resources: 849,609 BCPR 800,000 RBLAC TRAC Funds 49,609 Unfunded budget: 536,811 In Kind Contributions |
| --- | --- |

| Agreed by: | Name | Title | Date | Signature |
| --- | --- | --- | --- | --- |
| RBLAC |  |  |  |  |
| UNDP (Executing Entity) |  |  |  |  |

## I.	Brief Background of the Project

- Capacity in the Caribbean for managing climate-induced disaster risk is low despite gains made by the Caribbean Risk Management Initiative (CRMI) Phase one and other initiatives undertaken by regional governments, the United Nations, and other development partners. Through this project, UNDP will assist Caribbean countries to implement those sections of the Mauritius Declaration that call for establishing or strengthening national and regional climate-change coordination mechanisms; improving national disaster mitigation, preparedness and early-warning capacity; increasing public awareness about disaster reduction; stimulating interdisciplinary and inter-sectoral partnerships; and mainstreaming risk management. To do so, this project aims to establish disaster risk reduction centres, based on the Cuban model, to map hazards, vulnerability and risk due to climate and geological hazards and provide a tool for informed decision making and early warning system at the local and community level. In addition the project will build capacity and awareness among policy-makers and stakeholders in communities, technical agencies and government who work in the area of DRM and CCA, through courses, workshops, trainings and the sharing of best practices. The project strengthens documentation of best practices for improved south-south cooperation in the fields of DRM and CCA, as well as works to bring the two communities closer together.

- The CRMI II project has three expected outputs:

  - 1.0 Capacity for disaster risk reduction and adaptation to DRR-CCA developed within the region is strengthened;

  - 2.0 Management of knowledge on climate change adaptation and disaster risk reduction is improved; and

  - 3.0 Partnerships and Resource Mobilization are enhanced.

## II.	Justification for the Substantive Revision for the year 2014.

- The primary motive for the substantive revision is to align CRMI II with the new Regional Programme Document (RPD) for Latin America and the Caribbean 2014 – 2017. Among other key elements, the RPD identifies high vulnerability to risks related with natural events, insecurity and conflicts as a need to be addressed in the quest for resilience and sustainable human development. Preventive and risk reduction policies, as well as preparation plans, are not yet sufficiently incorporated or implemented effectively.  This revision aligns the outputs and activities of CRMI II with the RPD.

- This revision responds to the specific challenges, needs, priorities and opportunities of the Caribbean countries and takes into account the different development status and vulnerabilities of Small Island Developing States (SIDS). The exposure to natural events in the Caribbean is high; climate change and geographic characteristics create susceptibility to long term impacts.

- The revision reflects UNDP principles of regionality, specifically in the promotion of public service, dialogue at the Caribbean level and sharing knowledge.

- The revision supports Outcome 4 (UNDP Strategic Plan 5) and aims to lower the risk of natural events. It encompasses the systematization and sharing of knowledge and good practices and builds institutional capacities through the following outputs:

- Establish effective early warning mechanisms

- formulate and implement policies that effectively mainstream disaster risk reduction and adaptation to climate change

- develop strategies to integrate gender analysis into risk management and in adaptation strategies and tools. In the Caribbean a particular importance will be given to mainstream gender in disaster risk reduction and adaptation of relevant risk reduction models (in work with the Caribbean Disaster and Emergency Management Agency (CDEMA)),

- develop strategies to foster pre-disaster recovery planning including data collection

- develop strategies to improve capacities and coordination across sectors and within levels of government to adopt integral and effective approaches in risk reduction and early recovery

- In regards to the implementation of pilot Risk Reduction Management Centres in the five participating countries, CRMI II will undertake a non-cost extension until June 2014 due to delays in project execution at the country level stemming from the short implementation period impeding both activity completion  and procurement in many of the participating countries. In addition to re-program 2013 resources for the 2014 year, RBLAC has designated 16,000 USD additional funds to support CRMI II in 2014 which are reflected in the 2014 AWP.

- Many of the proposed activities and indicators in the CRMI II project document have been achieved. This includes advances  in RRMC implementation in each of the 5 participating countries (1.1), workshops and training on the RRMC model held in each participating country (1.2), three technical assistance missions carried out from Cuba to Jamaica, the Dominican Republic and Trinidad and Tobago (1.4, 1.6, 1.7, 1.8), the launch of the CRMI website and online document centre (2.1), regional workshops  on ‘strengthening public investment in disaster risk reduction and Post Disaster Needs Assessment’ and ‘Building Climate Resilience and Mainstreaming Disaster Risk Reduction Knowledge Management’ (2.2), and  emphasis on gender capacity development  (2.3). This revision aligns the remaining activities to the 2014-2017 Regional Programme Plan.

## III.	Summary of the Substantive Revision

- The Results Resource Framework now reflects the 2014-2017 Regional Programme Document, as the overarching framework.

- The CRMI project document outcomes, outputs, activities and inputs (resources) have not changed.

- The project timeline has been extended to December 2014.

# Results and Resources Framework

| Intended Outcome and Output as stated in the Regional Programme Document 2014-2017: Outcome 4 (Strategic Plan Outcome 5) : Countries are able to reduce the likelihood of conflict and lower the risk of natural disasters, including from climate change Output 4.3 (Strategic Plan Output 5.1) : Effective institutional, legislative and policy frameworks in place to enhance the implementation of disaster and climate risk management measures at national and sub-national levels |
| --- |
| Outcome indicators: Percentage of countries with disaster and climate risk management plans fully funded through national, local and sector development budgets (SP indicator 4, outcome 5) |
| Partnership Strategy: CDEMA, UWI, Cuban Civil Defense, GREDES, NDMOs, INSMET, CCCCC, CARICOM, CIMH, OECS, ECLAC, CELAC |
| Project title and ID (ATLAS Award ID): 00070622, Caribbean Risk Management Initiative II (CMRI II) |
| INTENDED OUTPUTS | OUTPUT TARGETS FOR (YEARS) | INDICATIVE ACTIVITIES | IMPLEMENTATION ENTITY | INPUTS |
| Output 1.0 Capacity for disaster risk reduction and adaptation to climate change developed within the Caribbean region is strengthened. |
| Indicator 1.1: South-south cooperation to increase institutional capacity to manage and reduce local risk through establishing local risk management centres in most vulnerable municipalities Baseline: 56 RRMC Centres established in Cuba but no others exist in the Caribbean. Incipient awareness of importance of coordinated information and decision-making at local level, but method and tool availability minimal. Limited sex-disaggregated data collection. | Targets (Year 2 - 2012) Establish guidelines for RRMC implementation Establish baseline information on local RR in the Caribbean pilots Develop training materials Build awareness in national and local authorities; train RRMC staff Targets (Year 3 and 4 - 2013/14) Establish 3 to 5 centres Identification of specific areas of technical assistance required per pilot Implementation of vulnerability and hazard studies, risk assessments, data collection, database management, GIS mapping of vulnerabilities, gender analysis, seismic risk and/or planning for recovery Guidelines for vulnerability and hazard mapping produced 4 -8 communities/ municipalities with improved DRM protocols and procedures, including data collection Review and improve 4 national databases, based on coordinated information provided by RRMC Replication Guidelines strengthened Documentation of best practices and lessons learned | Activity Result 1: RRMCs replication activities in 6 countries in the region Action 1.1.1: Organize awareness building workshop for national authorities Action 1.1.2 Coordinate agreements of territorial protocols and guidelines Action 1.1.3 Provide technical assistance in: integration of climate risk management; hazard and vulnerability assessments; data base management Action 1.1.4 Experience systematized, lessons learned document published and final guidelines for replication produced Activity Result 1.2: RRMC Training Workshops Action 1.2.1 Develop training materials and capacity development sessions. Action 1.2.2: Produce Guidelines to support replication. Activity Results 1.3 – 1.8: RRMC Implementation 1.3: British Virgin Island 1.4: Trinidad and Tobago 1.5: Guyana 1.6: Jamaica 1.7: Dom Republic (la Victoria) 1.8: Dom Republic (Luperon) | Cuban Civil Defense CDEMA NEMOs CCCCC Cuba CO GREDES | 25700 – Training, Workshop: 136,000 71200 – Intnl Consult: 19,000 71600 – Travel: 38,500 71200 – Service Contract: 10,000 74200 – AV/Publications: 9,000 72800 ITC – 15,000 71300 Local Consult 50,000- 72200 Equip/Furn – 10,000 74500 – Misc – 5,000 75100 – Facilities/Admin: 14,625 Subtotal: 307,125 |
| Output 2.0 Improved management of knowledge on climate change adaptation and disaster risk reduction |
| Indicator 2.1: Improved integration of DRR and CCA in Caribbean actors Baseline: There is no coherent community of practice addressing DRM and CCA in the Caribbean across all linguistic communities. CRMI website has been substantially redesigned and provides content in 3 languages to support the CoP. Indicator 2.2 Increased capacity building in emergent themes Baseline: As a result of the 2010 Haiti earthquake, emergent themes such as seismic risk and planning for recovery are taking greater priority. There is minimal regional awareness of these thematic areas. Indicator 2.3 Gender is integrated into national DRM and CCA structures, policies, plans and programs Baseline: Gender actions in the Caribbean not coordinated; regional action plan not in effect. Indicator 2.4 Improved knowledge sharing and management in climate change adaptation practices Baseline: Limited sectoral guidelines and procedures available at national and community levels for climate risk management. | Targets Year 1 (2011): 1 COP strengthened Online Pilot course (Gender, DRM and Public policy) developed Targets Year 2 (2012): Improved web portal in three languages, integrated with regional knowledge platform, with repository of tools, expert network and case studies for use Strengthen network of DRR and CCA practitioners Assess need for regional DRR-CCA approach Identify 2 best practices in mainstreaming DRR-CCA in Caribbean and Pacific SIDS Increased understanding of intersection of gender, DRR and public policy development thru pilot course delivery Improved understanding of PDNA in 20 countries 10-member Gender Working Group is convened; plan of action developed for 2013 Targets Year 3 (2013) National pre-planning for recovery plans are developed in at least 2 Caribbean nations 2 workshops in emergent themes such as seismic risk or pre-planning for recovery Experiences and practices shared between Pacific-Caribbean SIDS in meetings, platforms and documents Support to roll-out of at least 1 distance teaching program with University in Caribbean Gender Working Group supports 2013 action plan implementation Gender checklist is disseminated to all NDMOs in the region 1 training on gender integration in DRR is held with partners CDEMA 4 RRMCs pilots provided with support to include gender consideration in plans and actions 1 AV product on women’s leadership in DRM is produced with Pacific SIDS 2 best practices, studies and guidelines in CCA in tourism, agriculture and coastal zone management. 5 countries supported in processes of reporting risk reduction (HFA) Targets Year 4 (2014) Regional Seismic Risk Forum Support to adaptation of gender course to Caribbean | Activity Result 2.1: DRR and CCA communities share best practices in integrating Climate Risk management into policies and programs Action 2.1.1 Expand and strengthen web portal, ensure linkage with regional Knowledge Platform and Teamworks Action 2.1.2 Coordinate meeting of regional actors and policy makers in ministries of environment, disasters and planning, where strategies for DRR-CCA strategies for integration are discussed, at national and regional levels Action 2.1.3 Strengthen integration of DRR-CCA through awareness building at annual Community of Practices meeting Activity Result 2.2: Emergent themes such as seismic risk and planning for recovery are addressed in vulnerable Caribbean islands and best practices are identified Activity 2.2.1. Hold Post Disaster Needs Assessment workshop for national authorities, including participation of Ministries of Finances, Disaster and Planning and relevant line ministries Activity 2.2.2. Organize pre-planning for recovery training for national line ministries, involving Pacific SIDS experience where relevant Action 2.2.3 Organize seismic risk workshop for W Caribbean islands Action 2.2.4 Strengthen tsunami early warning systems and capacity in region Action 2.2.5 Share lessons learned from Pacific SIDS tsunami experience Action 2.2.6 Support to Caribbean participation in Annual CDM Conference Activity Result 2.3 Gender Integrated into DRR/M practices in national and regional actors Action 2.3.1 Establishment and functioning of Gender Working Group Action 2.3.2 Develop online course in Gender Integration into Public Policies for planning, development and disaster policy makers and practitioners in the Caribbean Action 2.3.3 Support transition of pilot course to regional university implementation and ownership Action 2.3.4 Coordination and follow-thru of gender activities in Caribbean region through multiple stakeholders & Gender Working Group Action 2.3.5 Launch, disseminate and integrate Gender Checklist into regional training efforts Action 2.3.6 Capacity development and technical assistance to integrate gender considerations in local disaster risk reduction initiatives, such as sex-disaggregated data collection, analysis and decision Action 2.3.7 Document best practices in women’s leadership in disaster management in island states Activity Result 2.4: Best practices and data translated into information useable by policy makers, decision makers & media at regional, national and local levels Action 2.4.1 Identify and document best practice, analysis and guidelines in Climate Change Adaptation in sectors such as agriculture, tourism and coastal zone management. Action 2.4.2 Share best practices, analysis and guidelines in CCA sector considerations with Caribbean and Pacific SIDS Actions 2.4.3 Support south-south cooperation efforts to share CBCCA experience in coastal zone management to select Caribbean islands Action 2.4.4 Strengthen national capacity to report HFA disaster risk reduction progress | UNDP CDEMA CCCCC CARICOM INSMET UNDP CIMH UWI CPREDENAC UNDP Pacific Centre SOPAC-SPC USP | 25700 – Training, Workshop: 368,500 71200 – Intnl Consult: 75,000 71600 – Travel: 25,000 61100 – NPO: 50,000 74200 – AV/Publications: 30,000 75100 – Facilities/Admin: 34,735 Subtotal: 729,435 |
| Output 3.0 Partnerships and Resource mobilization enhanced |
| Indicator 3.1 Resource Mobilization to implement CRMI II Baseline: CRMI II has commitment from UNDP for critical elements, but additional resources needed to realize the entirety of proposed project activities Indicator 3.2 Partnerships & Sustainability Baseline: Partnerships built or extended with key institutions including the INSMET in Cuba; CCCCC, CDEMA, UWI and others but CRMI still substantially a UNDP initiative Sustainability uncertain based on funding and regional ownership | Targets Year 2 (2012): Resource mobilization action plan completed. Communication plan implemented Pacific –Caribbean S-S SIDS representation at annual meetings S-S Pacific-Caribbean SIDS evaluation meeting held S-S Pacific-Caribbean SIDS contribution to project phase II Targets Year 3 (2013): Liaison with Governments and regional organizations Attendance at existing regional meetings for technical exchange Capacity & interest in project ownership evaluated Project transitioned to regional partner Monitoring Administration Execution Targets Year 4 (2014) 2 Proposals developed and funded Project implemented on time and on budget with all outputs delivered Regional partners established | Activity Result 3.1: Resource mobilization and Partnership plan formulated and implemented Action 3.1.1 Coordinate Management meeting Action 3.1.2 Advocacy and liaison with partners and donor community Action 3.1.3 Attendance at Regional meetings and other events Activity Result 3.2: Caribbean Participation in South-South Caribbean – Pacific Cooperation Initiated Action 3.2.1 CRMI will facilitate the participation of the Caribbean/South Pacific South-South cooperation. Activity Result 3.3: CRMI is managed Action 3.3.1 Hire Project Manager Action 3.3.2 Provide project admin support Action 3.3.3 Conduct final external evaluation Action 3.3.4 GMS – Facilities and Administration costs | UNDP Regional Centre CARICOM CDEMA | 71200 – Intnl Consult: 235,500 71600 – Travel: 59,500 72800 – ICT: 3,200 71300 Local Consult 35,000 Facilities/Admin: 16,660 Subtotal: 349,860 |
| TOTAL |  |  |  | 1,386,420 |

2014

| Expected OUTPUTS | Activities | Implementing Entity | PLANNED BUDGET |
| --- | --- | --- | --- |
|  |  |  | Funding Source | Budget Description | Amount (US$) |
| Output 1: Capacity for disaster risk reduction and adaptation to climate change enhanced within the Caribbean region (Project ID 76586) | Activity Result 1: RRMCs replication activities in 6 countries in the region Action 1.1.4 Experience systematized, lessons learned document published and final guidelines for replication produced | UNDP Cuba RSC | 26931 | 71400 – SC | 2,000 |
|  | Activity Result 1.2: RRMC Training Workshops Action 1.2.1 Develop training materials and capacity development sessions. | RSC, UNDP Cuba | 26931 | 71200 – Intnl Consult 72500 - Publication | 6,000 3,000 |
|  | Activity Result 1.3: British Virgin Island | Pilot Countries | 26931 | 71300 – Local Consult 75700 – Training | 2,000 3,000 |
|  | Activity Result 1.4: Trinidad and Tobago | Pilot Countries | 26931 | 72200 – Equip 72800 – Info | 2,000 2,000 |
|  | Activity Result 1.5: Guyana | Pilot Countries | 26931 | 72400- Comm 75700 - Training | 2,000 3,000 |
|  | Activity Result1.6: Jamaica | Pilot Countries | 26931 | 71300 – Local 72200 – Equip 75700 - Training | 5,000 5,000 5,000 |
|  | Activity Result 1.7: Dom Republic (la Victoria) | Pilot Countries | 26931 | 71300 – Local 72200 – Equip | 3,000 3,000 |
|  | Activity Result 1.8: Dom Republic (Luperon) | Pilot Countries | 26931 | 71300 – Local 72800 – Info 74200 – Audio-Visual | 2,000 2,000 1,000 |
|  | Sub total |  |  |  | 51,000 |
| Output 2.0 Improved management of knowledge on climate change adaptation and disaster risk reduction (Project ID 76587) | Activity Result 2.1: DRR and CCA communities share best practices in integrating Climate Risk management into policies and programs Action 2.1.1 Expand and strengthen web portal, ensure linkage with regional Knowledge Platform and Teamworks | RSC | 04230 | 71200 – Intnl Consultant | 4,000 |
|  | Activity Result 2.2: Emergent themes such as seismic risk and planning for recovery are addressed in vulnerable Caribbean islands and best practices are identified |  |  |  |  |
|  | Action 2.2.3 Organize seismic risk workshop for W Caribbean islands | UNDP Jamaica, DR, Haiti | 26931 | 75700 – Training/Wrksp | 6,000 |
|  | Activity Result 2.3 Gender Integrated in DRR agencies Action 2.3.1 Establishment and functioning Gender Working Group | RSC CDEMA | To be resourced | 71600 - Travel | 0 |
|  | Action 2.3.4 Coordination and follow-thru of gender activities in Caribbean region through multiple stakeholders & Gender Working Group | CDEMA RSC | To be resourced | 75700 – Training/Workshop | 0 |
|  | Action 2.3.6 Capacity development and technical assistance to integrate gender considerations in local disaster risk reduction initiatives, such as sex-disaggregated data collection, analysis and decision | RSC UWI | 04230 | 75700 – Training/Wrksp | 10,000 |
|  | Subtotal |  |  |  | 20,000 |
| Output 3.0 Partnerships and Resource mobilization enhanced (Project ID 76588) | Activity Result 3.1: Resource mobilization and Partnership plan formulated and implemented Action 3.1.1 Coordinate Management meeting | RSC | To be resourced | 71600 - Travel | 0 |
|  | Activity Result 3.3: CRMI is managed Action 3.4.1HireProject Manager | RSC | 26931 | 71200 – Intnl Consult | 8,000 |
|  | Action 3.3.3 Accompany , build capacity and support transition to Regional Agency | RSC, CDEMA | 04230 | 71200 – Intnl Consult | 4,000 |
|  | Action 3.3.4 Conduct final external evaluation | RSC | To be resourced | 71600 – Travel 71200 – Intnl Consult | 0 |
|  | Subtotal |  |  |  | 12,000 |
| Total for 2014 | 83,000 |

# VI. RISK ANALYSIS – Initial Risk Log

| Project Title: CARIBBEAN RISK MANAGEMENT INITIATIVE II | Award ID: 00060722 | Date: DEC 2013 |
| --- | --- | --- |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Financial sustainability of the project | Since project inception | Financial | The lack of funding will limit the implementation of the project’s activities. Initial project extension, requested for one year – until end of 2013, limited the project from developing adequately long-term resource mobilization strategies. This risk was realized, and extension requested into 2014 to provide ample time to resource mobilize. P = 3 I = 3 | Multi-donor resource mobilization strategy Prepare multi-year funding proposals to donors Assess project extension by 3rd quarter 2013 to reflect and complement success of resource mobilization strategy MoU with Country Offices to mobilize resources at the local level, particularly for RRMC pilot Activities that have received secure funding should be prioritized and implemented. | CPR - RSC | Who submitted the risk (In Atlas, automatically recorded) | When was the status of the risk last checked (In Atlas, automatically recorded) | e.g. dead, reducing, increasing, no change (in Atlas, use the Management Response box) |
| 2 | Transition to management by regional entity | Since inception (starting date) | Financial Operational Strategic | Concurrent project implementation and aim to transitional management of the project may be incompatible, as the success of transition relies on demonstrating impact and value of the project (a result of activity planned for implementation in 2013). This risk was identified in fall 2012. It remains the same for 2013, as transition to regional entity of key components is directly related to demonstration of results (currently visible in end of 2013), thus shifting the risk and the countermeasures to 2014. Management transition should also be accompanied by support and resources, which as per pt 1 are to be mobilized. P: 5 I: 4 | Project implementation should take priority with existing resources in first half of 2013, prior to discussions about transition. Project team should be prepared to support resource mobilization and accompaniment beyond 2013 for a successful transition. | CPR - RSC |  |  |  |
| 3 | Natural Disasters in the Region | Since Project Inception | Environmental Strategic | Impact of disasters in one or more participating countries can result in delayed implementation or in a shift in priorities to facilitate response and recovery. P: 3 I: 4 | Allocation of resources and prioritization of activity results may need to respond to situational context of a country(ies). | CPR - RSC |  |  |  |

# Footnotes

Note that with the development of Country Implementation Plans, the 2013 AWP budget was revised to reflect each countries budget. The amounts allocated per country in 1.1.5 did not change, just the organization of information for improved tracking and monitoring per country. The 2014 AWP reflects this structure.