United Nations Development Programme (UNDP)

Region: Latin American and the Caribbean (LAC)

Caribbean Risk Management Initiative Phase 2 (CRMI II) Project Document

2012-2013 Substantive Revision

| Project Title: | Caribbean Risk Management Initiative, Phase 2 |
| --- | --- |
| Expected RPD Outcome(s): | Focus Area 3: Enhancing conflict and disaster reduction and risk management capabilities This project combines aspects of UNDP’s corporate strategic plan (2008-2011) from operations areas: Crisis prevention and recovery – disaster risk reduction and : environment and sustainable development – promoting adaptation to climate change. The project falls under focus areas three and four from the RBLAC regional plan and the RBLAC key results areas Strengthened regional, national and local capacities to manage and mitigate the risks of disasters; and strengthened regional capacity to adapt to climate change |
| Expected RPD Output(s): | Programme Outputs as stated in the RBLAC RPD: 1. Joint multi-country initiatives and strategies to reduce and mitigate the risk of disasters; 2. Policies and systems for disaster management adopted 3. Small islands development via implementation of the Mauritius strategy RBLAC RPD Target: 8 countries supported, including at least 3 Caribbean islands, developing capacities to manage and mitigate the risks of disasters |
| Executing Entity: | UNDP Regional Center, Panama |
| Implementing Agencies: | UNDP, CDEMA, UWI, CARICOM (CCCCC), GREDES |

| Regional Programme Period: 2008 - 2013 Key Result Area (Strategic Plan) ______________ Atlas Award ID: 00060722 Start date: 15th March 2011 End Date 31st Dec 2013 PAC Meeting Date: August 26 – December 4, 2010 Management Arrangements Direct Execution | Total resources required (2011-2013) 1,386,420 Total allocated resources: Regular _________ Other: BCPR 800,000 RBLAC 33,609 Government _________ Unfunded budget: 552,811 In-kind Contributions _________ |
| --- | --- |

| Agreed by: | Name | Title | Date | Signature |
| --- | --- | --- | --- | --- |
| RBLAC |  |  |  |  |
| UNDP (Executing Entity) |  |  |  |  |

## I.	Brief Background of the Project

- Capacity in the Caribbean for managing climate-induced disaster risk is low despite gains made by the Caribbean Risk Management Initiative (CRMI) Phase one and other initiatives undertaken by regional governments, the United Nations, and other development partners. Through this project, UNDP will assist Caribbean countries to implement those sections of the Mauritius Declaration that call for establishing or strengthening national and regional climate-change coordination mechanisms; improving national disaster mitigation, preparedness and early-warning capacity; increasing public awareness about disaster reduction; stimulating interdisciplinary and inter-sectoral partnerships; and mainstreaming risk management. To do so, this project aims to establish disaster risk reduction centres, based on the Cuban model, to map hazards, vulnerability and risk due to climate and geological hazards and provide a tool for informed decision making and early warning system at the local and community level. In addition the project will build capacity and awareness among policy-makers and stakeholders in communities, technical agencies and government who work in the area of DRM and CCA, through courses, workshops, trainings and the sharing of best practices. The project strengthens documentation of best practices for improved south-south cooperation in the fields of DRM and CCA, as well as works to bring the two communities closer together.

- The CRMI II project has three expected outputs:

  - 1.0 Capacity for disaster risk reduction and adaptation to DRR-CCA is developed within the region is strengthened;

  - 2.0 Management of knowledge on climate change adaptation and disaster risk reduction is improved; and

  - 3.0 Partnerships and Resource Mobilization are enhanced.

- This project combines aspects of UNDP’s corporate strategic plan (2008-2013) from operations areas: Crisis prevention and recovery – disaster risk reduction and: environment and sustainable development – promoting adaptation to climate change. The project falls under focus areas three and four from the RBLAC regional plan and the RBLAC key results areas Strengthened regional, national and local capacities to manage and mitigate the risks of disasters; and strengthened regional capacity to adapt to climate change.

## II.	Justification of the Substantive Revision for the Project Extension for the year 2012-2013.

- Between 2011 – current, the implementation of project activities have been hampered by changes at the managerial level. A new coordinator has been hired to provide overall guidance and operationalization as well as technical and management support to project implementation. This has also resulted in an assessment of existing resources and focus of the project, in order to make it more coherent and respond strategically to the needs of the region.  An extension to end of 2013 for the project is required in order to make effective use of the assigned resources.

- Many of the proposed activities and indicators in the original CRMI II project document were achieved and should correctly be attributed to CRMI I (Cuba and Barbados COs). This includes RRMC national workshop (1.1.1), Gender guidelines (2.2.2), HFA mid-term study (2.3), establishment of a Gender Advisory Committee (2.5) and contribution of SIDS to the GAR 11 (2.6). The revision cleans up the project document to avoid confusion regarding attribution or achievement of project results.

- CRMI II needs a more coherent approach, whereby the proposed outputs and activities serve to strengthen and build upon the synergies between them. This substantive revision seeks to bring together key elements of the project in a more clarified manner. For example:  the integration of gender into DRM is reflected in including dis-aggregated data collection with the RRMC pilot, coordinating a regional gender working group and mainstreaming gender training with CDEMA; the adaptation component is reflected in identifying key sector strategies for climate change, sharing of practices with SIDS and bringing together the DRM and CCA communities for more articulated regional direction, and; the opportunity to strengthen practices in gender integration, local risk management, and climate adaptation initiatives through inter-regional exchange of knowledge and experience with the Pacific SIDS is incorporated.

- To optimize the existing resources, the project will focus its existing resource on south-south cooperation activities in local risk reduction. The replication of the Cuban best practices model and piloting it in 4-6 countries in the Caribbean will be the primary pillar of CRMI II and reflects the RBLAC Annual Business Plan 2012 – 2013.

- The revision also reflects themes that have emerged as priority areas for the Caribbean in the last two years. These include building capacity for addressing seismic risk in the Western Caribbean and strengthening tsunami warning systems with the Eastern region. In the wake of Hurricane Sandy, planning for recovery takes on greater importance; CRMI II is able to strategically build capacity in this area, supporting a multi-country initiative in PDNA.  Incorporating planning for recovery responds to the RBLAC 2012 contribution (Annual Business Plan) to the UNDP Integrated Workplan 2012.

- A substantive revision to the current work plan is necessary in order to meet regional strategic directives in south-south cooperation and planning for recovery. With a clear focus and structure, the revision will allow for more coordinated resource mobilization and partnership building. The revision also presents a reasonable aim for resource mobilization, with a modest 489,811 USD for the upcoming fiscal year rather than the 1,668,500 USD that was originally envisioned.

- According to the guidelines for Project Revisions (see POPP, Running a Project, section 2.5), this proposed change in the design of the project would qualify as a substantive revision.

## III.	Summary of the Substantive Revision

- The Project rationale and objectives are now coherent and well aligned with the Regional Programme Document and UNDP Integrated Work Plan. The Results and Resources Framework provides clear links with the RPDD intended outcomes, outcome indicators, baselines and targets.  The targets are more clearly formulated with quantifiable units of measurement. The total number of activities will be reduced from 15 to 8 organized around the three outputs, for more clearly articulated results. The quality management methods are revised to be more realistic and manageable. The logic and numbering of the project outputs, activity results and actions are now sequential.

- Output 1 - South-south cooperation: The main pillar of the project is south-south cooperation pilot project, whereby the Cuban model of Risk Reduction Management Centres (RRMC) are shared, adapted and implemented in 3-5 pilot countries. The RRMC model stresses the need to equip and build capacity at a local level in order to carry out local assessments of risk, produce hazard and risk maps, and compile information from different actors in a territory in order that decision-makers can make informed decisions in a potentially hazardous situation. RRMCs also form a focus point for managing and communicating socio-economic information on losses after an event such as derived from initial damage assessments, thus integrating the early recovery element.  Since these centres manage information on disaster risk reduction including vulnerability, they will also be well positioned to ensure that climate adaptation measures are incorporated into local programmes and projects.  In addition, they provide a vehicle for strengthening a gender-perspective in risk reduction analysis, ensuring its visibility in risk studies and assessments, as well as the collection of sex-disaggregated data. The revision better draws together the various elements in effective risk management, calls for a more realistic roll-out period for this pilot, provides the necessary training and technical support for pilot countries and aims to consolidate lesson learned,  allowing for further potential replication in the future. The revision also highlights the need for a sustainable approach from the beginning, allowing national level partners to assume responsibilities for the pilot and using regional-level resources as an initial leverage tool. Output 1 is reduced from two (2) indicators to one (1); the indicative activities reflect the logic of the replication process, resources available, technical support and ownership/sustainability.

- Output 2 – Improved knowledge management on CCA and DRR:  This output is more clearly formulated around four indicators, which include integration of CCA & DRR, planning for recovery and seismic risk as emergent themes, gender and sharing of best practices between and across regions. The 4 activity results areas are aligned coherently with the indicators, as are the output targets with progressive and complementary logic evident between the activity result areas.

- Output 3 – This output area is focuses on building partnerships with inter/regional stakeholders, actors and donors, as well as ensuring the project management. The budget reflects existing resources and highlights the areas requiring additional support for effective project administration and guidance.

# Results and Resources Framework

Project title and ID (ATLAS Award ID): 00060722, The Caribbean Risk Management Initiative Phase II

Relevant operational areas of the UNDP corporate strategic plan CPR Outcome 2: Strengthened national capacities, including the participation of women, to prevent, reduce, mitigate and cope with the impact of the systemic shocks from natural hazards EE Outcome 3: Strengthened capacity of developing countries to mainstream climate change adaptation policies into national development plans Intended Outcomes as stated in the RBLAC Regional Programme Results and Resource Framework 2008 - 2013: Strengthened regional, national and local capacities to manage and mitigate the risks of disasters; strengthened regional capacity to adapt to climate change Target: 8 Countries supported (Including at least 3 Caribbean Islands): Developing capacities to manage and mitigate Risks of Disaster.

Outcome indicators as stated in the Regional Programme Results and Resources Framework, including baseline and targets. Focus Areas 3 & 4: In the programme outcome for natural disaster reduction, UNDP will support multi-country initiatives help to develop policies and mechanisms for improved management while devoting particular attention to supporting recovery and development strategies in SIDS. Regional Programme Indicators: 1. Number of development policies that integrate strategies to reduce the risk of disasters; 2. Number of Caribbean islands implementing the Mauritius Strategy Regional Programme Baseline: Insufficient regional, national and local capacities to manage and mitigate the risks of disasters Programme Outputs as stated in the RBLAC RPD: 1. Joint multi-country initiatives and strategies to reduce and mitigate the risk of disasters; 2. Policies and systems for disaster management adopted 3. Small islands development via implementation of the Mauritius strategy RBLAC RPD Target: 8 countries supported, including at least 3 Caribbean islands, developing capacities to manage and mitigate the risks of disasters In the programme outcome for climate change adaptation Regional interventions will focus on supporting adaptation to climate change. It will also deliver policy advice to Governments on climate change adaptation and mitigation policies Indicator: Number of countries adopting strategies to adapt to climate change; resources invested in adaptation to climate change Baseline: Limited regional capacities to adapt to climate change and increase the use of renewable energy sources Programme Outputs as stated in the RBLAC RPD: 1. Adoption of regional instruments to adapt and mitigate the effects of climate change; 2. Adoption of innovative policies to adapt to climate change based on policy advice to national Governments; RBLAC RPD Target: Policies and institutional capacities strengthened in 5 countries to adapt to climate change

| Intended Outcome as stated in the Regional Programme Document - Results and Resource Framework (2008 – 2013): Strengthened regional, national and local capacities to manage and mitigate the risks of disasters; strengthened regional capacity to adapt to climate change Target: 8 Countries supported (Including at least 3 Caribbean Islands): Developing capacities to manage and mitigate Risks of Disaster. |
| --- |
| Outcome indicators, baseline and targets as stated in the Regional Programme Document - Results and Resources Framework (2008 – 2013). In the programme outcome for natural disaster reduction, UNDP will support multi-country initiatives help to develop policies and mechanisms for improved management while devoting particular attention to supporting recovery and development strategies in SIDS. |
| UNDP Integrated Workplan (2012 – 2013) Comprehensive disaster risk reduction and post-disaster recovery frameworks as well as accompanying institutional mechanisms developed and operational in at least 15-20 disaster-prone countries, to both reduce loss of life, livelihoods and assets and strengthen long-term resilience. Accelerated recovery underway with UNDP (and UN) support in selected sub-regions affected by large-scale natural disasters (Central America and the Caribbean, Horn of Africa and the Sahel) ¦ Lead: RBA, RBAS, RBLAC; Support: BCPR, BDP, BOM, BERA |
| RBLAC Key Results (2012 – 2013) Centers for local disaster risk management (RRMC) established in at least 2 Caribbean countries through South-South cooperation Early recovery elements incorporated into the Caribbean's Climate Risk Management Initiative |
| Partnership Strategy: CDEMA, UWI, Cuban Civil Defense, GREDES, NDMOs, INSMET, CCCCC, CARICOM, CIMH, |
| Project title and ID (ATLAS Award ID): 00070622, Caribbean Risk Management Initiative II (CMRI II) |
| INTENDED OUTPUTS | OUTPUT TARGETS FOR (YEARS) | INDICATIVE ACTIVITIES | IMPLEMENTATION ENTITY | INPUTS |
| Output 1.0 Capacity for disaster risk reduction and adaptation to climate change developed within the Caribbean region is strengthened. |
| Indicator 1.1: South-south cooperation to increase institutional capacity to manage and reduce local risk through establishing local risk management centres in most vulnerable municipalities Baseline: 56 RRMC Centres established in Cuba but no others exist in the Caribbean. Incipient awareness of importance of coordinated information and decision-making at local level, but method and tool availability minimal. Limited sex-disaggregated data collection. | Targets (Year 2 - 2012) Establish guidelines for RRMC implementation Establish baseline information on local RR in the Caribbean pilots Develop training materials Build awareness in national and local authorities; train RRMC staff Targets (Year 3 - 2013) Establish 3 to 5 centres Identification of specific areas of technical assistance required per pilot Implementation of vulnerability and hazard studies, risk assessments, data collection, database management, GIS mapping of vulnerabilities, gender analysis, seismic risk and/or planning for recovery Guidelines for vulnerability and hazard mapping produced 4 -8 communities/ municipalities with improved DRM protocols and procedures, including data collection Review and improve 4 national databases, based on coordinated information provided by RRMC Replication Guidelines strengthened Documentation of best practices and lessons learned | Activity Result 1: RRMCs replication activities in 6 countries in the region Action 1.1.1: Organize awareness building workshop for national authorities Action 1.1.2: Produce Guidelines to support replication. Action 1.1.3 Coordinate agreements of territorial protocols and guidelines Action 1.1.4: Develop training materials and capacity development sessions. Action 1.1.5: Installation of equipment Action 1.1.6 Provide technical assistance in: integration of climate risk management; hazard and vulnerability assessments; data base management Action 1.1.7 Experience systematized, lessons learned document published and final guidelines for replication produced | Cuban Civil Defense CDEMA NEMOs CCCCC Cuba CO GREDES | 25700 – Training, Workshop: 136,000 71200 – Intnl Consult: 19,000 71600 – Travel: 38,500 71200 – Service Contract: 10,000 74200 – AV/Publications: 9,000 72800 ITC – 15,000 71300 Local Consult 50,000- 72200 Equip/Furn – 10,000 74500 – Misc – 5,000 75100 – Facilities/Admin: 14,625 Subtotal: 307,125 |
| Output 2.0 Improved management of knowledge on climate change adaptation and disaster risk reduction |
| Indicator 2.1: Improved integration of DRR and CCA in Caribbean actors Baseline: There is no coherent community of practice addressing DRM and CCA in the Caribbean across all linguistic communities. CRMI website has been substantially redesigned and provides content in 3 languages to support the CoP. Indicator 2.2 Increased capacity building in emergent themes Baseline: As a result of the 2012 Haiti earthquake, emergent themes such as seismic risk and planning for recovery are taking greater priority. There is minimal regional awareness of these thematic areas. Indicator 2.3 Gender is integrated into national DRM and CCA structures, policies, plans and programs Baseline: Gender actions in the Caribbean not coordinated; regional action plan not in effect. Indicator 2.4 Improved knowledge sharing and management in climate change adaptation practices Baseline: Limited sectoral guidelines and procedures available at national and community levels for climate risk management. | Targets Year 1 (2011): 1 COP strengthened Online Pilot course (Gender, DRM and Public policy) developed Targets Year 2 (2012): Improved web portal in three languages, integrated with regional knowledge platform, with repository of tools, expert network and case studies for use Strengthen network of DRR and CCA practitioners Assess need for regional DRR-CCA approach Identify 2 best practices in mainstreaming DRR-CCA in Caribbean and Pacific SIDS Increased understanding of intersection of gender, DRR and public policy development thru pilot course delivery Improved understanding of PDNA in 20 countries 10-member Gender Working Group is convened; plan of action developed for 2013 Targets Year 3 (2013) National pre-planning for recovery plans are developed in at least 2 Caribbean nations 2 workshops in emergent themes such as seismic risk or pre-planning for recovery Experiences and practices shared between Pacific-Caribbean SIDS in meetings, platforms and documents Support to roll-out of at least 1 distance teaching program with University in Caribbean Gender Working Group supports 2013 action plan implementation Gender checklist is disseminated to all NDMOs in the region 1 training on gender integration in DRR is held with partners CDEMA 4 RRMCs pilots provided with support to include gender consideration in plans and actions 1 AV product on women’s leadership in DRM is produced with Pacific SIDS 2 best practices, studies and guidelines in CCA in tourism, agriculture and coastal zone management. 5 countries supported in processes of reporting risk reduction (HFA) | Activity Result 2.1: DRR and CCA communities share best practices in integrating Climate Risk management into policies and programs Action 2.1.1 Expand and strengthen web portal, ensure linkage with regional Knowledge Platform and Teamworks Action 2.1.2 Coordinate meeting of regional actors and policy makers in ministries of environment, disasters and planning, where strategies for DRR-CCA strategies for integration are discussed, at national and regional levels Action 2.1.3 Strengthen integration of DRR-CCA through awareness building at annual Community of Practices meeting Activity Result 2.2: Emergent themes such as seismic risk and planning for recovery are addressed in vulnerable Caribbean islands and best practices are identified Activity 2.2.1. Hold Post Disaster Needs Assessment workshop for national authorities, including participation of Ministries of Finances, Disaster and Planning and relevant line ministries Activity 2.2.2. Organize pre-planning for recovery training for national line ministries, involving Pacific SIDS experience where relevant Action 2.2.3 Organize seismic risk workshop for W Caribbean islands Action 2.2.4 Strengthen tsunami early warning systems and capacity in region Action 2.2.5 Share lessons learned from Pacific SIDS tsunami experience Action 2.2.6 Support to Caribbean participation in Annual CDM Conference Activity Result 2.3 Gender Integrated into DRR/M practices in national and regional actors Action 2.3.1 Establishment and functioning of Gender Working Group Action 2.3.2 Develop online course in Gender Integration into Public Policies for planning, development and disaster policy makers and practitioners in the Caribbean Action 2.3.3 Support transition of pilot course to regional university implementation and ownership Action 2.3.4 Coordination and follow-thru of gender activities in Caribbean region through multiple stakeholders & Gender Working Group Action 2.3.5 Launch, disseminate and integrate Gender Checklist into regional training efforts Action 2.3.6 Capacity development and technical assistance to integrate gender considerations in local disaster risk reduction initiatives, such as sex-disaggregated data collection, analysis and decision Action 2.3.7 Document best practices in women’s leadership in disaster management in island states Activity Result 2.4: Best practices and data translated into information useable by policy makers, decision makers & media at regional, national and local levels Action 2.4.1 Identify and document best practice, analysis and guidelines in Climate Change Adaptation in sectors such as agriculture, tourism and coastal zone management. Action 2.4.2 Share best practices, analysis and guidelines in CCA sector considerations with Caribbean and Pacific SIDS Actions 2.4.3 Support south-south cooperation efforts to share CBCCA experience in coastal zone management to select Caribbean islands Action 2.4.4 Strengthen national capacity to report HFA disaster risk reduction progress | UNDP CDEMA CCCCC CARICOM INSMET UNDP CIMH UWI CPREDENAC UNDP Pacific Centre SOPAC-SPC USP | 25700 – Training, Workshop: 368,500 71200 – Intnl Consult: 75,000 71600 – Travel: 25,000 61100 – NPO: 50,000 74200 – AV/Publications: 30,000 75100 – Facilities/Admin: 34,735 Subtotal: 729,435 |
| Output 3.0 Partnerships and Resource mobilization enhanced |
| Indicator 3.1 Resource Mobilization to implement CRMI II Baseline: CRMI II has commitment from UNDP for critical elements, but additional resources needed to realize the entirety of proposed project activities Indicator 3.2 Partnerships & Sustainability Baseline: Partnerships built or extended with key institutions including the INSMET in Cuba; CCCCC, CDEMA, UWI and others but CRMI still substantially a UNDP initiative Sustainability uncertain based on funding and regional ownership | Targets Year 2 (2012): Resource mobilization action plan completed. Communication plan implemented Pacific –Caribbean S-S SIDS representation at annual meetings S-S Pacific-Caribbean SIDS evaluation meeting held S-S Pacific-Caribbean SIDS contribution to project phase II Targets Year 3 (2013): 2 Proposals developed and funded. Liaison with Governments and regional organizations Attendance at existing regional meetings for technical exchange Capacity & interest in project ownership evaluated Project transitioned to regional partner Project implemented on time and on budget with all outputs delivered Monitoring Administration Execution | Activity Result 3.1: Resource mobilization and Partnership plan formulated and implemented Action 3.1.1 Coordinate Management meeting Action 3.1.2 Advocacy and liaison with partners and donor community Action 3.1.3 Attendance at Regional meetings and other events Activity Result 3.2: Caribbean Participation in South-South Caribbean – Pacific Cooperation Initiated Action 3.2.1 CRMI will facilitate the participation of the Caribbean/South Pacific South-South cooperation. Activity Result 3.3: CRMI is managed Action 3.3.1 Hire Project Manager Action 3.3.2 Provide project admin support Action 3.3.3 Conduct final external evaluation Action 3.3.4 GMS – Facilities and Administration costs | UNDP Regional Centre CARICOM CDEMA | 71200 – Intnl Consult: 235,500 71600 – Travel: 59,500 72800 – ICT: 3,200 71300 Local Consult 35,000 Facilities/Admin: 16,660 Subtotal: 349,860 |
| TOTAL |  |  |  | 1,386,420 |

# Annual Work Plan

2011 (For information only: reflects 2010 Project document, activities and actual expenditures)

| Expected OUTPUTS | Activities | Implementing Entity | PLANNED BUDGET |
| --- | --- | --- | --- |
|  |  |  | Funding Source | Budget Description | Amount (US$) |
| Output 2.0 Improved management of knowledge on climate change adaptation and disaster risk reduction (Project ID 76587) | Activity Result 2.1: Community of Practice established in DRM and CCA active Action 2.1.1 Hire a web-based manager | RSC | 26931 | 71200 – Intnl Con | 0 9,600 |
|  | Activity Result 7: Community of Practice Established | RSC | 04230 | 71600 – Travel 71200 – Intnl Con | 4,000 6,000 |
|  | Action 2.9.2 Develop short course for Professionals, including gender-sensitive DRM | RSC, Virtual School UNDP COs | 26931 | 71200 – Intnl Consult | 21,600 |
|  | Action 2.2.5 Support to Caribbean Nationals to attend annual CDM Conference | RSC | 26931 | 75700 – Training, Workshops, Conference | 65,000 |
|  | Action 3.3.4 GMS - Facilities and Admin Costs |  | 26931 | 75100 | 5,310 |
|  | Sub total |  |  |  | 111,510 |
| Output 3.0 Partnerships and Resource mobilization enhanced (Project ID 76588) | Activity Result 3.2: Resource Mobilization Plan and Partnership executed Action 3.2.2 Attend Regional meetings and other events |  | 04230 | 71600 - Travel | 2,000 |
|  | Activity Result 3.4: CRMI is managed Action 3.4 Provide project admin support | RSC | 04230 | 71200 – IC | 6,000 |
|  | Action 3.4.2 (3..3.4) GMS - Project Administration and facilities Costs (Total 2011 GMS - Project Admin and Facilities) |  | 26931 | 75100 | 400 (5,710) |
|  | Subtotal |  |  |  | 8,400 |
| Total 2011 | 119,910 |

2012

| Expected OUTPUTS | Activities | Implementing Entity | PLANNED BUDGET |
| --- | --- | --- | --- |
|  |  |  | Funding Source | Budget Description | Amount (US$) |
| Output 1: Capacity for disaster risk reduction and adaptation to climate change enhanced within the Caribbean region (Project ID 76586) | Activity Result 1: RRMCs replication activities in 6 countries in the region Action 1.1.2: Produce Guidelines to support replication. | UNDP Cuba CO Cuban Civil Defense UNDP RSC | 4230 | 71200 – Intl Consultant | 5,000 |
|  | Action 1.1.3 Coordinate agreements of territorial protocols and guidelines | UNDP RSC | 4230 | 71200 – Intl Consultant 71600 - Travel | 6,000 8,500 |
|  | Action 1.1.4: Develop training materials and capacity development sessions. | UNDP Cuba CO GREDES Cuban Civil Defense |  | 71400 – SC 75700 – Training, Workshops, Conference 74200 – Audio/Visual | 2,000 15,000 1,000 |
|  | Action 3.4.4 GMS - Facilities and Admin Costs |  |  |  | 1,875 |
|  | Subtotal | 39,375 |
| Output 2.0 Improved management of knowledge on climate change adaptation and disaster risk reduction (Project ID 76587) | Activity Result 2.1: DRR and CCA communities share best practices in integrating Climate Risk management into policies and programs Action 2.1.1 Expand and strengthen web portal, ensure linkage with regional Knowledge Platform and Teamworks | RSC | 26931 |  | 0 |
|  | Action 2.1.3 Strengthen integration of DRR-CCA through awareness building at annual Community of Practices meeting | RSC | 26931 | 71600 – Travel 61100 – NP Staff | 5,000 20,000 |
|  | Activity Result 2.2: Emergent themes such as seismic risk and planning for recovery are addressed in vulnerable Caribbean islands and best practices are identified Activity 2.2.1. Hold Post Disaster Needs Assessment workshop for national authorities, including participation of Ministries of Finances, Disaster and Planning and relevant line ministries | RSC UNDP BRB | 26931 | 75700 – Training, Workshops, Conference 61100 – NP Staff | 40,000 20,000 |
|  | Action 2.2.6 Support to Caribbean Nationals to attend Annual CDM Conference | RSC | 26931 | 75700 – Training, Workshops, Conference | 2,500 |
|  | Activity Result 2.3 Gender Integrated in DRR agencies Action 2.3.1 Establish functioning Gender Working Group | RSC | 26931 | 716000 - Travel | 10,000 |
|  | Action 2.3.2 Develop online course in Gender Integration into Public Policies for planning, development and disaster policy makers and practitioners in the Caribbean | RSC, Virtual School UNDP COs | 26931 | 71200 – Intnl Consult | 5,000 |
|  | Action 2.3.4 Coordination and follow-thru of gender activities in Caribbean region through multiple stakeholders & Gender Working Group | RSC, CDEMA | 26931 | 75700 – Training, Workshop, Conference | 10,500 |
|  | Action 2.3.5 Launch, disseminate and integrate Gender Checklist into regional training efforts | RSC | 26931 |  | 0 |
|  | Activity Result 2.4: Best practices and data translated into information useable by policy makers, decision makers & media at regional, national and local levels Action 2.4.4 Strengthen national capacity to report HFA disaster risk reduction progress | UNDP COs | 26931 | 61100 – NP Staff 75700 – Training, Workshops, Conferences | 10,000 12,500 |
|  | Action 3.3.4 GMS - Facilities and Admin Costs |  | 26931 | 75100 | 6,775 |
|  | Sub total |  |  |  | 142,275 |
| Output 3.0 Partnerships and Resource mobilization enhanced (Project ID 76588) | Activity Result 3.1: Resource Mobilization Plan and Partnership executed Action 3.1.2 Advocacy and liaison with partners and donor community | RSC | 26931 | 71600 - Travel | 2,500 |
|  | Action 3.1.3 Attendance at Regional meetings and other events |  | 26931 | 71600 - Travel | 10,000 |
|  | Activity Result 3.2: Caribbean Participation in South-South Caribbean – Pacific Cooperation Initiative Action 3.2.1 CRMI will facilitate the participation of the Caribbean/South Pacific South-South cooperation. | RSC UNDP BRB UNDP Pacific Centre | 26931 | 71600 - Travel | 0 |
|  | Activity Result 3.3: CRMI is managed Action 3.3.1 Hire Project Manager | RSC | 26931 | 71200 – IC 72800 – ITC Equip | 44,500 3,200 |
|  | Action 3.3.4 GMS - Project Administration and facilities Costs (Total 2012 GMS - Project Admin and Facilities) |  | 26931 | 75100 | 3,010 (11,660) |
|  | Subtotal |  |  |  | 63,210 |
| Total 2012 | 244,860 |

2013

| Expected OUTPUTS | Activities | Implementing Entity | PLANNED BUDGET |
| --- | --- | --- | --- |
|  |  |  | Funding Source | Budget Description | Amount (US$) |
| Output 1: Capacity for disaster risk reduction and adaptation to climate change enhanced within the Caribbean region (Project ID 76586) | Activity Result 1: RRMCs replication activities in 6 countries in the region Action 1.1.4: Develop training materials and capacity development sessions. | UNDP Cuba Cuban Civil Defense GREDES | 26931 | 71400 – SC 75700 – Training, Workshops, Conference | 8,000 61,000 |
|  | Action 1.1.5: Installation of equipment | UNDP COs (BRB, DR, Guyana, T & T, Belize, Jamaica) National Authorities | 26931 | 72800 – ITC Equip 71300 – Local Consults 72200 – Equip/Furn 75700 – Training/Wrksp 74500 - Misc | 15,000 50,000 10,000 60,000 5,000 |
|  | Action 1.1.6 Provide technical assistance in: integration of climate risk management; hazard and vulnerability assessments; data base management | UNDP Cuba Cuban Civil Defense | 26931 | 71600 - Travel | 12,000 |
|  | Action 1.1.7 Experience systematized, lessons learned document published and final guidelines for replication produced | RSC | 26931 | 71600 – Travel 71200 – Intnl Consult 72500 - Publication | 18,000 8,000 8,000 |
|  | Action 3.3.4 GMS - Facilities and Admin |  | 26931 | 751000 | 12,750 |
|  | Sub total |  |  |  | 267,750 |
| Output 2.0 Improved management of knowledge on climate change adaptation and disaster risk reduction (Project ID 76587) | Activity Result 2.1: DRR and CCA communities share best practices in integrating Climate Risk management into policies and programs Action 2.1.1 Expand and strengthen web portal, ensure linkage with regional Knowledge Platform and Teamworks | RSC | To be resourced | 71200 – Intnl Consultant | 15,000 |
|  | Action 2.1.2 Coordinate meeting of regional actors and policy makers in ministries of environment, disasters and planning, where strategies for DRR-CCA strategies for integration are discussed, at national and regional levels | RSC, UNDP COs CDEMA CCCCC INSMET | To be resourced | 75700 – Training, Workshops, Conferences | 75,000 |
|  | Action 2.1.3 Strengthen integration of DRR-CCA through awareness building at annual Community of Practices meeting |  | TBR |  | 10,000 |
|  | Activity Result 2.2: Emergent themes such as seismic risk and planning for recovery are addressed in vulnerable Caribbean islands and best practices are identified Activity 2.2.2. Organize pre-planning for recovery training for national line ministries, involving Pacific SIDS experience where relevant | RSC UNDP COs | 26931 To be resourced | 75700 – Training/Wrksp | 22,000 18,000 |
|  | Action 2.2.3 Organize seismic risk workshop for W Caribbean islands | RSC UNDP Cuba, Jamaica, DR, Haiti | 26931 To be resourced | 75700 – Training/Wrksp | 25,000 20,000 |
|  | Action 2.2.4 Strengthen tsunami early warning systems and capacity in region | UNDP BRB | To be resourced | 75700 – Training/Wrksp | 40,000 |
|  | Action 2.2.5 Share lessons learned from Pacific SIDS tsunami experience | RSC | To be resourced | 75700 – Training/Wrksp | 15,000 |
|  | Action 2.2.6 Support to Caribbean participation in Annual CDM Conference | RSC | To be resourced | 75700 – Training/Wrksp | 10,000 |
|  | Activity Result 2.3 Gender Integrated in DRR agencies Action 2.3.1 Establishment and functioning Gender Working Group | RSC | To be resourced | 71600 - Travel | 10,000 |
|  | Action 2.3.4 Coordination and follow-thru of gender activities in Caribbean region through multiple stakeholders & Gender Working Group | CDEMA RSC | To be resourced | 75700 – Training/Workshop | 40,000 |
|  | Action 2.3.5 Launch, disseminate and integrate Gender Checklist into regional training efforts | RSC CDEMA | 26931 | 75700 – Training/Wrksp | 18,000 |
|  | Action 2.3.6 Capacity development and technical assistance to integrate gender considerations in local disaster risk reduction initiatives, such as sex-disaggregated data collection, analysis and decision | RSC | To be resourced | 75700 – Training/Wrksp | 25,000 |
|  | Action 2.3.7 Document best practices in women’s leadership in disaster management in island states | RSC | To be resourced | 72500 – Audio Visual/Publication | 10,000 |
|  | Activity Result 2.4: Best practices and data translated into information useable by policy makers, decision makers & media at regional, national and local levels Action 2.4.1 Identify and document best practice, analysis and guidelines in Climate Change Adaptation in sectors such as agriculture, tourism and coastal zone management. | RSC | To be resourced | 71200 – Intnl Consultant | 40,000 |
|  | Action 2.4.2 Share best practices, analysis and guidelines in CCA sector considerations with Caribbean and Pacific SIDS | RSC | To be resourced | 72500 - Publication | 20,000 |
|  | Actions 2.4.3 Support south-south cooperation efforts to share CBCCA experience in coastal zone management to select Caribbean islands | RSC | To be resourced | 75700 – Training/Wrksp | 40,000 |
|  | Action 3.3.4 GMS - Facilities and Admin |  | 26931 | 751000 | 22,650 |
|  | Subtotal |  |  |  | 475,650 |
| Output 3.0 Partnerships and Resource mobilization enhanced (Project ID 76588) | Activity Result 3.1: Resource mobilization and Partnership plan formulated and implemented Action 3.1.1 Coordinate Management meeting | RSC | To be resourced | 71600 - Travel | 15,000 |
|  | Action 3.1.2 Advocacy and liaison with partners and donor community | RSC | 26931 | 71600 - Travel | 5,000 |
|  | Action 3.1.3 Attendance at Regional meetings and other events | RSC | 26931 | 71600 - Travel | 5,000 |
|  | Activity Result 3.2: Caribbean Participation in South-South Caribbean – Pacific Cooperation Initiated Action 3.2.1 CRMI will facilitate the participation of the Caribbean/South Pacific South-South cooperation. | RSC | 26931 | 71600 - Travel | 15,000 |
|  | Activity Result 3.3: CRMI is managed Action 3.4.1HireProject Manager | RSC | 26931 | 71200 – Intnl Consult | 110,000 |
|  | Action 3.3.2 Provide project admin support | RSC | To be resourced | 71300 – Local Consults | 35,000 |
|  | Action 3.3.3 Accompany , build capacity and support transition to Regional Agency | RSC, CDEMA | To be resourced | 71200 – Intnl Consult | 60,000 |
|  | Action 3.3.4 Conduct final external evaluation | RSC | To be resourced | 71600 – Travel 71200 – Intnl Consult | 5,000 15,000 |
|  | Action 3.3.4 Facilities and Admin (Total for 2013) |  | 26931 | 751000 | 13,250 (48,650) |
|  | Subtotal |  |  |  | 278,250 |
| Total for 2013 | 1,021,650 |
| Total for 2011-2013 | 1,386,420 |

# Monitoring Framework And Evaluation (2012-2013)

Quality Management for Project Activity Results

| OUTPUT 1: Capacity for disaster risk reduction and adaptation to climate change enhanced within the Caribbean region is strengthened. |  |
| --- | --- |
| Activity Result 1.1 (76586 – ACT 1) | RRMCs Replicated in 6 countries in the region | Start Date: 2011 End Date: 2013 |  |
| Purpose | What is the purpose of the activity? To concretize the lessons learned in the first 5 years of the Cuban model and outline conditions and criteria of success for the purpose of replication. |  |
| Description | Action 1.1.1: Organize awareness building workshop for national authorities Action 1.1.2: Produce Guidelines to support replication. Action 1.1.3 Coordinate agreements of territorial protocols and guidelines Action 1.1.4: Develop training materials and capacity development sessions. Action 1.1.5: Installation of equipment Action 1.1.6 Provide technical assistance in: integration of climate risk management; hazard and vulnerability assessments; data base management Action 1.1.7 Experience systematized, lessons learned document published and final guidelines for replication produced |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of participants in workshop | Project Progress Report | End of year 2 |
| Guidelines Developed | Copy of Guidelines | End of year 2 |
| Training Materials Developed | Copy of Materials | 1st Quarter year 3 |
| Capacity Building Workshop Conducted | Workshop Evaluations | 1st Quarter year 3 |
| Pilot RRMCs Experience Systematized | Report, Project Progress Report | End of year 3 |
| Equipment procured and installed | Project Progress Report, ATLAS Report | 2nd Quarter year 2 |
| Communication protocols established and territorial agreement concluded | Copy of Agreements or MOUs with participating Governments | 1st Quarter year 3 |

| OUTPUT 2: Improved management of knowledge on climate change adaptation and disaster risk reduction |
| --- |
| Activity Result 2.1 (76586-ACT 2.1) | DRR and CCA communities share best practices in integrating Climate Risk management into policies and programs | Start Date:2011 End Date: 2013 |
| Purpose | What is the purpose of the activity? To identify best practices in integrating DRR and CCA in the Caribbean region, thru enhanced knowledge platform and dialogue among stakeholders |
| Description | Activity Result 2.1: Action 2.1.1 Expand and strengthen web portal, ensure linkage with regional Knowledge Platform and Teamworks Action 2.1.2 Coordinate meeting of regional actors and policy makers in ministries of environment, disasters and planning, where strategies for DRR-CCA strategies for integration are discussed, at national and regional levels Action 2.1.3 Strengthen integration of DRR-CCA through awareness building at annual Community of Practices meeting Actions 2.1.4 Document best practices in mainstreaming DRR-CCA integration, in Caribbean and Pacific SIDS |
| Quality Criteria | Quality Method | Date of Assessment |
| Site up and running throughout the life of the project; number of users monitored; quantity of information downloaded | A report on the utility, functioning and potential of the web portal will be compiled and sent to the Project Manager. | End of year 2 |
| Number of group meetings | Meeting Minutes or Outcome documents, Project Progress Report | 2nd quarter of Year 3 |
| Review of best practice models in DRr and CCA integration | Project progress report | 3rd quarter of Year 3 |
| Activity Result 2.2 (76587 – ACT 2.2) | Emergent themes such as seismic risk and planning for recovery are addressed in vulnerable Caribbean islands and best practices are identified | Start Date: 2011 End Date: December 2012 |
| Purpose | To build capacity for risk reduction and planning for recovery in the region |
| Description | Activity 2.2.1. Hold Post Disaster Needs Assessment workshop for national authorities, including participation of Ministries of Finances, Disaster and Planning and relevant line ministries Activity 2.2.2. Organize pre-planning for recovery training for national line ministries, involving Pacific SIDS experience where relevant Action 2.2.3 Organize seismic risk workshop for W Caribbean islands Action 2.2.4 Strengthen tsunami early warning systems and capacity in region Action 2.2.5 Share lessons learned from Pacific SIDS tsunami experience Action 2.2.6 Support to Caribbean participation in Annual CDM Conference |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of participants | Workshop Evaluations, Project Progress Reports | 4th Quarter 2012, 4th Quarter 2013 |
| Number of presenters sharing best practices | Conference Agenda | 4th Quarter 2012, 4th Quarter 2013 |
| Activity Result 2.3 (76587 – ACT 2.3) | Gender Integrated into DRR/M practices in national and regional actors | Start Date: 2011 End Date: 2011 |
| Purpose | To strengthen capacity of local, national and regional actors to integrate gender into policy, data management, programs and projects |
| Description | Action 2.3.1 Establishment and functioning of Gender Working Group Action 2.3.2 Develop online course in Gender Integration into Public Policies for planning, development and disaster policy makers and practitioners in the Caribbean Action 2.3.3 Support transition of pilot course to regional university implementation and ownership Action 2.3.4 Coordination and follow-thru of gender activities in Caribbean region through multiple stakeholders & Gender Working Group Action 2.3.5 Launch, disseminate and integrate Gender Checklist into regional training efforts Action 2.3.6 Capacity development and technical assistance to integrate gender considerations in local disaster risk reduction initiatives, such as sex-disaggregated data collection, analysis and decision Action 2.3.7 Document best practices in women’s leadership in disaster management in island states |
| Quality Criteria | Quality Method | Date of Assessment |
| Reviewed comments by Gender Working Group and Experts in the Caribbean and Pacific on CRMI deliverables | Emails, meeting minutes | End of each year |
| Number of participants in the online course providing feedback | Written feedback; course revision & improvement; MOU with Caribbean University | 2nd quarter year 3 |
| Participation and coordination in regional gender and DRM activities | Meeting minutes, Outcome document | End of year 2 & 3 |
| Checklist utilized to build capacity in the region | Training agendas demonstrating use of checklist; press releases | End of Year 3 |
| Collection of sex-disaggregated data | Training agendas, database and collection tools used by decision-makers | End of Year 3 |
| Documentation on women’s leadership in DRM in SIDS | Press release; demand for product | End of Year 3 |
| Activity Result 2.4 (76587 – ACT 2.4) | Best practices and data translated into information useable by policy makers, decision makers & media at regional, national and local levels | Start Date:2011 End Date: 2013 |
| Purpose | What is the purpose of the activity? To provide useful information on disaster risk reduction and climate change adaptation measures to specific sectors |
| Description | Action 2.4.1 Identify and document best practice, analysis and guidelines in Climate Change Adaptation in sectors such as agriculture, tourism and coastal zone management. Action 2.4.2 Share best practices, analysis and guidelines in CCA sector considerations with Caribbean and Pacific SIDS Actions 2.4.3 Support south-south cooperation efforts to share CBCCA experience in coastal zone management to select Caribbean islands Action 2.4.4 Strengthen national capacity to report HFA disaster risk reduction progress |
| Quality Criteria | Quality Method | Date of Assessment |
| Consultant hired | Consultant’s and Project Progress Reports | End of year 3 |
| Quality of information generated | Assessments by regional stakeholders, including Pacific | End of year 3 |
| HFA reporting completed | Statistics from UNISDR | End of year 2 |

| Output 3.0 Partnerships and Resource mobilization are enhanced |
| --- |
| Activity Result 3.1 (76588 – ACT 3.1) | Resource mobilization plan developed and implemented | Start Date: 2012 End Date: 2013 |
| Purpose | To have a plan to guide the process for resource mobilization so project activities are financed and build partnerships for implementation and transition for project sustainability |
| Description | Action 3.1.1 Coordinate Management meeting Action 3.1.2 Advocacy and liaison with partners and donor community Action 3.1.3 Attendance at Regional meetings and other events |
| Quality Criteria | Quality Method | Date of Assessment |
| Management Committee meeting convened | Management Meeting Minutes | 1st Q year 3 |
| Resource Mobilization Plan elaborated | Existence of plan; 2 proposals drafted | 1st Quarter year 3 |
| CRMI Activities resourced | ATLAS and Project Manager’s Report MOUs, Commitments from partners and donor agencies to resource specific aspects of CRMI | End of 2013 |
| Activity Result 3.2 (76588 – ACT 3.2) | Caribbean Participation in South-South Caribbean – Pacific Cooperation Sustained | Start Date:2011 End Date: 2013 |
| Purpose | Facilitate S-S exchange of best practices, experiences and strategies for CCA and DRM |
| Description | Action 3.2 CRMI will facilitate the participation of the Caribbean/South Pacific South-South cooperation. |
| Quality Criteria | Quality Method | Date of Assessment |
| Caribbean- Pacific SIDs networked and sharing experiences | Joint activities visible in project progress reports | 2nd quarter year 3 |
| Activity Result 3.3 (76588 – ACT 3.3) | CRMI is managed | Start Date: 2011 End Date:2013 |
| Purpose | Effective management of the CRMI project |
| Description | Action 3.3.1 Hire Project Manager Action 3.3.2 Provide project admin support Action 3.3.3 Accompany , build capacity and support transition to Regional Agency Action 3.3.4 Conduct final external evaluation Action 3.3.4 GMS – Facilities and Administration costs |
| Quality Criteria | Quality Method | Date of Assessment |
| Project Manager hired | Annual report emitted | Annual report |
| Project is adequately administered | ATLAS reports | Annual CDR |
| Regional agency engaged in project activities and future plans | Minutes; funding resourced for accompaniment | 3rd quarter, year 3 |
| Project resourced | Annual report; project documents developed | Annual report |
| Final External Evaluation Conducted | Evaluation Report | 4th quarter of year 3 |

# VII. RISK ANALYSIS – Initial Risk Log

| Project Title: CARIBBEAN RISK MANAGEMENT INITIATIVE II | Award ID: 00060722 | Date: October 2012 |
| --- | --- | --- |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Financial sustainability of the project | Since project inception | Financial | The lack of funding will limit the implementation of the project’s activities. Also project extension, currently requested for one year – until end of 2013, will limit the project from developing adequately long-term resource mobilization strategies. P = 3 I = 3 | Multi-donor resource mobilization strategy Prepare multi-year funding proposals to donors Assess project extension by 2nd quarter 2013 to reflect and complement success of resource mobilization strategy MoU with Country Offices to mobilize resources at the local level, particularly for RRMC pilot Activities that have received secure funding should be prioritized and implemented. | CPR - RSC | Who submitted the risk (In Atlas, automatically recorded) | When was the status of the risk last checked (In Atlas, automatically recorded) | e.g. dead, reducing, increasing, no change (in Atlas, use the Management Response box) |
| 2 | Transition to management by regional entity | Since inception (starting date) | Financial Operational Strategic | Concurrent project implementation and aim to transitional management of the project may be incompatible, as the success of transition relies on demonstrating impact and value of the project (a result of activity planned for implementation in 2013). Management transition should also be accompanied by support and resources, which as per pt 1 are to be mobilized. P: 5 I: 4 | Project implementation should take priority with existing resources in first half of 2013, prior to discussions about transition. Project team should be prepared to support resource mobilization and accompaniment beyond 2013 for a successful transition. | CPR - RSC |  |  |  |
| 3 | Natural Disasters in the Region | Since Project Inception | Environmental Strategic | Impact of disasters in one or more participating countries can result in delayed implementation or in a shift in priorities to facilitate response and recovery. P: 3 I: 4 | Allocation of resources and prioritization of activity results may need to respond to situational context of a country(ies). | CPR - RSC |  |  |  |

# Footnotes

The targets and indicators for the CRMI project itself are in the next table

Note that project has been set up in Atlas with Project IDS corresponding to outputs. Each project ID calculates 0.05 GMS and is reflected as such in Atlas reports. For consistency, this AWP reflects GMS per output or project ID, although in the project document costs associated with project admin/facilitaties (ie. GMS) is budgeted in one line under Output 3. For the purpose of revision, and to improve project management, the GMS figure is represented in grey and is calculated per project ID/output, but acknowledged as Output 3.3.4, as identified in the project document. Total amount is in (brackets) in Output 3, but calculated per output.