First Quarterly Report – July 2016

| Project Title | El Nino Response and Recovery in Latin America and the Caribbean |
| --- | --- |
| Tipo de QPR | Q2 – April – June 2016 |
| Fecha de entrega al PNUD | July– 2,016 |
| Autor | Ruben Vargas |

| Award ID |  |
| --- | --- |
| Project ID |  |
| RPD Outcome(s): | Outcome 4. Countries are able to reduce the likelihood of conflict and lower the risk of natural disasters, including from climate change (SP outcome 5). |
| Expected RPD Output(s): | Output 4.3. Effective institutional, legislative and policy frameworks in place to enhance the implementation of disaster and climate risk management measures at national and sub-national levels (SP output 5.2) |
| Expected Output(s): | Output 1.: Enhanced regional monitoring mechanism [for early recovery interventions] Output 2: Strengthened national and regional capacities to respond to El Niño Output 3: lmproved regional coordination mechanisms |
| Implementing Partner: | UNDP CO in Guatemala, Honduras, El Salvador, Paraguay |
| Responsible Parties: | UNDP Regional HUB Panama |
| Award Start Date | March 30 2016 |
| Award End Date | December 31 2016 |
| Total Award Amount | USD 150,000.00 |

Breve descripción del Proyecto

The project El Nino Response and Recovery in Latin America and the Caribbean aims to improve response capacity and ensure that regional coordination and monitoring mechanisms are complemented by effective national level coordination and monitoring. The project enables UNDP in LAC to support efforts to articulate and bridge humanitarian actions into resilient development practices, ensuring the capacity, information access and analysis are strengthened for better risk-informed decision-making, planning and actions. The project will respond to outcome 4 of the RHLAC Regional Program Document: Countries are able to reduce the likelihood of conflict, and lower the risks of natural disasters, including from climate change. This outcome will be achieved through 3 expected outputs: Output 1: Enhanced regional monitoring mechanism (for early recovery interventions) Output 2: Strengthened national and regional (early recovery) capacities to respond to El Niño Output 3: Improved regional coordination mechanisms (for early recovery) The project will be implemented by UNDP (Regional Hub Panama) under the Direct Implementation Modality (DIM) by the Resilient and Sustainable Development team. The duration of this project is March 2016 – December 2016. The proposed budget is USD$150,000

I) Main project achievements

Description of the main project achievements for the period under consideration

Output 1: Enhanced regional monitoring mechanism (for early recovery interventions) Development of the conceptual framework of the Regional Monitoring Mechanism for Early Recovery (RMM-ER) interventions in the response to the 2015-2016 El Niño. The document has been prepared in consultation with REDLAC members that are part of the regional recovery cluster. The regional monitoring mechanism includes indicators at the output and outcome level. Additionally, the tool includes a set of indicators to monitor the level at which the early recovery approach has been integrated in the response to the 2015-2016 El Niño, including considerations on gender (impact indicators at outcome level) UNDP Country offices in the prioritized countries (El Salvador, Guatemala, Honduras and Paraguay) have started with the adaptation of the RMM-ER at the national level. The current Humanitarian Response Plans HRP (Honduras and Guatemala) and Strategic Response Plans SRP (El Salvador and Paraguay) have been used as reference to select a preliminary set of indicators to monitor recovery interventions. UNDP CO in coordination with national stakeholders in the prioritized countries (HCT – UNETE and NGOs) are reviewing these indicators. An instrument designed to gather information related to the “Impact Indicator” at outcome level is being reviewed by member of the regional cluster on recovery A preliminary Regional Recovery Needs Profile has been developed based on the review of secondary information. This includes information on the interventions by Humanitarian organizations and the Governments in the prioritized countries The draft of the first “Fact Sheet” with information about the interventions on early recovery in the prioritized countries has been prepared and sent to CO for their review and inputs Output 2: Strengthened national and regional (early recovery) capacities to respond to El Niño Capacity gaps and strengths of CO staff at the regional level to stablish and support coordination on early recovery process have been identified Capacity gaps and strengths of HCT and other partners in the prioritized countries to integrate early recovery approach have been identified Planning of the national workshops on recovery coordination is being discussed with national CO in the prioritized countries. The workshops will take place in the period July-August. Countries have requested to adjust the content and timing of the workshop to ongoing national process regarding development of national frameworks for recovery Output 3: Improved regional coordination mechanisms (for early recovery) The REDLAC recovery cluster has been established. The terms of reference defining roles and responsibilities as well as the cluster annual coordination action plan have been prepared. The cluster meets regularly to review and discuss progress in the implementation of the action plan, there have been two meetings in the last 3 months

II) PROJECT PERFORMANCE

Progress of planned activities in the Prodoc

| Results | Baseline | Goals | Indicators |
| --- | --- | --- | --- |
| Enhanced regional monitoring mechanism for El Niño crisis | Baseline 1.1: 0 non-agriculture or non-health recovery targets in monitoring mechanisms for El Niño | Target 1.1: at least three early recovery gender-sensitive indicators and targets | Results Indicator 1.1: # of early recovery indicators and targets developed for regional monitoring recovery framework for El Niño |
|  | Baseline 1.2 : 0 national monitoring frameworks | Target 1.2: at least 2 countries adapt monitoring framework to national level | Results Indicator 1.2: # of monitoring frameworks adapted at national level |
|  | Baseline 1.3 : 0 regional recovery profiles | Target 1.3: 1 regional recovery needs profile developed, disaggregated by country and sex | Results Indicator 1.3: # of regional recovery needs profiles on El Niño , including gender needs |
|  | Baseline 1.4: 0% of information bulletins with early recovery information | Target 1.4: 100% of information bulletins with early recovery updates | Results Indicator 1.4: % of REDLAC regional information bulletins on El Niño with early recovery information |

| Results Activity 1.1 | Goal/s indicator/s qualitative assessment | Method/s Qualitative assessment | Assessment of progress | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| 1.1 Inter-agency Regional Monitoring Mechanism for El Niño includes robust early recovery sector analysis and tracking 1.1.1 Define gender sensitive indicators, targets and data field gaps specific to early recovery 1.1.2 Develop monitoring framework for early recovery cluster 1.1.3 Integrate gender sensitive sector-specific recovery information and data variables 1.1.4 Regional inter-agency early recovery report produced | Meta: At least three early recovery gender-sensitive indicators and targets | Monitoring framework List of indicators | Chronogram ( AWP) |  | X |  |  |
|  |  |  | Indicator value |  | 2 |  |  |
|  |  |  | % of achievement |  | 30% |  |  |
| Comments | The Regional Monitoring Mechanism includes indicators at the output and outcome level. Indicators at the output level have been obtained from the HRP (Guatemala - Honduras) and SRP (El Salvador – Paraguay). The set of suggested output indicators are being reviewed at the country level Indicators at the outcome level look at the integration of the early recovery approach in the response to El Niño, including the level at which implemented actions are gender sensitive. This is defined using as reference the UNDP gender marker. An instrument designed to gather information related to the “Impact Indicator” at outcome level is being reviewed by member of the regional cluster on recovery. |

| Results Activity 1.2 | Goal/s and indicator/s Qualitative assessment | Qualitative assessment methods | Progress | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| AR 1.2 Support application of monitoring framework model at national level for El Niño 1.2.1 Adapt monitoring framework to national level in at least 2 countries 1.2.2 Provide training and technical assistance on use and coordination of monitoring tool for El Niño 1.2.3 Pilot monitoring tool in at least 2 countries | Meta: 1.2: at least 2 countries adapt El Nino monitoring framework to national level |  | Chronogram (AWP) |  | X | X |  |
|  |  |  | Indicator value |  | 2 | 2 |  |
|  |  |  | % of achievement |  | 50% |  |  |
| Comments | Four (4) CO are working together with national partners in the adaptation of the Regional Monitoring Framework to the national level (El Salvador, Guatemala, Honduras, y Paraguay) |

| Results Activity 1.3 | Goal/s and indicator/s Qualitative assessment | Qualitative assessment methods | Progress assessment | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| AR 1.3 Regional Recovery Needs Profile developed 1.3.1 Use Desinventar to calculate national level disaster losses and impact of El Niño , taking into account gender 1.3.2 Analysis and mapping of hazard, exposure and impact at regional level of extreme climate events, with national data aggregated and including sex-disaggregated information 1.3.2 Proposed short & medium-term recovery priorities for El Niño 1.3.4 Recovery Needs Profile produced and disseminated | Meta: 1 regional El Nino recovery needs profile developed, disaggregated by country and sex |  | Chronogram ( AWP) |  | X | X |  |
|  |  |  | Indicator value |  | 1 report | 1 report |  |
|  |  |  | % of achievement |  | 50% |  |  |
| Comments | A preliminary Regional Recovery Needs Profile has been developed based on the review of secondary information (including OCHA reports, Country briefs, News reports). This includes information about the interventions of the Humanitarian organizations and the Governments in the prioritized countries The report in being reviewed by the members of the regional recovery cluster and UNDP CO Final version of the report will be ready by the end of July Due to technical limitations DesInventar cannot be used to calculate national level disaster losses and impact of El Niño. DesInventar is designed to capture info on rapid onset events. The DesInventar database for the prioritized countries has not been updated with information regarding the impact of the last Niño event |

| Results Activity 1.4 | Goal/s and indicator/s Qualitative assessment | Qualitative assessment methods | Progress assessment | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| AR 1.4 Information Disseminated 1.4.1 El Niño Early Recovery fact sheets developed and shared with REDLAC members and national offices 1.4.2 Regular contribution to REDLAC El Niño information bulletins and humanitarian dashboard tool | Meta: 100% of information bulletins with early recovery updates |  | Chronogram (AWP) |  | X | X |  |
|  |  |  | Indicator value |  | 1 Bulletin | 1 Bulletin |  |
|  |  |  | % of achievement |  | 25% |  |  |
| Comments | The draft of the first “Fact Sheet” with information about the interventions on early recovery in the prioritized countries has been prepared and sent to CO for their review and inputs |

| Result 2 | Baseline | Goals | Indicators |
| --- | --- | --- | --- |
| Strengthened national and regional capacities to respond to El Niño | 2.1: 0 national level trainings in recovery coordination for extreme climate events | At least 3 workshops on recovery coordination and preparation for extreme climate events | 2.1: # of stakeholders trained in recovery coordination for extreme climatic events |

| Result Activity 2.1 | Goal/s and indicator/s Qualitative assessment | Qualitative assessment methods | Progress assessment | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| AR 2.1 National teams capable of engaging in coordination processes 2.1.1 Assess capacity of country teams and national partners to establish and support coordination and early recovery processes 2.1.2 Adapt training material targeted at country level to guide the formation and conduct of recovery cluster 2.1.3 National level workshops on early recovery coordination, needs assessment process, the development of recovery frameworks for El Niño, and preparation for extreme climate events | Meta: At least 3 workshops on recovery coordination and preparation for extreme climate events |  | Chronogram (AWP) |  | X | X |  |
|  |  |  | Indicator value |  | 3 |  |  |
|  |  |  | % of achievement |  | 20% |  |  |
| Comments | A survey was conducted to identify capacity gaps and strengths of CO staff at the regional level to stablish and support coordination on early recovery process. A report with the findings has been shared with CO. The same survey (with adaptation to the specific national context) is being applied to HCT and other Humanitarian actors in the prioritized countries Findings of the survey are used as reference for the preparation of the training materials to guide the formation and conduct of recovery clusters at the national level Planning of the national workshops on recovery coordination is being discussed with national CO in the prioritized countries. Workshops will take place in the period July – August 2016 |

| Result 3 | Baseline | Goals | Indicators |
| --- | --- | --- | --- |
| Improved regional coordination mechanisms | 3.1: No cluster action plan 3.2: 0 documented discussion 3.3: No webinar directed at COs in early recovery | 3.1 1 regional recovery coordination action plan 3.2: 1 discussion paper on El Niño Early Recovery Targets 3.2: At least 2 webinars | 3.1: # of early recovery action plans 3.2: # of dialogues regarding El Niño Early Recovery approaches 3.3: # of webinars offered to CO |

| Result Activity 3.1 | Goal/s and indicator/s Qualitative assessment | Qualitative assessment methods | Progress assessment | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| AR 3.1 REDLAC recovery cluster has capacity to collect, process and analyse information in a coordinated manner 3.1.1 Gap analysis of existing regional early recovery coordination mechanism 3.1.2 Produce a regional recovery coordination action plan 3.1.3 Sharing Practices series coordinated for cluster, including practices that address gender-differential | Regional recovery coordination action plan | . | Chronogram (AWP) |  | X | X |  |
|  |  |  | Indicator value |  | 1 |  |  |
|  |  |  | % of achievement |  | 100% |  |  |
| Comments | Regional recovery cluster has been established Regional recovery cluster coordination action plan has been produced |

| Result Activity 3.2 | Goal/s and indicator/s Qualitative assessment | Qualitative assessment methods | Progress assessment | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| AR 3.2 Coordination forum organized to enhance inter-agency planning efforts 3.2.1 Regional Forum on early recovery organized 3.2.2 Recovery coordination discussion paper prepared. | Meta: Discussion paper on El Niño Early Recovery |  | Chronogram (AWP) |  |  | X |  |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement |  |  |  |  |
| Comments | ToR for the preparation of the Discussion paper drafted. Process to hire consultant has been initiated Date for the Regional Forum has been set for August 30 – September 1 |

| Result Activity 3.3 | Goal/s and indicator/s Qualitative assessment | Qualitative assessment methods | Progress assessment | Period 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| AR 3.3 Knowledge products disseminated 3.3.1 Coordination and recovery webinar series conducted 3.3.2 Social media and virtual space utilized for dissemination of project knowledge products. | Meta: At least 2 webinars |  | Chronogram (AWP) |  | X | X |  |
|  |  |  | Indicator value |  | 1 | 1 |  |
|  |  |  | % of achievement |  | 30% |  |  |
| Comments | The first webinar took place on June 15. The CO of Chile, Ecuador and Cuba presented their experiences on the implementation of recovery programs/actions Second webinar scheduled for September to discuss lessons learned regarding early recovery in the response to El Niño |

| %total achievement Result 1 Average % achievement activities for the period under consideration | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
|  |  | 60% |  |  |

| %total achievement Result 2 Average % achievement activities for the period under consideration | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
|  |  | 30% |  |  |

| %total achievement Result 3 Average % achievement activities for the period under consideration | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
|  |  | 60% |  |  |

| Total achievement of results programmed in the Prodoc |
| --- |
| % total achievement results | Period 2016 |
|  | Q1 | Q2 | Q3 | Q4 |
|  |  | 50% |  |  |

III) RISK REGISTER

| Type of risk | Identification date | Description | Comments/ MGT Response |
| --- | --- | --- | --- |
| Financial |  |  |  |
| Strategic |  |  |  |
| Political |  |  |  |

IV) ISSUES REGISTER

| Type | Identification date | Description | Comments / MGT Response | Date solution |
| --- | --- | --- | --- | --- |
| Financial |  |  |  |  |
| Organizational |  |  |  |  |