QUARTERLY PROGRESS REPORT

| Project Title | Caribbean Risk Management Initiative Phase II |
| --- | --- |
| Delivery date: | July 10th, 2013 |
| Prepared by: | Jacinda Fairholm |
| Award No: | 60722 |
| Project ID: | 76586, 76587,76588 |
| Regional Programme Expected Outcomes: | Focus Area 3: Crisis Prevention and Recovery Strengthened regional, national and local capacities to manage and mitigate the risks of disasters Focus Area 4: Environment and sustainable development Strengthened regional capacity to adapt to climate change |
| Project Expected outputs: | Output 1.0: Capacity for disaster risk reduction and adaptation to climate change developed within the Caribbean region is strengthened. Output 2.0: Improved management of knowledge on climate change adaptation and disaster risk reduction Output 3.0: Partnerships and Resource mobilization are enhanced |
| Executing entity : | UNDP- Regional Centre |
| Implementation entities: | UNDP RSC-LAC, CDEMA, UVW, CIMH, INSMET (Cuba) |
| Award ID start date: | October 25th, 2010 |
| Award ID end date: | December 31st, 2012 |
| Total Project Budget (Award ID): | USD 950.000 |
| Participating countries: | Cuba, Jamaica, DR, Haiti, Guyana, Trinidad and Tobago, Belize, Barbados and OECS |
| Period of the report: | April – June 2013 |
| Total expenditure for the reporting period: | 120,034.65 |

Brief Description

This project combines aspects of UNDP’s corporate strategic plan (2008-2011) from operations areas: Crisis prevention and recovery – disaster risk reduction and: environment and sustainable development – promoting adaptation to climate change. The project falls under focus areas three and four from the RBLAC regional plan and the RBLAC key results areas Strengthened regional, national and local capacities to manage and mitigate the risks of disasters; and strengthened regional capacity to adapt to climate change. Capacity in the Caribbean for managing climate-induced disaster risk is low despite gains made by the Caribbean Risk Management Initiative (CRMI) Phase one and other initiatives undertaken by regional governments, the United Nations, and other development partners. To develop such capacity, this project will establish throughout the region, disaster risk reduction centres which will map hazards, vulnerability and risk due to climate change and geological hazards and be part of the national early warning system at the local government and community level. The project will support collection and generation of data on climate and the development of accurate climate change scenarios for key economic sectors to inform effective adaptation to climate change within the highly vulnerable SIDS of the Caribbean. Capacity to manage risk and adapt to climate change will be developed by establishing and supporting a Community of Practice, and developing educational courses and increasing awareness among, inter alia, the media, policy-makers and stakeholders in communities, technical agencies and government. The project will also support development of financial mechanisms and promulgation of guidelines for reducing risk and integrating climate change adaptation into livelihoods, policy and practice.

- MAIN ACHIEVEMENTS OF THE PROJECT

Description of the main achievements of the Project in this quarter

In the second quarter of 2013 (April - June), the main achievements of the Project were: Output 1: Capacity for disaster risk reduction and adaptation to climate change within the Caribbean region is strengthened. Ten-day (April 8 – 18th) training on the RRMC model, targeted at technicians from the five pilot countries, plus Chile, held in Havana, Cuba. Coordination and production of promotional-educational video on SSC in English and Spanish: Sharing What Works: Risk Reduction Management in the Caribbean. Launched at the UNISDR Global Platform on Risk Reduction in May 2013. Systematization of the RRMC model: Operational Procedures and Methodologies. All five pilot countries submitted an Implementation Plan; Approval granted to all five countries with agreement signed between UNDP CO and Regional Centre; implementation started in mid-May 2013 Output 2: Improved management of knowledge on climate change adaptation and disaster risk reduction CRMI website development ongoing. Enormous effort expended to provide guidance to EV. Launch date pushed back repeatedly; current date is end of July. Social media sites (Facebook and Twitter) activated for increased horizontal cooperation; Teamworks space created for UNDP DRR Focal Points. A two-day applied training, focused on operationalizing gender in DRM and conducting gender analysis of policy and programming, was provided to 22 National Disaster Coordinators and the CDEMA technical team, April 16 – 17th, 2013, due to collaboration between CRMI and CIDA to strengthen gender mainstreaming. Discussion Paper on “Gender mainstreaming and DRM” seeks to inform and guide the CDM 2014+ Strategy, currently in consultation phase across the region. The paper was finalized by end of June and will be disseminated in July 2013. Coordinated an exploratory mission on seismic risk to Jamaica, conducted by Dr. Eric Calais, Professor of Geophysics at the Ecole Normale Superieure in Paris, France. The mission resulted in a report, reiterating historical context, identifying current risk and providing a series of first step recommendations. CRMI and RSLAC CPR will be following up with UNDP Jamaica to consider next steps. Outcome 3: Partnerships and Resource mobilization are enhanced 2nd Quarterly CRMI Newsletter disseminated Participation and networking at UNISDR Global Platform, May 20 – 23rd Input and contribution to the Caribbean-Pacific S-S Project Evaluation; CRMI represented on the project planning committee for 2nd Phase of the Caribbean-Pacific South-South Cooperation project. Support to CDEMA Comprehensive Disaster Management Strategy 2014+ (May 8th – 9th, 2013) Coordinated efforts with six UNDP-COs in the region for implementation of RRMC South-south initiative

- PROJECT PERFORMANCE

Indicate the progress in the activities programmed for the quarter

| Result 1 | Baseline | Target | Indicator |
| --- | --- | --- | --- |
| Capacity for disaster risk reduction and adaptation to climate change enhanced within the Caribbean region is strengthened. | 56 RRMC established in Cuba but no others exist in the Caribbean | RRMCs Replicated in 6 countries in the region | South-south cooperation to increase institutional capacity to manage and reduce local risk through establishing local risk management centres in most vulnerable municipalities |
| Activity Result 1.1 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| RRMCs Replicated in 6 countries in the region | Target:Establish 3 to 5 centres Identification of specific areas of technical assistance required per pilot Documentation of best practices and lessons Quality Criteria: Number of Plans and agreements Signed Training Materials Developed Technical Assistance Provided Pilot Experience Systematized | Copy of Agreements Copy of Materials Reports; Project Progress Report Workshop Report; Publication; Progress Report | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 25% | 25% |  |  |
| Comments | All five pilot country agreements signed off and implementation has commenced; Training Materials for workshops developed; Reporting formats and guidance notes provided for all countries for documentation and systematization |
| Activitity Result 1.2 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| RRMC Training Workshops | Target: Guidelines for vulnerability and hazard mapping produced 4 -8 communities/ municipalities with improved DRM protocols and procedures, including data collection ; Replication Guidelines strengthened Quality Criteria: Number of participants in workshop Workshops Conducted Number & Quality of Evaluations | Project Progress Reports; Copy of Relatoria; Copy of Evaluations | Timeline (as perAWP) | x | x | x |  |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 5% | 25% |  |  |
| Comments | Orientation (12 participants) and Technical Training Workshops (11 participants) successfully conducted in collaboration with UNDP Cuba, Cuban Civil Defense, AMA and CUJAE. Toolkit and videos in development. |
| Activitity Result 1.3 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| BVI: RRMCs Replicated | Target: Pilot RRMC established Quality Criteria: Early Warning Point team established; Risk Profile Developed; Emergency communication Equipment & Use evident; Experience Shared | Contact data base of team; Copy of Risk Profile; Assessment Report; Training Agenda; Case Study, Press Release; Progress Reports | Timeline (as perAWP) |  | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement |  | 5% |  |  |
| Comments | Identified persons to be part of the Anegada Zonal Disaster Management Team (AZDMT), liaised with the BVI Red Cross on the incorporation of the VCA methodology into the training, identified the trainers; sourced quotations from the available vendors on Anegada to provide accommodation, land and sea transportation as well as catering for the training; initiated the compilation of the DDM housed background documentation for Risk Profile; initiated review of the emergency communications equipment required to effectively communicate with Anegada |
| Activitity Result 1.4 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Trinidad and Tobago: RRMCs Replicated | Target: Pilot RRMC established Quality Criteria: Number of participants in workshops; Numbers of EWPs established; GIS Implemented; RRMC equipment installed; Experience Shared | Workshop Report Progress Report GIS Assessments and Hazard Maps Atlas Report Case Study | Timeline (as perAWP) |  | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement |  | 5% |  |  |
| Comments | Series of technical planning meetings with project partners; TORS for EW and GIS Training Workshop completed; location of pilot early warning points (EWPs) confirmed and assessments completed; baseline site assessment including GIS Needs Assessment completed for local RRMC; procurement activities initiated for GIS and Early Warning (EW) components; Project mainstreaming within participating ministries and good degree of stakeholder buy-in to RRMC concept. |
| Activitity Result 1.5 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Guyana: RRMCs Replicated | Target: Pilot RRMC established Quality Criteria: Number of participants in workshops; RRMC equipment installed; Risk and Hazard Maps Disaster Risk Integrated into planning Experience Shared | Workshop Reports Evaluations Progress & Atlas Report Copy of Maps Copy of DRM Plan Case Study | Timeline (as perAWP) |  | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement |  | 0% |  |  |
| Comments | No report submitted yet from Guyana |
| Activitity Result 1.6 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Jamaica: RRMCs Replicated | Target: Pilot RRMC established Quality Criteria: Number of participants in workshops & forums; RRMC and EWP equipment installed; Risk and vulnerability Assessments Experience Shared | Workshop Reports Evaluations Progress & Atlas Report Copy of Risk Study Case Study | Timeline (as perAWP) |  | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement |  | 5% |  |  |
| Comments | Completed TORs for the engagement of GIS Technician, Drafting of TORs to procure storm surge modelling services has started, three (3) multidisciplinary stakeholder consultation conducted, GIS Software has been installed at the St. Catherine Parish Council, physical space identified to house RRMC |
| Activitity Result 1.7 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Dominican Republic (Santo Domingo): RRMCs Replicated | Target: Pilot RRMC established Quality Criteria: Number of participants in workshops; RRMC and EWP equipment installed; Risk and Hazard Maps Experience Shared | Participants Lists Progress & Atlas Report Copy of maps Case Study | Timeline (as perAWP) |  | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement |  | 5% |  |  |
| Comments | Planning meetings, MOU with local authorities; planning training activities with Luperon |
| Activitity Result 1.8 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Dominican Republic (Luperon): RRMCs Replicated | Target: Pilot RRMC established Quality Criteria: Number of participants in workshops; RRMC and EWP equipment installed; Risk and Hazard Maps Experience Shared | Participants Lists Progress & Atlas Report Copy of maps Case Study | Timeline (as perAWP) |  | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement |  | 5% |  |  |
| Comments | Visits to the sites where the early warning points will be established, definition of the Cuban technical assistance; evaluation of methodologies for the project; planning activities with La Victoria |

| Result 2 | Baseline | Target | Indicator |
| --- | --- | --- | --- |
| Improved management of knowledge on climate change adaptation and disaster risk reduction | Each Activity has baseline | See below for each activity result | Each activity result has indicator |
| Actividad Result 2.1 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Improved integration of DRR and CCA in Caribbean actors | Target: Caribbean stakeholders have access to information on DRR and CCA Quality Criteria: Site up and running thru the life of the project; number of users monitored; quantity of information downloaded; Number of group meetings; Review of best practice models in DRR and CCA integration | A report on the utility, functioning and potential of the web portal will be compiled and sent to the Project Manager; Meeting Minutes or Outcome documents, Project Progress Report | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 20% | 10% |  |  |
| Comments | The task was to support UNDP Virtual School in delivery of an agreed upon website. This task was delayed for several reasons: Mockups development and production took longer time than scheduled. The site design delivered did not fully adhered to CRMI’s stipulated graphic and usability requirements and to expected quality, and it had to be revised. The agreed upon May 6th deadline could not be met. UNDP Escuela Virtual requested more development time. The tasks were divided and new deadlines established: static pages by May 17th, and full site with Document Library by June 10th. New mockups were produced and agreed upon in order to move into development stage, but the pre–launch website produced at the 2nd set of deadlines also suffered of noticeable design and usability flaws, some of them already addressed and deemed solved during the design stage. Quality level was still below CRMI’s expectations. Social media sites (twitter, Facebook) being used; Teamworks space created for UNDP Focal Points in Pilot. Any other activities require further resource mobilization. |
| Activity Result 2.2 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Increased capacity building in emergent themes | Target: 2 workshops in emergent themes such as seismic risk or pre-planning for recovery; National pre-planning for recovery plans are developed in at least 2 Caribbean nations Quality Criteria: Number of participants; number of presenters | Workshop evaluations; project progress report; conference agenda | Timeline (as perAWP) |  | x | x |  |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 0% | 25% |  |  |
| Comments | Coordination an exploratory mission on seismic risk to Jamaica, conducted by Dr. Eric Calais, Professor of Geophysics at the Ecole Normale Superieure in Paris, France. CRMI and RSLAC CPR will be following up with UNDP Jamaica to consider next steps. Both PDNA Workshop planning underway; date of workshop is 17th – 19th July in Barbados. Any other activities require further resource mobilization. |
| Actividad Result 2.3 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Gender is integrated into national DRM and CCA structures, policies, plans and programs | Target: Support to roll-out of at least 1 distance teaching program with University in Caribbean; Gender Working Group supports 2013 action plan implementation; Gender checklist is disseminated to all NDMOs in the region; 1 training on gender integration in DRR is held with partners CDEMA Quality Criteria: Reviewed comments by GWG; # of participants providing feedback on online course; coordination of regional gender activities; checklist disseminated. | Emails; meeting minutes; written feedback; training agendas; outcome document; | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 20% | 25% |  |  |
| Comments | Collaboration with CIDA and CDEMA resulted in 2 day gender mainstreaming workshop (April 15th – 16th) and Discussion Paper. Online Gender Course completed in Feb 2013 and remains under review. Representation at CDM Regional Stakeholders meeting in May 2013; CRMI focus and contribution on gender mainstreaming. |
| Activitity Result 2.4 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Improved knowledge sharing and management in climate change adaptation practices | Target: 2 best practices, studies and guidelines in CCA in tourism, agriculture and coastal zone management; 5 countries supported in processes of reporting risk reduction (HFA); Experiences and practices shared between Pacific-Caribbean SIDS in meetings, platforms and documents Quality Criteria: Consultant hired; quality of information generated; HFA reporting complete | Consultant and Project Reports; UNISDR HFA Report & Stats; Assessment by other stakeholders | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 5% | 0% |  |  |
| Comments | Other activities require resource mobilization. |

| Result 3 | Baseline | Target | Indicator |
| --- | --- | --- | --- |
| Partnerships and Resource mobilization enhanced | CRMI II has commitment from UNDP for critical elements, but additional resources needed to realize the entirety of proposed project activities; Partnerships built or extended with key institutions including the INSMET in Cuba; CCCCC, CDEMA, UWI and others but CRMI still substantially a UNDP initiative | 2 Proposals developed and funded. Liaison with Governments and regional organizations Attendance at existing regional meetings for technical exchange Capacity & interest in project ownership evaluated Project transitioned to regional partner Project implemented on time and on budget with all outputs delivered Monitoring Administration and Execution | Resource Mobilization; Partnerships and Sustainability |
| Activity Result 3.1 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Resource mobilization plan developed and implemented | Target: 2 Proposals developed and funded. Liaison with Governments and regional organizations Quality Criteria: Management Committee meeting convened; Resource Mobilization Plan developed; CRMI activities resourced | Management Meeting Minutes; Existence of 2 plans; 2 proposals drafted; ATLAS and Project Manager reports; MOUs | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 10% | 10% |  |  |
| Comments | Draft Proposal for CIDA on gender circulated to stakeholders. |
| Activity Result 3.2 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Caribbean Participation in South-South Caribbean – Pacific Cooperation Sustained | Target: strengthen technical capacity in SIDS; Attendance at existing regional meetings for technical exchange Quality Criteria: Evidence of Exchange; networking | Joint Activities visible in Project reports | Timeline (as perAWP) | x | X | X | X |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 10% | 20% |  |  |
| Comments | Caribbean-Pacific South South project Phase II currently in planning phase; attended review session (April 2013) and planning meeting (June 2013). No funds allocated to this activity. |
| Activity Result 3.3 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| CRMI is managed | Target: Capacity & interest in project ownership evaluated Project transitioned to regional partner Project implemented on time and on budget with all outputs delivered Monitoring Administration & Execution Quality Criteria: Project is adequately administered; regional agency engaged in project activities; project resourced; final evaluation conducted. | Annual report emitted; ATLAS reports, minutes; funding resources; project documents developed; evaluation report | Timeline (as perAWP) | x | X | X | X |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 25% | 20% |  |  |
| Comments | CRMI II is fully operational; Intern integrated into team; UNDP CO DRR Focal Points supportive and supported; engagement with CDEMA to be strengthened. |

| Total of Achievement of Results Programmed |
| --- |
| % total of results achieved | Período |
|  | Q1 | Q2 | Q3 | Q4 |
|  | 17/25% | 12/25% |  |  |

III. Risk Log

| Type of Risk | Date of Identification | Description | Comments/Response |
| --- | --- | --- | --- |
| Financial | Jan 2013 and ongoing | Many activities are not under-resourced | Need to do more resource mobilization |
| Organizational | May 2013 | Institutional commitment with implementing partners | Meetings and overview of RRMC pilot; MOUs |
| Strategic | March 2013 and ongoing | Alignment with CDEMA for potential handover | Need to develop a plan and meetings to initiate this discussion |
| Political | April 2013 | Ministerial structures may lead to challenges in coordination and a lack of a shared understanding of the approach at a strategic level. | Consistent follow up by UNDP CO with key officials to provide information and help plan way forward. |
| Operational | May 2013 | Application of UNDP Financial Procedures (procurement; FACE form) for RRMC implementing partners Unclear definition of roles among partners Very short project time frame | COs working to explain procedures with partners Discuss and clarify roles with implementing partners and UNDP COs Acknowledge the short time line. Could request extension? |

IV. Problem Log

| Type | Date of Identification | Description | Comments/Response | Date of Solution |
| --- | --- | --- | --- | --- |
| Explaining and helping procurement with RRMC partners | May 2013 | Not all implementing partners are familiar with UNDPs procurement and financial procedures | Each CO has slightly different systems; each office takes lead with implementing partners | ongoing |
| Consistent information and reports from Pilot Countries | May 2013 | It can be difficult to track process and results in six countries. | Provide quarterly report formats for pilots and COs. | May 2013. |
| Communications | April 2013 | Need to ensure communication flow between CRMI team and UNDP COs to provide support, information and network | Newsletter; Skype calls with each team; Teamworks space; webinar idea | During the quarter |
| Website does not meet expectations; does not reflect UNDPs standards. | April 2013 | Design and functionality not adequate; deadlines pushed back 3 months | Continual guidance to EV partners. | ongoing |