**UNDP Romania**

ESF Project “The return of former convicts to the labour market and their integration in society”

Quarterly report (Q4) October – December 2013

Atlas # 78185

Within Activity 2 – Comparative study on social inclusion models we finalized the financial impact analysis of the future national reintegration strategy. Within Activity 4 - Develop and provide training package for prisoners” Education for reintegration in society” we finalized all 16 training sessions with detainees. Within the Activity 6 - Promoting social integration of former convicts we organized 2 regional seminars (Brasov and Bucuresti), 2 small scale seminars in Constanta and Sibiu and 2 seminars with potential employers, with the purpose of promoting the project and its objectives. We also finalized the second media and outdoor campaign that contributed to changing the perceptions and stereotypes regarding ex-convicts. To fully align the activities required for the implementation of the project with the information contained within the financing request, notifications to the financing contract were elaborated in collaboration with partners and submitted to the Programme management authority.