## Q1-2020 Plan and budget
Rwanda Meteorology Agency
Quarterly WORK PLAN
Project : Strengthening National and Local Disaster Risk Management Capacity, Resilience and Enhancing Preparedness and Early Warning System in Rwanda
Period: January - March 2020 (Year 2)
Intended Outcome as stated in the UNDAF/Country Programme Results and Resource Framework: Outcome 2: By 2023 Rwandan institutions and communities are more equitably, productively and sustainably managing natural resources and addressing climate change Outcome 4: By 2023 people in Rwanda, particularly the most vulnerable have increased resilience to both natural and man-made shocks and enjoy a life free from all forms of violence and discrimination
Applicable Output(s) from the UNDP Strategic Plan: Output 3 :Build resilience to shocks and crises
Project outcome : Increasing resilience to climate and natural disaster through evidence-based disaster preparedness and effective early warning system.
Output (cfr DRG4 Document) | Activities to deliver output | Detailed sequentiel activities | Indicators/baseline | Targets | TIMEFRAME (2020) |  |  | Implementing Partner | Quarter Budget |  |  |  | Reference/Annual budget (USD) | Planned | Balance |  | Planned
[5 empty] | Jan | Feb | Mar |  | TOTAL (RWF) | Total in USD | Inputs/Details | Source of Funds |  | Q1 | USD | FRW | Q2 | FRW | Adjustments | To request in USD | Equiv request in FRW |  | Total Qs
Project output 1: Institutions at national, district and community level have improved technical capacities to reduce risks, manage and respond to natural disasters and limit gender-differentiated impacts | 1.9 Support to developing and customizing Multi Hazard EWS and sharing best practices | Develop the Terms of Reference and start procurement process of a portal for the Meteogram | Automation process of forecast preparation | Automated Meteogram |  | X | X | METEO RWANDA | 0 | 0 |  | UNDP-TRAC |  | 0 | 0 | 0 | 8000 | 6976000 |  | 8000 | 6976000 |  | 6976000
Output 1 TOTAL | [8 empty] | 0 | 0 |  |  | 0 | #REF! | #REF! |  | #REF! |  |  | #REF! | 0
Output 3: Enhanced Multi Hazard Early Warning Systems (MHEWS) to enable effective preparedness, response and recovery | 3.3.Upgrade national disaster communication system and provide real-time early warnings | (i) Establishment of MHEWS and Implement and monitor the Common Alerting Protocol (CAP) and good practices in MHEWS | New Channel for weather warning dissemination | Common Alerting Protocol operational in Rwanda |  | X | X | METEO RWANDA | 6169900 | 6706.413 | Consulations Meetings | UNDP-TRAC |  | 0 | -6706.413 | -5847992.1739 | 5000 | 4360000 |  | -1706.413 | -1487992.1739 |  | 4681907.8261
| 3.4. Support to improve the generation of weather forecasts and dissemination | Continue the development of the Early Warning System (EWS) Impact Tables (Wind parameter) | Percentage of disasters from extreme weather warned 24 hours before occurring | Impact tables relevant to Disaster, Agriculture and Health validated |  | X | X | METEO RWANDA | 4388400 | 4770 | Hotel, DSA,Travel | UNDP-TRAC
| 3.4. Support to improve the generation of weather forecasts and dissemination | Development of the Terms of Reference and start Procurement of Equipment required for Radar displays at airports | Percentage of disasters from extreme weather warned 24 hours before occurring | 90% of extreme weather warned 24 hours before occurring | X | X | X | METEO RWANDA | 0 | 0 |  | UNDP-TRAC
| 3.4. Support to improve the generation of weather forecasts and dissemination | Organise climate data necessary to Produce Temperature and rainfall trending report | Percentage of disasters from extreme weather warned 24 hours before occurring | 90% of extreme weather warned 24 hours before occurring |  | X | X | METEO RWANDA | 0 | 0 |  | UNDP-TRAC
| 3.5.Support the improvement of a national climate database providing accurate data and information | Pay for the data backup service | Updates of the National Climate data bank | Safe and Uptudated data bank | X | X | X | METEO RWANDA | 6417489 | 6975.5315 | Service | UNDP-TRAC |  | 13000 | 6024.4685 | 5253336.513 | 36800 | 32089600 |  | 42824.4685 | 37342936.513 |  | 43760425.513
|  | Carry out stations maintenance (preventive and corrective) |  |  | X | X | X | METEO RWANDA | 14404836 | 15657.4304 | DSA, Travel and Spare parts | UNDP-TRAC
|  | Consult and prepare agreement to Connect Stations to Rwanda Energy Group (REG) Electricity |  |  |  | X | X | METEO RWANDA | 0 | 0 | Service | UNDP-TRAC
|  | Conduct data rescue |  |  |  |  | X | METEO RWANDA | 5597840 | 6084.6087 | Contractual | UNDP-TRAC
| 3.6 Support the setup of National Framework for Climate Services (NFCS) provided | Consultation meetings |  | Nomination of the NFCS members |  | X | X | METEO RWANDA | 4999280 | 5434 | Venue | UNDP-TRAC
| 3.7. Support the quality assurance capability | Develop and process tender to Develop and deploy the phase II version of the Volunteer Observer system under Internet Of Tthings (IOT) | Performance of volunteer weather stations | Daily data from All volunteer manned stations transmitted via the system |  | X | X | METEO RWANDA | 0 | 0 |  | UNDP-TRAC |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0
Output 3 TOTAL | [8 empty] | 41977745 | 45627.9837
Project Management | Pay project staff salaries | Salaries and benefits | % of project staff remunerated | Program manager and accountant | X | X | X | METEO RWANDA | 3823619 | 4156.1076 | Staff salaries | UNDP-TRAC
| Pay project staff communication fees | Airtime |  |  | X | X | X | METEO RWANDA | 190000 | 206.5217 | Staff communication costs | UNDP-TRAC
| Bank charges | Bank charges | Bank Account reports | Bank charges paid | X | X | X | METEO RWANDA | 9000 | 9.7826 | Periodic cost | UNDP-TRAC
Project Management | [8 empty] | 4022619 | 4372.412 |  |  | 0 | [6 empty] | 41118.0554 | 42830944.3391 | 35854944.3391
Grand Total | [8 empty] | 46000364 | 50000.3957 |  |  | 0 | [7 empty] | For Q1 and Q2
|  |  | Approved by: | [5 empty] | Submitted by | [11 empty] | 88831308.3391
|  |  | Stephen Anthony Rodriques | [5 empty] | GAHIGI Aimable
|  |  | UNDP Resident Representative | [5 empty] | Director General of Meteo Rwanda
Note on U22: Mr. Jean: Request for UNDP to process

## FACE Q1 request
Funding Authorization and Certificate of Expenditures | [5 empty] | UN Agency: | UNDP |  |  | Date: | 2020-01-15
Country: |  |  | RWANDA | [5 empty] | Type of Request:
Programme Code & Title: | [8 empty] | √ Direct Cash Transfer (DCT)
Project Code & Title: |  |  | 00117911 Strengthening National and Local Disaster Risk Management Capacity, Resilience and Enhancing Preparedness and Early Warning System in Rwanda | [5 empty] | □ Reimbursement
Responsible Officer(s): |  |  | GAHIGI Aimable/DG Meteo Rwanda | [5 empty] | Direct Payment
Implementing Partner: |  |  | METEO RWANDA
Currency: |  |  | Rwf |  | FINANCIAL REPORT |  |  |  | REQUESTS/AUTHORIZATIONS
Activity Description from AWP with Duration |  |  |  | Coding for UNDP, UNFPA and WFP | Authorised Amount | Actual Project Expenditure | Actual Project Expenditures accepted by Agency | Balance before 8/04/2019 | New Request & Amount | Authorised Amount | Outstanding Authorised Amount
2019-04-11
[5 empty] | A | B | C | D = A - C | E | F | G = D + F
Output Number00115031.: Improve technical capacities
Activity 2 Support Multi Hazard EWS - 1.9 Support to developing and customizing Multi Hazard EWS and sharing best practices - | [11 empty] | 0
Total 1 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
Output Number00115032 :Enhance multi hazard early warning systems | [11 empty] | 0
Activity 1 disaster coms sys&real-time EW: 3.3.Upgrade national disaster communication system and provide real-time early warnings ( | [11 empty] | 0
Activity 1 disaster coms sys&real-time EW: 3.3.Upgrade national disaster communication system and provide real-time early warnings | [11 empty] | 0
Activity 1 disaster coms sys&real-time EW: 3.3.Upgrade national disaster communication system and provide real-time early warnings | [11 empty] | 0
Activity 2 Improved Weather forecasts: 3.4 Support to improve the generation of weather forecasts and dissemination -(Validation of Development of Impact tables)_Venue Meeting |  |  |  | Fund: 04000 Donor: 00012 Account: 73125 | [7 empty] | 0
Activity 2 Improved Weather forecasts: 3.4 Support to improve the generation of weather forecasts and dissemination -(Development of Impact tables) _Travel_transport |  |  |  | Fund: 04000 Donor: 00012 Account: 72140 | [7 empty] | 0
Activity 2 Improved Weather forecasts: 3.4 Support to improve the generation of weather forecasts and dissemination -(Development of Impact tables) _DSA Mission |  |  |  | Fund: 04000 Donor: 00012 Account: 72140 | [7 empty] | 0
Activity 3 Improved National climate database: 3.5 Support the improvement of a national climate database providing accurate data and information - Climate data backup at National Data Centre AOS |  |  |  | Fund: 04000 Donor: 00012 Account: 72140 |  |  |  |  | 6417489 |  |  | 6417489
Activity 3 Improved National climate database: 3.5 Support the improvement of a national climate database providing accurate data and information - |  |  |  | Fund: 04000 Donor: 00012 Account: 72810 | [7 empty] | 0
Activity 3 Improved National climate database: 3.5 Support the improvement of a national climate database providing accurate data and information - Climate data rescue |  |  |  | Fund: 04000 Donor: 00012 Account:71405 |  |  |  |  | 5597840 |  |  | 5597840
Activity 3 Improved National climate database: 3.5 Support the improvement of a national climate database providing accurate data and information - Weather stations spare parts |  |  |  | Fund: 04000 Donor: 00012 Account: 72140 | [7 empty] | 0
Activity 3 Improved National climate database: 3.5 Support the improvement of a national climate database providing accurate data and information - Weather stations maintenance activities (Transport) |  |  |  | Fund: 04000 Donor: 00012 Account: 72140 | [7 empty] | 0
Activity 3 Improved National climate database: 3.5 Support the improvement of a national climate database providing accurate data and information - Weather stations maintenance activities (DSA) Mission |  |  |  | Fund: 04000 Donor: 00012 Account: 72140 | [7 empty] | 0
Total 3 | [8 empty] | 12015329
Output Number00115033. : Project Support
Activity1 Project Management - Salary for project staff (Support to PMU) Salary |  |  |  | Fund : 04000 Donor : 00012 Account : 71405 |  |  |  |  | 3823619
Activity1 Project Management - Project Staff Communication Cost |  |  |  | Fund: 04000 Donor: 00012 Account: 72425 |  |  |  |  | 190000
Activity1 Project Management - Bank charges |  |  |  | Fund: 04000 Donor: 00012 Account: 74510 |  |  |  |  | 9000
Total 4 |  |  |  |  | 0 | 0 |  |  | 4022619 |  |  | 12015329
Grand Total |  |  |  |  | 0 | 0 |  |  | 16037948 |  |  | 12015329
CERTIFICATION
The undersigned authorized officer of the above-mentioned implementing institution hereby certifies that:
√ | The funding request shown above represents estimated espenditures as per AWP and itemized cost estimates attached.
The actual expenditures for the period stated herein has been disbursed in accordance with the AWP and request with itemized cost estimates. The detailed accounting documents for these expenditures can be made available for examination, when required, for the period of five years from the date of the provision of funds.
Date Submitted: |  | 2020-01-15 |  |  | Name: | GAHIGI Aimable |  | Title: | Director General (Meteo Rwanda)
NOTES: | * | Shaded areas to be completed by the UN Agency and non-shaded areas to be completed by the counterpart.
FOR AGENCY USE ONLY:
FOR ALL AGENCIES | [8 empty] | FOR UNFPA USE ONLY
Approved by: | [6 empty] | Liquidation Information |  | New Funding Release
DCT Reference:
[7 empty] | CRQ ref. no., Liquidation ref. no. |  | Activity 1 | 0
[7 empty] | DCT Amount | 0 | Activity 2 | 0
Name: | _____________________________________________________ |  |  |  |  | 0 | Less:
[6 empty] | 0 | Liquidation
Title: | _____________________________________________________ |  |  |  |  | 0 | Amount | 0
0
Date: | _____________________________________________________ |  |  |  |  | 0 | Balance | 0 | Total | 0