## Sheet1
Project | Indicator | Baseline | Target | Scope of Work/Activities results | Focus of Data Collection/What to collect | Data Collection Tool | Source of Information/Target Institution | Location | Contact address/Focal Point Person of the IP | Beneficiary Feedback | Verification of activities | Tentative Starting Date | Tentative Ending Date | UNDP rresponsible Person
ACU | OUTPUT 1:Strengthened Effectiveness and Coordination through the SDRF Aid Architecture
| Indicator 1: Frequency of briefings to PWG core group members on the SDRF Operations manual | 0 | Meetings held to brief and educate PWG core members on the SDRF Operations Manual. | Meetings held to brief and educate PWG core members on the SDRF Operations Manual. | Review of meetings held | Interview | Progress Report, Consolidated tracking sheets, minutes of the meetings and participants list/AID Coordination Unit - OPM | Mogadishu | Mr. Muhumed Hussein: ACU Director - Office of the Prime Minister: muhumed.hussein@opm.gov.so : Please note thatthere is a new Director Muktar Ahmed Mohamed mmuktaar@gmail.com and WhatsApp: +254722289893. |  | Request for the SDRF Ops Manual. Carry out a short survey with pWG core members on how they perceive the Ops Manual and whether it is fit for purpose. |  | 2021-08-01 | Tendai Chabvuta: Tendai.Chabvuta@undp.org
| Indicator 2: Number of PWG meetings that comply with agreed core requirements for effective management and strategic focus | 0 | Each FMS reports back on challenges and progress made against components of PWGs AWPs which are relevant for them at least twice a year | PWG meetings held to strengthen the management and strategic focus of the ACU | Review of meetings held | Post meeting surveys | Progress Report, Consolidated tracking sheets, minutes of the meetings and participants list/AID Coordination Unit - OPM | Mogadishu | Mr. Muhumed Hussein: ACU Director - Office of the Prime Minister: muhumed.hussein@opm.gov.so : Please note thatthere is a new Director Muktar Ahmed Mohamed mmuktaar@gmail.com and WhatsApp: +254722289893. | Carry out 2 surveys for the Social Sector PWG held on 24 June and the Economic Pillar Working Group held on 29 June 2021. The survey will seek to assess a number of issues including whether meeetings were held, information shared on time, arisng matters were tabled and disucssed. | Collect reports from the different FMS, Review theissues tabled |  | 2021-08-01 | Tendai Chabvuta: Tendai.Chabvuta@undp.org
| Indicator 3: Number of SDRF SC meetings that comply with agreed core requirements for effective management and strategic focus | 0 | Somali Partnership Forum is organized twice a year in a successful manner | SDRF SC meetings held to strengthen management and strategic focus of meeting core MOPIED;ACU | Review of meetings held | Post meeting surveys | Progress Report, Consolidated tracking sheets, minutes of the meetings and participants list/AID Coordination Unit - OPM | Mogadishu | Mr. Muhumed Hussein: ACU Director - Office of the Prime Minister: muhumed.hussein@opm.gov.so : Please note thatthere is a new Director Muktar Ahmed Mohamed mmuktaar@gmail.com and WhatsApp: +254722289893. |  |  |  | 2021-08-21 | Tendai Chabvuta: Tendai.Chabvuta@undp.org
Output 2: National capacity for aid management and coordination enhanced
| Indicator 2: Standard Operating Procedures (SOPs) and/or guidance packages for improved aid management developed | 0 | At least 4 Standard Operating Procedures are documented and rolled out with clear role and responsibility distribution, with associated comprehensive guidance packages (when required) | SOPs developed | Finalised SOPs |  | SOPs/Guidance packages/ACU - OPM | Mogadishu | Mr. Muhumed Hussein: ACU Director - Offcie of the Prime Minister: muhumed.hussein@opm.gov.so> |  |  |  | 2021-08-01 | Pau Blanquer: Pau.Blanquer@undp.org
Project output 3: Monitoring NPS, MAF, UCS implementation
| Indicator 1: MOPIED and ACU have the capabilities to monitor NPS implementation | 0 | At least 1 aid coordination workshop organized per year in line with need | New Partnership for Somalia | Meeting held | KII | third party mechanism report, progress report, monitoring reports, hird party mechanism, Workshops reports | Mogadishu | Mr. Muhumed Hussein: ACU Director - Office of the Prime Minister: muhumed.hussein@opm.gov.so : Please note thatthere is a new Director Muktar Ahmed Mohamed mmuktaar@gmail.com and WhatsApp: +254722289893. |  |  |  | 2021-08-01 | Tendai Chabvuta: Tendai.Chabvuta@undp.org
| Indicator 2: Progress on MAF implementation regularly monitored and reported | 0 | 2 MAF progress reports produced reported per year | MAF principles are monitored as per government implementation and reported on. |  | Review of documents | MAF report | Mogadishu | Mr. Muhumed Hussein: ACU Director - Offcie of the Prime Minister: muhumed.hussein@opm.gov.so> |  |  |  | 2021-08-01 | Tendai Chabvuta: Tendai.Chabvuta@undp.org
| Indicator 3: Aid flows analysed and reported regularly | 1 | 1 | Aid flows from different agencies to the government through different funding streams are analysed and reports produced | Aid flows information | Review of documents | Aid flow reports | Mogadishu | Mr. Muhumed Hussein: ACU Director - Office of the Prime Minister: muhumed.hussein@opm.gov.so : Please note thatthere is a new Director Muktar Ahmed Mohamed mmuktaar@gmail.com and WhatsApp: +254722289893. | Carry out survey with key donor and government partners on the 2020 Auid flows report and how it has been received by stakeholders. | Verify if the 2020 report has been finished and released. |  | 2021-08-01 | Tendai Chabvuta: Tendai.Chabvuta@undp.org
Digital Transformation | Project output 1:Future Ready project finalized and approved
| Indicator 1: ﻿Number of mobile start-ups set up, experimented and successful out of the total number of startups piloted | 5 start-up enterprises are in incubation | at least 5 new start-ups developed and functional. | Start ups set up and are registered in Somalia by Somalis. | Start ups set up | KII | Project reports | Mogadishu and Garowe |  |  |  |  | 2021-08-01 | Abdiwahab Ali: Abdiwahab.Ali@undp.org
Project output 2:Establishment of the Crowdfunding eco-system
| Indicator 1: ﻿Number of crowdfunding campaigns designed and launched | 1 | 3 crowdfunding campaigns launched | Campaigns will be launched to deal with different development problems affecting Somalia in different regions of the country through any UNDP project supported by this project. | The set activities to be reviewed | KII |  | Mogadishu and Garowe |  |  | Were these activities carried out. What did they achieve, when were they held and what were the results? |  | 2021-08-01 | Abdiwahab Ali: Abdiwahab.Ali@undp.org
| Indicator 2: Number of S – S partnership engagements established | 0 | At least 4 S - S partnership engagements attended | South - South partnership engagements wil be pursued and followed up on for implementation. | S-S partnerships established | Review of documents | S- S partnership agreements and monitoring of trips and exchanges carried out | Mogadishu and Garowe |  |  | Any S- S cooperation activities carried out, what were the results? If not, why were these not carried out? |  | 2021-08-01 | Abdiwahab Ali: Abdiwahab.Ali@undp.org
| Indicator 3: Crowdfunding Project Document finalized | Initial draft made | To be finalized and receives donor financing | Crowdfunding project document to be drafted by a consultant. | Project document | Review of documents | Project document | Mogadishu and Garowe |  |  | Has the document been finalised and did it meet the requirements of the prodoc for UNDP? |  | 2021-08-01 | Abdiwahab Ali: Abdiwahab.Ali@undp.org
Project output 3: Establish the Citizen Engagement Platform
| Indicator 1:% of participants reporting knowledge and awareness regarding the Consul platform | 0 | at least 90% of participants able to articulate the aims of the Consul platform | A Consul platform will be created by the project. This indicator seeks to measure the number of people who will be utilising the Consul platform for different uses. | Information on the Consul platform. How it works. | KII | Campaigns on the Consul as well as reports generated | Mogadishu and Garowe |  |  |  |  | 2021-08-01 | Abdiwahab Ali: Abdiwahab.Ali@undp.org
| Indicator 2: Number of TOT and business development training | 0 | 4 national organisations will have received TOT training and started business development using the platform | The number of trainings on business (Training of local Municipality team on Consul adminstration) | Contents of the trainings and the attendees. | Interviews with attendees and Kis. | Post meeting surveys; training materials | Mogadishu and Garowe |  | Interview trainees that attnded the ToT sessions on the usefulness of the trainings, the quality of the trainers and materials used. |  |  | 2021-08-01 | Abdiwahab Ali: Abdiwahab.Ali@undp.org
| Indicator 3: Civic Engagement Project Document finalized | Draft project developed during 2019 | Full project document finalised and socialized among the donor community | Civic Engagement project document is drafted and finalised by an international consultant | Document finalized |  | Project document | Mogadishu and Garowe |  |  | Has the document been finalised and did it meet the requirements of the prodoc for UNDP? |  | 2021-08-01 | Abdiwahab Ali: Abdiwahab.Ali@undp.org
Planning | Project output 1:Federal Planning Framework
| Indicator 2: # of FMS strategic plans aligned to NDP 9; | 0 FMS strategic plans aligned to NDP 9 | 5 FMS strategic plans aligned to NDP 9; | Statistics Framework supported | Review of Government Documents when plans have been finalised | Desk study | Government Documents /MOPIED | Mogadishu | MOPIED |  | Collect 5 FMS strategic plans and review them to see how well they are aligned to the NDP9 |  | 2021-08-01 | Omar Isack: Omar.isack@undp.org
| Indicator 3: Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Not yet established,law approved. | Somali National Bureau of Statistics established and adequately staffed. | Support to SNBS | Review the work and operations of the SNBS as per the agreement in the LOA | KII | Government statute establishing new office and other documents / MOPIED | Mogadishu | MOPIED | Interview staff working at the SNBS - verify TORs, number of staff working there against target staff members and what they have delivered between Jan - June 2021. |  |  | 2021-08-01 | Omar Isack: Omar.isack@undp.org
Project output 3:SDG Alignment
| Indicator 1:# of Guidelines for SDG localization finalized | Guidelines not yet made; | Guidelines for SDG localization in Somalia developed and finalized | Guidelines for SDG localisation | Are the SDG Guidelines localised? | Documents review | Review of Government Documents when plans have been finalised/MOPIED | Mogadishu | MOPIED |  | Review documents and assess whether they have been localised or not? |  | 2021-08-01 | Omar Isack: Omar.isack@undp.org
| Indicator 2:SDG reporting arrangements developed and operationa | No consolidated structure for reporting on progress of SDG implementation exists | A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia | Structures for SDG reporting set up | Is there a structure and template for SDG reporting? | KII | SDG report finalised and reviewed /MOPIED | Mogadishu | MOPIED |  | Is this structure now available? Review the template and check for reports. |  | 2021-08-01 | Omar Isack: Omar.isack@undp.org
| Indicator 3:Planning capacity of MOPIC Somaliland for SDGs | SDG Unit in MOPIC Somaliland recently established | SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Staffing and unit set up | Review of documents | KII | Staff reports / MOPIED | Mogadishu | MOPIED |  | Interview members of the SDG Unit and asssess what work they have been doing aligned to the SDG reporting. |  | 2021-08-01 | Omar Isack: Omar.isack@undp.org
| Indicator 4: Longer Term Support arrangements to Planning, M&E and Statistics | zerpo | Develop longer term support in planning on federal and FMS level | Review the modalities of support given to the government | what kind of support has been offered and what is it achieving? | KII | Project report by the government /MOPIED | Mogadishu | MOPIED |  |  |  | 2021-08-01 | Omar Isack: Omar.isack@undp.org