UNDP South Sudan

2014 Annual Work Plan

| Project name | Amount |
| --- | --- |
| HIV/AIDS Prevention and Care Programme in South Sudan: Global Fund for AIDS, TB and Malaria (GFATM) Round 4 | US$6,693,491 |

| Hon. Aggrey Tisa Sabuni Minister Ministry of Finance, Commerce, Investment and Economic Planning Government of the Republic of South Sudan | Balázs Horváth Country Director UNDP South Sudan Programme |
| --- | --- |
| Signature: | Signature: |
| Date: | Date: |

United Nations Development Programme

South Sudan

Annual Work plan 2014

| Project Title: | HIV Prevention and Care Programme for South Sudan: GFATM Round 4 |
| --- | --- |
| UNDAF Outcome(s): | Key service delivery systems are in place laying the groundwork for increased demand |
| Expected CP Output(s): | Health sector infrastructure expanded, and pharmaceutical supply chain systems transition to Government management. |
| Implementing Partner: | UNDP |
| Responsible Parties: | Ministry of Health (MoH), South Sudan HIV/AIDS Commission (SSAC), Catholic Diocese of Torit (CDoT), International HIV/AIDS Alliance (IHAA), WHO, UNICEF (and UNAIDS as counterpart) |

Agreed by Ministry of Finance, Commerce, Investment and Economic Planning, Government of South Sudan:

Agreed by UNDP:

# Annual Workplan

Year 2014:

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Treatment, care and support services for people and families living with HIV/AIDS maintained Baseline: 62.5% (2012) Indicator: percentage of patients on ART who have a stable or improving clinical outcome using at least one of the two wellness criteria (CD4 and clinical indicators) Targets: 70% Baseline: TBD Indicator: Estimated percentage of child infections from HIV-infected women delivering in the past 12 months - estimated mother-to-child transmission Targets: TBD Baseline: 4,426 Indicator: Number of eligible adults and children who are currently receiving ART (age and by regimen) Targets: 10,546 Baseline: 9,343 Indicator: Number of adults and children enrolled in HIV care currently receiving co-trimoxazole prophylaxis Targets: 14,281 Baseline: 203 Indicator: Number of Health Care Providers and PLHIV trained on new national consolidated ART guidelines (disaggregated by cadre, training type) Targets: 100 Baseline: 44 Indicator: Number of Laboratory technicians trained on Laboratory diagnostics Targets: 44 Baseline: 22 Indicator: Number of people trained on Supplies management Targets: 22 Baseline: 22 Indicator: Number of Data management staff in HIV/AIDS data collection tools Targets: 22 Baseline: 82% Indicator: Percentage of ART facilities submitting complete and timely reports per national guidelines Targets: 95% Baseline: 14% Indicator: % and Number of Health facilities providing ART/HIV care with functional community care teams Targets: 68% Baseline: 717 Indicator: Number and Percentage of HIV-positive pregnant women who received anti-retrovirals therapy to reduce the risk of mother-to-child transmission Targets: 720 Baseline: 0 Indicator: Number and Percentage of Infants born to HIV-infected women who receive a virological test for HIV within 2 months of birth Targets: 264 Baseline: 62.5% (2012) Indicator: Percentage of adults and children with HIV known to be on treatment 12 months after initiation of antiretroviral therapy (HIV-16) Targets:70% Related CP outcome: Key service delivery systems are in place laying the groundwork for increased demand. | 1. Activity Result: Prophylaxis for opportunistic infections, and Antiretroviral therapy and monitoring 1.1. Activity action: Conduct annual training for PLHIV support persons and CBOs volunteers on psychosocial support/home care | x | x | x | x | UNDP in support of IHAA | GFATM/30078 | 72600 (Grants) 72300 (Materials & Goods) 73405 (maintenance of other office Equipment) 61100 (Staff Cost) GMS (7%) Activity 1 Subtotal | US$ 1,208,760 US$ 2,215,065 US$ 157,980 US$ 1,455,553 US$ 352,615 US$ 5,389,973 |
|  | 1.2. Activity action: Support to community mobilisation and home visits by PLHIV, NSA & CBOs | x | x | x | x | UNDP in support of IHAA | GFATM/30078 |  |  |
|  | 1.3. Activity action: Organize quarterly review meetings with providers of home-based care & psychosocial support (PLHIV and CBOs) | x | x | x | x | UNDP in support of IHAA | GFATM/30078 |  |  |
|  | 1.4. Activity action: Support remuneration of PLHIV groups (10 persons PLHIV per site) to provide adherence support, counselling and act as liaisons between ART sites and community | x | x | x | x | UNDP in support of IHAA | GFATM/30078 |  |  |
|  | 1.5. Activity action: Community based activities - Project Support Unit HR cost | x | x | x | x | UNDP in support of IHAA | GFATM/30078 |  |  |
|  | 1.6. Activity action: Community based activities - Project Support Unit Supervision site visits | x | x | x | x | UNDP in support of IHAA | GFATM/30078 |  |  |
|  | 1.7. Activity action: Organization and provision of mother-to-mother support groups | x | x | x | x | UNDP in support of UNICEF | GFATM/30078 |  |  |
|  | 1.8. Activity action: Provision of allowances for mother-to-mother support groups | x | x | x | x | UNDP in support of UNICEF | GFATM/30078 |  |  |
|  | 1.9. Activity action: Manage early infant diagnosis (EID) and Establish Referal system for Early Infant Diagnosis | x | x | x | x | UNDP in support of UNICEF | GFATM/30078 |  |  |
|  | 1.10. Activity action: PMTCT Project Support Unit cost | x | x | x | x | UNDP in support of UNICEF | GFATM/30078 |  |  |
|  | 1.11. Activity action: Remuneration for staff at ART sites managed by CDoT under category C | x | x | x | x | UNDP in support of CDOT | GFATM/30078 |  |  |
|  | 1.12. Activity action: Remuneration for PMTCT staff | x | x | x | x | UNDP in support of CDOT | GFATM/30078 |  |  |
|  | 1.13. Activity action: BCC for PMTCTand ART | x | x | x | x | UNDP in support of CDOT | GFATM/30078 |  |  |
|  | 1.14. Activity action: Supervision site visits by 2 persons/quarter | x | x | x | x | UNDP in support of CDOT | GFATM/30078 |  |  |
|  | 1.15. Activity action: Operational cost of project unit | x | x | x | x | UNDP in support of CDOT | GFATM/30078 |  |  |
|  | 1.16. Activity action: Remuneration of Project Manager | x | x | x | x | UNDP in support of CDOT | GFATM/30078 |  |  |
|  | 1.17. Activity action: Remuneration for staff at ART sites managed by WHO under category A | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.18. Activity action: Running cost for ART sites managed by WHO under category A | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.19. Activity action: Remuneration for staff at ART sites managed by WHO under category A | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.20. Activity action: Running cost for ART sites managed by WHO under category A | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.21. Activity action: Remuneration for staff at ART sites managed by WHO under category A | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.22. Activity action: Running cost for ART sites managed by WHO under category C | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.23. Activity action: Training on the new consolidated clinical guideline (IMAI) | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.24. Activity action: WHO operational costs to support MoH capacity strengthening | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.25. Activity action: WHO supervision costs to support MoH capacity strengthening | x | x | x | x | UNDP in support of WHO | GFATM/30078 |  |  |
|  | 1.26. Activity action: MoH Zonal Directorate Human Resources | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.27. Activity action: Number of ART sites operational (Incentives for 6 Gov ART Sites in Category C (Rumbek, Bentiu, Lui, Aweil, Magwi, Renk) | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.28. Activity action: Running cost for 6 Gov ART Sites in Category C (Rumbek, Bentiu, Lui, Aweil, Magwi, Renk) | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.29. Activity action: Number of ART sites operational (Incentives for 5 Gov ART Sites in Category A managed by UNDP (Yambio, Yei, Ezo, JTH, Wau) | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.30. Activity action: Running cost for 5 Gov ART Sites in Category A managed by UNDP (Yambio, Yei, Ezo, JTH, Wau) | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.31. Activity action: Number of ART sites operational (Incentives for 5 Gov ART Sites in Category B managed by UNDP (Bilfam, Kajokeji, Torit, Bor, Malakal) | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.32. Activity action: Running cost for 5 Gov ART Sites in Category B managed by UNDP (Bilfam, Kajokeji, Torit, Bor, Malakal) | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.33. Activity action: Conduct two 3-day refresher training for Dispensers/Pharmacists (1 participant per ART site) on Drug-Supplies Management | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.34. Activity action: Conduct four 2-day refresher training for 12 Laboratory Technicians (4x12) in Juba Teaching Hospital on ART Treatment Monitoring (incl CD4, viral load) | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.35. Activity action: Conduct two 2-day refresher training for 25 Data Assistants (2x25) (One participant per ART site) on ART/HIV-care Patient Monitoring | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.36. Activity action: Conduct follow up and clinical mentoring visits to ART sites by MoH Clinical Mentoring teams (3-day visits per site on quarterly basis) | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.37. Activity action: Purchase 3 motorcycles for conducting community care activities | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.38. Activity action: MoH Central level staff costs | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.39. Activity action: MoH administrative / operational costs | x | x | x | x | UNDP in support of MOH | GFATM/30078 |  |  |
|  | 1.40. Activity action: Maintenance contract for 22 CD4 machines | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.41. Activity action: First line ARVs procured for PLWHA | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.42. Activity action: Second line ARVs | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.43. Activity action: Paediatric ARVs procured for PLWHA | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.44. Activity action: PMTCT ARV prophylaxis procured for PLWHA | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.45. Activity action: Co-trimoxazole procured for PLWHA | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.46. Activity action: OI Treatment procured for PLWHA | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.47. Activity action: CD4 consumables for PARTEC machines procured for comprehensive HIV treatment services | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.48. Activity action: Health equipment: PIMA machines procured for comprehensive HIV treatment services | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.49. Activity action: Lab Reagents procured for comprehensive HIV treatment services | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.50. Activity action: Supplies for ART Health Facilities for comprehensive HIV treatment services | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.51. Activity action: PCR reagents procured for comprehensive HIV treatment services | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.52. Activity action: Laboratory Reagents for OI's, STI's and other HIV/ART monitoring procured for comprehensive HIV treatment services | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.53. Activity action: Testing mothers for HIV for 2 years procured for comprehensive HIV treatment services | x | x | x | x | UNDP | GFATM/30078 |  |  |
|  | 1.54. Activity action: Estimated Freight, Insurance & QA (10%+6%) to ensure timely delivery of HIV supplies | x | x | x | x | UNDP | GFATM/30078 |  |  |

| Output 2: Management of TFM Strengthened Baseline: 32 (2013) Indicator: PMU staff maintained Targets: 32 Baseline: 24 Indicator: Field visits for supportive supervision Targets: 24 Related CP outcome: Key service delivery systems are in place laying the groundwork for increased demand. | 2. Activity Result: Strengthened management of the HIV TFM Project 2.1. Activity action: UNDP PMU allocated staff cost 2.2. Activity action: PSM (SCM)- distribution + transport for 2 Yrs 2.3. Activity action: Procurement of equipment for the PMU 2.4. Activity action: Field visits for supportive supervision, 4 people per trip and 2 trips every month (tkt $400+ DSA $73/day for 5 days one visit every month) 2.5. Activity action: Utilities (fuel, insurance, internet, maintenance, communication) 2.6. Activity action: Office supplies | x | x | x | x | UNDP | GFATM/30078 | 75105 (Facilities & Admin – Implement) 61100 (Staff Cost) GMS (7%) Activity 2 Subtotal Contribution (office common security): 1%: Reimbursement Cost (to UNDP for support services):1%: GMS (7%) | US$ 244,149 US$ 851,433 US$ 76,691 US$ 1,172,273 US$ 61,329 US$ 61,329 US$ 8,586 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | US$ 6,693,491 |

# Management Arrangements

The project will be managed by UNDP under UNDP’s Direct Implementation DIM) Modality in close collaboration with the MoH. The project will operate under the oversight of a Project Board which includes the Chair Person of CCM-SS (Country Coordinating Mechanism South Sudan), the Country Director for UNDP and the Director General of Community and Public Health. The Project Board will meet on a quarterly basis. The Project Board is responsible for the overall direction and management of the project and has responsibility and authority for the project within the remit of the project mandate.  The Project Board approves all major plans and authorises any major deviation from agreed plans.  It is the authority that signs off the completion of each year of the project, as well as authorises the start of the next year.  It ensures that required resources are committed, and arbitrates on any conflicts within the project, negotiating solutions to any problems between the project and external bodies.

The Project Board is ultimately responsible for assuring that the project remains on course to deliver the desired outcome of the project as defined in the Project Document.  According to the size, complexity and risk of the project, the Project Board may decide to delegate some of this Project Assurance responsibility.

The overall project organisation structure is as follows:

The Global Fund project is part of the Human Development and Inclusive GrowthUnit and is supported by other Units such as Operations and Programme and Partnership Support Unit (PPSU).  In South Sudan, UNDP has been serving as the Principal Recipient (PR) of last resort since 2004 for five GFATM grants.  The PR works in collaboration with national and international partners involved in the fight against HIV and AIDS.  The Global Fund resources are additional to national resources as well as resources from other partners.

The PR has a number of Conditions Precedent and Special Terms and Conditions that should be fulfilled during various stages of the project Grant Agreement.  These Conditions Precedent and Special Terms and Conditions are outlined in Sections B and C of the Annex A to the Grant Agreement between the Principal Recipient and the Global Fund.

The Country Coordination Mechanism (CCM) performs the oversight function as well as monitoring and evaluation of the Global Fund projects in the country.  Different stages of project implementation such as project amendments, phase two continuation requests, and no cost extension requests, are cleared by and submitted to the Global Fund through the CCM.

The Local Fund Agent (LFA)serves as Global Fund’s representative in the country.  It provides oversight to project implementation, conducts verification of the programmatic and financial reports and makes recommendations to the Global Fund with regards to project progress and disbursement of funds.

The Project management Unit ( PMU)of the PR has four major functions detailed below.

Project Management: This is comprised of Project Managers and Project Analysts. The Project Manager is fully responsible for the overall coordination of the project activities.  The Project Manager and the Analyst work in close collaboration with national counterparts and other stakeholders to implement the project.

Procurement and Supply Chain Management: This team is headed by a Procurement and Supply Chain Management Specialist and supported by a Procurement Analyst and an Associate. Under the grant agreement signed between UNDP as PR and the Global Fund, all procurement activities are exclusively done by the PR.  The PR is responsible for the quantification of all drugs and supplies.  It is also responsible for proper storage of these drugs and other consumables and timely distribution to various health facilities.  The PR conducts support supervision to the health facilities and trains the health care providers in the rational use of drugs.

Finance Management: This team is made up of a Finance Specialist, an Analyst, two Finance Associates, and one Administrative Assistant.  The finance team is responsible for budget management.

Monitoring and Evaluation: This team is composed of an M&E Specialist and two Analysts based at central locations.  The team is responsible for monitoring of project activities, review and verification of data and preparation of progress reports to the donor.

The PR will subcontract five agencies (Sub-Recipients – SRs) to execute this project as follows:

Community and Public Health Directorate, Ministry of Health, Republic of South Sudan (MoH-RSS)

The Ministry of Health (MoH) of the Republic of South Sudan (RSS) will be responsible for managing incentives for health workers at 16 government-run health facilities.  Additionally, the MoH-RSS will maintain key project staff directly involved in the implementation of activities for Continuity of Services (COS) for essential and lifelong treatments such as Antiretroviral Treatment (ART) services and Prevention of Mother to Child Transmission (PMTCT) services.

WHO

WHO will continue providing technical support to the MoH-RSS in managing the ART programme as well as clinical mentorship to all 22 ART sites. WHO will maintain key technical staff to carry out the clinical mentorship and will also be responsible for managing incentives for health workers at six (6) NGO-run health facilities.

UNICEF, Catholic Diocese of Torit (CDoT), and International HIV/AIDS Alliance (IHAA)

UNICEF and CDoT will continue managing the Prevention of Mother to Child Transmission (PMTCT) programme covered under Continuity of Services (COS), including early infant diagnosis.  The PMTCT programme is implemented at 37 health facilities across South Sudan.  UNICEF and CDoT will maintain key staff to manage the programme.  The International HIV/AIDS Alliance (IHAA) is a new SR to management activities related to the involvement of People Living with HIV/AIDS (PLWHA).

Audit arrangements

Article 7b, points i. and ii. of the Special Terms and Conditions of the Grant Agreement between UNDP and the Global Fund state that:

- The Principal Recipient shall have annual financial audits conducted of project expenditures.  Subject to the approval of the Global Fund, which approval shall not be unreasonably withheld, the Principal Recipient shall select an independent auditor to conduct the audits and set the terms of reference pursuant to which they shall be conducted.  The cost of such special audit shall be borne by the Programme.

- Should the Global Fund have reason to request a special purpose audit on the use of Global Fund resources, UNDP agrees to be responsible for: (i) securing the appointment of a mutually agreed independent auditor; and (ii) preparing mutually agreed audit Terms of Reference which reflect, as necessary, circumstances giving rise to the Global Fund’s request for said audit.  The cost of such special audit shall be borne by the Programme.

The PR is also required to conduct annual audits of the SRs.

Agreement on intellectual property rights and use of logo on the project’s deliverables

The Principal Recipient must enter into an agreement with the Global Fund prior to using the Global Fund logo.  The logo must be used in accordance with the terms and conditions of that agreement.

# Monitoring Framework And Evaluation

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Quality Management table below.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted, a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, a Project Progress Reports (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format available in the Executive Snapshot.

- A project lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project

- A Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events

Annual reports

Annual Reports: Article 13, b. (2) states that Not later than 45 days after the close of each fiscal year of the Principal Recipient, the Principal Recipient shall submit to the Global Fund, in form and substance satisfactory to the Global Fund, an annual financial and programmatic monitoring report (in addition to the six-monthly reports) covering the preceding fiscal year.

Annual Project Review: Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment.  This review is driven by the Project Board (the Country Coordinating Mechanism) and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes.

Additionally, in accordance with the Standard Terms and Conditions in the grant agreement between the Principal Recipient and the Global Fund, the project will be monitored as follows:

Six monthly reports

Article 13, b. (1) states that “not later than 45 days after the close of each reporting period of the specific programme grant agreement, the Principal Recipient shall submit to the Global Fund, in form and substance satisfactory to the Global Fund, a periodic report on the Programme. The report shall reflect (i) financial activity during the reporting period in question and cumulatively from the beginning of the Programme until the end of the reporting period; and (ii) a description of progress towards achieving the agreed-upon milestones set forth in Annex A of the Grant Agreement.  The Principal Recipient shall explain in the report any variance between planned and actual achievements for the period in question”.

Project Evaluation

The Global Fund projects are subject to two types of evaluations. Midterm evaluations are conducted for projects transitioning from phase I to phase II.  Final evaluations are conducted at the end of phase II of the project. The HIV Round 4 grant is in phase II of project implementation and a final evaluation is planned at the end of the project.

Quality Management for Project Activity Results

| OUTPUT 1: Transitional Funding Mechanism (TFM): Treatment, care and support services for people and families living with HIV/AIDS maintained |
| --- |
| Activity Result 1 (Atlas Activity ID) | Treatment, care and support services for people and families living with HIV/AIDS maintained | Start Date: 1 Jan 2014 End Date: 31 Dec 2014 |
| Purpose | To provide treatment, care and support services for people and families living with HIV/AIDS maintained |
| Description | 70% of patients on ART who have a stable or improving clinical outcome using at least one of the two wellness criteria (CD4 and clinical indicators) Estimated percentage of child infections from HIV-infected women delivering in the past 12 months - estimated mother-to-child transmission 10,456 eligible adults and children who are currently receiving ART (age and by regimen) 14,281 adults and children enrolled in HIV care currently receiving co-trimoxazole prophylaxis 100 health Care Providers and PLHIV trained on new national consolidated ART guidelines (disaggregated by cadre, training type) 44 Laboratory technicians trained on Laboratory diagnostics 22 people trained on Supplies management 22 Data management staff in HIV/AIDS data collection tools 95% of ART facilities submitting complete and timely reports per national guidelines 68% of Health facilities providing ART/HIV care with functional community care teams 720 HIV-positive pregnant women who received anti-retrovirals therapy to reduce the risk of mother-to-child transmission 264 Infants born to HIV-infected women who receive a virological test for HIV within 2 months of birth Percentage of adults and children with HIV known to be on treatment 12 months after initiation of antiretroviral therapy (HIV-16) Estimated percentage of child infections from HIV-infected women delivering in the past 12 months - estimated mother-to-child transmission |
| Quality Criteria | Quality Method | Date of Assessment |
| 70% of patients on ART who have a stable or improving clinical outcome using at least one of the two wellness criteria (CD4 and clinical indicators) | Progress reports | March, June, September, December 2014 |
| Estimated percentage of child infections from HIV-infected women delivering in the past 12 months - estimated mother-to-child transmission | Facility reports | March, June, September, December 2014 |
| 10,456 eligible adults and children who are currently receiving ART (age and by regimen) | Facility reports | March, June, September, December 2014 |
| 14,281 adults and children enrolled in HIV care currently receiving co-trimoxazole prophylaxis | Facility reports | March, June, September, December 2014 |
| 100 health Care Providers and PLHIV trained on new national consolidated ART guidelines (disaggregated by cadre, training type) | Facility reports | March, June, September, December 2014 |
| 44 Laboratory technicians trained on Laboratory diagnostics | Progress reports | March, June, September, December 2014 |
| 22 people trained on Supplies management | Facility reports | March, June, September, December 2014 |
| 22 Data management staff in HIV/AIDS data collection tools | Facility reports | March, June, September, December 2014 |
| 95% of ART facilities submitting complete and timely reports per national guidelines | Facility reports | March, June, September, December 2014 |
| 68% of Health facilities providing ART/HIV care with functional community care teams | Facility reports | March, June, September, December 2014 |
| 720 HIV-positive pregnant women who received anti-retrovirals therapy to reduce the risk of mother-to-child transmission | Progress reports | March, June, September, December 2014 |
| 264 Infants born to HIV-infected women who receive a virological test for HIV within 2 months of birth | Facility reports | March, June, September, December 2014 |
| Percentage of adults and children with HIV known to be on treatment 12 months after initiation of antiretroviral therapy (HIV-16) | Facility reports | July 2014 |
| Estimated percentage of child infections from HIV-infected women delivering in the past 12 months - estimated mother-to-child transmission | Facility reports | July 2014 |

| Activity Result 2 | Strengthening management of the HIV TFM Project | Start Date: 1 Jan 2014 End Date: 31 Dec 2014 |
| --- | --- | --- |
| Purpose | To strengthen management of the HIV TFM Project |
| Description | Recruit staff Liaise and report to CCM Conduct Annual Review Conduct Quarterly Reviews against Annual Work Plan Conduct field monitoring trips |
| Quality Criteria | Quality Method | Date of Assessment |
| Regular reports to CCM | Documented interactions with CCM | March, June, September, December 2014 |
| Quarterly and annual reviews against annual work plan | Quarterly review meeting reports | March, June, September, December 2014 |
| Field monitoring trips conducted | Quarterly field monitoring reports | March, June, September, December 2014 |

# Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document”.

Annex 1. RISK LOG

| Project Title: Transitional Funding Mechanism for HIV/AIDS | Award ID: | Date: October 2013 |
| --- | --- | --- |
| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| 1 | Delayed functionality of Central PCR Reference Laboratory. | 2013 | Operational | Lack of functional PCR lab means targets for HIV testing of infants within 2 months of birth cannot be achieved. P = 4 I = 3 | Actions taken to counter: i) use of in-country mechanical engineers (UNOPS contracted) to accelerate the process; ii) follow up with Global Fund for the fund; iii) Follow up with procurement unit and UNDP HQ | Global Fund Coordinator, Director of Diagnostics | Project Manager | October 2013 | No change. |
| 2 | The full implementation of the project ended on 30 November 2011, and it is the main source of funding for HIV/AIDS interventions in South Sudan and the only source of funding for ART services | Early 2011 | Operational | From 1 December 2011 onwards, no new clients will be enrolled in PMTCT, pre-ART and ART programme. The programme will only maintain existing clients. Additionally all other programmes such as BCC,VCT, STIs, Blood Safety and Universal precautions have come to an end. P =4 I = 3 | MDTF and PEPFAR provided one-off supplies of ARVs and OIs in 2013 but there is need for partners and government to commit to providing supplies in 2014 and beyond. Additionally HIV test kids provided by PEPFAR are only for PMTCT sites, leaving the general population without test kits except at functional PEFAR VCT sites which are mainly in Western Equatorial. | Project Manager, HIV/AIDS Unit | Project Manager | October 2013 | No change |
| 3 | TB/HIV collaborative activities weakened | October 2013 | Financial Operational | Given the phasing out of a TB/HIV Round 5 project, most activities supported by this project will come to an end. Thus, HIV testing will decline because of lack of test kits, provision of CPT may be compromised, and health education activities may also decline because of lack of funds. P =3 I = 2 | Countermeasures: i) Liaise with other donors to provide the basic kits and CPT; ii) coordinate with state HIV coordinators to strengthen collaborative works. | Project manager, NTP manager | Project manager | October 2013 | No change |

Annex 2. PROJECT STAFF COSTS

|  | Name of Position | Location | International/ | Status | Months | Proforma Cost | Shared to this project | Budgeted in AWP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | National |  |  |  |  | Output | Activity Result |
| 1 | Coordinator – NOD | Juba | National | In post | 12 | 107,511.72 | 53,756 | Improved coordination and management of GFATM projects | Technical support and advisory services to GFATM |
| 2 | Project Manager HIV – P3 | Juba | International | In post | 12 | 238,286.00 | 238,286 | Overall project management and enhanced project delivery | Technical support to the overall project management |
| 3 | Project Specialist NOC | Juba | National | In post | 12 | 40,973.42 | 40,973 | Overall project management and enhanced project delivery | Technical support to the overall project management |
| 4 | M&E Specialist – P3 | Juba | International | In post | 12 | 238,286.00 | 119,143 | Enhanced M&E capacity, delivery, and data quality | Technical support to the M&E system |
| 5 | Finance Specialist – P3 | Juba | International | In post | 12 | 238,286.00 | 119,143 | Enhanced Finance capacity, delivery and quality reporting | Technical support, finance services and delivery |
| 6 | Pharmaceutical Management Specialist | Juba | International | In post | 12 | 269,346.00 | 134,673 | Enhanced Pharmaceutical capacity and pharmaceutical management | Procurement and Supply Chain Management services |
| 7 | M&E Analysts (2) – NOB | Juba | National | In post | 12 | 40,973.42 | 7,113 | Enhanced M&E capacity and data quality at State, County and Facility level | M&E functions and delivery |
| 8 | Procurement and Contracting Analyst – NOB | Juba | National | In post | 12 | 40,973.42 | 13,658 | Manage PSM capacity and delivery | Procurement services |
| 9 | Finance Analyst – NOB | Juba | National | In post | 12 | 40,973.42 | 13,658 | Support to finance capacity, delivery and quality reporting | Finance services |
| 10 | Finance Associates (2) – G6 | Juba | National | In post | 12 | 23,590.98 | 7,864 | Support to finance capacity, delivery and quality reporting | Finance services |
| 11 | Procurement Associate – G6 | Juba | Vacant | In post | 12 | 23,590.98 | 7,864 | Support PSM capacity and delivery | Procurement services |
| 12 | Asset Associate – G6 | Juba | National | In post | 12 | 23,590.98 | 7,864 | Manage assets at PR, SR and facility level | Assets management |
| 13 | Admin Associate – G6 | Juba | National | In post | 12 | 23,590.98 | 7,864 | Support office administration services | Administrative support |
| 14 | Drivers (5) – G2 | Juba | National | In post | 12 | 72,757.22 | 24,252 | Transport and maintenance of vehicles | Transport and maintenance |
| 15 | Security guards (3) – G2 | Juba | National | In post | 12 | 27,618.66 | 9,206 | Staff security, property and premises | Security services |
| 16 | Cleaner – G2 | Juba | National | In post | 12 | 9,206.22 | 3,069 | Cleaning services to premises | Cleaning services |
| 17 | Supply Chain Associates (2) – G6 | Juba | National | In post | 12 | 47,181.96 | 15,727 | Support Supply Chain Management | Supply Chain Management |
| 18 | Supply Chain Assistants (3) – G5 | Juba | National | In post | 12 | 43,654.33 | 14,551 | Support Supply Chain Management | Supply Chain Management |
| 19 | Warehouse Driver | Juba | National | In post | 12 | 14,551.44 | 4,850 | Logistics | Logistics |
| 20 | Warehouse Cleaner – G2 | Juba | National | In post | 12 | 23,757.66 | 7,919 | Cleaning services to premises | Cleaning services |
|  | TOTAL CHARGED TO THE PROJECT | 851,433 |  |  |

# Text boxes

Brief Description

The HIV/AIDS Prevention and Care project aims to strengthen a coordinated South Sudan response to HIV/AIDS by building capacity at the Central, State and County levels, and supporting the scale up of comprehensive HIV/AIDS services. The major objectives are to: (i) improve knowledge and practice of HIV and Sexually Transmitted Infections (STI) preventative measures by the general adult population, youth and vulnerable population subgroups during 2005-2010: (ii) develop and expand treatment, and care and support services for people and families living with HIV/AIDS: and (iii) build the capacity of the South Sudan HIV/AIDS Commission (SSAC), NGOs and local institutions to effectively manage and monitor HIV/AIDS programmes. The previous project ended on 30 November 2011 after five (5) years and four (4) months of implementation. From 1 December 2013, the project implementation activities are under the Continuity of Services (COS) for essential services and lifelong treatment such as Antiretroviral Treatment (ART) and Prevention of Mother to Child Transmission (PMTCT). In 2014, the project will continue focusing on implementing activities for Transitional Funding Mechanism to support people and families living with HIV/AIDS.

2014 AWP budget:                   US$ 6,693,491

Total resources required:         US$ 6,693,491

Total allocated resources:        US$ 6,693,491

- Regular:	           _________

- Other:

  - Global Fund

  - US$ 6,693,491

  - Government        _________

Unfunded budget:                      US$ 0

In-kind Contributions:

Programme Period:	     2012-2016

Programme Component:     Poverty Reduction

and Millennium

Development Goals

Atlas Award ID:	                   00061397

Start Date:		      1 January 2014

End Date :	                   31 December 2014

PAC Meeting Date:			______________

Management Arrangements:		DIM [most projects

in South Sudan are Direct Implementation]

GFATM Coordinator

Project Board

Senior Supplier

UNDP, Donor (Global Fund)

Executive

Ministry of Health - CCM

Senior Beneficiary

Directorate of Preventive Health Services: MoH-RSS

Project Assurance

(Team Leader/Programme Specialist)

Project Support - (M and E, Procurement, and Finance Team)

Project Organisation Structure

Project Manager and Project Specialist

Round 4 HIV/AIDS