Suriname

United Nations Development Programme

Country: Suriname

Initiation Plan

Project Title:	Strengthening resilience of vulnerable communities and Ecosystems in Suriname

Expected CP Outcome(s):	1.4:  An enhanced sustainable natural resources planning and management system is in place.

Initiation Plan Start Date:	          	__________26 Oct 2011___________________________

Initiation Plan End Date:	         	________26 Jul 2012_____________________________

Implementing Partner:	Ministry of Labour, Technological Development and Environment

Agreed by UNDP:

# Purpose

The proposed project seeks to reduce the vulnerability of communities and ecosystems in specific coastal areas of Suriname to increased sea level rise and altered rainfall pattern by focusing on two key issues of coastal erosion, flooding and related water management.

The Netherlands Climate Assistance Programme (NCAP): With regard to climate studies, Suriname has executed the second phase of the NCAP. The first phase was carried out in 1996-1999. The main areas covered in this phase include a first assessment of the vulnerability of the coastal zone and a greenhouse gas inventory. The main priority to be addressed in NCAP-phase 2 is the linkage between climate change and livelihood. Adaptation measures will be also elaborated to mitigate the adverse impacts of sea level rise and the ongoing human intervention on the coastal ecosystems located north of the districts Paramaribo and Wanica. The NCAP-2 project makes recommendations on the sectors Ecology, Geomorphology, Water resources, Agriculture, Socio-economics and Human Health regarding their possible future development, including possible expansion (growth) of the urban areas within the coastal districts Paramaribo and Wanica.

Studies clearly indicate that Suriname will be severely impacted by sea level rise and increased wave action and the associated coastal erosion and flooding. The climate change projections for Suriname also show that rainfall, rainfall is decreasing in general form and will become more irregular. Much of the precipitation will fall in sharp bursts, creating the risk of flooding, while there will be extended period of drought.

Suriname has the highest percentage of national population affected (8%) because of greater impacts on urban areas (4% inundated). Estimated total agricultural land loss was highest in Suriname (4%).

Suriname is therefore looking to strengthen its capacity to maintain current ecosystem functions and services as well as build resilience to be better placed to respond to the projected impacts from increased climate variability and climate change.

The project will seek to reduce these vulnerabilities by spearheading ecosystem based adaptation by restoring and strengthening ecosystem functionality, and enhancing ecosystem resilience

to secure and enhance two critical ecosystem services (coastal protection and water regulation/flood attenuation). The project will invest in up scaling mangrove reforestation, building on mangrove Afforestation techniques that have been piloted in Suriname and adapting these by reflecting on best practices from the world, integrated water resource management, aligning hard infrastructure measures with ecosystem resilience building for enhanced benefits to most disadvantaged and vulnerable communities, ecosystem based adaptation will be integrated into the country’s development planning and financing framework, further ensuring that environmental impact assessments and management measures for coastal development include the restoration and protection of ecosystems providing these critical ecosystem services, and moreover generate funding to assure sustainability.

| Project Components | Expected Outcomes |
| --- | --- |
| 1. Ecosystem-based adaptation approaches along the coastlines of the Suriname wider North Paramaribo/Wanica and Coronie to reduce the vulnerability of communities and ecosystems to increased climatic events and climate change induced sea level rise and surge in wave action. | Enhanced ecosystem integrity and functionality covering a total area of % hectares in the coastal area of Suriname providing for coastal protection and water management / flood management services to the coastal communities. |
| 2. Ecosystem-based adaptation approach to enhancing water management in North Paramaribo/ Wanica and Coronie. | Vulnerable coastal communities from North Paramaribo/ Wanica and Coronie and where appropriate and relevant benefit from enhanced ecosystem water management. |
| 3. Ecosystem based adaptation mainstreamed into National planning and financing. | Government of Suriname, civil society actively support and benefit from the enhanced ecosystem regulation services (coastal protection, water management / flood attenuation). |

# Expected Outputs

| IP activities | Budget code | Budget USD |
| --- | --- | --- |
| Conduct a thorough baseline review and determine key ecosystem variables pertaining to the ecosystems’ coastal protection and water regulation and provisioning services and associated conditions, identify/verify site specific drivers that cause negative impacts in the targeted landscapes, and develop adequate baseline and targets for measuring improvement in ecosystem resilience; | 71200 | 5,000 |
| Elaborate baseline and additionality reasoning for project components and carry out detailed analysis to quantify environmental, social and economic benefits projected through the project activities, considering opportunity costs and timing of materialization of the benefits | 71200 | 7,500 |
|  | 71300 | 5,000 |
| Conduct a thorough cost-effective analysis, comparing the costs and benefits of the project outcomes, outputs and resource allocation with measurable outcomes, and costs of other possible options, in order to validate costs, benefits and project cost effectiveness | 71200 | 10,000 |
|  | 71300 | 5,000 |
| Conduct results and resource framework and stakeholder meetings on project development and a learning session on climate change adaptation for officials of the relevant Government and national entities | 72100 | 5,000 |
|  | 71600 | 2,500 |
| Project Concept note and project document endorsed by the Designated National Authority | 71200 | 10,000 |

# Management Arrangements

# Monitoring

| Date | Output | Means of verification |
| --- | --- | --- |
| 25-10-11 | LPAC held | LPAC report |
| 03–11-11 | International Consultant contracted | IC contract |
| 03-11-11 | Initial background information submitted to international consultant | List of documents |
| 07-11-11 | Detailed work plan prepared | Work plan |
| 10-11-11 | 1st Draft Concept note submitted | Concept note |
| 15-11-11 | Stakeholder Workshop | Workshop report |
| 14-11-11 | In country mission of International consultant completed | Mission and meeting reports |
| 24-11-11 | Additional information required submitted to international consultant | List of documents |
| 12-01-12 | Concept note completed and submitted | Communication to AF |
| 05-02-12 | Feedback AF Incorporated into concept note | Revised concept note |
| 21-02-12 | First Draft PRODOC with Annexes Submitted to UNDP CO, UNDP/RTA Panama, AF DNA | Draft prodoc |
| 05-03-12 | Second Draft PRODOC with Annexes Submitted to UNDP CO, UNDP /RTA Panama, AF DNA | Draft prodoc |
| 19-03-12 | Final Draft PRODOC and CEO Request Submitted to UNDP CO, UNDP/GEF/RTA Panama, AF DNA | prodoc / Submission letter |

# ANNUAL WORK PLAN

Year:

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1 Baseline: no ongoing Adaptation Fund initiatives Indicators: Concept note and project document for AF Board available & submitted Targets: 1st Concept note submitted by Jan 2012 and project document for AF Board submitted by March 2012 to AF Related CP outcome: | 1. Activity Result - Conduct a thorough baseline review and determine key ecosystem variables pertaining to the ecosystems’ coastal protection and water regulation and provisioning services and associated conditions, identify/verify site specific drivers that cause negative impacts in the targeted landscapes, and develop adequate baseline and targets for measuring improvement in ecosystem resilience; |  |  |  |  | Min. ATM | UNDP | 71200 | 5,000 |
|  | 2. Activity Result -Elaborate baseline and additionality reasoning for project components and carry out detailed analysis to quantify environmental, social and economic benefits projected through the project activities, considering opportunity costs and timing of materialization of the benefits -Activity action |  |  |  |  | Min ATM | UNDP | 71200 71300 | 7,500 5,000 |
|  | 3. Activity Result - Conduct a thorough cost-effective analysis, comparing the costs and benefits of the project outcomes, outputs and resource allocation with measurable outcomes, and costs of other possible options, in order to validate costs, benefits and project cost effectiveness- Action |  |  |  |  | Min ATM | UNDP | 71200 71300 | 10,000 5,000 |
|  | 4. Activity Result -Conduct results and resource framework and stakeholder meetings on project development and a learning session on climate change adaptation for officials of the relevant Government and national entities-Action |  |  |  |  | Min ATM | UNDP | 72100 71600 | 5,000 2,500 |
|  | 5. Activity Result - Project Concept note and project document endorsed by the Designated National Authority |  |  |  |  | Min ATM | UNDP | 71200 | 10,000 |
| TOTAL |  |  |  |  |  |  |  |  | 50,000 |

# Footnotes

SNC project document 2009, p. 6

An Overview of Modelling Climate Change Impacts in the Caribbean Region with contribution from the Pacific Islands, page 40

Ibid, Page 20

Ibid, Page 26

# Text boxes

Brief Description

The objective of this initiation plan is to develop a Concept note (proposal) and comprehensive project document in support of the government of Suriname towards reducing the vulnerability of populations of the coastal zone, specifically those in the target area of North Paramaribo/Wanica (Pomona) and Coronie. This by strengthening resilience of coastal ecosystems and communities in North Paramaribo/Wanica (Pomona) and Coronie through interventions that strengthen the ecosystem ability to respond to current stresses due to past and current national and international anthropogenic actions as well as stress from increased climatic events and climate change. Foreseen interventions such as mangrove reforestation and improved water management will strengthen ecosystem resilience to maintain if not enhance their coastal protection services and water regulation services.

Total resources required           	50,000

Total allocated resources:	_________

- Regular			50,000

- Other:

  - Donor		_________

  - Donor		_________

  - Donor		_________

  - Government	_________

Unfunded budget:		_________

In-kind Contributions		_________

Programme Period:		2008 - 2011

CPAP Programme Component:

Atlas Award ID:			______________

PAC Meeting Date		25 Oct 2011

Project Organisation Structure

Project Support

Project Assurance

(UNDP)

Senior Supplier

UNDP / UvS

Executive

ATM

Senior Beneficiary

GOS

Project Board

Project Manager