## Sheet2
EXPECTED OUTPUTS | PLANNED ACTIVITIES ( List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME |  |  |  |  | RESPONSIBLE PARTY | BUDGET
|  | 2021 | [5 empty] | Budget Description | Amount (USD)
|  | March | April | May | June | July
Output 1: Enhanced Coordination Capacity for response and recovery from floods and landslides | 1.1 Provide technical support to national and Tinkhundla structures for coordination and information sharing | X | X | X | X | X | UNDP, NDMA | 75700 Training, Workshop and conferences | 2142.86
[7 empty] | UNDP, NDMA | 72400 Communications and audio-visual equipment | 5785.71
[7 empty] | UNDP, NDMA | 71300 Local Consultants | 24285.72
1.2 Provide technical assistance to facilitate data collection and monitoring, and information analysis, sharing and management,
| 1.3 Sensibilization and establishment of mechanisms on Disaster Data (Reporting storage analyses and management) |  | X | X | X | X | UNDP, NDMA | Equipment and furniture (72200) | 15928.56
[7 empty] | UNDP, NDMA | 71300 Local Consultants | 10714.29
[7 empty] | UNDP, NDMA | 72400 Communications and audio-visual equipment | 1000
Output 2. Multi-sectoral assessment to determine early recovery needs response measures. | 2.1 Facilitate joint assessments to determine specific community recovery needs to enhance resilience of the affected population. | X | X | X |  |  | UNDP, NDMA | Workshops and Training (75700) | 3000
[8 empty] | 71600 Travel | 1000
| 2.2 Support early recovery planning processes and the development of multi-sectorial early recovery plan for transition from relief to early recovery and mid-term recovery and reconstruction | X | X | X |  |  | UNDP, NDMA | Workshops and Training (75700) | 2000
[7 empty] | UNDP, NDMA | 71300 Local Consultants | 32142.86
[7 empty] | UNDP, NDMA | 71600 Travel | 1000
[7 empty] | UNDP, NDMA | 72400 Communications and audio-visual equipment | 1000
Subtotal | [8 empty] | 100000
TOTAL BUDGET