# Quarterly Project Progress Report from Implementer to Post.

(Refer to project bidding form/contract when completing this report. Focus on activities completed in the quarter, outputs achieved and progress towards project purpose)

# Basic Information

| Fund/Programme | Arab Partnership Fund |
| --- | --- |
| AP Impact Area | Securite Sectore Reform- SSR |  | Public Voice |  | Good Governance | X | Inclusive and sustainable economic growth |  |
| Project Title | A Court of Accounts making a difference in the citizens lives |
| Name of Implementer | Court of Accounts |
| Quarter this report covers (mm/yy-mm/yy) | 07/15-09/15 |
| Planned start Date | 01 April 2015 | Actual start date | 30 May 2015 |
| Planned end Date | 31 March 2015 | Actual end date | 30 May 2016 |
| Please explain any variance in planned start and end dates | Delays occurred during the selection phase in order to: Precise more the performance indicators, the M&E Plan and the multi-year budget, due to the specificities of the project results and the necessary coordination with the Court of Accounts, who is the implementing partner; Endorse the new project by the Local Project Appraisal Committee (LPAC) and to ensure the ownership of the process which must remain with the national institution. Celebrate the signature of the new agremment and the start of the project through a signing ceremony under the patronage and in the presence of His Excellency the Ambassador of United Kingdom, His Eexcellency the First President of the Court of Account, a representant from the Ministry of Foreign Affairs and the Resident Representative of UNDP. |

- Summary

One paragraph summarising the key achievements and challenges faced to date (not a description of activities). Include any changes to project design (outputs, activities, budgets, duration etc.)*

Efforts to start the implemention of the project was deployed during the last three months especially for a rapid mobilization of high quality experts in charge of the structing mission of the project. Until there, we finalised three important Termes of References (ToR) and the bid processes related to (i) the Strategic Plan, (ii) the job analysis schedule (competencies) and (iii) the Information System. Moreover, a competitive process for the selection of the project manger was finalised. Given the urgency of finalizing the draft law governing the mandate of the Court and its operations, the project was able to ensure an effective mediator role and to provide prompt technical assistance. As a result of the negotiations between high levels of Government and the magistrates of the Court of Accounts, the draft law was finalized and submitted to the Assembly of the Representatives of People.

* Please consult your Embassy Project Officer when any significant changes are required.

- Activities

| Original Activities (Include ALL the planned activities for this quarter, from your bidding form/contract)* | Brief description of progress this quarter | Planned Budget for the activity this quarter (from activity based budget) | Actual Expenditure this quarter |
| --- | --- | --- | --- |
| 1. Support and facilitation of the dialogue with the national stakeholders. | Selection process of high level experts to support to dialogue on the Strategic Plan is finalized and contract was signed | 10 483,95 USD | 538,78 USD |
| 3. Organise a national workshop to present the final version of the strategic plan & organic law to the strategic partners of the Court. | Draft of organic law was discussed as part of a conference of some 70 magistrates of the central and regional levelS; | 12 251,51 USD | 107,14 USD |
| 6. Organise internal retreats and complete a job analysis and description of the main Court position. | Selection process is finalized and contract was signed. Briefing internal sessions was organised in order to ensure the better organisation of the mission. | 36 283,33 USD | 0 |
| 10. Design and implement Information System facilitating access and management of the Court file in a secure and efficient way. | Selection process is finalized and contract was signed. | 195 081,81 USD | 0 |
| * Include and highlight any new/changed activities **Add more lines here, as necessary. | Totals | 254 100,60 USD | 645,92 USD |

| Explain any significant variance in planned and actual expenditure (including changes in start/end date): If there is significant variance (>10%) between plans and actual spend you must submit a new Activity Based Budget |
| --- |
| As mentioned above, a delay in the launch of the project activities was recorded. This explains well the small amounts spent to date. However, three important ToR were finalized and contracts have been signed which has allowed the selected experts to start working . therefore, several payment commitments were established generating future major expenses in the months of November and December. Other activities will also be launched which will also lead to other commitments for the same period. |
| Activities Planned for the next quarter |
| Activity: | Budget (for activity): |
| 1. Support and facilitation of the dialogue with the national stakeholders. | 9 945,17 USD |
| 2. Organise a high-level round table inviting European Court of Accounts on the ISC role. | 32 984,85 USD |
| 3. Organise a national workshop to present the final version of the strategic plan & organic law to the strategic partners of the Court. | 12 144,37 USD |
| 5. Organise a press conference for the launch of the strategic plan of the Court. | 4712,12 USD |
| 6. Organise internal retreats and complete a job analysis and description of the main Court position. | 36 283,33 USD |
| 10. Design and implement Information System facilitating access and management of the Court file in a secure and efficient way. (expert fees) | 195 081,81 USD |
| Based on waht you have/have not done this quarter, does your Project Activity Based Budget need to be updated? If YES, please attche an updted ABB. | YES/NO ( Delete as appropriate) YES |

- Progress against Purpose and Outputs

| Output 1*:Strengthened strategic vision and dialogue | On track |
| --- | --- |
| Milstones (for curent quarter) | Indicators (for curent quarter) | Baseline (for curent quarter) | Target (for curent quarter) | Actual | Narrative on Progress (for curent quarter) | Rang Red/Amber/Geen (please put a rang in this box) |
| New Strategic Plan covering the 2015-2019 period elaborated and adopted by the Court by 31/12/2015 | A new strategic plan is discussed with the partners and in place | The first strategic plan produced for the 2009-2011period. An update was elaborated during the transitional period (2012-2014) | New 5-year Strategic Plan | A draft of the strategic Plan is finalised | After finalizing the stage of expert selection and contract signature, an internal briefing for the launch was organized in order to plan the mission and to ensure its successful implementation. On this basis and after meeting His Excellency the First President of the Court of Accounts, the expert will transmit the final schedule of the mission. | Green |
| New Court’s Organic Law adopted in conformity of the constitution and international standards (by 31/12/2015). | Publication of the law in the Official Gazette | The new constitution confirmed the status of the Court as an independent judicial institution. An organic law is required. | New Court’s Organic Law adopted | A draft law is discussed, finalised and submitted to the Parliament | After successufeul negotiations between high levels of Government and the magistrates of the Court of Accounts, the draft law was finalized and submitted to the Assembly of the Representatives of People. | Green |
| Output 2*: Strengthened organisational structure | On track |  |
| Milstones (for curent quarter) | Indicators (for curent quarter) | Baseline (for curent quarter) | Target (for curent quarter) | Actual | Narrative on Progress (for curent quarter) | Rang Red/Amber/Geen (please put a rang in this box) |
| A job analysis schedule (competencies) elaborated (by 31/12/2015) and diffused within the staff of the Court (by 15/03/2016) | Detailed job analysis and competency frameworks elaborated from scratch. | The Court elaborated a Human Resources Strategy establishing a new performance culture. | New performance-based Human Resources management and organisational structures on a revision of the job description and staff allocation | The methodology note for the mission is finalised and discussed internaly. | After finalizing the stage of expert selection and contract signature, an internal briefing for the launch was organized in order to plan the mission and to ensure its successful implementation. On this basis and after meeting His Excellency the First President of the Court of Accounts, the expert will transmit the final schedule. | Green |
| New Information System designed and implemented (by 15/03/2016) | The percentage of case files and records that meet standards of accuracy, completeness, currency, and accessibility. | The current paper management system limited the Court performance. The decentralization reform call for a more appropriate and integrated system. | New Information System to manage the Court’ files in a secure and efficient way. | The methodoly note was submitted and the mission will start by next week. | The slection of company is already finalized and contract has been just signed. An internal working group was formed at the court of accounts and will be the direct counterparts of experts. | Green |

# *From your bidding form/contract.  (Increase lines as necessary to include all project Outputs).

# Risk

| Update your risk register for this project. Include the risks mentioned in your project bidding form and any new risks. (Report on any changes to level of fiduciary, delivery, context, reputational or stakeholder risks) For each risk compare the original likelihood and impact (at the start of the project) with the risk now. |
| --- |
| Risk basline | Likelihood (H/M/L) | Impact (H/M/L) | How are you managing these risks? |
|  | Original | Now | Original | Now |  |
| 1. The short duration of mission implementation impacts negatively the participation of the magistrates and their involvement in the finalisation of the structuring documents. |  | M |  | H | Through the different missions, the approach adopted should be oriented to a focus groups in order to ensure the situation analysis and a sort of retreat regouping the differents groups to validate the output producted. |
| 2. Unavailability of the magistrates of the Court and their regional dispersion. | M |  | M |  | Organisation of internal retreat for the exercise that need a collective working session (job analysis schedule). |
| 3. Retirement of part of the staff of the Court | M |  | L |  | Organisation of the exercise of preserving the internal memory before the month of June 2015 |
| 4. Instability in the political situation in the country and risk to have government changes during the year | L |  | L |  | The project will coordinate with the technical units at the Ministry levels. |

- Impact examples :

Please provide us withe some impact examples (max 3 per quarter)

Involvement of the court staff in the launched activities

- Context

Has there been a change in the level of support and engagement from local partners or host government? Please briefly describe. Any necessary additional background or commentary?

No changes, a serious support and engagement still being expressed by the court top management, presidents of chambers and magistrates . More over, the project is being more and more a permanent element of the agenda of theG 17 periodical meeting, the highest level of decision making of the court of account.

- Lessons Learned

| What Lessons have you identified so far, and what have you done as a result (max 3 per quarter) |
| --- |
| Lesson Identified | Action Taken |
| We are in a stage where the project just started and approaches are preliminary. However and thanks to the specificity and the importance of this project, the progress of activities to achieve the objectives will bring lessons that serve as references in future projects. |  |

- Sustainability

Outline any steps taken to ensure sustainability

The involvement of young motivated magistrates increases their ownership and ensure sustainability of achievements such as the new organic law and strategic plan

Signature…………………………………………………..				Name………………………………………………………..

Position…………………………………………………….. 				Date…………………………………………………………..

Please now pass this to the Project Officer in the Post to complete the final section:

- Project Officer Assessment and Comments

Please now pass this to the Project Officer in the Post to complete the final section.

| Project Officer / Post Comments |
| --- |
| Are you satisfied that this report is a fair and accurate description of progress to date? | Yes / No (delete as appropriate) |
| What checks have you done on progress? | Yes / No |
| Do you believe the Project is still viable? | Yes / No |
| Is the plan of activities for the next period realistic and appropriate? | Yes / No |
| If the answer to any of these questions is NO, please provide details |  |
| Signature |  |
| Name |  |
| Position |  |
| Post |  |
| Date |  |