ANNEX I

TABLE 1- ORIGINAL BUDGET  AND WORKPLAN TABLE IN THE PROJECT DOCUMENT

Year: 2011 - 2012

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
| And baseline, indicators including annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Stocktaking and impact analysis of Turkey’s Progress towards UNCSD between 1992 – 2010. Baseline: Sectoral Policy assessment completed under the project titled as: Integrate Sustainable Development Policies into Sectoral Policies. 9th Development Plan. Indicators: • Consultation meetings report. • Number and level of stakeholders participation in the consultation meetings. • Number of parameters and cross sectoral matrix considered in the final reporting. Related CP outcome: | 1. Multi-stakeholders consultation process to assess Turkey’s progress towards UNCSD between 1992 – 2010. Activity 1.1: Prepare baseline/discussion documents. Activity 1.2: Develop the methodology to be used during the consultation meetings. Activity 1.3: Consultation meetings with relevant government ministries and key stakeholders. Activity 1.4: Identification of relevant organizations and identifying experts to facilitate the process. Activity 1.5: A series of multi-stakeholder meetings in central and selected regions, comprising plenary sessions with brief expert introductions and roundtable discussions incorporating diverse perspectives and interactive debates; and breakout sessions devoted to assess successful experiences and initiatives. Activity 1.6: Identification of legislative developments and activities (projects/ activities/ new procedures) of government and/or private sector to analyze level of implementation of Johannesburg Plan of Implementation. Activity 1.7: Draft the content of the final report. Activity 1.8: Draft an outcome document based on the recommendations of the consultation meetings. | 1 | 1 | 1 |  | SPO / UNDP | SPO | 71300 - Local Consultants | 0 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 16.000 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 10.000 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 44.961 |
|  |  |  |  |  |  |  |  | 72200 - Equipment and Furniture | 690 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 540 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 1.200 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.950 |
|  |  |  |  |  |  |  |  | 73200 - Premises Alterations | 1.000 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 0 |
|  |  |  |  |  |  |  |  | Total | 76.341 |
| Output 2: Support to World Bank Policy Paper and Capacity Building on Green Growth Baseline: Sectoral reports developed under the project titled as: Integration of Sustainable Development Principles into Sectoral Policies. Indicators: • Number of sectors selected for the Green Growth analysis. • Number of reference reports consulted for data collection. Related CP outcome: | 2. Sustainable Development related data collected and harmonized. Methodology to assess potential green growth alternatives for Turkey identified and analysis completed. Activity 2.1: Data Collection to support the WB policy paper preparation Activity 2.2: Collection of background information documents and reports to serve the WB policy paper and ICSA Report preparations. Activity 2.4: Multi-stakeholder meetings, interviews, soliciting of information, and background and follow up work. | 1 | 1 |  |  | SPO / UNDP | SPO | 71300 - Local Consultants | 24.000 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 10.667 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 2.500 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 3.329 |
|  |  |  |  |  |  |  |  | 72200 - Equipment and Furniture | 0 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 360 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 800 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.300 |
|  |  |  |  |  |  |  |  | 73200 - Premises Alterations | 0 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 0 |
|  |  |  |  |  |  |  |  | Total | 42.955 |
| Output 3: Enhance national capacity for RIO+20. Baseline: NCDS capacity assessment report prepared under the project titled as: Integration of Sustainable Development into Sectoral Polices. Indicators: • Number of decision makers participated in the preparatory meeting. • Number of capacity building discussion meetings organized for the Rio +20 upcoming event. Related CP outcome: | 3.Five Capacity Building activities delivered to decision makers before the Rio +20 event. At least 20 Rio +20 delegation members prepared for the mission. |  | 1 | 1 | 1 | SPO / UNDP | SPO | 71300 - Local Consultants | 15.000 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 16.000 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 5.000 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 38.456 |
|  |  |  |  |  |  |  |  | 72200 - Equipment and Furniture | 0 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 540 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 1.200 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.950 |
|  |  |  |  |  |  |  |  | 73200 - Premises Alterations | 0 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 0 |
|  |  |  |  |  |  |  |  | Total | 78.146 |
| Output 4: In – Dept Analysis and Synthesis of Best Practices in Turkey. Baseline: TBSCD vision 2050. Strategy document. Indicators: • Number of private sector consulted in the process. • Number of feedback received from private sector partners on the potential best practices. | 4. At least 10 best practices identified and presented to NCSD to be selected and to include into the national report. Activity 4.1: Stakeholder meetings with private sector representatives to identify the definition of best practices. Activity 4.2: Collect potential best practices cases to be considered. Activity 4.3. Select best practices and merge them into one publication. |  | 1 | 1 |  | SPO / UNDP | SPO | 71300 - Local Consultants |  |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 10.667 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 2.500 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 35.000 |
|  |  |  |  |  |  |  |  | 72200 - Equipment and Furniture | 0 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 360 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 800 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.300 |
|  |  |  |  |  |  |  |  | 73200 - Premises Alterations | 0 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 0 |
|  |  |  |  |  |  |  |  | Total | 50.627 |
| Output 5: Visibility and Advocacy to facilitate the RIO +20 National and International Participation. Baseline: no baseline Indicator: Number of publications and visibility materials prepared. | 5.At least 5 awareness raising activities organized for at least 60 participants. One web – site developed and kept active during the project implementation period. At least one information sheet, one booklet are developed and published. Activity 5.1: Develop and agree upon the awareness raising materials to be used during the preparatory phase for the Rio +20 event. Activity 5.2: Revisiting and updating based on the SPO’s requirements of web-site initiated with ISDSP Project and upload the project related materials. Activity 5.3: Develop and organize information sheets, booklets, billboards, media events, news, e-group and other public talks to share information on the preparations for the summit and also raise awareness for the long run discussions and planning. | 1 | 1 | 1 | 1 | SPO / UNDP | SPO | 71300 - Local Consultants | 11.000 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 21.333 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 17.400 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 30.000 |
|  |  |  |  |  |  |  |  | 72200 - Equipment and Furniture | 0 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 0 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 0 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 0 |
|  |  |  |  |  |  |  |  | 73200 - Premises Alterations | 0 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 43.000 |
|  |  |  |  |  |  |  |  | Total | 122.733 |
| Output 6: National Synthesis Report for RIO +20. Baseline: 9th Development Plan; Other national strategy documents. Indicator: • Number of consultation completed to record the impact of the Johannesburg at the national level. • Number of interviews organized in line with the project needs. | 6.National Synthesis Report for RIO +20 prepared and endorsed by SPO. Activity 6.1: Agree on the content of the National Synthesis report. Activity 6.2: Draft national synthesis report and submit it to SPO for approval. Activity 6.3: Draft an executive summary of the reports prepared and submit it to SPO for approval. Activity 6.3: Launch the National Synthesis in a national event. | 1 | 1 | 1 | 1 | SPO / UNDP | SPO | 71300 - Local Consultants | 40.000 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 21.333 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 5.000 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 0 |
|  |  |  |  |  |  |  |  | 72200 - Equipment and Furniture | 0 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 0 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 0 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 0 |
|  |  |  |  |  |  |  |  | 73200 - Premises Alterations | 0 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 0 |
|  |  |  |  |  |  |  |  | Total | 66.333 |
| TOTAL DIRECT COST | 437.136 |
| OVERHEAD COST – F&A (3%) | 13.114 |
| TOTAL COST | 450.250 |

TABLE 2- REVISED BUDGET AND WORKPLAN TABLE ACCORDING TO ADDITIONAL CONTRIBUTION OF THE MOEF

Year: 2011 - 2012

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
| And baseline, indicators including annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Stocktaking and impact analysis of Turkey’s Progress towards UNCSD between 1992 – 2010. Baseline: Sectoral Policy assessment completed under the project titled as: Integrate Sustainable Development Policies into Sectoral Policies. 9th Development Plan. Indicators: • Consultation meetings report. • Number and level of stakeholders participation in the consultation meetings. • Number of parameters and cross sectoral matrix considered in the final reporting. Related CP outcome: | 1. Multi-stakeholders consultation process to assess Turkey’s progress towards UNCSD between 1992 – 2010. Activity 1.1: Prepare baseline/discussion documents. Activity 1.2: Develop the methodology to be used during the consultation meetings. Activity 1.3: Consultation meetings with relevant government ministries and key stakeholders. Activity 1.4: Identification of relevant organizations and identifying experts to facilitate the process. Activity 1.5: A series of multi-stakeholder meetings in central and selected regions, comprising plenary sessions with brief expert introductions and roundtable discussions incorporating diverse perspectives and interactive debates; and breakout sessions devoted to assess successful experiences and initiatives. Activity 1.6: Identification of legislative developments and activities (projects/ activities/ new procedures) of government and/or private sector to analyze level of implementation of Johannesburg Plan of Implementation. Activity 1.7: Draft the content of the final report. Activity 1.8: Draft an outcome document based on the recommendations of the consultation meetings. | 1 | 1 | 1 |  | SPO / UNDP | SPO | 71300 - Local Consultants | 2.400 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 24.934 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 12.500 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 54.961 |
|  |  |  |  |  |  |  |  | 72200 - Equipment and Furniture | 690 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 540 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 1.200 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.950 |
|  |  |  |  |  |  |  |  | 73200 - Premises Alterations | 1.000 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 1.031,49 |
|  |  |  |  |  |  |  |  | 74500 – Misc Expenses | 512.97 |
|  |  |  |  |  |  |  |  | Total | 101.719,46 |
| Output 2: Support to World Bank Policy Paper and Capacity Building on Green Growth Baseline: Sectoral reports developed under the project titled as: Integration of Sustainable Development Principles into Sectoral Policies. Indicators: • Number of sectors selected for the Green Growth analysis. • Number of reference reports consulted for data collection. Related CP outcome: | 2. Sustainable Development related data collected and harmonized. Methodology to assess potential green growth alternatives for Turkey identified and analysis completed. Activity 2.1: Data Collection to support the WB policy paper preparation Activity 2.2: Collection of background information documents and reports to serve the WB policy paper and ICSA Report preparations. Activity 2.4: Multi-stakeholder meetings, interviews, soliciting of information, and background and follow up work. | 1 | 1 |  |  | SPO / UNDP | SPO | 71300 - Local Consultants | 0 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 10.667 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 5.000 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 3.329 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 360 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 800 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.300 |
|  |  |  |  |  |  |  |  | Total | 21.456 |
| Output 3: Enhance national capacity for RIO+20. Baseline: NCDS capacity assessment report prepared under the project titled as: Integration of Sustainable Development into Sectoral Polices. Indicators: • Number of decision makers participated in the preparatory meeting. • Number of capacity building discussion meetings organized for the Rio +20 upcoming event. Related CP outcome: | 3.Five Capacity Building activities delivered to decision makers before the Rio +20 event. At least 20 Rio +20 delegation members prepared for the mission. |  | 1 | 1 | 1 | SPO / UNDP | SPO | 71300 - Local Consultants | 15.000 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 12.000 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 10.000 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 123.456 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 540 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 1.200 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.950 |
|  |  |  |  |  |  |  |  | Total | 164.146 |
| Output 4: In – Dept Analysis and Synthesis of Best Practices in Turkey. Baseline: TBSCD vision 2050. Strategy document. Indicators: • Number of private sector consulted in the process. • Number of feedback received from private sector partners on the potential best practices. | 4. At least 10 best practices identified and presented to NCSD to be selected and to include into the national report. Activity 4.1: Stakeholder meetings with private sector representatives to identify the definition of best practices. Activity 4.2: Collect potential best practices cases to be considered. Activity 4.3. Select best practices and merge them into one publication. |  | 1 | 1 |  | SPO / UNDP | SPO | 71300 - Local Consultants | 15.000 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 10.887 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 7.500 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 40.000 |
|  |  |  |  |  |  |  |  | 72400 - Communication & Audio Visual Equipment | 360 |
|  |  |  |  |  |  |  |  | 72500 - Supplies | 800 |
|  |  |  |  |  |  |  |  | 72800 - Information Technology Equipment | 1.300 |
|  |  |  |  |  |  |  |  | Total | 75.847 |
| Output 5: Visibility and Advocacy to facilitate the RIO +20 National and International Participation. Baseline: no baseline Indicator: Number of publications and visibility materials prepared. | 5.At least 5 awareness raising activities organized for at least 60 participants. One web – site developed and kept active during the project implementation period. At least one information sheet, one booklet are developed and published. Activity 5.1: Develop and agree upon the awareness raising materials to be used during the preparatory phase for the Rio +20 event. Activity 5.2: Revisiting and updating based on the SPO’s requirements of web-site initiated with ISDSP Project and upload the project related materials. Activity 5.3: Develop and organize information sheets, booklets, billboards, media events, news, e-group and other public talks to share information on the preparations for the summit and also raise awareness for the long run discussions and planning. | 1 | 1 | 1 | 1 | SPO / UNDP | SPO | 71300 - Local Consultants | 7.500 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 18.000 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 77.400 |
|  |  |  |  |  |  |  |  | 72100 - Contractual Services - Companies | 50.000 |
|  |  |  |  |  |  |  |  | 74200 - Audio Visual & Print Production Costs | 50.500 |
|  |  |  |  |  |  |  |  | Total | 203.400 |
| Output 6: National Synthesis Report for RIO +20. Baseline: 9th Development Plan; Other national strategy documents. Indicator: • Number of consultation completed to record the impact of the Johannesburg at the national level. • Number of interviews organized in line with the project needs. | 6.National Synthesis Report for RIO +20 prepared and endorsed by SPO. Activity 6.1: Agree on the content of the National Synthesis report. Activity 6.2: Draft national synthesis report and submit it to SPO for approval. Activity 6.3: Draft an executive summary of the reports prepared and submit it to SPO for approval. Activity 6.3: Launch the National Synthesis in a national event. | 1 | 1 | 1 | 1 | SPO / UNDP | SPO | 71300 - Local Consultants | 40.000 |
|  |  |  |  |  |  |  |  | 71400 - Contractual Services - Individual | 18.000 |
|  |  |  |  |  |  |  |  | 71600 - Travel | 6.500 |
|  |  |  |  |  |  |  |  | Total | 64.500 |
| TOTAL DIRECT COST | 631.068,46 |
| OVERHEAD COST – F&A (3%) | 18.932,05 |
| TOTAL COST | 650.000,51 |