## Project 79012 Annual Work Plan 2014/15

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount (USD) |
| Output 1: POPC leads a national stakeholders’ dialogue on evidence-based pro-poor and environmentally sustainable growth with medium-term and Long-Term development perspectives beyond MDG 2015. Baseline: Vision 2025 in place, Development of Long Term Development Plan has commenced 2011. Targets: (i) Long Term Development Plan and M & E system includes environmental sustainability targets and PE indicators; (ii) Targets: consultative dialogues Post 2015 National development (iii) Selected growth sector plans and budgets integrate environmental sustainability and PE indicators Indicators: Level of inclusion of PE targets and indicators in LTP, Sector Plans and Budget: | 1.1 Support consultations/dialogue with national actors to provide inputs to Post–2015 Global Development Agenda and national plans development. Review consultations reports and distil the localization findings / recommendations. And hold one consultative dialogue on pro-poor, gender and environmentally sustainable growth and LTDP M&E | x | x | X | x | POPC | UNDP | Consultants, meetings, communication materials , | 20,000 |
|  | 1.2 Support consultations/dialogue with national actors including sectors, academic and research institutions, civil society, private sector and development partners to provide inputs to review implementation of FYDP 2015/16 and development of FYDP 2015/16 – 2020/21. Undertake consultative review for FYDP 2015/16 and FYDP 2015/16 – 2020/21 | x | x | X | x | POPC | UNDP | Consultants, workshops, meetings, materials | 45,000 |
|  | 1.3 Support implementation of pro-poor growth activities at sub-national level (4 districts - MAF) including sharing of lessons and best practices with key policy makers 4 pro-poor growth projects developed, implemented and scaling up (targeting women and youth) | X | X | X | x | POPC (LGAs) | UNDP | Workshops, meetings | 95,000 |
| Output 2: POPC formulates Public investment plans, integrating pro-poor and environmentally sustainable activities and oversight on implementation of programmes and projects Baseline: Draft Public Sector Investment Plan (MPIP), FYDP and MKUKUTA II Targets: Trade, Agriculture, and Tourism programmes are reviewed from a pro-poor perspective angles Indicators: investment programmes include analysis of impact to poor and vulnerable groups. | 2.1 Technical assistance in selecting and evaluating pro-poor projects/programmes during the implementation phase of FYDP - evaluation of poverty impacts of various projects. 2 national projects selected and evaluated on gender-poverty environment impact | X | X | X | X | POPC | UNDP | Consultants | 20,000 |
|  | 2.2 Integrate environmental sustainability assessments in the priority sectors under the – local development plan. Environment assessment undertaken in Agriculture / fishery and establish environmental standards for fish farming. | X | X | X | X | POPC (LGAs) | UNDP | Consultants | 30,000 |
|  | 2.3 Carry out priority capacity development interventions including training on integrated economic, gender and environmental assessments for planning officers and M and E Training. Two training sessions on integrated assessments tools for planning carried out | x | x | x | X | POPC | UNDP | Consultants, training sessions, training materials | 20,000 |
| Output 3: Research and analytical studies on employment-enhancing and environmentally sustainable growth and evidence-based policy management process made available to Government Directors, Permanent Secretaries and Ministers. Baseline: Key staff in MoF, UDSM and REPOA and ESRF pro-poor growth knowledgeable, Ad-hoc meetings on pro-poor; low Human Development , Targets: Targets: At least 80 key staff in POPC, MDAs and academicians are imparted with pro-poor knowledge and skills, regular annual dialogue Indicators: Number of trainees, Feedback reports, documentation available through TAKNET / TZonline; # and quality of Research Papers, media briefs produced by UDSM / Nyerere chair; quality and effectiveness of policy dialogues and conferences. | 3.1 Analytic studies & Training on macro / micro-data analysis using survey data such as HBS, NPS, Census, ILFS for growth, poverty and employment and learning about poverty/welfare measurement at outcome level (e.g. indices, HDI, MPI) Avail learning opportunities for key POPC, MoF and academic staff on Human Development and Sustainable development courses including indexes | x | x | x | x | POPC | UNDP | Training fees, travel costs, Consultants | 65,000 |
|  | 3.2 Strengthening knowledge sharing mechanism/platforms under ESRF (K-Mobile, TAKNET and TZonline) Support generation of national contents for pro-poor growth focusing on policy and local implementation – district level. | x | x | x | x | ESRF | UNDP | Fees, running costs | 38,000 |
|  | 3.3 Support selected activities of UDSM / Mwalimu Nyerere chair on Economic Analysis. Tanzania Economic Trends publication and Annual General Meeting | x | x | x | x | POPC (UDSM) | UNDP | Travel cost, DSA, Consultants and Conference packages | 15,000 |
|  | 3.4 Develop and disseminate key publications to decision makers, private sector and civil society on environmental sustainability, growth and poverty reduction in Tanzania Support to Center of Environment for Development - UDSM (synthesize analytic reports, develop policy briefs, Annual dissemination meeting) | x | x | x | x | POPC (UDSM) | UNDP | Consultants, workshops, travel | 22,000 |
| Output 4: A Centre of South-South Cooperation established to facilitate knowledge sharing on growth and development (including: gender-sensitive and environmentally sustainable strategies). Baseline: No South-South Centre to coordinate growth issues under leadership of POPC. Targets: One centre established Indicators: Centre in place | 4.1 Undertake a diagnostic study on SSC landscape and profile in Tanzania and produce an action plan to guide and enhance future SSC initiatives, incorporating recommendations and evidence based on ‘best practices’ of SSC. Diagnostic study on SSC in Tanzania and develop action plan | X | x | x | x | POPC | UNDP | Consultancy, conference, media, travel, DSA | 20,000 |
|  | 4.2 Review/produce country/regional level research papers/reports and share country experiences with a wider community including at the regional level (e.g. Africa Economic Outlook) Tanzania country report for the African Economic Outlook (AEO) produced AEO is launched and key messages are disseminated |  |  | X | x | UNDP | UNDP | Consultancy, conference, media, travel, DSA | 5,000 |
| Output 5: Enhanced capacity of POPC, MOF and PMORALG for budgeting and monitoring of Five Year Development Plan and MKUKUTA II Goals and targets on gender and environmental sustainability. Baseline: MKUKUTA II contains specific targets and indicators on environmental sustainability and climate change. FYDP document completed Targets: Budget guidelines include environmental sustainability objectives; Improved availability of PE indicators in national monitoring system; Public environment expenditure reviews institutionalised Indicators: No PEER carried out; Availability of P-E data and indicators in national systems of monitoring budget and planning | 5.1 Support engendering of budget guidelines and gender-based budgeting (salary: gender and nutrition adviser – PO) Advise to the President of URT on gender-nutrition perspectives and interventions | x | x | X | X | POPC | UNDP | Salary, fees | 30,000 |
|  | 5.2 Establish institutional coordination for reporting of PE Indicators in FYDP and MKUKUTA monitoring systems Develop P-E-G Report 2014 and dissemination | x | x | X | x | MOF (NBS) | UNDP | Working sessions, travel, DSA | 29,000 |
| Project technical and management support | Programme support staff (equipment, monitor, etc) | X | X | x | X | POPC | UNDP | DSA, travel, communication | 9,000 |
|  | Develop monitoring and data collection tools to capture implementation progress of the project. | x | x | x | x | POPC/UNDP | UNDP | Consultants, cost of data collection using M&E tools | 20,000 |
|  | Project communication, meetings | X | X | x | X | UNDP | UNDP | Travel, meetings | 12,000 |
| TOTAL |  |  |  |  |  |  |  |  | 495,000 |