## Compnoent 1 TFS
TANZANIA UNDP-GEF COASTAL FORESTS PROJECT
COMPONENT 1TANZANIA FORESTS SERVICES (TFS) PROGRESS REPORT April - June 2013
EXPECTED OUTPUTS | PLANNED ACTIVITIES | ACTIVITY/TASK DESCRIPTION | PERFOMANCE
Outcome 1. Strengtherned Enabling Environment is functional for conservation of Coastal Forests in mainland Tanzania, leading to inceased funding, staffinf and oversight.
Output 1.1: Capacity built in Tanzania Forest Service) to lead and oversee a Tanzania Coastal Forest Conservation Programme | 1.1 .1 To acquire additional facilities and equipment for TFS unit including 1 photcopier machine for TFS and 4 GPS for DFOs | Acquiring additional facilities and equipment for TFS unit including 1 photcopier machine for TFS,Anti virus, 4 cartilages and 4 GPS for DFOs by June 2014 | One LCD projector and one computer laptop was bought | 3250000
| 1.1.2 To establish networks among parties in the management of coastal forests | Conducting one stakeholders meeting involving 40 participants for 1 day by June 2014 | One workshop which involved TFS staffs from HQ, District Forest Officers and District Managers from TFS in 8 district plus 1 Town council was conducted. The district involved were Kisarawe, Bagamoyo,Mkuranga, Rufiji, Kibaha, Pangani, Muheza, Mkinga and Kibaha Town Council. TFS Zonal Managers from Eastern Zone, Northern Zone and Southern were also invited as the activities are being carried out in their areas. Purpose of the workshop was to establish network among parties and strengthen collaboration between TFS staffs in the districts and DFO and agree in principle to implement Coastal Forests activities in collaboration as well as share the work plan so as to avoid overlaping of activities and funds. | 9246000
| 1.1.3 To facilitate TFS unit to oversee day to day implementation of activities | Facilitating TFS unit to oversee day to day implementation of activities by June 2013 | One meeting were conducted btween TFS, UNDP, WWF,ZNZ; Major service was done to TFS vehicle, stationaries was bught for TFs and staffs were facilitated with airtime | 8500000
Output 1.2. Coastal Forest Reserves (non- reserves) within target landscapes are assessed as to priority for conservation on biodiversity and threat criteria, and conservation strategy developed | 1.2.1 To support identified potential income generating activities plus community tree growing initiatives (e.g. cashew nut farming, beekeeping, fish farming, fruit trees, passion) | Providing support to the local communities to implement identified potential income generating activities by June 2014 | 58 sets of beekeeping equipments were bought and some have been distributed to communities in Bagamoyo, 25 groups were established and trained in beekeeping ( 3, Handeni,3 Bagamoyo, 3 KibahaTC, 8 in Muheza at kwabada, kwabojo, mbambara, mhamba, kwabota, mtindiro, and mto wa mbu, 8 in Pangani.) A total of 335 communities were trained in Beekeeping and Tree planting in the same areas including 50 youth members in Rifiji. 2 proposal draft proposals for Pangani have been produced (i for irrigation at Mseko village and another for Vikoba for five villages surrounding Msumbugwe Forest Reserve | 52500000
| 1.3.3. To accomplish establishment of Forest Reserves under different PA management models for landscape sytems including Nature reserves and FRs,VLFRs |  | The porcess of upgrading Rondo Forest Reserve to be a Nature Reserve is at the final stage. Resurvey to separete Rondo Nature Reserve and Rondo Plantation have been completed. The process of gazzetment is at the State Atony leve for Gazetment. Maps are in place. Management plan for Rondo Proposed Nature Reserve has been prepared. Three forests in Bagamoyo i.eTembe 950.71acres, Kiona 816 and Kipaku 716 acres has been identified for gazzettement as VLFR. Resurvey and boundaries identification has been completed and map production have been completed. 3 VLFR in Mkinga are at district level for declaration | 15000000
| 1.3.4 To consolidate boundaries of existing forest reserves in four Districts |  | 100 beacons were installed at vikindu F/R, Fireline was cleared and 52 beacons was installed in Gendagenda Forest reserve, Resurvey of Masanganya forest reserve and installation of 10 beacon was done in Kisarawe areas, and map production of Masanganya is in process. Awareness raising was done to 50 membeers of Kwafungo and Bwitini and signbords were put at Kwani and Tongwe forest reserves in Muheza district. 40,000 seedlings were distributed and planted in District Council plot at Miwaga village and schools in Rufiji District , 9,200 tree seedlings were bought and distrubuted to communities living around Msumbugwe Forest Reserve in Pangani Resurvey of boundaries at Lukenge and and Msua VLFR in Kibaha District was done. Boundaries of Tukamisasa and Mkoko VLFRs were demarcated in Bagamoyo district. | 24000000
| 1.3.5 To facilitate establishment and functioning of VECs (VNRCs) including working gears. | Strengthening and enebling the functioning of the VNRCs by provinding working gears by engaging 2 staff for 2 days by June 2013 | 4 bicycles were distributed to Pangani district( 2 for Behe and 2 for BojoVNRC), Kwakibuyu VNRC were facilitated with Identity cards | 550000
|  |  | Vehicle maintenance was done in Pangani and Handeni districts were procured, and 9 districts were facilitated with airtime | 2000000
| 1.4.2 To support nine (9) districts in implementation of the project activities | Supporting nine districts in implementation of the project activities by June 2013
| 1.4.4 To support the development identified tourists attractions | Supporting the development of 4 identified tourists attractions by June 2013 | 3 youth groups who practice tourism activities were identified and formulated in Pangani district at Bweni, Msaza villages. | 2245000
Output 1.6. Monitoring and Evaluation at Project Level Implemented | 1.6.1 To carry out M&E for continuous feedback of the project implementation | Carrying out M&E for continuous feedback of the project implementation by June 2013 | Field visit was done in 8 districts of Mkuranga, Bagamoyo, Handeni, Kibaha, Muheza, Pangani, Rufiji and Kisarawe Districst. to make follow up of the project activities and give back ups | 4000000
TOTAL OUTCOME 1 |  |  |  | 121291000

## Compnent 2 Zanzibar
TANZANIA UNDP-GEF COASTAL FORESTS PROJECT
COMPONENT 2: ZANZIBAR - DNRNR - PROGRESS REPORT April - June 2013
OUTCOME 2. | OUTPUT | S/N | PLANNED ACTIVITY | FUND | DONOR | Budget description | ACTUAL ACHIEVEMENTS, PROGRESS AGAINST OUTPUTS, TARGETS AND INDICATORS | AMOUNT SPENT ( TSH) | PENDING ISSUES/ REASON FOR ADJUSTMENTS
2.1 The Protected Area System for Zanzibar is strengthened in terms of both representativeness, connectivity, financing and managerial capacity. | 2.1.1 Reconsitute Protected Area Board capacity to provide oversight and leadership | 2.1.1.1. | Stake holders workshop discussing the draft of FPAB |  |  |  | draft standing order prepared and proposed list of group/board members. Note : It was suggested from the planning workshop held at Nyumbani Hotel in Tanga that this should be not a Board BUT "forest advisory group" rather than "Forest Comference" | part of consultant cost | will be continued to July-Dec 2013
|  | 2.1.1.2 | Preparation of NPAB standing order |  |  |  | draft order prepared but not submitted to DFNR | part of consultant cost | will be continued to July-Dec 2014
|  | 2.1.1.3 | Conduct FPAB standing order agreement meetings with relevant stakeholders. |  |  |  | Not yet done | n/a | This will be conducted upon completeion of group or board structure for stakeholders consumprion and comments
|  | 2.1.1.4 | Launch of FPAB (NPAB) |  |  |  | Not yet done | n/a
|  | 2.1.1.5 | Orient FPAB (NPAB) to PAs of Unguja and Pemba
| 2.1.2 Support functions of DFNR conservation Section in management of Protected Areas through maintainance of equipments, staff trainings and its operations | 2.1.2.1 | Support general operation and management of the project |  |  | Project work supervision & follow-up | DFNR office superivisor travelled to Pemba to send motorbike (DFP 8734, Project accountant sent project expenditure documents to Dar -PMU, Asst Project focal person travelled to Pemba to supervise project activities. | 1192000 | planned activities are progressing | Jan-March 2013
[7 empty] | Project staff (3 Unguja and 2 Pemba) participate five days project planning meeting held at Nyumbani Hotel in Tanga. This was for preparation of July-December 2013 through to Jan-June 2014. This activity cost include Airtickets, DSAs and inland TAXI. Note: There are some staff tarvel all the way from Unguja via Pemba to Tanga while other were from Pemba to Tanga | 4362000 | done
[6 empty] | Procure printer and antivirus Computer accessories) | Two printers and 2pcs of antivirus procured. | 1360000 | done (Jan-March 2013) | Jan-March 2013
[6 empty] | Vehicle maintenance (Vehicle tyres) | Two vehicle tyres for DFNR -Field vehicle were procured. The vehicle with registrtaion number SMZ 6227 was used to support project works. | 1180000 | done ( Jan-March 2013) | Jan-March 2014
|  | 2.1.2.2 | Design and print year 2013 Callender for Forest Protection and related activities Unguja and Pemba |  |  | 1,000 callenders printed | This activity wasn’t implemented | 0 | Carried forward to July -Dec 2013 for 2014 calender production | April -June 2013
|  |  | 2.1.2.3 Conduct short term training (tailor made training) on enforcemnet to DFNR staff and CBO members |  |  | CS-Staff trained in Forest Law enforcement at Persiansi-Mwanza | Two DFNR staff from forest law enforcement unit (Pemba1: Unguja 1) attended 30days short course at Persiansi-Mwanza | 8443000 | Still more Law enforcement staff to be trained. Next step the trained staff will conduct inhouse training course(ToT) within DFNR | Jan-March 2014
|  | 2.1.2.4 | 2.1.2.4 DFNR senior staff trained in project Planning,monitoring and finnancial management at Dar-University |  |  | Tuition fees, DSA, Flight ticket and land transport | 10 DFNR staff (2 Pemba: 8 Unguja) attended five days course at Bussiness school of University of Dar-es-salaam with Certification. Main areas of study including Project planning, Project activities monitoring and Evaluation, and Project financial/control management | 14140000 | done | April -June 2013
|  | 2.1.2.6 | In-house computerised course in forest fire detection to GIS unit |  |  | DSA training participants,Facilitation and stationary | Not yet done | 0 | Will be conducted in 2013, July-Dec 2013 | April -June 2014
|  |  | 2.1.2.8 Enteprenership training on initiating feasible altrnative income generating activities for community at Ushirika University- Moshi |  |  | Training to both DFNR sellected staff and CBOs members arround 6 key protected areas ( Jozani, Ngezi, Kiwengwa, Msitu-Mkuu, Ras Kiuyu and Masingini) | Not yet done | 0 | Carried foward to July-Dec 2013. Will be conducted within Zanzibar and not at Ushirika University-Moshi, so that to reduce course costs and train more people at ago. | April -June 2015
|  | 2.1.2.11 | PAs-Natural Forest fire prevention and supression cost |  |  | Mobilize and motivate participants to PAs forest fire supression | Two forest fires occurred in two different days at Kiwengwa Forest Reserve and extinguished in four days by 218 people (including community members and govenrmnet institutions. The fore burnt down 11.5 hectares. | 4610000 | done | April -June 2016
|  | 2.1.2.12 | Hold project partners meeting for project planning |  |  | DSA, Land Transport , conference package | 50 DFNR staff participate in two days projects plans review meeting at Wesha-Pemba. The meeting involved managers of other projects within DFNR. Managers shared working experience, challenges and lessons but focus was to avoid doublication of activities and issue of co-financing among interplaying projects. | 8040000 | 12 % of the allocated activity budget was overspent to cater for unforeseen expenses during planning (including high cost of hall rent and Land transport in Pemba) | Jan-March 2014
|  | 2.1.2.12 | Provide necessary facilitites at work for Conducive working environment at MFR and NVNR PAs |  |  | New lap top computer for focal person Unguja & Pemba | 2 Lap top Computer procured and distributed to ( see budget description in the activity 2.1.2.1)-above | 2940000 | done | Jan-March 2015
|  |  | Construct permanent resting benches at NVNR visitors resting hut. |  |  | Five benches construction | This work completed with well constructed visitors resting benches at Ngezi resting hut which is nearby Ngezi visitor centre-entrance gate | 750000 | done | April -June 2013
[6 empty] | Desk top computer to Masingini | One desk top computer procured | 1350000 | done | Jan-March 2013
|  | 2.1.2.13 | Maintain Refurbish MFR & KPFR field stations' with water and power supply |  |  | Engage electrition constancy for MFR office/station power supply ( For Masingini ) | Power supply/fixation in the Masingini house/office completed but final instalment ( 1,000,000 Tsh) to electrician isn't paid yet . This work was budgetted to cost 2,000,000 Tsh to electrician . In the first instalment he was paid 1,000,000 Tsh only ( Jan-March 2013) and final instalment will be done upon submission of the written report ( not just workds/physical observation-project need permanent written notes for reference purposes. AND This activity was pre-planned | 0 | Electrician hasn’t submit his work completion report so final instalment is with held until such condition is fulfilled as per TOR. | April -June 2013
[6 empty] | Purchase SIM TANK water tank and water pump | One Water pump and SIM TANK for (Kiwengwa) and SIM TANK for Masingini procured | 1450000 | done | Jan-March 2013
| 2.1.3 Raise awareness to Key stakeholders on PAs conservation (Meetings) | 2.1.3.1 | Prepare TV documentary for public awareness on PAs conservation |  |  | Local consultant (TV documnetary for two Pas) | Preliminary work of script for the work prepared with no cost | 0 | This work will be conduced in the period of July-Dec 2013
[6 empty] | Engage local consultant to prepare PAs guide book | N/A | 0 | Carrief forward to July-December 2013
|  | 2.1.3.2 | Mgelema and Msiyakwe community leaders study tour -to PAs in Unguja. |  |  | Boat ticket +DSA (Pemba/Unguja -round trip) | 11 people (three women and eight men) including two DFNR staff all from Pemba conducted five days field study tour to IGAs. Partcipants names were: Names: Bakari Haji Bkari, Abdi Ussi Othman, Mohammed Omar Ali, Mtumwa Omar Haji, Rajab Juma Haji, Hafidh Mohammed Jumah, Amour Ali Zaina, Omar Abdi Zaina, Zuhura Juma Shaame, Jamila Suleiman Mohammed Assaa Sharif Ngwali. They originate formMsiakwe, Wambaam, Msiakwe, Mgelema Mgelema, and DFNR The delegation visited Jozani N. Park (ecotourism) and Kiwengwa community forest and Forest reserve to learn how to protect community forests and benefits and trip proceeded Kitogani village where community is undertaking beekeeping activities , then winded up to Charawe village where they see well protected community forest.The trip involved Shehias of Wambaa, Msiakwe and Mgelema purposely to expose them to intergrated forest conservation and development | 4838000 | done | April -June 2013
Output 2.2 Terrestrial Protected Area Network expanded to include key gaps in coral rag and thicket communities of high biodiversity, with buffer and connectivity forests
| 2.2.1 Increase number of Protected Areas (connectivity) based on the Spatial planning study information. | 2.2.1..2 | Prepare notice of intent to gazzete Kangagani proposed new PAs |  |  | Facilitation (Notice of intent write-up and follow-up) | Not yet done | 0 | This will be facilitated in July-December 2013
Sub total
|  | 2.2.1.3 | Mobilize and sensitize community to creation of Village committees for proposed Kangagani F. Reserve |  |  | DSA for meeting participants (Village members - VCC, Village leaders) | Not yet done | 0 | This will be implementated in the period of July-December 2013
|  | 2.2.1.4 | Establish notice of intent and public announcement for proposed Ufufuma-Pongwe Forest corridor |  |  | Notice of intent | Draft work of Notice of intent prepered -ready for submission to Ministerial level for approval | 0 | In the process of preparation
|  | 2.2. 1.5 | Call for public hearing for proposed Jambiani-Muyuni claim collection |  |  |  | done through Radio Zanzibar | 0 | successful
|  | 2.2.1.6. | Collection of public claims from community for Jambiani- Muyuni propose reserve |  |  | Understand the actual number & type of claims | Opinion collection is progressing well, inline with snap shooting for pictorial evidence as well as GPS location within Jambiani-Muyuni (proposed) forest reserve.In the first report it was about report about opinion collection (Field work) but this time is for information organization and report writing stage. | -9600000 | Report writing is done in the periof of April-June 2013 (Overal budget for this work indicated in the last quarter of Jan-March 2013) not reflected in the period of April-June 2013. | April -June 2013 | `
|  | 2.2.7 | Claims verification and Aproval for the Jambaiani-Muyuni community by the village leaders /VCC |  |  | claims verification | Claims verification was done on camera. The documentary for this work was prepared.This work was started in the period of previous qrt but finalized in the period of April-June 2013. The budget was materialzie in the last reporting period, that is why inidacted -9,600,000 |  | Claims verified but in depth property assessment will follow (Overal budget for this work indicated in the last quarter of Jan-March 2013) not reflected in the period of April-June 2013. | April -June 2013
Output 2.3: Key forest Protected Areas are consolidated, and their management status improved
| 2.3.1 Harmonize guidline of Protected Areas with Land use and Tourism development plans. | 2.3.1.1 | Conduct harmonized sensitization meeting for guidelines of PAs tourism (Tourism, land, Districts, Forestry, Lawyer, Environment, ZAWA) |  |  | Inter-sectoral workshop ( local transport, DSA ) | Not yet done ( still in the preparatory stage) | 0 | Will be done during 2013/2014
|  | 2.3.1.1 | Develop guideline for PAs with Land use and Tourism development plans. |  |  | Guideline draft report | Not yet done ( still in the preparatory stage)1 | 0 | Will be done during 2013/2014
|  | 2.3.1.2 | Aproval of guide lines at Ministry level |  |  | Workshop with Departmental and Ministerial leaders for comments (DSA, Transport) | N/A | 0 | This will be implementated after guideline draft work
|  | 2.3.2 | Employ consultant to cary out economoc analysis of protected area to identify viable alternative income generating activities to enhence N.R conservation sustainability |  |  | Pay last consultancy installment | The final consutancy work report submitted to the DFNR after final presentation workshop of the draft work held at DFNR meeting room. One of the important comment was for every protected area to get "business manager" for Protected areas and surroudning communities to be economically managed. Currently, non of the PAs has business professional staff. | 3287890 | Consultant final payment is under final touch | April -June 2013
|  | 2.3.2.2 | KFR information Centre (IC) grounds Facelifting |  |  | Procure and spread:- gravels, sand and stone on the ground floor arround the Information Centre. | Not yet done | 0 | This activity has been carried forward to 2013/2014 | April -June 2013
|  | 2.3.2.3 | Refurbish NVNR toilet building and appliances |  |  | Engage local contractor- consultant for the work | The lrefurbishment of the exiting old toilet which is in the existing (African toilet) was abolished for new western toilet construction. Then DFNR did site sellection and with simple new floor plan, then toilet constructed to stage of walling and roofing. This structure is located nearby Ngezi entrance gate and visitor center, that will serve both for women and men visitors, separately. | ? (5,000,000) | The existed toilet structure at Ngezi visitor centor wasn’t to hygenic standard and appliances weren't to standard that suit hygenic and visitors facilities as toilet. Finishing work ( plumbining and power supply will be completed in the July-December 2013 | April -June 2013
|  |  | Install Solar power panel at NVNR |  |  | Solar power | The idea of Solar pannel installation abolished for High tension power of TANESCO. This need extra budget to buy Electricty generator which worth 25,000,000 and not 10,000,000 Tsh which has been budgetted for this activity.In the previous work plan it was planned to spend Tsh 10,000,000 Tsh to install solar power energy at Ngezi BUT DFNR found it not sustainable over TANESCON power. That is reason behind review of its budget during Tanga planning meeting and agreed with alternative idea to with TANESCO to procure transfoma | 0 | Transfoma will be fixed in the July-December 2013 (using new/ reviewed budget of July-Dec 2013 to Jan-June 2014 )
|  | 2.3.2.3 | Mapping KPFR road net work to easy forest fire access and supresion |  |  | KPFR road network map | In the process and waiting for initial payment to laborers | 1440000 | Will be complelted in the period of April-June 2013
|  | 2.3.2.4 | Mapping Ras Kiuyu road net work to easy forest fire access and supresion |  |  | Msitu Mkuu forest road network map | Not yet tackled | 0 | Will be tackled in the July-Dec 2013
| 2.3.3 Develop, review and implement management plans for Ngezi, Jozani, Msitu mkuu, Masingini and Muyuni Protected Areas | 2.3.3.1 | Develop Msitu Mkuu & Ras Kiuyu Forest Management plans |  |  | Consultancy ToR, and agreements | It is the process of TOR preparation | 0 | Actual field work will be carried forward to July-Dec 2013 | April -June 2017
| 2.3.4 Upgrade status of Masingini Forest Reserve (MFR) to Nature reserves and Muyuni, Ufufuma and Kangani from Public to Reserve | 2.3.4.1 | Upgrade status of MFR to Nature reserve (intensive biodiversity survey) |  |  | Engage consultant (ToRs ) and agreement | TOR and contract for special task entered for Mr. Tamrin and Miza of DFNR-staff to do this work and they were paid advance of 1,800,000Tsh being first instalment.This is not consultant work but special task to DFNR staff. Normally, consultancy work is given to an expert for those activities beyond DFNR capacity to do but for Upgrading work/process and documentation, meetings and so forth …DFNR can do using her staff. | 1800000 | Will be coning July-Dec 2013 | April -June 2017
|  | 2.3.4.2 | Prepare MFR Management Plan |  |  | Pay consultancy final installment | This work completed by paying final installment to TAFF and Masingini F. Management plan is in place. | 2134200 | done | Jan-March 2015
|  | 2.3.5.2 | Prepare tourism plan for MFR and KPFR |  |  | Engage consultant (ToRs) and agreement | Not yet done |  | Will be tackled within 2013/2014
| 2.3.6 Implement Business activities for PAs of JCBNP &MFR based on recommendation in the Business plan consultant report | 2.3.6.1 | Meeting to identify PAs Research priorities for sustainable PAs income generation and surrounding communities |  |  | Meeting (DSA and participants land transport) | Not yet done | 0 | Carried forward to July-Dec 2013
| 2.3. 7 Support GIS unit for map production | 2.3.10 | Support GIS unit for COFMA map production. |  |  | Assign Special task- for CoFMAs maps production | One CoFMAs of Makangale community around Ngezi-Vuma wimbi Nature Reserve was prepared at same time for communities arround Msitu Mkuu ( Wingwi-mapofu, Wingwi-mtemani, and Majenzi ) | 6000000 | done | April -June 2013
[6 empty] | Draw maps of three CoFMA P/ mchangani, Kandwi Kilombero & Upenja and Tunduni Unguja | not yet done | 0 | Carried forward to July-Dec 2013
Output 2.4 Community Forest Management Areas provide sustainable buffering and connectivity support, whilst contributing to household security
| 2.4.2 Develop and review thirteen (13) Community Forest Management Agreements(CoFM). | 2.4.2.1 | Establish the two remaining COFMA Pemba (Makangale and Kiuyu-mbuyuni) |  |  | Makangale and Kiuyu- mbuyuni CoFMAs (Meeting (DSA and participants land transport) | Mbuyuni village meeting was conducted and community conseravtion committee of 54 (44 men and 9 women) was formulated, and draft Community Forest Management Agreement was prepared, while Makangale village did the same but they formulated a committee of 53(35men and 18women - Note: Number of CoFMA members varies from one Shehia and another/others. They range 25, 35 upto 50 individuals….depending on the nature of the village hamlets and live support systems/ livelihood | 5080000 | Draft CoFMA (meeting report and CoFMA doc) are in place) for legal editorial work and endorsement | April -June 2013
TRAC FUND | Output 1. Establishment of effective wood alternative cooking energy stoves for communities arround Kiwengwa Pongwe and Ras Kiuyu Forest Reserve ( villages of ; Matemwe, Kiwengwa and Pwani-Mchangani and Ras Kiuyu)
| 1.1 Zanzibar wide Awareness prorogramme on the importance and need for shiflting from open fire cooking stoves for modern/improved stoves | 1.1.1 | Collection of locally available stoves construction materials within Zanzibar. |  |  | Clay soil collection trips (@ 7tons ) to women groups in 4 Shehias Unguja (Kiwengwa, Pwani mchangani and Matemwe-Kigomeni & Mfuru matonga)-Unguja | 56 tons of loamy soil and 28 tons of sand procured /collected and distributed to improved cooking stove makers : Kiwengwa, Matemwe, Matemwe-KigomaniPwani-mchangani | 1200000 | The collection work is progressing using allocated budget (July-Dec 2013) | April -June 2013
[6 empty] | Clay soil collection trips(@ 7tons) to Ras Kiuyu woman groups-Pemba | colleted to Kiuyu Mbuyuni and Kiuyu kipangani and Ngezi where stoves moulding took place | 1120000 | done | April -June 2013
[6 empty] | Sand collection (in tons) for Unguja | see 1.1.1 above | 0 | see 1.1.1 | April -June 2013
|  | 1.1.2 | Community groups Construct Cooking energy saving Stoves |  |  | Facilitation fee-Pemba to make 200 stoves-Ras Kiuyu-Pemba | Shehia of Ras Kiuyu in Pemba became pilot in the component 2 of the project in Pemba for improved stoves making. So far the UMOJA NI NGUVU group of Ras Kiuyu-Mbuyuni with 30 members (26 women and 4 men) has managed to make 272 (+ 36%) cooking stoves and sold 50 stoves to some community members. The stove making activity has been extended to community groups arround Ngezi where selected 30 community members (26 women and 4 men) were trained on how to mould mixed soil to make stoves, facilitated with materials and training. | (see activity 1.1.2 | done
[6 empty] | 500 stoves constructed (Kiwengwa, Pwani mchangani and Matemwe-Kigomeni & Mfuru- matonga)-Unguja (Groups work Facilitator's fee ) | Stove contruction delayed due to delayed soil collection in the absence budget to support material transport cost | 0 | Follow up to understand number of stoves will be assessed during July-Dec 2013
[6 empty] | Purchase set of charcoal and firewood cooking stoves making models with funels | This activity scaled down due to the fact that existing models are found to be suffice for the intended purposes | 0 | Redandant ( will not be procured) . Project will help community to mould stoves using existing models purchased in the past.
|  | 1.1.2 | Monitoring cooking stove training & facilitate community group works |  |  | Stoves making facilitation fee-Pemba | Shehia of Ras Kiuyu in Micheweni district of Pemba became pilot in the component 2 of the project for improved stoves making. So far the UMOJA NI NGUVU group of Ras Kiuyu-Mbuyuni with 30 members (26 women and 4 men) has managed to make 272 (+ 36%) of the targetted 200 cooking stoves and sold 50 stoves to some community members. The stove making activity has been extended to community groups arround Ngezi where selected 30 community members (26 women and 4 men) were trained on how to mould mixed soil to make stoves. Therefore Coastal Forest project facilitate them with materials and training. | 720000 | The programme will be improved in the period of July-December 2013 through to 2014. | April -June 2013
[6 empty] | Stoves making facilitation fee-Unguja | Soil and sand collected | 0 | Will be tackled in preriod of Aprl-June 2014. Delayed fund disbursement to Project Component 2.
Output 2.0 Work with beekeeping association (ZABA) to create and support seven new communities beekeeping groups ( arround Jozani, Kitogani and Bwejuu , Kiwengwa Forest Reserve (Kiwengwa and Pongwe) and arround Msitu-mkuu in Pemba)
| 2.1.Improve modern beekeeping beehives,quality honey production and personel safety | 2.1.1 | Modern beehives construction (top bar beehives)- 300 pcs Unguja and Pemba |  |  | 350 beehives (Engage local consultant) | Pemba: 170 Beehives construction work completed and 13,110,000 Tsh which is 100% while in Unguja: 150 hives conststruction work is progressing with first instalment of 6,375,000 Tsh. | 19485000 | 150 beehives construction work and distribution will be dealt with during July-December 2013 | April -June 2013
|  | 2.1.2 | Train community Beekeeping groups in site sellection for appiary |  |  | Training workshops training reports (Engage local trainers/facilitator-Unguja and Pemba for Train of Trainers (TOT). | Five days training on beekeeping sites sellection was done to 15 people (One field trip and 4 class work orientation). The participants originated from 14 beehive groups/CBOs. These group names are; Jukunumi, 2.Mwanzo Mgumu, 3.U/M-Wingwi, 4.Cobeka, 5 Tupendane, 6.Walemavu, 7.Moh'd Beekeeper,8. 9.Kiuyu-mbuyuni, 10.Jumwatu, 11.Kikwale, 12.Kiuyu-Minungwini, 13.Gando, and 14 Changamka group | 3850000 | done | April -June 2013
|  | 2.1.3 | Distribution of 300 new beehives to beekeeping groups |  |  | 300 Hive transport fees-Pemba and Unguja | N/A as beehives have not constructed | 0 | Will be tackled in preriod of July -Dec 2013
|  | 2.1.4 | Carry out baseline study/survey to identify and assess beekeeping activities |  |  | Beekeeping Baseline data report (Assign special task (ToR, and agreements)-local consultancy) | Not yet done | 0 | Will be tackled in preriod of Aprl-June 2014. Delayed fund disbursement to Project Component 2.
|  | 2.1.5 | Purchase of bees honey harvesting protective geares |  |  | Purchase sets of honey harvesting protective kit/ gears ( Veil, overall, smokers, gloves, harvesting knives, rainboots) | Not yet done | 0 | Will be tackled in preriod of 2013/2014. Delayed due to lack of budget | April -June 2013
| 2.2 Project Management | 2.2.1. | Office work facilities in new Beekeeper's office-at Chake-chake Pemba |  |  | Essential stationary procured |  | 0 | Will be tackled in preriod of 2013/2014. | April -June 2013
[6 empty] | Set of office Table and chairs | Not yet done | 0 | wasn’t implemented due to limmited fund. Will be tackled in preriod of July-Dec 2013.
|  | 2.2..2 | Project overall field supervision /monitoring with project DFNR support staff |  |  | Field visit and project work facilitation fees | One motobike received from Project PMU transferred to Pemba. During April -June 2013 Component 2 received vehicle from UNDP which is under minor correctiive maintenance bfore it fully used for project works | 0 | Still under corrective maintenance at Budda Auto Garage/workshop in Zanzibar . Total corrective maintenance cost will be reftected in the coming report. | April -June 2013
|  | 2.2.3 | Fuel for beekeeping activities followup |  |  | Fuel | Not yet done | 0 | Will be tackled in preriod of Aprl-June 2014. Delayed fund disbursement to Project Component 2.
|  | 2.2.5 | Purchase of bee wax to attract bees to new beehives |  |  | Purchase Bee wax cost for Unguja and Pemba (kg) | 50 kgs of bee wax to attract bees to beehives procured for be keeping groups. | 750000 | Wax will be distributed to beekeeping groups in Unguja and Pemba in the period of July-Dec 2013 | April -June 2013
|  | 2.2.6 | Conduct beekeepers groups cross-visit within Zanzibar (Pemba/ Unguja) |  |  | DSA, flight and land transport for 20 beekeepers from Unguja and Pemba (round trip report) | Not yet done | 0 | Will be tackled in preriod of July-Dec 2013 | April -June 2013

## Component 3 Landscape
TANZANIA UNDP-GEF COASTAL FORESTS PROJECT
COMPONENT 3: WWF-KILWA, RUFIJI AND LINDI - PROGRESS REPORT April - June 2013
PLANNED BUDGET
OUTCOME | OUTPUT | ACTIVITY NO. | PLANNED ACTIVITY | FUND | DONOR | BUDGET DESCRIPTION | ACTUAL ACHIEVEMENTS, PROGRESS AGAINST OUTPUTS, TARGETS AND INDICATORS | AMOUNT SPENT (USD) June '13 Rate; Tsh/$ 1600 | PENDING ISSUES/REASON FOR ADJUSTMENTS
| Output 3.1 Landscapes (Rufiji, Kilwa, Rondo – Lindi) are agreed, described and assessed as to issues of connectivity, gaps and buffer functions | 3.1.1 | Develop knowledge management systems, capture project lessons, package for appropriate stakeholders and disseminations | 62000 | 10003 | 71600 Contractual service | Not done to all 3 landscapes | 0 | Planned start in 1st Quarter of FY 14 to all 3 landscapes
Outcome 3: Effective PA Management Systems in place at three project priority landscapes, with co-management between central, local and village government partners, leading to improved conservation of biodiversity values. |  | 3.1.2 | Facilitate stakeholders to participate in landscape conservation Plan | 62000 | 10003 |  | Lindi landscape: 1 group (with 8 members 4 Female and 4 Male) of tree nursery establishment at Mhima village was formed and trained on nurseries techniques which will assist in issues of connectivity, gaps and buffer functions along the PAs | 700000 | Planned to be done in 1st Quarter of FY 14 for Kilwa and Rufiji landscapes
|  | 3.1.3 | TRAC funding: Landscape stakeholders Capacity buidling | 62000 | 10003 |  | Kilwa landscape: A total of 217 (74 Female and 143 male) beekeeping group members from 5 villages of Nanjilinji, Kiranjeranje , Nakiu , Likawage , Mandawa and Mchakama were trainied on modern beekeeping practices and technques was achieved. Rufiji landscape: A target group of 90 beekeeping group members 3 sub-villages of Shella (12 Female and 18 Male), Kungulwe (6 Female and 24 Male) and Chemchem-Golani (10 Female and 20 Male)were trained on modern beekeeping practices and technques was achieved. A total of 30 commercial beehives from Tusongembele group from Nyandumbi sub village and Mshikamano group from Kipei sub-village were purchased following the awareness raising exercise and entrepreneurial skills gained from the training. Lindi landscape: A total of 6 beekeeping groups with 70 members from villages of Mhima (4), Mndawa (1) and Namtamba (1) were trained on practical mordern beekeeping and participated in selection of the bee apiary sites. mhima 4 1 ndawa 1 namtamba A total of 110 beehives were fabricated from slabs (forest offcuts) after training of beekeeping group and local carpenter from the village. | Kilwa landscape: 4,438,000 Rufiji Landscape: 10,413,855 Lindi landscape: 12,395,000
|  |  | TRAC funding: Group members training in Community Conservation Bank (COCOBA) Model | 62000 | 10003 |  | Kilwa Landscape: A total of 5 beekeeping groups (Namichele, Ukombozi, Changamoto, Mapambazuko and Ukombozi) of villages of Kiranjeranje(1), Mandawa (2), Najilinji (1 ) and Nakiu (1 ) having 63 (31 Female and 32 male) participants were trained on COCOBA from villages of Mchakama (1)and Likawage (2) so as to improve the socio-economic well-being of women and men within the respective villages. The members have started banking operations i.e shares, welfare funds mobilization and other income on weekly basis where a total shares, welfare fund worth Tsh 812,000 were obtained. Mchakama group of Mchakama Village deposited Tshs 424,000, Zinduka group of Likawage Village Tshs 176,000 and Jitegemee group of Likawage deposited 216,000. Rufiji landscape: COCOBA training was not conducted this quarter Lindi landscape: A total of 9 groups of villages of Ntene (6Male and 28Female); Mnara (9Male and 10Female); Vumilia; Liganga (2 groups of Mvuto and Mtaji wa Masikini), Ndawa 1 (group of Misitu ni Uhai) and Mihima 2 groups (Boresha Mazingira and Umoja). The groups provided Tsh. 5,408,000 as Loans, Cash in box amounted Tsh. 867,850 and Tsh. 637,400as social funds. | Kilwa landscape: 4,438,000 Rufiji Landscape: 0 Lindi landscape: 6,490,000 | Kilwa landscape: Target was to train 5 groups but was not achieved due to the fact that the training happened during harvesting season of of simsim crop. Rufiji Landscape: Carried to next quarter after formation and training of beekeeping groups in villages of Utunge,Shella villa, Kungulwe and Chemchem-Golani sub-village.
| Output 3.2 Gaps in landscape plan filled by strategic development of Local area FRS and VLFRs | 3.2.2. | Faciliate establishment of forums for protected areas in landscapes. | 62000 | 10003 | 72100 Contractual Services | Not done by all 3 landscapes | 0 | Planned to be done in 1st Quarter of FY 14 to all 3 landscapes
|  | 3.2.3 | Advocacy with communities and village authorities in key identified areas for connectivity and buffer functions (Capacity building to communities). |  |  | 72100 Contractual Services | Not done by all 3 landscapes | 0 | Planned to be done in 1st Quarter of FY 14 to all 3 landscapes
|  | 3.2.4 | The final management plans and bylaws approved at village and ward levels. This is the final stage towards declaration of proposed VLFRs. The prevous stages on Land use planning and survey and demarcations are completed. |  |  | 72100 Constractual services | Not done by all 3 landscapes | 0 | Planned to be done in 1st quarter FY 14 to all 3 landscapes
| Output 3.3 Landscape Conservation Plan developed and agreed with local district and national partners | 3.3.1. | Land scape plan(s) developed and approved by partners | 62000 | 10003 | 71300 | Landscape conservation plan was completed and distributed to respective partners in the 3 landscapes (Lindi,Kilwa and Rufiji). The next plan is to incorporate the landscape conservation plan into district plan | 0 | Planned to be done in 1st Quarter of FY 14 to all 3 landscapes
|  | 3.3.2 | Work with MCDI toward certification process of Nanjirinji Village VLFR | 62000 | 1003 | 71600 Contractual service | Not done in Kilwa this quarter | 0 | Planned to be done in 1st Quarter of FY 14 to all 3 landscapes
| Output 3.4 Conservation plans under implementation with key indicator baselines completed and new area METT scores completed | 3.4.1. | Undertake METT scores & Thread reduction Assesments | 62000 | 10003 | 71300 Local Consultants | Was completed in the 3rd quarter and reported was out in time. | 0
|  | 3.4.2. | METT score completed at new sites | 62000 | 10003 | 72100 Contractual Services | This activity was completed and reported in previous quarters. | 0
|  | 3.4.4 | Monitor and record offtake levels , income and revenue earned from reserves using revfenuw forecasting framework. | 62000 | 10003 | 72100 Contractual services | Not done by all 3 Landscapes this quarter. | 0
|  | 3.4.5 | Support process of upgrading Rondo Forest reserve to a Nature reserve | 62000 | 10003 | 72100 Contractual services | This activity was completed and reported in previous quarters.
[7 empty] | TOTAL | Kilwa landscape: 8,876,000 Rufiji Landscape: 10,413,855 Lindi landscape: 19,585,000