## M&E Plan OUTCOME 1 TFS
MONITORING PLAN FOR GEF COASTAL FOREST PROJECT OUTCOME 1 (TFS)
Project Goal | The coastal Forest Biodiversity and Ecosystem Values are Conserved and Provide Sustainable Benefit Flows at Local, National and Global Levels
Project purpose | Indicator | Baseline 2011 | Planned Target by EOP | Data source | Data collection Methods | Responsibility and analysis | Frequency of data collection | Desired Results |  |  |  | FY 2010/11 Monitoring |  |  | FY 2011/12 Monitoring |  |  | FY 2012/13 Monitoring |  | FY 2013/14 Monitoring
[8 empty] | End of FY 2010/2011 | End of FY 2011/2012 | End of FY 2012/2013 | End of FY 2013/2014 | Actual FY Results | Actual VS Desired results(%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Actual FY Results | Actual VS Desired results(%)
Objective: The Spatial coverage and management effectiveness of the Coastal Forest PA sub system is expanded and strengthened | 1. Increase in extent (ha) of PA network that includes Coastal Forests, and a network with increased legal protection and management of biodiversity values, including four Forest Nature Reserves | 19,570ha is under improved management of which none is Forest Nature Reserve (FNR) | 12,000ha as Forest Nature reserve and 100,000 ha as VLFRs | Ministry anf Departmental reports, and Project documents. Project documents,Landscapes plans, maps and GIS files, MTE and Terminal Evaluation(TE) National reports to CBD | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | N/A | N/A | NA | 12,000 as FNR | NA | 0% | Project activities did not start, the project was doing baseline studies | N/A | 0% | Project interventions did not start, the project was doing baseline studies | 12,000 ha of Rondo Forest Reserve is under final process for upgrading to Nature Reserve. Approval has been obtained at Village, Ward and District Council levels, awaiting the Regional and National level approvals and declaration. | 60% | The Rondo Forest Reserve covering 12,000ha is under the final process for gazettment and upgrading into a Nature Reserve by the Ministry of Natural Resource and Tourism. The dossier (containing the agreement from surrounding villages, the district, the region, and the Tanzania Forest Service) was submitted to the cabinet in June 2013 | 85%
| 2. Increase in area under landscapes conservation, with functional corridors and buffer-zones, managed under detailed landscape conservations plans | Nil | 1,277million ha | Same as Indicator 1. | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | N/A | NA | NA | 1,277million ha | N/A | 0% | Project interventions did not start, the project was doing baseline studies | 142,044 ha put proper land use plan out of which 56,900 ha have been demarcated as forest reserves in Lindi and Kilwa LS. | 30% | NA | A total of 402,136 ha have been put into proper Land use plans out of which 153,077ha have been demarcated as Local Authority and Village Land Forest Reserves in Rufiji, Kilwa and Lindi landscapes. | 65% | In this reporting period a total of 514,665.86 Ha are under proper management status within the landscapes of Kilwa, Rufiji and Lindi landscapes. There are 296,938.57Ha under Village Land Forest Reserves; 117,860.71 Ha under Central Government Forests reserves; 77,824.79Ha under Wildlife Management Areas; 84,883.97Ha under proposed Wildlife Management Areas and 22,370.31Ha under Local Authority Forest Reserves. | 75%
| 3. Business plans show improved Financial scorecard for national system of CF protected areas and target landscape (Rufiji, Lindi, Kilwa and Zanzibar) | Average fo financial scorecard is 22.2% | An increase of over 40% in finance score card scores | Financial scorecard | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | NA | NA | NA | An increase of over 40% in finance score card scores | N/A | 0% | N/A Baseline studies are still in progress | N/A. Baseline studies stil in progress | 0% | N/A. Baseline studies stil in progress | Baseline study (completed in 2011) revealed a low level of implementation of existing regulatory frameworks i.e. by-laws, financial instruments in implementing forest conservation activities in coastal districts (27.5% only) as well as application of revenue collection tools which was only 20.2% . | 70% | At this reporting period, the average Financial Scorecard in the Kilwa, Rufiji and Lindi landscapes averaged at 43%; an increase of two folds from the previous baselines. In Zanzibar, the Financial Scorecard had a score of 44%. In general there is a significant improvement in revenue collection both at the Tanzania Forest Service (TFS) and Department of Forest and Non-Renewable Natural Resources (DFNNR) in Zanzibar | 85%
| 4.METT scores for PAs and PA landscapes show improvement in targeted landscapes | The average METT score for PAs is 44.2% | An over increase of 20% in the METT score | METT reports, survey reports | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | NA | NA | NA | An over increase of 20% in the METT score | N/A Baseline studies are still in progress | 0% | N/A. Baseline studies still in progress | N/A. Baseline studies still in progress | 0% | N/A. Baseline studies still in progress | METT scores for around 20 forest sites were completed during PPG phase. However, as the project is about the Coastal Forest sub-system across the entire Tanzania coastal mainland Districts and Zanzibar, we conducted a study of METT for all 146 reserves in the coastal area that we could access | 50% | The up-dated METTs for the PAs in the baseline were completed in Jan 2013. These show an average of 7% improvement and the TFS appears to have greater capacity to deal with coastal forests than in the past. | 85%
Outcome 1: Strengthened Enabling Environment is functioning for Conservation of Coastal of Forests in Mainland Tanzania, Leading to increased funding and oversight | 1. Institutional collaboration for management effectiveness of coastal forests between FBD/TFS and Districts strengtherned | No section and MOUs | Section in place with >2staff, and at least 6 MOUs with District signed | Annual Government and partner PA status reports | Review documents | FBD/TFS Focal person and PMU | Annually | NA | NA | NA | Section with 3 staff, and 3 MOUs with District signed | FBD appointed Officer responsible for Coastal Forests and no MoU signed | 30% | NA | Section in place with 3 staff | 50% | NA | Coastal Forest Section is in place and Four (4) Memorandum of Understanding signed between TFS and four district councils of Mkinga, Muheza, Pangani and Handeni in Tanga region. Implementation of actvities commenced | 50% | 9 Memorandum of Understanding (MoU) agreements over joint responsibilities in conservation of coastal forests were signed between TFS and Districts of Mkinga, Handeni, Muheza, Pangani, Bagamoyo, Mkuranga, Kisarawe, Rufiji, and Kibaha. | 100%
| 2. Increase in staffing levels and funding levels for CF in all four landscapes. Better articulated PA financing needs lead to improved local government budgetary subvention for PAs in 8 districts | Average staff per District on Mainland is <5.Funding <10,000USD | Average staff increased to >10 in 3 districts. Funding exceeds 30,000USD in each of 3 Districts | Annual Government and partner PA status reports | Review documents | FBD/TFS Focal person and PMU | Annually | NA | NA | NA | Average staff increased to >2 in 4 Landscapes. Funding exceeds 15,000USD in each of 2 Districts | NA | 0% | Records of staff increase could not be obtained. | N/A | 0% | NA | FBD/TFS is undertaking staff rellocation exercise and employment in pipeline. Funding level has improved but still remains low in all coastal districts. Only US$33,000 has been ploughed back to utilization control and protection activities during the reporting period | 60% | There has been an increase and relocation of staff at District level. At the beginning of the project there were 27 staff, but at the end of this reporting period there are 72 staff. The increase is as follows: Kisarawe 15(10 for TFS), Bagamoyo 7(3 TFS), Mkuranga 6(2 for TFS),Pangani 7 (3 for TFS), Mkinga8 (7 for TFS), Muheza 8 (7 for TFS), and Handeni 27 (18 for TFS). Total funding for the 9 district was amounting to USD 250,375. | 100%
| 3. Significance % increase in competence levels of protected area institutions for PA including co-management partners;using UNDP-GEF PA Scorecard | Average is 48.5% | None set | UNDP PA Scorecard | Review documents | FBD/TFS Focal person and PMU | Annually | None set | NA | NA | None set | NA | 0% | NA | N/A | 0% | NA | PA Financial score-card baseline study (completed in 2011) revealed a low level of implementation of existing regulatory frameworks i.e. by-laws, financial instruments in implementing forest conservation activities in coastal districts (27.5% only) as well as application of revenue collection tools which was only 20.2% . The score card was applied in the main implementation districts in southern Tanzania (Lindi, Kilwa and Rufiji) | 45% | There was an average of 63.5% for 4 Pas | 70%
| 4.Number of reports produced synthesizing the Annual Status of the PA network (using the ''State-Pressure-Response Models) | Average is 48.5% | 4 by EOP (annual reports for each of the year that the project will run) | METT Annual Report, Annual PA status Reports | Review documents | FBD/TFS Focal person and PMU | Annually | NA | NA | NA | NA | NA | 0 | NA | N/A | NA |  | During the year the project produced a hugely comprehensive assessment of the coastal forest PA network. This include completing METT in 146 reserves, PA score cards in three districts, landscape connectivity analyses in the mainland and on Zanzibar. | 0% | This indicator has been deleted as recommended in the Mid Term Evaluation Report of April 2013. The deletion was endorsed at the PSC meeting in February 2013 and Project planning meeting in May 2013.
| 5. No of VLFR - District Forestry collaborations on Management Plan and households befenefit from IGAs | Nil | At 2 VLFRs in each 4 Districts | Annual reports | Review documents | FBD/TFS Focal person and PMU |  | NA | NA | NA | At least 3 VLFRs in two Districts | NA | 0% | NA | N/A | 0% | Project activities did not start, the project was doing baseline studies | A total of 11 VLFR covering 19,500 ha identified and surveyed in districts of Bagamoyo, Handeni, Mkinga and Pangani. Three VLFR of Kwamduma (4000ha) in Bagamoyo district, Mbuta (2106ha) and Mwakikoya (182ha) in Mkinga district have been gazetted | 65% | A total of 34 Village Land Forest Reserves (VLFRs) covering. A total of 34,103.72ha were demarcated and surveyed. The VLFRs are located in the following districts: Pangani 9 VLFR (19,144.99Ha); Handeni 2 VLFRs (1,933.8Ha); Muheza 7 VLFRs(1,328Ha); Mkinga 4 VLFRs (2,570Ha); Bagamoyo 4 VLFRs (4,677.9Ha) and Kisarawe 8 VLFRs(4,449.04Ha). | 100%
Project Outputs | Indicator | Baseline 2011 | Planned Target by EOP | Data source | Data collection Methods | Responsibility and analysis | Frequency of data collection | Desired Results |  |  |  | FY 2010/11 Monitoring |  |  | FY 2011/12 Monitoring |  |  | FY 2012/13 Monitoring |  | FY 2013/14 Monitoring
[8 empty] | End of FY 2010/2011 | End of FY 2011/2012 | End of FY 2012/2013 | End of FY 2013/2014 | Actual FY Results | Actual VS Desired results(%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Actual FY Results | Actual VS Desired results(%)
Output 1: Capacity built in Tanzania Forest Service) to lead and oversee a Tanzania Coastal Forest Conservation Programme | Staffing level for costal forests | No designated officers | 2 staff at FBD and 2 staff in each District | FBD/TFS report | Review and Interview | FBD/TFSFocal Person | Annual | section in place and officer appointed | at least 2 Officers at FBD | 2 staff in 4 Districts | 2 Staff in 4 Districts | 1 Officer appointed for Coastal Forest | 50% | NA | 2 staff at FBD and one in each eight Districts are in place. | 70% | NA | FBD/TFS is undertaking staff rellocation exercise and staff employment is pipeline. | 75% | There has been an increase and relocation of staff at District level. At the beginning of the project there were 27 staff, but at the end of this reporting period there are 72 staff. The increase is as follows: Kisarawe 15(10 for TFS), Bagamoyo 7(3 TFS), Mkuranga 6(2 for TFS),Pangani 7 (3 for TFS), Mkinga8 (7 for TFS), Muheza 8 (7 for TFS), and Handeni 27 (18 for TFS). | 100%
| Funding level | < 5,000 US$ | Funding exceeds 30,000USD in each of 3 District | Annual Reports and Budgets | Review document | FBD/TFSFocal Person | Annual | Funding exceeding 15,000 US$ in each of 3 Districts | Funding exceeding 15,000 US$ in each of 3 Districts | Funding exceeding 15,000 US$ in each of 2 Districts | Funding exceeding 15,000 US$ in each of 8 Districts | Districts have allocated < 10,000 US$ for forest related operations | 0% | NA | Districts have allocated < 10,000 US$ for forest related operations | 50% | NA | Funding level has improved but still remains low in all coastal districts. Only US$33,000 has been ploughed back to utilization control and protection activities during the reporting period | 60% | Total funding for the 9 districtS was amounting to USD 250,375 | 85%
| Increased stakeholder participation | Not established | Networks in each district eastablished | AnnuaL Reports | Review document | FBD/TFSFocal Person | Annual | Mechanism for establishing networks with various stakeholders initiated | At least 2 networks with NGOs established | At least 3 networks ( NGOs, CBOs and LGA) Interaction) established | At least 2 networks (NGOs, LGAs and TFS interaction) established | Not Implemented | 0% | This process has been going very slow because of staff allocation issues that is going within TFS | Two meetings conducted involving MJUMITA and 5 CBOS on the importance of coastal forest resources | 30% | NA | One meeting with DFOs from Handeni,Pangani,Mkinga and Muheza,RFO of Coast Region ,TFS staffs and WWF staffs was conducted for the purpose of developing Action Plan for 2012/2013. The same workshop was used to provide inputs of developing Communication and Awarenes Strategy lead by a Consultant. | 70% | No meetings were done because of fund delay issues between UNDP and PMU | 65%
Output 2. Coastal Forest Reserves (non reserves) within target landscapes are assessed as to priority for conservation on biodiversity and threat criteria, and conservation strategy developed | Coastal Forest Reserve Area increased and conservation strategy developed and implemented | No conservation plan | Conservation Plan for Coastal Forests | National Forest Programme | Review document | FBD/TFSFocal Person | Annual | NIL | initiate the process | process on progress | finalizing and produce the plan | NIL | 0% | NA | The process of development of Conservation Strategy has not yet started | 0% | NA | The process of development of Conservation Strategy has not yet started | 0% | Consultants have submitted a draft of the Conservation Strategy to TFS for review and comments. The Strategy is expected to be finished before end of project closure. | 75%
| Number and area assessd | 146 Forest Reserves in Costal Forests | 8 VLFRs established, one FR upgraded to NR and 145 Forest reserves and 1 NR managed | GN and Maps | field visit | FBD/TFSFocal Person | Annual | 3 VLFRs established in two Districts | 3 VLFRs established in two Districts | 3 VLFRs established in two Districts | 3 VLFRs established in two Districts | 2 VLFRs established in Bagamoyo and Pangani Districts | 70% | NA | 2 VLFRs established in Mkinga District | 75% | NA | 2 VLFRs established in Mkinga District | 65% | Six districts of Pangani (Msaraza & Mtonga VLFRs), Kisarawe (Gwata VLFRs), Bagamoyo, Mkinga, Kibaha( Lukenge VLFRs) and Handeni ( Mkalamo and Magulumatali VLFRs) have been supported to accomplish PFM processes with communities in these districts trained on PFRA exercise. 80 beacons have been installed at Gwata VLFR. | 100%
Output 3. Conservation management framework established | Coastal forests are managed based approved conservation strategy | 146 Forest Reserves in Costal Forests | 145 Forest reserves and 1 NR managed | Management Plans | review document | FBD/TFSFocal Person | Annua; | At least all Forest Reserves in 4 Districts managed | At least all Forest Reserves in 4 Districts managed | At least all Forest Reserves in 8 Districts managed | At least all Forest Reserves in 8 Districts managed | Not Implemented | 0% | NA | 4 Districts signed MoU to faciltate and manage exisiting coastal forests | 50% | NA | 4 Districts signed MoU to faciltate and manage exisiting coastal forests | 50% | 9 Memorandum of Understanding (MoU) agreements over joint responsibilities in conservation of coastal forests were signed between TFS and Districts of Mkinga, Handeni, Muheza, Pangani, Bagamoyo, Mkuranga, Kisarawe, Rufiji, and Kibaha. | 100%
Output 4. MOU put in place with Coastal Forest Districts over joint responsibilities in conservation of Coastal Forests. | Improved coastal forests management | No MoUs | 6 MoUs | annual reports | review document | FBD/TFSFocal Person | annual | 2 MoUs signed | 3 MoUs signed | 2 MoUs signed | 2 MoUs signed | No MoU signed | 0% | NA | 4 Districts signed MoU to faciltate and manage exisiting coastal forests | 100% | NA | 4 Districts signed MoU to faciltate and manage exisiting coastal forests | 100% | 9 Memorandum of Understanding (MoU) agreements over joint responsibilities in conservation of coastal forests were signed between TFS and Districts of Mkinga, Handeni, Muheza, Pangani, Bagamoyo, Mkuranga, Kisarawe, Rufiji, and Kibaha. | 100%
Output 5. REDD initiatives adopted for Coastal Forest Landscapes, management | REDD initiatives incorporated into coastal forest management | REDD National Framework | 5 forest reserves adopt REDD initiatives | National Carbon Monitoring Centre | Review and Interview | FBD/TFSFocal Person | annual | SOrrounded communities in 2 FRs informed on REDD | surrounded communities in 2 FRs informed on REDD | Communities in 3 FRs practice REDD plans | Communities in 2 FRs practice REDD plans | Communities adjacent Pugu and Kazimzumbwi were involved in REDD activities through WCST project | 50% | NA | Communities adjacent Pugu and Kazimzumbwi were involved in REDD activities through WCST project | 25 | NA | Communities adjacent Pugu and Kazimzumbwi were involved in REDD activities through WCST project | 50% | The same as previous quarter | 50%
Output 6. Monitoring and Evaluation at Project Level Implemented | Number of M&E conducted | M&E system for MDA and LGAs | Monitoring conducted quarterly and Evaluation semi- annually | M&E plan | review document | FBD/TFSFocal Person and PMU (WWF) | annual | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted in 3 Districts (Pangani, Mkinga and Muheza) two times | 60% | NA | Monitoring of project activities has been conducted in two quarters at Rondo FR and two Districts of Mkinga and Pangani | 60% | NA | Monitoring of project activities has been conducted in two quarters at Rondo FR and two Districts of Mkinga and Pangani | 60% | Monitoring of project activities was conducted in Mkinga,Bagamoyo, Kisarawe, Muheza and Pangani districts assessing the progress of community groups that are involved in tree planting and horticulture activities. | 100%
Project Activities | Indicator | Baseline 2011 | Planned Target by EOP | Data source | Data collection Methods | Responsibility and analysis | Frequency of data collection | Desired Results |  |  |  | FY 2010/11 Monitoring |  |  | FY 2011/12 Monitoring |  |  | FY 2012/13 Monitoring |  | FY 2013/14 Monitoring
[8 empty] | End of FY 2010/2011 | End of FY 2011/2012 | End of FY 2012/2013 | End of FY 2013/2014 | Actual FY Results | Actual VS Desired results(%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Actual FY Results | Actual VS Desired results(%)
1.1 To acquire facilities and equipment for TFS unit | Facilities and equipment provided and maintained | No Computers, Vehicle, assessories and furnitures | 3 Computers, 1 pick up, 4 office chairs, I cabnet, 1 camera and 2 GPS p | Ledger book | Review Document | FBD/TFSFocal Person | Annual | 3 Computers, 1 pick up, 4 office chairs, I cabnet, 1 camera and 2 GPS available | NA | NA | NA | Not Imolemented | 0% | By this reporting period the project activities did not start. | 3 Computers, 1 pick up, 4 office chairs, I cabnet, 1 camera and 2 GPS procured | 100% | NA | NA | NA | NA | NA
1.2 To establish networks among parties in the management of coastal forests | Networks among parties established | No networks exist | Networks in each district eastablished | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | Mechanism for establishing networks with various stakeholders initiated | At least 2 networks with NGOs established | At least 3 networks ( NGOs, CBOs and LGA) Interaction) established | At least 2 networks (NGOs, LGAs and TFS interaction) established | Not Implemented | 0% | By this reporting period the project activities did not start. | Two meetings were conducted involving MJUMITA and 5 CBOS on the importance of coastal forest resources | 60% | NA | The results are the same as the previous monitoring and reporting period | 60% | The results are the same as the previous monitoring and reporting period | 60%
1.3 To facilitate TFS unit to oversee day to day implementation of activities | Office run expenses met | No facilities to maintain | Purchase Diesel for Vehicle, stationeries, tonners and maintained and service equipment | Ledger books | Review Document | FBD/TFSFocal Person | Annual | Purchase Diesel for Vehicle, stationeries, tonners and maintained and service equipment | Purchase Diesel for Vehicle, stationeries, tonners and maintained and service equipment | Purchase Diesel for Vehicle, stationeries, tonners and maintained and service equipment | Purchase Diesel for Vehicle, stationeries, tonners and maintained and service equipment | Not Implemented | 0% | By this reporting period the project activities did not start. | Various items purchased, one vehicle serviced and maintained | 100% | NA | The results are the same as the previous monitoring and reporting period | 100% | The results are the same as the previous monitoring and reporting period | 100%
1.4 To conduct capacity needs assessment at TFS,district /landscape levels (staff, infrastructure, training) | Capacity needs assessed | No Information | Capacity needs conducted for coastal Forests | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | Capacity needs assessment conducted for coastal forests at FBD, in Districts and Landscape levels | Capacity needs assessment conducted for coastal forests at FBD, in Districts and Landscape levels | NA | NA | Capacity needs assessed for Staff and available resources at FBD and Districts to manage well coastal forests | 100% | NA | Completed | 100% | NA | Completed | 100% | Completed | 100%
1.5 To prepare training modules based on training needs assessment | Training modules developed | No Information | Training module developed | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | Develop training modules based on capacity needs assessment reports | NA | NA | NA | Training modules developed based on capacity needs assessment report | 100% | NA | Completed | 100% | NA | Completed | 100% | Completed | 100%
1.6 To support tailor made courses for staff (TFS, Districts, and NGOs) based on needs assessment. | Number of staff trained and type of tailor made course | NIL | at least 100 trainees from TFS, Districts, NGOs | Annual reports and Attendance/Certificates | Review Document | FBD/TFSFocal Person | Annual | at least 30 trainees from TFS, Districts, NGOs | at least 20 trainees from TFS, Districts, NGOs | at least 40 trainees from TFS, Districts, NGOs | at least 10 trainees from TFS, Districts, NGOs | 23 staff from TFS, Districts and NGOs tained on Project Planning and Entrepreneurship at UDSM | 90% | NA | 17 Staff from TFS and Districts trained on forest management and governance at MSTCDC Arusha | 50% | NA | No staff received tailor made courses | 0% | No staff received tailor made courses | 0%
1.7 To facilitate consultative fora among stakeholders | Number of consultative fora conducted and stakeholders reached | NIL | Four stakeholders fora organised, one forum each year to improve collaborative measures on coastal forest management | Annual Reports, Attendance Sheets | Review Document | FBD/TFSFocal Person | Annual | Stakeholders forum to improve collaborative measures on coastal forest management organised | Stakeholders forum to improve collaborative measures on coastal forest management organised | Stakeholders forum to improve collaborative measures on coastal forest management organised | Stakeholders forum to improve collaborative measures on coastal forest management organised | One stakeholder forum was organized with stakeholders from five districts of Tanga region on management of Coastal Forests | 100% | NA | Forum on stakeholder collaborative in the management of coastal forests was organised in Tanga. | 100% | NA | One meeting with DFOs from Handeni,Pangani,Mkinga and Muheza,RFO of Coast Region ,TFS staffs and WWF staffs was conducted for the purpose of developing Action Plan for July-December 2012. | 100% | One meeting involving DFOs, DFMs from 9 districts of Panngani, Muheza, Mkinga Handeni, Kisarawe, Mkuranga, Kibaha , Bagamoyo and Kibaha Town Council. The meeting was held to prepare the workplan and budgets for implementation of coastal forests activities for the next quarter and assessing challenged in implementing project activities. | 100%
2.1 To undertake protected area gap analysis and identify location of potential new reserves and corridors in the coastal region | New reserves and corridors identified | 146 FRs | Engage Consultant gap analysis and identify new reserves | Report | Review Document | FBD/TFSFocal Person | Annual | Engage Consultant gap analysis and identify new reserves | NA | NA | NA | Not Implemented | 0% | NA | The Consultant was recruited in January 2011 and the study was completed in June 2011 | 100% | NA | Completed | 100% | Completed | 100%
2.2 To undertake study on economic analysis of Coastal Forests and financing for management effectiveness | Economic study conducted and Financing proposals/opportunities prepared for funding | NIL | Engage Consultant to carryout economic study and financing proposals | Report | Review Document | FBD/TFSFocal Person | Annual | NA | Engage Consultant to carryout economic study and financing proposals | NA | NA | Not Implemented | 0% | NA | The Consultant was recruited in May 2011 and the study was completed in October 2011 | 100% | NA | Completed | 100% | Completed | 100%
2.3 To identify and support potential income generating activities plus community tree growing initiatives (e.g. cashew nut farming, beekeeping, fish farming, fruit trees, passion) | Number of Households participating in tree growing and engaged in IGAs | NIL | at least 100 household in each District supported | Report | Review Document | FBD/TFSFocal Person | Annual | N/a | at least 25 household in each District supported | at least 40 household in each District supported | at least 30 household in each District supported | Not Implemented | 0% | The project was still doing baseline studies. | Not Implemented | 0% | NA | A total of 130 Villagers from 10 groups were trained on beekeeping skills and marketing of beekeeping products. Training was done in four District namely Pangani (Kwakuyu and Mtoga villages , Muheza(Bwiti and Mbambara villages), Handeni (Gendagenda , Kwadihwahwala) and Mkinga (Bamba and Kichangani villages). | 100% | Completed | 100%
2.4 To review feasibility of establishing different PA management models for landscape systems | Feasibility study conducted | NIL | Form taskforce to carryout feasibility study | Report | Review Document | FBD/TFSFocal Person | Annual | N/a | N/a | Form taskforce to carryout feasibility study | NA | Not Implemented | 0% | NA | Not Implemented | 0% | NA | Not Implemented | 0% | Not Implemented | 0%
2.5 To prepare conservation strategy for coastal forests within the NFP framework | Conservation strategy developed | NIL | Develop ToR and engage consultant | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | N/a | N/a | Develop ToR and engage consultant | NA | Not Implemented | 0% | The project was still doing baseline studies. | Not Implemented | 35% | NA | TORs developed and advertizement done to select a Consultant for the Activity | 35% | The Consultant has been engaged and has prepared and submitted a draft 1 to TFS/PMU for review process | 65%
2.6 To identified and scale up PFM best practices | PFM best practices identified and replicated | NIL | Form taskforce to identify best practices, scale up best practices by organise 8 exchange visits and conduct field training workshops | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | N/a | Form taskforce to identify best practices, | scale up best practices by organise 4 exchange visits and conduct field training workshops | scale up best practices by organise 4 exchange visits and conduct field training workshops | Not Implemented | 0% | The project was still doing baseline studies. | Taskforce formed and best practices identification on progress | 50% | NA | The same as on previous reporting period | 50% | The same as on previous reporting period | 50%
3.1 To train communities on business plan in operationalizing IGAs | Number of communities trained | NIL | at least 8 groups (>10) in each district trained | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | N/a | N/a | at least 4 groups (>10 members) in each district trained | at least 4 groups (>10 Members) in each district trained | Not Implemented | 0% | The project was still doing baseline studies. | Not Implemented | 0% | NA | A total of 130 Villagers from 10 groups were trained on beekeeping skills and marketing of beekeeping products. Training was done in four District namely Pangani (Kwakuyu and Mtoga villages , Muheza(Bwiti and Mbambara villages), Handeni (Gendagenda , Kwadihwahwala) and Mkinga (Bamba and Kichangani villages). | 100% | Completed | 100%
3.2 To facilitate and support communities to develop business plan and undertake IGAs. | Number communities facilitated | NIL | at least 8 groups (<20) in each district facilitated | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | N/a | N/a | at least 4 groups (<20 Members) in each district facilitated | at least 4 groups (<20 Members) in each district facilitated | Not Implemented | 0% | The project was still doing baseline studies. | Not implemented | 0% | NA | A total of 130 Villagers from 10 groups were trained on beekeeping skills and marketing of beekeeping products. Training was done in four District namely Pangani (Kwakuyu and Mtoga villages , Muheza(Bwiti and Mbambara villages), Handeni (Gendagenda , Kwadihwahwala) and Mkinga (Bamba and Kichangani villages).Beekeeping will be an alternative source of income to the communities adjacent to forest. 2) A total of 200 beehives constructed/ordered for distribution to the communities. | 85% | Trained groups received support from TFS including support to hire tractor for Hotculltural activities in Pangani for ploughing 100has weeding 30 Has Farms as well as well as procurement of quality seeds | 95%
| Number of business plans developed and type of IGA | NIL | 32 business plans developed | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | N/a | N/a | 16 business plans developed | 16 business plans developed | Not Implemented | 0% | The project was still doing baseline studies. | Not Implemented | 0% | NA | Not Implemented | 0% | Not Implemented | 0%
3.3 To establish Forest Reserves under different PA management models for landscape systems including Nature Reserves and FRs, VLFRs. | Number and type of reserve established and or upgraded | 1 FR identified for upgrading | 8 VLFRs established and 1 FR upgraded to NR | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | 2 VLFRs established and upgrading process FR to NR started | 2 VLFRs established and upgrading process FR to NR on progress | 2 VLFRs established and upgrading process FR to NR on progress | 2 VLFRs established and 1 FR upgraded to NR | Not Implemented | 0% | The project was still doing baseline studies. | Two VLFRs established in Bagamoyo districts | 100% | NA | A total of 23 forests have been identified for VLFRs processes in Mkinga, Pangani, Handeni, Muheza, Kisarawe, Kibaha and Bagamoyo districts | 90% | 34 VLFRs (10 have been approved at Community and District levels) have been established in Mkinga, Pangani, Handeni, Muheza, Kisarawe, Kibaha and Bagamoyo districts. Rondo FR has been upgraded to Nature Reserve. | 100%
3.4 To consolidate boundaries of existing forest reserves in four Districts | Number and area of forest boundaries resurveyed and maintained in four Districts | FRs in for Districts | 1200 km of forest bounderies reserveyed | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | 200 km of forest bounderies resurveyed | 400 km of forest bounderies resurveyed | 400 km of forest bounderies reserveyed | 200 km of forest bounderies resurveyed | Not Implemented | 0% | At this reprorting report the project was still doing baseline studies | 142 km of forest bounderies resurveyed and assingment on progress. | 45% | NA | Boundary resurvey of existing forest reserves was done in four Districts namely Muheza, [ Kwani FR (29.3 km) and Tongwe FR (13.9 km)], Mkinga [Mlungui FR (6.5 km), Bamba FR (13.5km)], Pangani [Msubugwe FR (28.7km)]. Boundary cleared of vegetation was also done. | 65% | Boundary verification and resurvey has been done and becons installed in Kibaha and Bagamoyo districts for Vikindu, Gendagenda, Lukenge and Msua, Masanganya FRs while Tukamisasa and Mkoko VLFRs were demarcated in Bagamoyo. district. | 85%
3.5 To facilitate establishment and functioning of VECs (VNRCs) including working gears. | Number of VECs in place | VNRCs in place | at 10 VECs formed in each four Districts | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | NA | NA | At least 10 VECs formed in each four Districts | At least 10 VECs formed in each four Districts | Not Implemented | 0% | NA | Not Implemented | 0% | NA | Not Implemented | 0% | Not Implemented | 0%
| Number and type of working gears provided | NIL | 20 sets of working gears provided | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | NA | NA | 10 sets of working gears provided | 10 sets of working gears provided | Not Implemented | 0% | NA | Not Implemented | 0% | NA | Not Implemented | 0% | Not Implemented | 0%
4.1 To prepare MOU for overseeing and managing coastal forests between TFS and Districts | Number of MoU signed | NIL | 6 MoUs signed | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | NA | 2 MoUs signed | 2 MoUs signed | 2 MoUs signed | No MoU signed | 0% | The project delayed to start activities | 4 MoUs were signed between TFS and Districts of Mkinga, Muheza, Pangani and Handeni. | 100% | NA | No MoU was signed. | 0% | 9 Memorandum of Understanding (MoU) agreements over joint responsibilities in conservation of coastal forests were signed between TFS and Districts of Mkinga, Handeni, Muheza, Pangani, Bagamoyo, Mkuranga, Kisarawe, Rufiji, and Kibaha. | 100%
4.2 To support four (4) Districts in implementation of the project activities | Funding levels for coastal forest management in each district | < 5,000 US$ | Funding exceeds 30,000USD in each of 3 District | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | Funding exceeding 15,000 US$ in each of 3 Districts | Funding exceeding 15,000 US$ in each of 3 Districts | Funding exceeding 15,000 US$ in each of 2 Districts | Funding exceeding 15,000 US$ in each of 8 Districts | Districts have allocated < 10,000 US$ for forest related operations | 0% | NA | Districts have allocated < 10,000 US$ for forest related operations | 50% | NA | Funding level has improved but still remains low in all coastal districts. Only US$33,000 has been ploughed back to utilization control and protection activities during the reporting period | 60% | Total funding for the 9 districtS was amounting to USD 250,375 | 85%
4.3 To assess feasibility of promoting tourism in coastal forest areas | Number of tourism attractions identified | Coastal Tourism Master Plan | Develop ToR, engage consultant and provide recommendation for identified attractions | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | NA | NA | Develop ToR, engage consultant and provide recommendation for identified attractions | NA | Not Implemented | 0% | NA | Same as previous reorting period | 0% | NA | Same as previous reporting period | 0% | Same as previous reporting period | 0%
4.4 To support development of tourism attractions identified | Number of tourism attractions supported | NIL | At least 2 identified attractions supported in each District | Annual Reports | Review Document | FBD/TFSFocal Person | Annual | NA | NA | One identified attraction supported in each district | One identified attraction supported in each district | Not Implemented | 0% | NA | Same as previous reorting period | 0% | NA | Same as previous reporting period | 0% | Same as previous reporting period | 0%
5.1 To link communities with REDD initiatives for sustainable management of coastal forests in 4 Districts. | Number of communities linked with REDD initiatives | REDD National Framewrok | 5 forest reserves adopt REDD initiatives | National Carbon Monitoring Centre | Review Document | FBD/TFSFocal Person | Annual | Sorrounding communities in 2 FRs informed on REDD | Sorrounding communities in 2 FRs informed on REDD | Communities in 3 FRs practice REDD plans | Communities in 2 FRs practice REDD plans | Communities adjacent Pugu and Kazimzumbwi were involved in REDD activities through WCST project | 50% | NA | Communities adjacent to Pugu and Kazimzumbwi FRs were involved in REDD activities through WCST project | 50% | NA | Communities adjacent Pugu and Kazimzumbwi were involved in REDD activities through WCST project | 50% | Same as previous reorting period | 50%
To carry out M&E for continous feedback | Number of M&E conducted | M&E system for MDA and LGAs | Monitoring conducted quarterly and Evaluation semi- annually | M&E plan | Review Document | FBD/TFSFocal Person and PMU (WWF) | Annual | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted quarterly and Evaluation semi- annually | Monitoring conducted in 3 Districts (Pangani, Mkinga and Muheza) two times | 75% | Communities have gained knowledge on the importance of coastal forests. | Monitoring conducted in two quarters at Rondo FR and two Districts | 55% | NA | Monitoring visits have been conducted in Districts of Bagamoyo, Mkinga and Pangani to check the progress of new VLFRs. | NA | Monitoring visits were done in Mkinga, Pangani, Bagamoyo and Handeni with WWF PMU team to assess and record radio and TV programs for awareness raising on project activities and Coastal Forest | 85%

## M&E Plan OUTCOME 2 DFNNR Z'BAR
MONITORING PLAN FOR GEF COASTAL FOREST PROJECT OUTCOME 2 DFNNR ZANZIBAR)
Project Goal | The coastal Forest Biodiversity and Ecosystem Values are Conserved and Provide Sustainable Benefit Flows at Local, National and Global Levels
Project purpose | Indicator | Baseline 2011 | Planned Target by EOP | Data source | Data collection Methods | Responsibility and analysis | Frequency of data collection | Desired Results |  |  |  | FY 2010/11 Monitoring |  |  | FY 2011/12 Monitoring |  |  | FY 2012/13 Monitoring |  | FY 2013/14 Monitoring
[8 empty] | End of FY 2010/2011 | End of FY 2011/2012 | End of FY 2012/2013 | End of FY 2013/2014 | Actual FY Results | Actual VS Desired results(%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Actual FY Results | Actual VS Desired results(%)
Outcome 2: The protected Area system for Zanzibar is strengthened in terms of both representativeness, connectivity, financing and managerial capacity | 1. The protected Area Authourity is reconstituted, with viable TOR and meets frequently. | Defunct, has not met in over two years | Reconstituted PAA, with updated ToR, and meets twice annually | Government report, meeting minutes and project reports | Review documents | DFNRNR focal person and PMU | Semi annually | End of FY 2010/2011 | End of FY 2011/2012 | End of FY 2012/2013 | End of FY 2013/2014 | Actual FY Results | Actual VS Desired results(%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Actual FY Results | Actual VS Desired results(%)
[8 empty] | Consultant engaged to review the Protected Area Board and produce report. | Reconstitution of the Board | Board functional through meetings and visit PAs | Board functional through meetings and visit PAs | The Consultant was engaged to review the Board reconstitution process. | 100% | NA | The Consultant produced the report, the process to reconstitute the new board has started. | 70% | The process is taking longer than expected. | Review process on re-formation of the NPA Board is in progress , presentation of a Cabinet paper to the Minister of Environment who in turn wil take it to the Cabinet is underway. | 40% | The National Protected Area Board was reviewed and cabinet paper presented to respective ministries. The Board has been reconstituted with new members and ToRs. 13 members will now sit on the Board. | 45%
| 2. DFNRNR has a conservation section in place that is staffed and functional | No distinct section | Section with sufficient staff and resources to implement mandate | DFNRNR updated organogram, project reports | Review documents | DFNRNR focal person and PMU | Semi annually
[8 empty] | Consutant engaged to review Conservation Section and propose the structure. | Conservation section staff nominated and facilitated to perform their duties. | Conservation staff empowerd with trainings and working facilities. | Conservation staff empowerd with trainings and working facilities | Consultant has been engaged to review and propose structure of the Conservation section. | 100% | NA | Consultant produced report and project staff nominated. | 100% | NA | Full function Conservation Section (now known as Biodiversity Conservation and Managementis) in place and strengtherned with additional staff as Assistant to Focal Person of CFP | 100% | Conservation (Biodiversity) section has been established and staff appointed. The section has a mandate to oversee and manage protected areas and sufficient resources and facilities to support the implementation of activities. | 100%
| 3. The terrestrial PA network increases in area and connectivity | Six PAs totalling 12,241ha | System increased by atleast 3 gazetted PAs(at least 5,000ha), with improved connectivity between existing sites | Maps, Governement and project reports | Review documents | DFNRNR focal person and PMU | Annually | Potential areas for protection identified | 4000 ha Surveyed, mapped and gazetted as new areas for conservation. | 2000 ha Surveyed, mapped and gazzetted as new areas for conservation. | System increased by atleast 3 gazetted PAs(at least 5,000ha), with improved connectivity between existing sites | NA | 0% | The project was doing baseline studies | Project activities for this task did not start because the project was still doing baseline studies. | 0% | Project activities for this task did not start as the project was still doing baseline studies. | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. | 75% | Jambiani-Muyuni Protected Area (4,200Ha) and the Ufufuma Pongwe Corridor (6,000Ha) formed a total area of 10,200ha which have been demarcated and mapped. Final gazettement process is underway | 85%
| 4. Village partners and CBOs/NGOs involved in PA conservation through VFRs, with financial and technical support from Government | Community Forest Areas in 12 sites | Community Forest Areas provide buffer functions around All Forest PAs | Government and project reports | Review documents | DFNRNR focal person and PMU | Annually
[7 empty] | Annually | 4 communities/NGOs supported | 4 communities/NGOs Supported | 4 communities/NGOs Supported | NA | NA | 0% | The project was doing baseline studies | NA | 0% | Project activities for this task did not start because the project was still doing baseline studies. | Two new Community Forest Management Agreements (CoFMA) developed around Ufufuma-Pongwe forest corridor FR and Seven (7) old one reviewed. | 60% | Seven new Community Forest Management Areas have been established with a total area of 1,928.58Ha. These are from Pagali (174.8Ha), Uroa (1,014.3Ha), Pwani Mchangani (60.23Ha), Pongwe (416.3Ha), Kandwe (194.92Ha), Pangeni (49.83Ha) and Konde (18.2Ha | 80%
| 5. Protected Areas with Management plans approved and under implementation leading to improved METT scores | Two forest PAs (Ngezi and Jozani) with plans; but limited implementation. METT averages 51% | All six PAs (Jozani, Ngezi, Ras Kiuyu, Masingini, Kiwengwa and Msitu Mkuu Management plans under implementation. METT > 20% increase | METT filed form, Government and project reports | Review documents | DFNRNR focal person and PMU | Annually | NA | NA | NA | All six PAs (Jozani, Ngezi, Ras Kiuyu, Masingini, Kiwengwa and Msitu Mkuu Management plans under implementation. METT > 20% increase | NA | 0% | NA | Review of one management plan for Kiwengwa Forest Reserve was completed and preparation of management plan for Masingini forest reserves commenced. METT scores (Kiwengwa FR -53, and Masingini FR-45 | 50% | NA | Review of one management plan for Kiwengwa Forest Reserve was completed and preparation of management plan for Masingini forest reserves commenced. METT scores (Kiwengwa FR -53, and Masingini FR-45) | 70% | Two Management plans have been developed, approved and are being used, covering Kiwengwa-Pongwe and Masingini Forest Reserve. Also Jozani Chwaka Bay National Park regulations have been reviewed. METTs for 4 PAs ( Mtende, Jozani-Chwaka, Ngezi and Muyuni) has exceeded the previous by 63%. | 75%
| 6. Significance % increase in competence levels of protected area institutions for PA including co-management partners;using UNDP-GEF PA Scorecard | Average is 51% | Increase by 20% | UNDP PA Scorecard | Review documents | DFNRNR focal person and PMU | Annually | NA | NA | NA | Increase by 20% | NA | 0% | NA | N/A | 0% | Project baseline studies were in progress | PA Financial score-card baseline study (completed in 2011) revealed a low level of implementation of existing regulatory frameworks i.e. by-laws, financial instruments in implementing forest conservation activities in coastal districts (27.5% only) as well as application of revenue collection tools which was only 20.2% . The score card was applied in the main implementation districts in southern Tanzania (Lindi, Kilwa and Rufiji). All data are retained in the form of a report and excel files and this will allow changes by EOP to be measured. | 0% | This indicator has been dropped as recommended in the Mid Term Evaluation Report of April 2013. The deletion was endorsed at the PSC meeting in February 2013 and Project planning meeting in May 2013. | 0%
| 7.Number of reports produced synthesizing the Annual Status of the PA network (using the ''State-Pressure-Response Models) | Nil | 4 by EOP (annual reports for each of the year that the project will run) | METT Annual Report, Annual PA status Reports | Review documents | DFNRNR focal person and PMU | Annually | NA | NA | NA | 4 by EOP (annual reports for each of the year that the project will run) | NA | 0% | NA | NA | 0% | NA | NA | 0% | This indicator has been dropped as recommended in the Mid Term Evaluation Report of April 2013. The deletion was endorsed at the PSC meeting in February 2013 and Project planning meeting in May 2013. | 0%
| 8. No of VLFR(COFMA) - with Government collaborations on Management Plans | Nil | 4 By EOP ( annual reports from the project) | Annual reports | Review documents | DFNRNR focal person and PMU | Annually | NA | NA | NA | 8. No of VLFR(COFMA) - with Government collaborations on Management Plans | The project was still doing baseline studies. | 0% | NA | NA | 0% | DFNNR was still nominating staff to carry out activities. | Two new Community Forest Management Agreements (CoFMA) developed around Ufufuma-Pongwe forest corridor FR while Seven (7) old COFMAs have been reviewed. | 70% | Two new Community Forest Management Agreements (CoFMA) developed around Ufufuma-Pongwe forest corridor FR while Seven (7) old COFMAs have been reviewed. | 70%
Output 2.1 Government of Zanzibar with a functional and sustainable institutional structure for terrestrial Protected Areas at Board level and Conservation Section within Forest Department | Board reconstituted and functional | Defunct, has not met in over two years | PAB reconstituted, with updated ToR, and meets twice a year | Board meetings minutes and project reports | Review documents | Board secretariate and focal person | Semi annually | Consultant engaged to review the Protected Area Board and produce report. | Reconstitution of the Board | Board functional through meetings and visit PAs | Board functional through meetings and visiting PAs | The Consultant was engaged to review the Board reconstitution process | 100% | NA | The Consultant produced the report, the process to reconstitute the new board has started | 70% | The process is taking longer than expected. | Review process on re-formation of the NPA Board is in progress , presentation of a Cabinet paper to the Minister of Environment who in turn wil take it to the Cabinet is underway. | 40% | The National Protected Area Board was reviewed and cabinet paper presented to respective ministries. The Board has been reconstituted with new members and ToRs. 13 members will now sit on the Board. | 45%
| Number of staff with capacity allocated for Conservation Section(CS) | No distinct section | Section with sufficient staff and resources to implement mandate | project reports | Review documents | DFNRNR focal person | Semi annually | Conservation section reviewed | Conservation section staff nominated and facilitated to perform their duties. | Conservation staff empowerd with trainings and working facilities. | Conservation staff empowerd with trainings and working facilities | Consultant has been engaged to review and propose structure of the Conservation section. | 100% | NA | Consultant produced report and project staff nominated. | 100% | NA | Full function Conservation Section (now known as Biodiversity Conservation and Managementis) in place and strengtherned with additional staff as Assistant to Focal Person of CFP | 100% | Conservation (Biodiversity) section has been established and staff appointed. The section has a mandate to oversee and manage protected areas and sufficient resources and facilities to support the implementation of activities. | 100%
Activities 2.1.1 - 2.1.6
2.1.1 Review present institutional structures for conservation of biodiversity as to functionality | Institutional structure reviewed. | No distinct section | Section with sufficient staff and resources to implement mandate | , project reports | Review documents | DFNRNR Focal person | Once | Conservation section reviewed | 20 conservation staffs nominated | Staff empowerment | Staff empowerment through trainigs | Consultant has been engaged to review and propose structure of the Conservation section. | 100% | NA | Consultant produced report and project staff nominated. | 100% | NA | Full function Conservation Section (now known as Biodiversity Conservation and Managementis) in place and strengtherned with additional staff as Assistant to Focal Person of CFP | 100% | Full function Conservation Section (now known as Biodiversity Conservation and Managementis) in place and strengtherned with additional staff as Assistant to Focal Person of CFP | 100%
2.1.2 Reconstitute National Protected Area Board with capacity to provide oversight and leadership. | PAB reconstituted and functiomal | Defunct, has not met in over two years | PAB reconstituted, with updated ToR, and meets twice a year | Board meetings minutes and project reports | Review documents | Board secretariate and Focal person | Semi annually | Consultant engaged to review the Protected Area Board and produce report. | Reconstitution of the Board | Board functional through meetings and visit Pas | Board functional through meetings and visiting Pas | The Consultant was engaged to review the Board reconstitution process. | 100% | NA | The Consultant produced the report, the process to reconstitute the new board has started | 70% | The process is taking longer than expected. | Review process on re-formation of the NPA Board is in progress , presentation of a Cabinet paper to the Minister of Environment who in turn wil take it to the Cabinet is underway. | 40% | The National Protected Area Board was reviewed and cabinet paper presented to respective ministries. The Board has been reconstituted with new members and ToRs. 13 members will now sit on the Board. | 45%
| Board standing orders in place. | Nil | Board standing orders in place. | Official Gazzete, Project Reports | Review documents | DFNRNR Focal person and Board secretariet | Once | Board standing orders in place. | Board standing orders in place. | Board standing orders in place. | Board standing orders in place. | The Consultant was engaged to review the Board reconstitution process. | 40% | NA | The Consultant produced the report, the process to reconstitute the new board has started | 50% | The process is taking longer than expected. | Review process on re-formation of the NPA Board is in progress , presentation of a Cabinet paper to the Minister of Environment who in turn wil take it to the Cabinet is underway. | 60% | The National Protected Area Board was reviewed and cabinet paper presented to respective ministries. The Board has been reconstituted with new members and ToRs. 13 members will now sit on the Board | 70%
2.1.3 Empower Conservation Section that manages the Protected Areas (material, fund and personel). | CS staff with management capacity | Nill | CS staff appointed | Reports | Review documents | DFNRNR Focal person | Once | Consutant engaged to review Conservation Section and propose the structure. | Conservation section staff nominated and facilitated to perform their duties. | Conservation staff empowerd with trainings and working facilities. | Conservation staff empowerd with trainings and working facilities | Consultant has been engaged to review and propose structure of the Conservation section. | 100% | NA | Consultant produced report and project staff nominated. | 100% | NA | Full function Conservation Section (now known as Biodiversity Conservation and Managementis) in place and strengtherned with additional staff as Assistant to Focal Person of CFP | 100% | Conservation (Biodiversity) section has been established and staff appointed. The section has a mandate to oversee and manage protected areas and sufficient resources and facilities to support the implementation of activities. | 100%
2.1.4 Conduct Training need assessment for Conservation section | Number of trainings | Nill | Training need assessment | Reports | Review documents | DFNRNR Focal person | Once | Conservation section reviewed | Training need assessment | Training need assessment | NA | Not Done | 0% | The project was doing baseline studies | The Consultant has been engaged to conduct staff training needs assessmenyt | 50% | NA | 5 DFNNR staff attended training on project management and MS Excel in Morogoro. | 75% | Done | 75%
2.1.5 Support tailor made courses for staff (DFNRNR, District and NGOs) based on need assessment and training plan. | Number. of tailor made courses | Nill | Enterprenewship, ToT , Low enforcement, Payment and environmental service, Computer data analysis, Driving, Fire management Conflict managenet and business plan NR mgt and governance | Reports | Review documents | DFNRNR Focal person | Quarterly | Enterprenewship, ToT , Low enforcement, Payment and environmental service, Computer data analysis, Driving, Fire management Conflict managenet and business plan NR mgt and governance | Enterprenewship, ToT , Low enforcement, Payment and environmental service, Computer data analysis, Driving, Fire management Conflict managenet and business plan NR mgt and governance | Enterprenewship, ToT , Low enforcement, Payment and environmental service, Computer data analysis, Driving, Fire management Conflict managenet and business plan NR mgt and governance | Enterprenewship, ToT , Low enforcement, Payment and environmental service, Computer data analysis, Driving, Fire management Conflict managenet and business plan NR mgt and governance | Not Done | 0% | The project was doing baseline studies | This activity was not done during this period because DFNNR was dealing with staff structuring issues. | 0% | Not done because of staff structuring issues at DFNNR. | Two staff attended short course on Computer accounting and Stores Management skills and Methods at the Institute of Sales promotion. Also Two staff attended short course on Industrial Advanced driving Skills -STAGE II at National Insititute of Transport, Dar-es-salaam-Tanzania. | 100% | 10 DFNR staff (2 Pemba: 8 Unguja) attended five days course at Bussiness school of University of Dar-es-salaam with Certification. Main areas of study including Project planning, Project activities monitoring and Evaluation, and Project financial/control managementMwanza | 100%
Output 2.2 Terrestrial Protected Area Network expanded to include key gaps in coral rag and thicket communities of high biodiversity, with buffer and connectivity forests | Number of PAs identified | Six Protected Areas | 3 Protected Areas | Reports , Government notice, maps | Survey,and review documents | DFNRNR Focal person | Quarterly reports | Not applicable | 1PA | 1 PA | 1 PA | NA | 0% | The project was doing baseline studies | Two stakekeholders consultative and awareness workshop were held and attended by 58 distinguished participants from different institutions and communi The participants accepted Ufufuma Pongwe Forest corridor protections. The meetings proposed new 2 PAs which are Jambiani Muyuni Forest Reserve (4,200 ha) and Ufufuma Pongwe. Notice of intent to gazzete the forest was prepared and sent to the Principal Secretary of the Ministry of Agric and Natural Resources through Director DFNRNR for further legal proceedings.. | 100% | NA | Survey and mapping of Jambian - Muyuni proposed conservation areas was conducted and 6000 ha has been dermarcated as potential PA. One consultative meeting for Ufufuma-Pongwe Advisory Committee was conducted for the establishment of the corridor. | 100% | Survey and mapping of Jambian - Muyuni proposed conservation areas was conducted and 6000 ha has been dermarcated as potential PA. One consultative meeting for Ufufuma-Pongwe Advisory Committee was conducted for the establishment of the corridor. | 50%
| Area ( Hectares) gazzeted | Six PAs totalling 12,241ha | 6000 ha increased | Survey reports and maps | Survey,and review documents | DFNRNR focal person | Quaterly reports | NA | 2 Course on VIP Driving, 2 Computer and 2 store management, Business plan | 2 Enterprenueship,2 Conflict management 12 Law enforcement, 12 Fire management |  |  | 10% |  | CF staff have attended training in Computer applications, Accounting, Project planning and management, Forest law enforcemnet, Vehicle driving skills, Forest resources governance and study tours to Amani Nature Reserve and TATEDO. | 50% | NA | CF staff attended training in Computer applications, Accounting, Project planning and management, Forest law enforcemnet, Vehicle driving skills, Forest resources governance and study tours to Amani Nature Reserve and TATEDO. | 70% | CF staff attended training in Computer applications, Accounting, Project planning and management, Forest law enforcemnet, Vehicle driving skills, Forest resources governance and study tours to Amani Nature Reserve and TATEDO. | 70%
Activity 2.2.1 - 2.2.2 | NA | [15 empty] | NA | Three protected areas have been identified. These are Ufufuma-Pongwe Forest Corridor, Jambiani-Muyuni Forest and Kangagani Forest. | 70% | Three protected areas have been identified. These are Ufufuma-Pongwe Forest Corridor, Jambiani-Muyuni Forest and Kangagani Forest. | 70%
2.2.1 Carry out Study on Spatial Planning of Protected Areas network for biodiversity and connectivity. | Areas (ha) identified | Nil | 6000ha | Reports , Government notice, maps | Survey,and review documents | DFNRNR focal person | Quaterly reports | NA | 4,200ha surveye and maped | Survey and, mapping 2000 ha | 6000ha | N/A | The project was still doingbasline studies. | 0% | 4,200ha surveyed and mapped | 60% | NA | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. | 70% | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. | 80%
2.2.2 Increase areas of Protected Areas (connectivity) based on the Spatial planning study information. | Area ( Hectares) gazzeted | Six PAs totalling 12,241ha | 6,000ha gazetted | Survey reports and maps | Survey,and review documents | DFNRNR focal person | Quaterly reports | NA | NA | NA | 6,000ha gazetted | NA | The project was still doingbasline studies. | 0% | Meetings done with communities and stakeholders to identify new Pas for gazettement. The meetings proposes Jambiani Muyuni( 4200ha) and Ufufuma Pongwe as new Pas for gazetement. | 65% | NA | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. | 70% | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. Notine of Intent has been prepared and sent to Ministty of Agriculture and Natural Resources for furhetd leagal proceedings on gazettment process.
Output 2.3: Key forest Protected Areas are consolidated, and their management status improved | No. of approved management plan of PAs | 2 Management plan of Jozani and Ngezi | Review 2 ,management plan and prepare 7 new management plan | Reports | Survey , Review documents and consultation meeting with stakeholders | DFNRNR focal person | Annually | Engage consultance | Consultancy report, Area identified , surveyed and maped |  |  |  | 100% |  | Proposed Protected AreAs identified |  | NA | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. | 100% | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. | 65%
| No of PAs upgraded | Nill | 1 Forest reserve to Natuture reserve and 3 Public forest to forest reserve | Reports, maps | Survey , Review documents and consultation meeting with stakeholders | DFNRNR focal person | Annually | NA | 4,200ha surveye and maped | Survey and, mapping 2000 ha | Boundary consolidation for 6 PAs | N/A | NA | NA | 4,200ha surveye and maped | 60% | NA | Two new PAs identified and surveyed with a total of 10600 ha. These are Jambiani-Muyuni forest (4200ha) and Ufufuma-Pongwe corridor with 6400 ha. | 80% | Jambiani-Muyuni Protected Area (4,200Ha) and the Ufufuma Pongwe Corridor (6,000Ha) formed a total area of 10,200ha which have been demarcated and mapped. Final gazettement process is underway | 100%
| No. of PAs with established permanent boundaries | 4 Pas with Permanent boundaries | 5 PAs boundary reviewed and 4 PAs established | Survey reports and maps | Survey , Review documents and mapping | DFNRNR focal person | Annually | NA | 2 management plan of Kiwengwa and Masingini developed | 5 Management plans of Raskiuyu, Muyuni, Ufufuma, Kangagani and Msitu mkuu | Implementation of Plans | N/A |  |  | 2 management plan of Kiwengwa and Masingini developed | 25% | NA | Three Management plans for Kiwengwa Forest, Masingini Reserve and Msitu-Mkuu Forest Reserve have been approved. Review is ongoing for Ngezi and Jozani national park that are old and need re | 70% | Three Management plans for Kiwengwa Forest, Masingini Reserve and Msitu-Mkuu Forest Reserve have been approved. Review is ongoing for Ngezi and Jozani national park that are old and need re | 80%
2.3.1 Establish and review Protected Areas permanent boundaries | Number of PAs with permanent boundaries . | 4 Pas with Permanent boundaries | 5 PAs boundary reviewed and 4 PAs established | Survey reports and maps | Survey , Review documents and mapping | DFNRNR focal person | Annually | NA | One Notice of intent | 3 notice of intent | 4 PA Gazzetted | N/A |  |  | 1 Notice of intent | 25% | NA | Upgrading of Ufufuma-Pongwe, Jambiani-Muyuni and Kangagani Forest is Masingini Forest Reserve (566ha) to status of Nature Reserves is underway while Jambiani-Muyuni Forest ( 4,200ha) andUfufuma -Pongwe ( 6,200ha) are in the public opinion collection stage. | 70% | Upgrading of Ufufuma-Pongwe, Jambiani-Muyuni and Kangagani Forest is Masingini Forest Reserve (566ha) to status of Nature Reserves is underway while Jambiani-Muyuni Forest ( 4,200ha) andUfufuma -Pongwe ( 6,200ha) are in the public opinion collection stage. | 70%
2.3.2 Develop, review and implement management plans for Protected Areas. | Number of management plans developed | 2 Management plan of Jozani and Ngezi | Review 2 and prepare 7 newmanagement plan | Reports | Survey , Review documents and consultation meeting with stakeholders | DFNRNR focal person | Annually | Review boundary and Installation of beacon in Masingini | Review boundary and Installation of beacon in 2 PAs (Jozani, Ngezi) | Establish boundary in 3 New Pas and review boundary in 2 PA | Establish boundary in 2 New Pas | Review boundary and Installation of beacon in Masingini | 10% |  | Review boundary and Installation of beacon in 2 PAs (Jozani, Ngezi) | 20% | NA | 5 key Protected Areas (Masingini FR, Jozani Chwaka Bay NP, Kiwengwa Pongwe FR, Ngezi Vuma Wimbi NR and Msitu Mkuu FR have permanent boundaries with beconds while establishmment for the remaining Ras Kiuyu Forest Reserve in Pemba is underway. | 80% | 5 key Protected Areas (Masingini FR, Jozani Chwaka Bay NP, Kiwengwa Pongwe FR, Ngezi Vuma Wimbi NR and Msitu Mkuu FR have permanent boundaries with beconds while establishmment for the remaining Ras Kiuyu Forest Reserve in Pemba is underway. | 80%
2.3.3 Upgrade of Protected Areas | No of PAs upgraded | Nill | 1 Forest reserve to Natuture reserve and 3 Public forest to forest reserve | Reports, maps | Survey , Review documents and consultation meeting with stakeholders | DFNRNR focal person | Annually | Review boundary and Installation of beacon in Masingini | Review boundary and Installation of beacon in 2 PAs (Jozani, Ngezi) | Establish boundary in 3 New Pas and review boundary in 2 PA | Establish boundary in 2 New Pas | Review boundary and Installation of beacon in Masingini | 10% |  | Review boundary and Installation of beacon in 2 PAs (Jozani, Ngezi) | 20% | NA | Review boundary and Installation of beacon in 2 PAs (Jozani, Ngezi) |  | 5 Protected Areas (Masingini FR, Jozani Chwaka Bay NP, Kiwengwa Pongwe FR, Ngezi Vuma Wimbi NR and Msitu Mkuu FR have permanent boundaries with beconds while establishmment for the remaining Ras Kiuyu Forest Reserve in Pemba is underway.
2.3.4 Identify and assess key indicators for Protected Areas plan implementation. | Key indicators developed. | Nill | PAs perfomance | Reports | Review documents | DFNRNR focal person | Annually | NA | 2 management plan of Kiwengwa and Masingini | 2 Management plans of , Muyuni, Msitu mkuu, | 3 Management plans of Raskiuyu, Muyuni, Ufufuma, Kangagani | N/A |  |  | 2 management plan of Kiwengwa and Masingini | 25% | NA | 3 new management plans for Msitu Mkuu Forest Reserve, Masingini Forest Reserve and Kiwengwa-Pongwe Forest Reserve have been developed. | 80% | A total of 5 management plans have been developed for, Jozani NP, Ngezi FR, Msitu Mkuu Forest Reserve, Masingini Forest Reserve and Kiwengwa-Pongwe Forest Reserve have been developed. | 80%
2.3.5 Undertake study on economic analysis of Protected Area. | Consultant engaged and Study reports produced. | Nill | 6 PAs | Reports | Social survey | DFNRNR focal person | Once | NA | One Notice of intent | 3 notice of intent | 4 PA Gazzetted | N/A |  |  | 1 Notice of intent | 25% | NA | Upgrade for Masingini FR, Jambiani- Muyuni FR, Ufufuma-Pongwe, and Kangagani FR in-Pemba is underway. | 40% | Upgrade for Masingini FR, Jambiani- Muyuni FR, Ufufuma-Pongwe, and Kangagani FR in-Pemba is underway. | 40%
2.3.6 Harmonize guidline of Protected Areas with Land use and Tourism development plans. | Harmonized guidelines developed | Guidlines | Guidlines harmonized | Reports | Review documents | DFNRNR focal person | Annually | Engage consultant | Consultancy report | Measure perfomance | Measure perfomance | N/A |  |  | Key Indicators have been developed. | 50% | NA | Done and report available in the DFNNR Office | 100% | Done and report available in the DFNNR Office | 100%
2.3.7 Refurbish ecotourism based on harmonized tourism plans in PAs | Number of PAs refubrished | 4 PAs tourism infrastructure | 4 PAs refubished | Reports, direct observation | Review documents | DFNRNR focal person | Annually | NA | Conduct Economic analysis for 6 Pas | Business plan for 6 Pas developed | Implementation of business plan | N/A |  |  | Conduct Economic analysis for 6 Pas | 75% | NA | The study are ongoing in 6 Pas | 100% | The studies werecompleted in June 2013 and report in place | 100%
2.3.8 Conduct feasibility study on PAs retention and revolving fund for sustainable management. | Number. of scheme | One retantion scheme | Review Jozani and 3 new schemes Ngezi , Kiwengwa and Masingini | Reports, direct observation | Review documents | DFNRNR focal person | Annually | NA | N/A | Not Done | Not Done | Not Done |  |  | Not Done | 0% |  | Not Done | 0% | Not Done | 0%
2.3.9 Develop business plan for six Protected Areas | Number of business plans developed | Nill | 6 business plan | Repots | Review documents | DFNRNR focal person | Once | N/A | Refrubshmment of ecotourism facilities include water and sanitation systems and general repairs of tourist facilities like house repairs has began in Masingini. | 1 PA ( Masingini 566ha ) renovated. | 1 PA ( Masingini 566ha ) renovated with improved water and sanitation facilities and house repair to improve tourism facilities. | Refubishment started | 60% |  | Not Done |  |  | Not Done | 60% | 1 PA ( Masingini 566ha ) renovated with improved water and sanitation facilities and house repair to improve tourism facilities. | 60%
2.3.10 Support GIS unit for map production | Number of PAs maps | 4 maps | Review 4 maps and develop 5 new maps | Repots | Survey,and review documents | DFNRNR focal person | Annually | NA | N/A | NA | Review 4 maps and develop 5 new maps | N/A | The project was still doing baseline studies. | NA | N/A | 30% | One staff (GIS unit of DFNRNR) attended five days tailor made course on field data collection based on Mobile GIS technology( using TerraSync and ArcGIS) held at Togo Tower House-Mobile-GIS Technology-GIS & ITC Solution in Dar-es-salaam by GEODATA.• | Same results as previous reporting period | 30% | Same results as previous reporting period | 30%
Output 2.4 Community Forest Management Areas provide sustainable buffering and connectivity support, whilst contributing to household security | No. of CoFMA | 7 COFMA | Review 7 COFMA and formulate 6 new COFMA | Repots | Survey,and review documents | DFNRNR focal person | Annually | NA | NA | NA | Review 7 COFMA and formulate 6 new COFMA | N/A | 0% | The project was still doing baseline studies during this reporting period. | Not Done | 0% | DFNNR was involved in staff structure and re-organization issues | Two new Community Forest Management Agreements (CoFMA) developed around Ufufuma-Pongwe forest corridor FR and Seven (7) old one reviewed. | 45% | Seven new Community Forest Management Areas have been established with a total area of 1,928.58Ha. These are from Pagali (174.8Ha), Uroa (1,014.3Ha), Pwani Mchangani (60.23Ha), Pongwe (416.3Ha), Kandwe (194.92Ha), Pangeni (49.83Ha) and Konde (18.2Ha | 100%
| Number of Community supported in IGA | 7 Shehia around PAs | 35 communities around PAs | Repots | Direct observation and review documents | DFNRNR focal person | Quaterly | NA | NA | NA | 35 communities around PAs | NA | 0% | The project was still doing baseline studies during this reporting period. | Not Done | 0% | DFNNR was involved in staff structure and re-organization issues | Training including practical work on construction and use of improved cooking stoves was conducted in both island (Unguja & Pemba) involving communities living adjacent project areas. A total number of 112 participants attended. | 100% | Same results as previous reporting period | 100%
2.4.1 Assess community forest activities , identify and adapt best practices | Number of best practice identified and Community supported | 7 comminities around PAs | 35 communities around PAs | Repots | Direct observation and review documents | DFNRNR focal person | Quaterly | NA | NA | NA | 35 communities around PAs | NA | 0% | The project was still doing baseline studies during this reporting period. | Not Done | 0% | DFNNR was involved in staff structure and re-organization issues | Training including practical work on construction and use of improved cooking stoves was conducted in both island (Unguja & Pemba) involving communities living adjacent project areas. A total number of 112 participants attended. Some communities members have commenced business of production and sale of improved cooking stoves. | 85% | Same results as previous reporting period | 85%
2.4. 2 support communities develop business plan and implement around PAs. | Number of Communities around PAs. | Nill | 3 Business plan around Jozani, Kiwengwa and Ngezi | Repots | Social survey and review documents | DFNRNR focal person | Once | NA | NA | NA | 3 Business plan around Jozani, Kiwengwa and Ngezi | N/A | 0% | The project was still doing baseline studies during this reporting period. | Not Done | 0% | NA | Not Done | 0% | Not Done | 0%
2.4.3 Develop and review Community Forest Management Agreements. | Number of CoFMA | 7 COFMA | Review 7 COFMA and formulate 6 new COFMA | Repots | Survey,and review documents | DFNRNR focal person | Annually | NA | NA | NA | Review 7 COFMA and formulate 6 new COFMA | N/A | 0% | The project was still doing baseline studies during this reporting period. | Not Done | 0% | DFNNR was involved in staff structure and re-organization issues | Two new Community Forest Management Agreements (CoFMA) developed around Ufufuma-Pongwe forest corridor FR and Seven (7) old one reviewed. | 45% | Seven new Community Forest Management Areas have been established with a total area of 1,928.58Ha. These are from Pagali (174.8Ha), Uroa (1,014.3Ha), Pwani Mchangani (60.23Ha), Pongwe (416.3Ha), Kandwe (194.92Ha), Pangeni (49.83Ha) and Konde (18.2Ha | 100%

## M&E Plan OUTCOME 3 LANDSCAPES
Project Goal | The coastal Forest Biodiversity and Ecosystem Values are Conserved and Provide Sustainable Benefit Flows at Local, National and Global Levels
Project purpose | Indicator | Baseline 2011 | Planned Target by EOP | Data source | Data collection Methods | Responsibility and analysis | Frequency of data collection | Desired Results |  |  |  | FY 2010/11 Monitoring |  |  | FY 2011/12 Monitoring |  |  | FY 2012/13 Monitoring |  | FY 2013/14 Monitoring
[8 empty] | End of FY 2010/2011 | End of FY 2011/2012 | End of FY 2012/2013 | End of FY 2013/2014 | Actual FY Results | Actual VS Desired results(%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Lessons learned/changes needed | Actual FY Results | Actual VS Desired results (%) | Actual FY Results | Actual VS Desired results(%)
Objective: The Spatial coverage and management effectiveness of the Coastal Forest PA sub system is expanded and strengthened | 1. Increase in extent (ha) of PA network that includes Coastal Forests, and a network with increased legal protection and management of biodiversity values, including four Forest Nature Reserves | 19,570ha is under improved management of which none is Forest Nature Reserve (FNR) | 12,000ha as Forest Nature reserve and 100,000 ha as VLFRs | Ministry anf Departmental reports, and Project documents. Project documents,Landscapes plans, maps and GIS files, MTE and Terminal Evaluation(TE) National reports to CBD | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | NA | NA | NA | 12,000ha as Forest Nature reserve and 100,000 ha as VLFRs | Nothing was achieved at this reporting period because the project did not start . | N/A | N/A | No hectares were achived because the project was still doing baseline studies before start of the project activities. | NA | NA | 12,000 ha of Rondo Forest Reserve is under final process for upgrading to Nature Reserve. Approval has been obtained at Village, Ward and District Council levels, awaiting the Regional and National level approvals and declarationlevels, awaiting the Regional and National level approvals and declaration. | 75% | The Rondo Forest Reserve covering 12,000ha is under the final process for gazettment and upgrading into a Nature Reserve by the Ministry of Natural Resource and Tourism. The dossier (containing the agreement from surrounding villages, the district, the region, and the Tanzania Forest Service) was submitted to the cabinet in June 2013. After this final step the reserve will be gazetted and the gazettment notice will be published in the government gazett. and Tourism. The dossier (containing the agreement from surrounding villages, the district, the region, and the Tanzania Forest Service) was submitted to the cabinet in June 2013 | 85%
| 2. Increase in area under landscape conservation, with functional corridors and buffer-zones, managed under detailed landscape | Nil | 1,277million ha | Same as Indicator 1. | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | NA | NA | NA | 1,277million ha | Nothing was achieved at this reporting period because the project did not start . | NA | NA | 142,044 ha put proper land use plan out of which 56,900 ha have been demarcated as forest reserves in Lindi and Kilwa LS | 35% | NA | A total of 402,136 ha have been put into proper Land use plans out of which 153,077ha have been demarcated as Local Authority and Village Land Forest Reserves in Rufiji, Kilwa and Lindi landscapes. Other beneficiary districts in this process are in Tanga region where additional village land forest reserves will be declared and the area of these will reported in the next PIR | 45% | In this reporting period a total of 514,665.86 Ha are under proper management status within the landscapes of Kilwa, Rufiji and Lindi landscapes. There are 296,938.57Ha under Village Land Forest Reserves; 117,860.71 Ha under Central Government Forests reserves; 77,824.79Ha under Wildlife Management Areas; 84,883.97Ha under proposed Wildlife Management Areas and 22,370.31Ha under Local Authority Forest Reserves. | 60%
| 3. Business plans show improved Financial scorecard for national system of CF protected areas and target landscape (Rufiji, Lindi, Kilwa and Zanzibar) | Average fo financial scorecard is 22.2% | An increase of over 40% in finance score card scores | Financial scorecard | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | NA | NA | NA | An increase of over 40% in finance score card scores | Nothing was achieved at this reporting period because the project did not start . | N/A | NA | By this reporting period the baseline studies were ongoing( in progress) | NA | NA | Baseline study (completed in 2011) revealed a low level of implementation of existing regulatory frameworks i.e. by-laws, financial instruments in implementing forest conservation activities in coastal districts (27.5% only) as well as application of revenue collection tools which was only 20.2% . | NA | At this reporting period, the average Financial Scorecard in the Kilwa, Rufiji and Lindi landscapes averaged at 43%; an increase of two folds from the previous baselines. In Zanzibar, the Financial Scorecard had a score of 44% | 75%
| 4.METT scores for PAs and PA landscapes show improvement in targeted landscapes | The average METT score for PAs is 44.2% | An over increase of 20% in the METT score | METT reports, survey reports | Review documents | Coordinators (FBD, DFNRNR), WWF FLC and PMU | Annually | NA | NA | NA | An over increase of 20% in the METT score | Nothing was achieved at this reporting period because the project did not start . | N/A |  | By this reporting period the baseline studies were ongoing( in progress) | NA | NA | METT scores for around 20 forest sites were competed during PPG phase. However, as the project is about the Coastal Forest sub-system across the entire Tanzania coastal mainland Districts and Zanzibar, we conducted a study of METT for all 146 reserves in the coastal area that we could access. This far more comprehensive assessment of the METT situation in the system was completed in 2011. The average score ranged from 30% for the central government forest reserves and 60% for village managed forest reserves and Forests within in national parks. This extensive review allows us to track changes accross the system and also between management categories of reserve, and contribute the data into the UNDP - TRAC linked funding that was provided for a 'coastal forest information system' within the Tanzania Forest Service. All METT data are now entered in Excel and in the TFS database | NA | The up-dated METTs for the PAs in the baseline were completed in Jan 2013. These show an average of 7% improvement and the TFS appears to have greater capacity to deal with coastal forests than in the past. | 45%
Outcome 3: Effective PA management systems in place at three project priority landscapes, with co-management between central, local and village government partners, leading to improved conservation of biodiversity | 1.Number of Landscapes with broad conservation plans in place, approved and implemented | Nil | All target Project Areas (and – at EOP An additional 10,000 ha of village Forest reserves established within the Kilwa and Lindi landscapes | Project reports, District reports | Review documents | PEs, FLC and PMU | Annually | NA | NA | Engage Consultant to develo Conservation Plans for the 3 Landscapes( Kilwa, Lindi and Rufiji) | All target Project Areas (and – at EOP An additional 10,000 ha of village Forest reserves established within the Kilwa and Lindi landscapes | N/A | N/A | Nothing was achieved at this reporting period because the project did not start . | By this reporting period 23291ha of village forest reserves have been demarcated in Lindi and Kilwa LS). Plans for engagimg Consultnat for developing the Conservation Plan for the 3 Landscapes is uderway. | 35% | NA | A total of 402,136 ha have been put under proper land use plans in priority Landscapes of Rufiji, KIlwa and Lindi of which forest reserves covers 144,931 ha. | 100% | Conservation Plans for Matumbi (Rufiji), Kilwa, and Lindi landscapes were completed and approved. Implementation of Conservation plans are reflected in the FY14 workplans. | 100%
| 2.Number of protected areas with update and approved management and business plans | Nil | One FNRs, 20 VLFRs with management plans and 3 pilot business plans | Project reports, District reports | Review documents | PEs, FLC and PMU | Annually | N/A | N/A | Accomplish development of 15 management plans and 6 business plan | One FNRs, 20 VLFRs with management plans and 3 pilot business plans | N/A | N/A | NA | Initiated the process of developing management plans in 15 VLFR and LAFR | 35% | NA | Three (3) Local Authority Forest Reserves with a total of 77,521 ha dermacated, and 12 Village Land Forest Reserves have also been demarcated with a total area of 56,056 ha in the priority Landscapes. Management plans and bylaws are in final processes for approvals and gazetttement are at District and National levels respectively. | 75% | A total of 15 Village Land Forest Reserves with 117,738Ha have been demarcated. A total of 12,000Ha of Rondo Nature Reserve has been approved by the Ministry of Natural Resources and Tourism and a total of 146,749Ha Local Authority Forest Reserves (Mirambani LAFR 9,572.93Ha (Kilwa); Mbarawala LAFR 46,180Ha (Kilwa); Kichi Hills LAFR 22,357Ha(Rufiji) and Ruhoi LAFR 68,639Ha (Rufiji) have been put into management. | 100%
| 3.Village governments support CF conservation through creation of VLFRs as buffers and corridors, and prevent alienation for bio fuels in key biodiversity | Nil(apart from stand alone VLFRs) | Atleast 15 villages participate actively in Forest Conservation process (>5 per Landscapes) | Project reports, District reports | Review documents | PEs, FLC and PMU | Annually |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | N/A | N/A | 3 Villages of Ntene, Liganga and Likawage are actively involved in forest managemnt and instituting proper land use plans covering a total of 142,044ha | 100%
| 4. Management effectiveness of PAs improved as a result of co-management, using GEF METT Score Card | Averages is 40.5% | Average improved by 20% | Project reports, District reports | Review documents | PMU | Annually | NA | NA | NA | Average improved by 20% | N/A | NA | Nothing was achieved at this reporting period because the project did not start . | NA | Baseline studies ongoing | NA | METT scores for 146 protected areas (Forest reserves and National parks) were completed. Results ranged from 30 - 60% for low to high effective management of protected areas. Most of LVFRs ranked high in the scores. | 80% | METTs were completed for the Kilwa, Rufiji and Lindi landscapes. These show an improvement from 31.9% to 40.8%. | 100%
Output 3.1 Landscapes (Rufiji, Kilwa, Rondo – Lindi) are agreed, described and assessed as to issues of connectivity, gaps and buffer functions |  | 0 | 15VLFRs, 6LAFRs | Maps, Reports | Survey, field observation & interviews | PEs, FLC and PMU | Annually | N/A | Demarcation of 16 VLFR in Rufiji,Kilwa and Lindi ( 13 VLFR and 3 LAFR) | Demarcation of 7 ( 4 Lindi, 2 Rufiji, 1 Kilwa) in new buffers and corrodors | Consolidate 21 VLFR and LAFR in terms of status and sizes | N/A
3.1.1 Outline concept and develop agreed model for landscape conservation (e.g. From WCPA guidelines etc) | Developed Models? |  |  | Reports | [13 empty] | N/A |  | N/A
3.1.2 Assess landscapes coverage for management effectiveness | Area (Ha) assessed , Ownership status (VLFRs & LAFRS, VLUPs) | Total area of landscape 15699.86, 41 VLFRs, 2 LAFRs | Total area of landscape15699.86, 15VLFRs, 2LAFRs | Assessment report ,Maps Field observations | GIS, Survey, field observation & interviews | Consultants, PEs, FLC and PMU | Annually | NA | NA | NA | Total area of landscape15699.86, 15VLFRs, 2LAFRs |  |  | NA | Initiated the process of developing management plans in 15 VLFR and LAFR | NA
3.1.3 Identify and facilitate stakeholders participation in landscape conservation | Number of stakeholders identified and facilitated. | 51 | 60 | Reports, field observation | meetings & workshops | PEs, FLC and PMU | Annually | 0 | 51 | 9 | 0 | 0
3.1.4 Support livelihood initiatives and credit schemes in key villages | Number of environmentally friendly livelihoods initiatives | 0 | NIL | Reports, field observation | interventions, interview | Pes & FLC | Annually | N/A | NA | NA | NA | NA | 0% | Project activities did not start at this reporting period. | Training on modern Beekeping skills Rufiji, Kilwa and Lindi landscapes: A total of 67 beekeeping group members were trained on morden beekeeping skills. Group members agreed to collect offcuts from forests for fabrication of beehives. Group members also were trained markets, harvesting, handling of bee products and processing techniques. | 60% |  | 17 beekeeping and 24 COCOBA groups formed and actively participating in livelihood intiatives in all Landscapes ( Rufiji, Kilwa and Lindi) | 100% | 17 beekeeping and 24 COCOBA groups formed and actively participating in livelihood intiatives in all Landscapes ( Rufiji, Kilwa and Lindi) | 100%
2013
Output 3.2 Gaps in landscape plan filled by strategic development of Local AREA FRS and VLFRs |  | Area under VLFR and LAFR at baseline year 175830ha | Additional areas under VLFRs & LAFRs (100,000 ha) from the baselines data. | Maps | Review documents, Field Visits | PEs, FLC and PMU | Annually | N/A
3.2.1 Facilitate TFS (GIS unit) to deliver landscapes output in terms of planning materials. | Number of maps | 0 | 22 | Maps | Review documents | PEs, FLC and PMU | Annually | 0 | 9 | 9 | 4 | 0 |  | N/A | 5 |  | Land Grabbing | 13 VLFR maps produced
3.2.2 Conducting field reconnaissance to identify key conservation areas | Number and Areas identified | 8 Area were already established | 16 New area which reconnaissance carried out | Reports, Maps, Field observations | Review Documents | PEs, FLC and PMU | Annually | 0 | 8 | 6 | 2 | 0 |  |  | 6 | 75
3.2.3 Advocacy with communities and village authorities in key identified areas for connectivity and buffer functions. | Number of village authorities participating in management of buffer and corridors | NIL | NIL | Reports , Approved LUPs | Review Documents (LUPs) | PEs, FLC and PMU | Annually | NA | NA | NA | Atleast 15 villages participate actively in Forest Conservation process (>5 per Landscapes) | N/A | N/A | Nothing was achieved at this reporting period because the project did not start . | 3 Villages of Ntene, Liganga and Likawage are actively involved in forest managemnt and instituting proper land use plans covering a total of 142,044ha | 60% | NA | A total of 12 villages are participating in forest management through creation of VLFRs with a total of 56,056 ha. Two villages in Lindi landscape (Mihima and Nndawa villages) started piloting sustainable harvesting of timber from their VLFRs after securing authorization from the government. A total of USD $ 2,564.10 (TShs 4,000,000) have been earned by selling of 25cm3 of timber | 85% | More than 15 villages are actively participating in forest conservation, 6 in Lindi; Ndawa, Mihima, Liganga, Ntene, Mnara and Namtamba. 4 in Kilwa; Hotelitatu, Likawage, Nakiu, Kiwawa; and 5 in Rufiji; Tawi, Kungulwe, Utunge, Kipo, Kipugira. | 100%
3.2.4 Establish and Gazette proposed PAs (VLFR and LAFR) | Number of gazetted PA | 0 | 26 | Maps, Reports | Reports | PE | Annually | 0 | 15 | 7 |  | 0 |  |  | 15
| Areas of gazetted PA | N/A | 100000 | Maps | Maps |  | Annually | 0 | 87800 | 10000 | 2200 | 0 |  |  | 87800
Output 3.3 Landscape Conservation Plan developed and agreed with local district and national partners
3.3.1 Develop and approve conservation plan(s) | Number of conservation plans | NIL | 3 Conservation Plans developed | Reports, field visits | Document, Reports | PMU | Annually | NA | NA | Engage consultant to develop 3 landscapes conservation plans | 3 Conservation Plans developed3 | NA | NA | Nothing was achieved at this reporting period because the project did not start . | NA | 0% | NA | A total of 402,136 ha have been put under proper land use plans in priority Landscapes of Rufiji, KIlwa and Lindi of which forest reserves covers 144,931 ha. | 65% | Conservation Plans for Matumbi (Rufiji), Kilwa, and Lindi landscapes were completed and approved. Implementation of Conservation plans are reflected in the FY14 workplans. | 100%
3.3.2 Implement Landscape plans with partners, seeking sustainable financing (certified timber) | Number of villages implementing group certification schemes | 0 | NIL | Reports | Document, Reports | FLC | Annually | NA | NA | NA | NIL | NA | NA | Nothing was achieved at this reporting period because the project did not start . | NA | NA | NA | WWF Landscape began discussion on group FSC issues with MCDI as partner in identifying villages for FSC,. | 35% | 3 villages in Rufiji Landscape( Nakiu and Nyamwage) and Nanjirinji in Kilwa Landscape are engaged in FSC with our partnet MCDI | 100%
Output 3.4 Conservation plans under implementation with key indicator baselines completed and new area METT scores completed
3.4.1 Undertake Baseline assessments (biodiversity, threat analysis and community participation/ benefits) | Number of baselines undertaken | 0 | 6 | Reports | Consultants | PMU | Annually | NA | Engage Consultants to conduct baseline studies and assessments |  | 6 Baseline studies/assessments completed | NA | NA | Project activities did not start at this reporting period. | Baseline survey haVE started on the ground after signing of the contrats. Draft reports are expected from July -September period. | 40% | Baseline studies ongoing | Consultancy reports for "Biodiversity Survey on Coastal Forests of Southern Tanzania and Zanzibar for Coastal Forest Project, Spatial Planning Baseline Focusing on Coastal Forests of Tanzania mainland and Impact Evaluation( Baseline) Survey Focusing on Coastal Forests of Southern Tanzania and Zanzibar studies completed and submitted to WWF TCO Office. | 50% | All planned 6 Baseline studies completed and submitted to WWF TCO office. | 100%
3.4.2 Undertake METT scores | Management effectiveness of PAs improved as a result of co-management, using GEF METT Score Card | Averages is 40.5% | Average improved by 20% | Reports, METT score cards | Consultants | PEs, FLC and PMUPes & FLC | Annually | NA | NA | NA | Average improved by 20% | N/A | NA | Nothing was achieved at this reporting period because the project did not start . | NA | Baseline studies ongoing | NA | METT scores for 146 protected areas (Forest reserves and National parks) were completed. Results ranged from 30 - 60% for low to high effective management of protected areas. Most of LVFRs ranked high in the scores. | 80% | METTs were completed for the Kilwa, Rufiji and Lindi landscapes. These show an improvement from 31.9% to 40.8%. | 100%
3.4.3 Monitor and record resources off take levels and revenue. | Frequency of data collection | NA |  | Reports, Records | Document reviews | Pes & FLC | Annually | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Done | This inidicator was removed based on MTE recommendation of April 2013.
3.4.4 Promote sustainable logging in buffer VLFRs in collaboration with partners (eg Mpingo conservation and Development Initiatives, Mama Msitu and District) | Number of promotion and awareness events | 0 | 21 | Reports, Records | interview, questionnares & field observations | PEs, FLC and PMUPes & FLC | Annually | NA | NA | NA | 21
2000
0