The United Republic of Tanzania

United Nations Development Programme

Quarterly Progress Report July-September 2013

Project Title: Extending the Coastal Forest Protected Areas Subsystem in Tanzania

1.  Summary Highlights of achievement July-September 2013

| Component 1: Tanzania Forest Service( TFS) | Project Output 1.1: Capacity built in Tanzania Forest Service) to lead and oversee a Tanzania Coastal Forest Conservation Programme. Activities for this output have been carried over to the next quarter (October-December); planned activities could not be done due project fund delays. |
| --- | --- |
|  | Project Output 1.2. Coastal Forest Reserves (non- reserves) within target landscapes are assessed as to priority for conservation on biodiversity and threat criteria, and conservation strategy developed. In this reporting period only one activity out of seven planned activities has been done due project funds delay. Preparation for Conservation Strategy has begun with a consultant engaged to prepare Conservation Strategy for the Landscapes. Inception Report for the strategy activity has been submitted by the Consultant, review of inception report is on-going. |
| Component 2: Department of Forests, Non-Renewable and Natural Resources in Zanzibar. | Project Output 2.1.1: Formulate Forest Protected Area Advisory Group (FPAAG) to provide oversight and leadership. Activities for this output have been carried over to the next quarter due project funds delays in this quarter. |
|  | Project Output 2.1.2: Support functions of DFNR conservation Section in management of Protected Areas through maintenance of equipment’s, staff trainings and its operations. Activities for this output have been carried over to the next quarter due project funds delays in this quarter |
|  | Project Output 2.1.3: Raise awareness to Key stakeholders on PAs conservation. Activities for this output have been carried over to the next quarter done due project funds delays in this quarter |
|  | Project Output 2.2.1: Increase number of Protected Areas (connectivity) based on the Spatial planning study information Activities for this output have been carried over to the next quarter due project funds delays in this quarter |
|  | Project Output 2.3.1: Harmonize guidelines of Protected Areas with Land use and Tourism development plans. Activities for this output have been carried over to the next quarter done due project funds delays in this quarter |
| Component 3: WWF Kilwa, Rufiji and Lindi Landscapes. | Output 3.1 Landscapes (Rufiji, Kilwa, Rondo – Lindi) are agreed, described and assessed as to issues of connectivity, gaps and buffer functions. Planned activities for this output have been carried over to the next quarter done due project funds delays in this quarter to all Landscapes. |
|  | Output 3.2 Gaps in landscape plan filled by strategic development of Local area FRS and VLFRs. Planned activities for this output have been carried over to the next quarter done due project funds delays in this quarter to all Landscapes. |
|  | Output 3.3 Landscape Conservation Plan developed and agreed with local district and national partners. Planned activities for this output have been carried over to the next quarter done due project funds delays in this quarter to all Landscapes. |
|  | Output 3.4 Conservation plans under implementation with key indicator baselines completed and new area METT scores completed. Planned activities for this output have been carried over to the next quarter done due project funds delays in this quarter to all Landscapes. |
| Component 4: Project Management Unit (PMU) | Activity 4.1.: Procurement and ensure all requests facilities and communication channels for effective project management are in place. Not Done |
|  | Activity 4.1: Review of FY14 implementation progress with all IP's based on the agreed work plans. Expected to be done in November 2013 and May 2014. To be done in December 2013. |
|  | Activity 4. 1.3: Follow up implementation of Project M&E framework to all IP's after every three months Project field visits were done in Landscape (Kilwa, Lindi and Rufiji) and Zanzibar in August and September by Head PMU & Project Coordinator, Project International Advisor and Project M&E Officer assessing progress of implemented activities. Very good progress has been observed on TRAC fund activities among Beekeeping groups and community savings and credit schemes locally known as COCOBA that have been introduced by the project . A total 387 members (254 male and 133 women) from 24 beekeeping groups and more than 150 (55 Women and 95 Men) in Zanzibar are actively participating in these livelihood initiatives introduced by the project. To date over 1138 hives are in place and more than fifteen per cent (15%) have been colonized, sales for honey expected in the coming quarter. |
|  | Activity 4.1.4: Follow-up retirement from the field and capacity building to IP's accountants by PMU accountant monthly. Not Done Activity 4.1.5: Implementation of communication strategy matrix, TV and Radio Presentation, Field visit with Journalist to Landscape and Zanzibar for Project activities documentation. This activity has been carried over to the next quarter (October-December 2013). |
|  | Activity 4.1.5: Prepare Annual PSC meeting To be done first week of November 2013 in Bagamoyo. |

- Technical: Actual against planned Outputs

| Component 1 Tanzania Forest Service( TFS) | Project Output 1.1: Capacity built in Tanzania Forest Service) to lead and oversee a Tanzania Coastal Forest Conservation Programme |
| --- | --- |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | 1.1.1: To acquire additional facilities and equipment for TFS unit including 1 photocopier machine for TFS and 4 GPS for DFOs | Acquiring additional facilities and equipment for TFS unit including 1 photocopier machine for TFS, Anti-virus, 4 cartilages and 4 GPS for DFOs | This activity has been carried over to the next quarter of October-December 2013 due project fund delays. |
|  | 1.1.2: To facilitate one consultative forum among stakeholders | Facilitating two consultative forums among stakeholders by engaging 40 participants for 2 days forum. | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  | 1.1.3: To facilitate TFS unit to oversee day to day implementation of TFS activities | Diesel, Vehicle maintenance, Airtime and top up cards DSA driver, Stationery Lumpsum, Meetings participants and per-diem | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  | Project Output 1.2. Coastal Forest Reserves (non- reserves) within target landscapes are assessed as to priority for conservation on biodiversity and threat criteria, and conservation strategy developed |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | 1.2.1 To support identified potential income generating activities plus community tree growing initiatives (e.g. cashew nut farming, beekeeping, fish farming, fruit trees, passion) | Providing support to the local communities to implement identified potential income generating activities | This activity has been carried over to the next quarter of October-December 2013 due project fund delays. |
|  | 1.2.2: To prepare conservation strategy for coastal forests within the NFP framework. | Prepare Conservation Strategy for coastal forests with the NFP framework. | Preparation for Conservation Strategy has begun with a consultant engaged to prepare Conservation Strategy for the Landscapes. Inception Report for the strategy activity has been submitted by the Consultant, review of inception report is on-going. |
|  | 1.2.3. To accomplish establishment of Forest Reserves under different PA management models for landscape systems including Nature reserves and FRs,VLFRs. | Completing the process of establishing 10 VLFRs in 5 districts. | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  | 1.2.4. To consolidate boundaries of existing forest reserves in four Districts | Consolidating boundaries of forest reserves in 5 districts by demarcation, resurveying and mapping for 30 days. | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  |  | Trees planting on forest boundaries for 20 days | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  | 1.2.5: To support nine (9) districts in implementation of the project activities | Supporting nine districts in implementation of the project activities. | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  | 1.2.6 To assess feasibility of promoting tourism in coastal forest areas | Assessing the feasibility of promoting tourism in 4 coastal forest reserves. | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  |  | Facilitating publicity of project activities through TV and radios programmes, t-shirts, leaflets, signboards and posters | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
| Component 2: Department of Forests, Non-Renewable and Natural Resources in Zanzibar. | Project Output 2.1.1: Formulate Forest Protected Area Advisory Group (FPAAG) to provide oversight and leadership |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | Stakeholders workshop discussing the draft of Forest Advisory Group. | Facilitate stakeholders workshop discussing the draft of Forest Advisory Group. | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  | Finalize preparation of the (FPAAG) standing order | Facilitate finalization preparation of the (FPAAG) standing order. | This activity has been carried over to the next quarter of October-December 2013 due project fund delays |
|  | Project Output 2.1.2: Support functions of DFNR conservation Section in management of Protected Areas through maintenance of equipment’s, staff trainings and its operations. |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | Design and print year 2014 Calendar for Forest FPAs | 1,000 calendars printed | This activity has been carried over to the next quarter of October-December 2013 due project fund delays. |
|  | Conduct on job training to forest guards by Persiansi trained staff. | PAs Forest guards and Community patrol groups trained | This activity has been carried over to the next quarter of October-December 2013 due project fund delays. |
|  | Project Output 2.1.3: Raise awareness to Key stakeholders on PAs conservation |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | Prepare TV documentary for public awareness on PAs conservation | TV documentary for two PAs (Local consultant and Protected Areas information outreach through TV/Radio ) -pay for radio and TV | This activity has been carried over to the next quarter of October-December 2013 due project fund delays. |
|  | Project Output 2.2.1: Increase number of Protected Areas (connectivity) based on the Spatial planning study information |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | Install concrete beacons around Jambiani-Muyuni Forest with area cover mapping. | Jambiani-Muyuni Forest beacon installed and boundary map produced ( permanent boundary of Jambiani-Muyuni Forest established) | This activity has been carried over to the next quarter of October-December 2013 due project fund delays. |

| Component 3: WWF Kilwa, Rufiji and Lindi Landscapes | Output 3.1: Landscapes (Rufiji, Kilwa, Rondo – Lindi) are agreed, described and assessed as to issues of connectivity, gaps and buffer functions. |
| --- | --- |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | Production of Audio-visual material for Publicity and Radio Programme at Print & broadcasting Media. | Facilitate | This activity has been carried over to the next quarter of October-December 2013 due project fund delays in all landscapes. |
|  | Output 3.2: Gaps in landscape plan filled by strategic development of Local area FRS and VLFRs |
|  | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
|  | Boundaries verification in all Landscapes | Facilitate Boundaries verification in all Landscapes | Not done in all landscapes, will be done in the next quarter of October-December 2013. |
|  | The final management plans and by laws approved at village and ward levels. | Facilitate approval of management plans at village and ward levels | Not done in all landscapes, will be done in the next quarter of October-December 2013. |
|  | Output 3.3: Landscape Conservation Plan developed and agreed with local district and national partners |
|  | Implement landscape conservation plans with partners, seeking sustainable financing (Certified Timber) | Facilitate implementation of landscape conservation plans with partners, seeking sustainable financing( Certified Timber) | Not done in all landscapes, will be done in the next quarter of October-December 2013. |
|  | Work with MCDI toward certification process of Nanjirinji Village VLFR | To work with MCDI toward certification process of Nanjirinji Village VLFR | Not done in Kilwa landscape, will be done in the next quarter of October-December 2013. |
|  | Output 3.4: Conservation plans under implementation with key indicator baselines completed and new area METT scores completed |
|  | Undertake METT scores & Thread reduction Assessments | To undertake METT scores & Thread reduction Assessments. | To be done in November 2013 in all landscapes. |

| Component 4: Project Management Unit (PMU) | Activity | Activities planned for the period July-September 2013 | Progress during the reporting period |
| --- | --- | --- | --- |
|  | Procurement and ensure all requests facilities and communication channels for effective project management are in place. | Facilitate procurement of Stationaries, Fuel Communication (mobile charges), Land telephone charges, Project Standing Banners Procurement (Replacement of laptops for six project staffs), maintenance of transport and other equipment | Procurement of stationaries done, and fuel costs covered. Other procurement of other facilities will be done in the next quarter October-December 2013 |
|  | Review of FY14 implementation progress with all IP's based on the agreed work plans. Expected to be done in November 2013 and May 2014. | Facilitate workshop to review work plans with IPs | To be done in December 2013 |
|  | Follow up implementation of Project M&E framework to all IP's after every three months | Conduct field visits to all IPs to check progress of activities | Project field visits were done in Landscape (Kilwa, Lindi and Rufiji) and Zanzibar in August and September by Head PMU & Project Coordinator, Project International Advisor and Project M&E Officer assessing progress of implemented activities. Very good progress has been observed on TRAC fund activities among Beekeeping groups and community savings and credit schemes locally known as COCOBA that have been introduced by the project. A total 387 members (254 male and 133 women) from 24 beekeeping groups and more than 150 (55 Women and 95 Men) in Zanzibar are actively participating in these livelihood initiatives introduced by the project. To date over 1138 hives are in place and more than fifteen per cent (15%) have been colonized, sales for honey expected in the coming quarter. |
|  | Prepare Annual PSC meeting | Facilitate annual PSC meeting in July 2013. | To be done first week of November 2013 in Bagamoyo |

- Project Impacts to date-Milestones  toward the  Goal

This part will be reported in the next coming quarter of January-March 2014

- Adaptive Management (Constraints, Opportunities and Lessons Learned)

This part will be reported in the next coming quarter of January-March 2014.

- Key planned activity for the next reporting period.

Since most of planned activities for quarter of July to September 2013 could not be done due project funds delay. Activities for this quarter have been carried over to next reporting period of October-December 2013.