Management Support Unit (MSU) Annual Work Plan

| Output | Planned Activities | Implementation Period/Time Frame | Responsible party | Source of funds | Budget Description | Budget per quarter | Total Budget |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  |
| Outcome: 1 Quality of programme management and delivery enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1 Programme and Projects Monitored & Evaluated | Activity 1 Progress review workshop |  |  |  | X |  | 04000 04000 04000 04000 04000 | 71200 71300 71600 72100 74500 |  |  |  |  | 2,000 |
|  | Activity 2 Work planning workshops | X | X | X | X |  | 04000 04000 | 72100 74500 |  |  |  |  | 5,000 2,572 |
|  | Activity 3 Planning for Project evaluation |  |  |  | X |  | 04000 | 74500 |  |  |  |  | 1,000 |
| Output 2 Programme and project, management and implementation audited | Activity 1 Contracting auditing Firms | X |  |  |  |  | 04000 04000 | 74100 74500 |  |  |  |  | 80,000 3,000 |
|  | Activity 2 Briefing Workshop for Auditing Firms | X |  |  |  |  | 04000 04000 | 72100 74500 |  |  |  |  | 3,000 2,000 |
|  | Activity 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3 Programme and IP staff trained in RBM and project management related issues | Activity 1 Training for programme staff |  | X |  |  |  | 04000 04000 04000 04000 04000 04000 04000 04000 | 71100 71400 71600 72100 72200 72500 73400 74500 |  |  |  |  | 39,600 60,300 5,000 5,000 6,000 |
|  | Activity 2 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall Budget |  |  |  |  |  |  |  |  |  |  |  |  | 214,472 |

Budget Description

| SN | Account Description | Code |
| --- | --- | --- |
| 1 | ALD Employee costs | 71100 |
| 2 | International Consultants | 71200 |
| 3 | Local Consultants | 71300 |
| 4 | Contractual Services – Individual | 71400 |
| 5 | Travel | 71600 |
| 6 | Contractual Services – Companies | 72100 |
| 7 | Equipment & Furniture | 72200 |
| 8 | Supplies | 72500 |
| 9 | Rental & Maintenance of other Equipment | 73400 |
| 10 | Miscellaneous Expenses | 74500 |