Annual Work Plan Year: 2015 (January 1st- March 31st)

Project: 00070018 “Promotion of Mainstream Policies and Services for Persons with disabilities”

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Budget Description | Amount |
| Output 1: The sub-national authorities, organizations of persons with disabilities and wider public in two selected rayons of Kharkiv Oblast apply accessibility and universal design principles Baseline: 0 Indicator: Community initiatives in key areas (employment, health care and social services). Targets: At least 3 community initiatives implemented | Activity 6: Community initiatives implemented jointly by local authorities, civil society organisations and UN agencies on cost-sharing basis from the local authorities to demonstrate how accessibility and universal design principles could be put in practice | X |  |  |  | UNDP | 30000 | 72 100 (contractual services- companies) 75100 (F&A) | 7 476,64USD 523,36 |
|  | Total |  |  |  |  |  |  |  | 8,000 USD |
|  | Total for Output 1 8,000 USD |
| Output 2: Awareness among national authorities, civil society organisations of persons with disabilities and wider public on disability, accessibility and universal design principles raised at the national level Indicator 2. Number of public education and awareness raising activities/events/products Baseline: 0 Target: 5 activities/events/products Indicator 3. Accessibility and universal design sectoral regulations and/or training programmes developed and adopted. Baseline: 0 Target: at least one sectoral regulation and/or training curricula programmes developed | Activity 2: Evidence-based set of good practices in accessibility and universal design are identified and shared, and the national information and awareness raising campaign is conducted | X |  |  |  | UNDP | 30000 | 72 100 (contractual services- companies) 71 400 (contractual services- Project Manager, PR Specialist, ) 74500 (miscellaneous, incl. ISS, F&A) 75100 (F&A) | 6,000 USD 10 034,99 USD 1,215.48 USD 2 649,53 USD |
|  | Total | 19,900 USD |
|  | Activity 3: Ministries or educational institutions are supported to develop and adopt accessibility and universal design sectoral regulations and/or training programmes | X |  |  |  | UNDP | 30000 | 71200 (International Consultants) 71 400 (contractual services- individuals 72 100 (contractual services- companies) | 5,365 USD 1,212 USD 1,523 USD |
|  | Total |  |  |  |  |  |  |  | 8,100 USD |
|  | Activity 4: The first national conference to promote the universal design principles and share practical experience and demonstrate project results is organized in partnership with central and local authorities | X |  |  |  | UNDP | 30000 | 72 100 (contractual services- companies) | 12,500 |
|  | Total |  |  |  |  |  |  |  | 12,500 USD |
|  | Total for Output 2 |  |  |  |  |  |  |  | 40,500 USD |
| TOTAL | 48,500 USD |

Prepared by			Approved by													       Endorsed by

Kristina Bagramian			                  Katerina Rybalchenko      				             	    Inita Paulovica

Project Manager			                 Senior Programme Manager                                                                UNDP Deputy Representative