## AWP 2015
Annual Workplan of Community Based Approach to Local Development Project phase III (CBA III)
Year: | 2017
Dept.: | Ukraine
Project Title: | Community Based Approach to Local Development Project phase III
Award Id: | 00083522
Implementing Partner: | 001981 (UNDP) | [8 empty] | Prepared (date): 29/12/2016
Project Number: 00091957
EXPECTED OUTPUTS and baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions |  |  | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET ($) |  |  |  |  | BDGT RVSN A ($) |  | O Rdtch | O Rb | Ttl
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Account | Amount |  | Add/Sub | Revised
Output - 1: | Activity 1: Strengthened capacity of local communities and local authorities in applying community led development
Enhanced capacity of local communities and local authorities to initiate and maintain participatory process on local sustainable development and public services delivery | 1.1 Update videos, leaflets to reflect CBA-III information | [6 empty] | 001981 | 30079 | 10159 | 74200 | 2000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 74200 | 5290.57 | [5 empty] | 0
| 1.2 Project closing events / CBA staffs and regional authorities on implementation of CBA-III methodology | [6 empty] | 001981 | 30079 | 10159 | 71600 | 10000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 27331.54 |  |  |  | 32000 | 24000 | 56000
Indicators: | 1.3 Support local/regional authorities in replication of CBA methodology | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5000 | [5 empty] | 0
1. # of community organisations proactive in the local planning process with appropriate legal status availability of sustainability fund, community development plan; 2. # of community members and local officials trained on participatory decision making; 3. # of replications of CBA methodology in non-CBA areas; 4. # of rayon authorities using LDF for participatory decision making; 5. # of community development plans incorporated in the local development plan; 6. # of regional development funds (RDF) established to support community initiatives; 7. # of community initiatives for improving basic social and communal infrastructure and services supported; Targets: 1 At least 60% of target 900) community organisations showing evidence of financial sustainability and proactivity in the local planning process by 2016. 2. 8000 executives and members of community organisations and 2000 officials of local/regtonal authorities trained by 2017 with minimum of 50% of female participation. 3. Authorities of at least 10 regional/rayon applied CBA methodology in non-CBA territory. 4. At least 55% of rayon authorities use LDF for participatory decision making by 2016 5. At least 80% of community organisations succeed in getting their CDPs incorporated in the local development plan of rayons by 2016. 6 At least two regional development funds are established by 2017; 7 At least 925 community projects supported, including 150 projects on innovative energy efficiency Gender Marker Rating and Motivation - 2 A particular emphasis will be made to empower women and raise gender awareness in communities by supporting women to lead in the identification, planning and implementation of development projects to set up community organizations and promoting the establishment of women led agricultural and other) cooperatives. Related CP outcome: People-centered decentralisation of local public governance Sustainable economic development through pro-poor policy reform | [17 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 5387.98 |  |  |  | 15700 | 15700 | 31400
| 1.4 Lessons learned on local communities and local/regional stakeholders mobilization to get organized/ networked for implementation of CBA-III | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 2811.12 |  |  |  | 8160 | 8160 | 16320
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 15000 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 5447.4847 |  |  |  | 3910.2 | 3350.2 | 7260.4
0
0
0
0
0
0
0
0
0
| SUBTOTAL | [10 empty] | 83268.6947 |  |  |  | 59770.2 | 51210.2 | 110980.4
| Activity 2: Decentralized and participatory governance mechanisms integrated in the standard practice of local governments resulting in improved joint decision-making, planning, and service delivery | [16 empty] | 0
| 2.1 Develop partnership with local/regional authorities | [6 empty] | 001981 | 30079 | 10159 | 71600 | 0 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 0 | [5 empty] | 0
| 2.2 Provide logistics and ICT support to strengthen rayon/reginonal level CRCs | [6 empty] | 001981 | 30079 | 10159 | 72200 | 0 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 72800 | 0 | [5 empty] | 0
| 2.3 Support establishment of 'regional development fund' (RDF) | [6 empty] | 001981 | 30079 | 10159 | 71300 | 0 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 0 |  |  |  | 320 | 320 | 640
| 2.4 Lessons learned on functioning of local development forums (LDFs) and regional coor-dination councils (RCCs) for participatory decision-making | [6 empty] | 001981 | 30079 | 10159 | 75700 | 32974.4 |  |  |  | 13950 | 13800 | 27750
| 2.5 Lessons learned on community-based strategic planning and preparation of community development plans (CDPs) | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 5622.24 |  |  |  | 2700 | 2700 | 5400
| 2.6 Support local government in realization and integration of decentralized and participatory governance mechanism | [6 empty] | 001981 | 30079 | 10159 | 71600 | 15000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 32030 |  |  |  | 20000 |  | 20000
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 20000 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 7743.8648 |  |  |  | 2587.9 | 1177.4 | 3765.3
| SUBTOTAL | [10 empty] | 118370.5048 |  |  |  | 39557.9 | 17997.4 | 57555.3
| Activity 3: Community-based initiatives for sustainable rehabilitation management and operation of basic social and communal infrastructure supported | [16 empty] | 0
| 3.1 Conduct training on planning, implementation and reporting on micro-projects | [6 empty] | 001981 | 30079 | 10159 | 71600 | 0 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 0 |  |  |  | 1800 | 2520 | 4320
| 3.2 Provide seed grants to implement regular/ replication micro-projects | [6 empty] | 001981 | 30079 | 10159 | 72600 | 216902 |  |  |  | 100500 | 125266 | 225766
[8 empty] | 001981 | 04000 | 00012 | 72600 | 232766
| 3.3 Provide seed grants to implement energy efficiency micro-projects | [6 empty] | 001981 | 30079 | 10159 | 72600 | 359539 | [5 empty] | 0
| 3.4 Provide technical backstopping for implementation of community projects | [6 empty] | 001981 | 30079 | 10159 | 71600 | 10000 |  |  |  | 5000 | 4500 | 9500
| 3.5 Support transfer and sustainability of the completed projects | [6 empty] | 001981 | 30079 | 10159 | 75700 | 5000 |  |  |  | 1140 | 1440 | 2580
| 3.6 Document/publish experiences in energy efficiency in rural context | [6 empty] | 001981 | 30079 | 10159 | 71300 | 20000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 72100 | 0 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 74200 | 2000 |  |  |  | 5000 | 5000 | 10000
| 3.7 Conduct events and /training to increase public awareness about energy efficiency options, involving key stakeholders at local level | [6 empty] | 001981 | 30079 | 10159 | 71600 | 2000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 10000 |  |  |  | 11680 | 11440 | 23120
[8 empty] | 001981 | 30079 | 10159 | 74200 | 5290.57 | [5 empty] | 0
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 17000 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 45341.2099 |  |  |  | #REF! | 10511.62 | #REF!
| SUBTOTAL | [10 empty] | 925838.7799 |  |  |  | #REF! | 160677.62 | #REF!
| TOTAL Project # 00091957 | [10 empty] | 1127477.9794 |  |  |  | #REF! | 229885.22 | #REF!
[8 empty] | Total UNDP (00012) |  |  |  | 232766 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[8 empty] | Total EC (10159) |  |  |  | 894711.9794 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Project Number: 00091958 | [17 empty] | 0
EXPECTED OUTPUTS and baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions |  |  | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET ($) | [8 empty] | 0
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Account | Amount | [5 empty] | 0
Output - 2 | Activity 1: Small farm and non-farm businesses developed and promoted in rural areas through cooperatives | [16 empty] | 0
Community-based agro-service cooperatives created for small business promotion in rural areas | 1.1 Lessons learned on communities and local/regional authorities partners mobilisation to develop cooperatives in rural areas using document/publish experiences on RED component | [6 empty] | 001981 | 30079 | 10159 | 74200 | 4824.65 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 74200 | 10581.15 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 14865.4 |  |  |  | 23400 |  | 23400
[8 empty] | 001981 | 30079 | 10159 | 75700 | 5622.24 |  |  |  | 2300 |  | 2300
Indicators: 1 # of agro-based service cooperatives ¦ to promote small businesses established. Baseline: Small producers across in rural Ukraine lack access to market and processing facilities Target: At least 40 cooperatives established Gender Marker Rating and Motivation - 2 1 A particular emphasis will be made to empower women and raise gender awareness in communities by i supporting women to lead in the identification, planning and implementation of development projects to set up cooperatives and promoting the establishment of women led agricultural and other cooperatives. Related CP outcome: Sustainable economic development through pro-poor policy reform | 1.2 Establish and strengthen technical information centres | [6 empty] | 001981 | 30079 | 10159 | 72200 | 0 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 |  |  |  |  | 32200
[8 empty] | 001981 | 30079 | 10159 | 72800 | 0 | [5 empty] | 0
| 1.3 Provide training and technical support for development of business skills | [6 empty] | 001981 | 30079 | 10159 | 71300 | 15000 |  |  |  | 6000 |  | 6000
[8 empty] | 001981 | 30079 | 10159 | 71600 | 2000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 5000 | [5 empty] | 0
| 1.4 Provide small grants to implement economic initiatives | [6 empty] | 001981 | 30079 | 10159 | 72600 | 405766.64 |  |  |  | 236000 |  | 236000
| 1.5 Provide technical backstopping for implementation and sustainability of the economic initiatives | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5000 |  |  |  | 3600 |  | 3600
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 7000 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 33296.2056 |  |  |  | 21245 | 0 | 21245
| SUBTOTAL | [10 empty] | 508956.2856 |  |  |  | 324745 | 0 | 324745
| TOTAL Project # 00091958 | [10 empty] | 508956.2856 |  |  |  | 324745 | 0 | 324745
[8 empty] | Total UNDP (00012) |  |  |  | 0 |  |  |  | 0 | 0 | 0
[8 empty] | Total EC (10159) |  |  |  | 508956.2856 |  |  |  | 324745 | 0 | 324745
Project Number: 00091959 | [17 empty] | 0
EXPECTED OUTPUTS and baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions |  |  | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET ($) | [8 empty] | 0
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Account | Amount | [5 empty] | 0
Output -3: | Activity 1: Established and strengthened homeowners associations capacities as the self-governance bodies to jointly maintain the common parts of the multi-apartments buildings | [16 empty] | 0
Improved delivery of municipal housing services through community-led approach and innovative governance practices | 1.1 Update guidelines/leaflets to reflect urban specifics of CBA approach | [6 empty] | 001981 | 30079 | 10159 | 74200 | 2000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 74200 | 10581.15 | [5 empty] | 0
| 1.2 Update guidelines for comprehensive energy saving technologies in housing sector at the municipal level | [6 empty] | 001981 | 30079 | 10159 | 71300 | 12012.02 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 74200 | 3000 | [5 empty] | 0
Indicators: 1 # cities where support to creation of ACMBs is provided 2. # cities where comprehensive technical solutions in multi- apartment buildings are implemented. 3 # of high-visibility events to raising public awareness on energy saving options. 4 # of community members and local/regional authorities trained in energy planning and efficient energy use (with at least 50% of women participating). 5 Financial model is designed for the sustainable and replicable retrofitting of housing stock. Baseline: 1. Only 25% of all multi-apartment buildings in Ukraine is managed by ACMBs 2 Comprehensive technical solutions in housing sector are implemented in limited number of Ukrainian cities. 3 Majority of active community members, local/regional authorities and recently elected officials lack skill in energy planning. 4. The amount of energy consumption of the Ukrainian households is 3-7 times higher than the average in Europe 5 There is no viable financial model to support comprehensive renovation of housing stock affordable for ACMB. Targets: 1. At least in 25 cities simple renovation in multi-apartment buildings are supported 2. At least in 5 cities comprehensive technical solutions in multi-apartment buildings are supported. 3. 50 high-visibility events to raising public awareness on energy saving options organised. 4. At least 10,000 people, including community members and local/regional authorities trained in energy planning and efficient energy use (with at least 50% of women participating). 5. Financial model is designed for the sustainable and replicable retrofitting of housing stock. Gender Marker Rating and Motivation - 2 Significant involvement and participation of women in key activities on energy planning, training and implementation of micro-projects on I energy efficiency will be promoted in ' all activities Related CP outcome: People-centered decentralisation of local public governance Sustainable development policies and practices make the difference | 1.3 Develop manuals on ACMB creation and functioning | [6 empty] | 001981 | 30079 | 10159 | 74200 | 0 |  |  |  |  | 8400 | 8400
| 1.4 Organise training for communities and municipal authorities in energy planning and energy efficiency, and ACMBsfunctioning | [6 empty] | 001981 | 30079 | 10159 | 71600 | 2000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 7000 |  |  |  |  | 11250 | 11250
| 1.5 Organize information campaign on lessons learned of ACMB as a progressive form of management of multi-apartment buildings promotion | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 4865.4 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 8433.36 |  |  |  |  | 6000 | 6000
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 7000 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 4332.4351 |  |  |  | 0 | 1795.5 | 1795.5
| SUBTOTAL | [10 empty] | 66224.3651 |  |  |  | 0 | 27445.5 | 27445.5
| Activity 2: Replicable community mobilisation model for building retrofitting developed and tested in practice. | [16 empty] | 0
| 2.1 Mobilise municipal communities and authorities to get organized/networked for implementation of CBA methodology | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5000 | [5 empty] | 0
[9 empty] | 30080 | 10159 | 71300 | 22086.57 |  |  |  |  | 30000 | 30000
[9 empty] | 30079 | 10159 | 75700 | 5000 |  |  |  |  | 5000 | 5000
| 2.2 Support technical design of selected priority projects | [6 empty] | 001981 | 30079 | 10159 | 75700 | 0 | [5 empty] | 0
0
| 2.3 Provide seed grants to implement municipal HAs' micro-projects | [6 empty] | 001981 | 30079 | 10159 | 72600 | 500000 |  |  |  |  | 416604 | 416604
| 2.4 Provide seed grants to implement building retrofitting micro-projects | [6 empty] | 001981 | 30079 | 10159 | 72600 | 1639344.2623 |  |  |  |  | 1664817 | 1664817
| 2.5 Provide technical backstopping for implementation of community projects | [6 empty] | 001981 | 30079 | 10159 | 71600 | 15262.3 |  |  |  |  | 12000 | 12000
[9 empty] | 30079 | 10159 | 75700 | 5000 |  |  |  |  | 20000 | 20000
| 2.6 Support transfer and sustainability of the completed projects | [6 empty] | 001981 | 30079 | 10159 | 71600 | 2000 |  |  |  |  | 0 | 0
[9 empty] | 30079 | 10159 | 75700 | 2500 |  |  |  |  | 17340 | 17340
| 2.7 Document experiences in multiappartment houses retrofitting | [6 empty] | 001981 | 30079 | 10159 | 74200 | 4000 |  |  |  |  | 2000 | 2000
| 2.8 Conduct events and /training to increase public awareness about energy efficiency options in housing sector | [6 empty] | 001981 | 30079 | 10159 | 71600 | 2000 | [5 empty] | 0
0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 2500 |  |  |  |  | 23500 | 23500
| 2.9 Conduct summary events/roundtables related to energy efficiency in housing sector | [6 empty] | 001981 | 30079 | 10159 | 75700 | 8433.36 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 75700 | 20000 | [5 empty] | 0
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 24262 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 158017.1945 |  |  |  | 0 | 153388.27 | 153388.27
|  |  |  | SUBTOTAL | [7 empty] | 2415405.6868 |  |  |  | 0 | 2344649.27 | 2344649.27
| TOTAL Project # 00091959 | [10 empty] | 2481630.0519 |  |  |  | 0 | 2372094.77 | 2372094.77
[8 empty] | Total UNDP (00012) |  |  |  | 0 |  |  |  | 0 | 0 | 0
[8 empty] | Total EC (10159) |  |  |  | 2481630.0519 |  |  |  | 0 | 2372094.77 | 2372094.77
Project Number: 00091960 | [17 empty] | 0
EXPECTED OUTPUTS and baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions |  |  | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET ($) | [8 empty] | 0
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Account | Amount | [5 empty] | 0
Output - 4: | Activity 1: Knowledge management and experience dissemination mechanism established at local/regional/national level | [16 empty] | 0
Enabling environment created at national and local level for replication of the principles of community-based approach to local sustainable development | 1.1 Develop partnership with universities and training institutions | [6 empty] | 001981 | 30079 | 10159 | 71600 | 1500 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 75700 | 3646 | [5 empty] | 0
| 1.2 Expose local and regional authorities, universities and training institutions to CBA best practice | [6 empty] | 001981 | 30079 | 10159 | 71600 | 4000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 75700 | 8000 | [5 empty] | 0
Indicators: 1 # of universities/training institutes which included in their teaching curricula a training module on local governance, public participation and sustainable development. 2 % of CO-members, LAs officials, who participated in training, exposure visits, roundtables, etc. state their understanding of and their intention to adopt participatory approaches in all relevant spheres of local governance. 3 National level knowledge management hub in the field of participatory governance and community based development strengthened. Baselines: 1 Academia and authorities of all tiers of government lack access to grassroots-based knowledge. 2 Public participation mechanisms are not fully applied in everyday practices of local governments. 3 National level repository of UADRC dedicated to community based approach lacks capacity. 4. Legal framework for decentralized governance is in the process of revision. 5 Insufficient number of national level advocacy held in past on community based approach 6. Limited number of innovative approaches to the provision of municipal services. Targets. 1. At least 20 universities/training institutions introduce courses on CBA methodology by 2015. 2 At least 500 CO-members/officials and local/regional authorities from non- CBA communities participated in training, exposure visits roundtables demonstrate understanding and willing to adopt participatory approaches in all relevant spheres of local governance. 3. The national level knowledge management hub established at UADRC is functioning in linkage with regional and rayon community resource centres. 4 Recommendations to at least 7 legal acts developed and discussed. 5. At least 4 national roundtables held to discuss and advocate for required policy changes to ensure full-fledged participatory decision making at the local level. 6 At least 100 innovative municipal governance projects supported contributing to improved services delivery Gender Marker Rating and Motivation - 2 Empowering women and promoting gender awareness will be achieved through motivating women leaders to come forward to develop their skills and knowledge Related CP Outcome: People-centered decentralisation of local public governance | 1.3 Provide technical/ advisory support for curriculum development on community development | [6 empty] | 001981 | 30079 | 10159 | 71300 | 50000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 72100 | 1200 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 74200 | 9000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 75700 | 12440 | [5 empty] | 0
| 1.4 Strengthen capacity of the national knowledge management hub at the ‘Ukrainian Association of Local and Regional Authorities’ | [6 empty] | 001981 | 30079 | 10159 | 71600 | 0 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 72600 | 0 | [5 empty] | 0
| 1.5 Establish partnership with and provide support to All-Ukrainian Association of Village and Settlement Councils, Association of Small Cities and Agricultural Service Cooperatives Union of Ukraine for promotion of community-led local sustainable development approach | [6 empty] | 001981 | 30079 | 10159 | 71600 | 0 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 72600 | 15000 | [5 empty] | 0
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5500 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 7720.02 |  |  |  | 0 | 0 | 0
| SUBTOTAL | [10 empty] | 118006.02 |  |  |  | 0 | 0 | 0
| Activity 2: General policy framework on community based approach to local sustainable development is presented to and discussed among national stakeholders | [16 empty] | 0
0
| 2.1 Organize a nationwide discussion of lessons learned under implementation of practices and procedures of participatory governance | [6 empty] | 001981 | 30079 | 10159 | 71300 | 50000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 71600 | 6000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 75700 | 15000 | [5 empty] | 0
| 2.2 Provide support to relevant government agencies in development of legal framework for community led development | [6 empty] | 001981 | 30079 | 10159 | 71300 | 20000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 72100 | 5000
| 2.3 Produce and disseminate visibility materials to promote CBA vision among stakeholders at all level | [6 empty] | 001981 | 30079 | 10159 | 72100 | 5500 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 74200 | 4500 | [5 empty] | 0
| 2.4 Provide donors, media and partners with up to date information on CBA activities | [6 empty] | 001981 | 30079 | 10159 | 71600 | 15000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 72200 | 0 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 74200 | 3000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 74220 | 4000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 75700 | 2342.6 | [5 empty] | 0
| 2.5 Maintain CBA website | [6 empty] | 001981 | 30079 | 10159 | 72100 | 7500 | [5 empty] | 0
| 2.6 Organise roundtables donors/partners/media visits | [6 empty] | 001981 | 30079 | 10159 | 71600 | 5000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 74220 | 0 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 75700 | 10222 | [5 empty] | 0
| 2.7 Publish CBA experiences and related documents for wider dissemination | [6 empty] | 001981 | 30079 | 10159 | 72100 | 20000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 74220 | 3000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 71600 | 5000 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 12674.522 |  |  |  | 0 | 0 | 0
| SUBTOTAL | [10 empty] | 193739.122 |  |  |  | 0 | 0 | 0
| Activity 3: Enhanced skills and capacity among municipal communities and authorities in applying innovations to increase the living standards of the population | [16 empty] | 0
| 3.1 Organize information campaign on lessons learned under capacity development package | [6 empty] | 001981 | 30079 | 10159 | 75700 | 8909.088 | [5 empty] | 0
| 3.2 Organize trainings for municipal authorities and communities on innovative governance practices | [6 empty] | 1981 | 30079 | 10159 | 71600 | 10000 | [5 empty] | 0
[9 empty] | 30079 | 10159 | 75700 | 10335.18 | [5 empty] | 0
| 3.3 Provide seed grants to implement municipal projects on social infrustructure re-habilitation | [6 empty] | 001981 | 30079 | 10159 | 72600 | 64917.26 |  |  |  |  | 20000 | 20000
| 3.4 Provide seed grants to implement municipal projects on innovative governance initiatives | [6 empty] | 001981 | 30079 | 10159 | 72600 | 515870 | [5 empty] | 0
| 3.4 Support for internal displaced persons | [6 empty] | 001981 | 30079 | 10159 | 71600 | 1000 | [5 empty] | 0
[11 empty] | 72600 | 0 | [5 empty] | 0
| 3.5 Consolidate lessons learned and ensure knowledge sharing | [6 empty] | 001981 | 30079 | 10159 | 74200 | 3000 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 74200 | 5290.59 | [5 empty] | 0
| TICKETS | [6 empty] | 001981 | 30079 | 10159 | 71600 | 9000 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 43982.5483 |  |  |  | 0 | 1400 | 1400
| SUBTOTAL | [10 empty] | 672304.6663 |  |  |  | 0 | 21400 | 21400
| Activity 4: Effective project management and advisory support provided for implementation of CBA activities | [16 empty] | 0
| 3.1 Provide national/ international expertise and support services |  | Gross cost on expatriate/international staffs |  |  |  |  | 001981 | 30079 | 10159 | 61300 | 168692.42 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 62300 | [6 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 63300 | [6 empty] | 0
| 3.2 Arrange logistics and operational support services | [6 empty] | 001981 | 30079 | 10159 | 63500 | [6 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 65100 | [6 empty] | 0
|  |  | Contracrt Services - Individuals |  |  |  |  | 001981 | 30079 | 10159 | 71400 | 1631988.51 | [5 empty] | 0
|  |  | Security Cost |  |  |  |  | 001981 | 30079 | 10159 | 72100 | 66592.6748 | [5 empty] | 0
|  |  | Montioring of field operations |  |  |  |  | 01981 | 30079 | 10159 | 71300 | 9089.575 | [5 empty] | 0
| 3.3 Carry out management reviews audits and assessments of the project implementation |  | Internet, communication services |  |  |  |  | 001981 | 30079 | 10159 | 72100 | 81700.8845 | [5 empty] | 0
|  |  | Project MT evaluation |  |  |  |  | 001981 | 30079 | 10159 | 74100 | 0 | [5 empty] | 0
|  |  | Office equipment and furniture |  |  |  |  | 001981 | 30079 | 10159 | 72200 | 43181.1979 | [5 empty] | 0
|  |  | Materials&Goods |  |  |  |  | 001981 | 30079 | 10159 | 72300 | 50000 | [5 empty] | 0
|  |  | Communic&Audio Vis Equipment |  |  |  |  | 001981 | 30079 | 10159 | 72400 | 0 | [5 empty] | 0
|  |  | Supplies/Expendable Equipments |  |  |  |  | 001981 | 30079 | 10159 | 72500 | 47732 | [5 empty] | 0
|  |  | Rental and Maintenance - Premises |  |  |  |  | 001981 | 30079 | 10159 | 73100 | 272153.5313 | [5 empty] | 0
|  |  | Vehicle Maintenance and Repair |  |  |  |  | 001981 | 30079 | 10159 | 73400 | 112777.55 | [5 empty] | 0
[8 empty] | 001981 | 30079 | 10159 | 73400 | 4774.27 | [5 empty] | 0
|  |  | Staff & Vehicle insurance |  |  |  |  | 001981 | 30079 | 10159 | 74505 | 21496.4629 | [5 empty] | 0
|  |  | Miscellaneous Expenses (Petty Cash) |  |  |  |  | 001981 | 30079 | 10159 | 74525 | 35100 | [5 empty] | 0
| F&A + Misc. | [6 empty] | 001981 | 30079 | 10159 | 75100 | 178169.5353 |  |  |  | 0 | 0 | 0
| SUBTOTAL | [10 empty] | 2723448.6117 |  |  |  | 0 | 0 | 0
| TOTAL Project # 00091960 | [10 empty] | 3707498.4199 |  |  |  | 0 | 21400 | 21400
[8 empty] | Total UNDP (00012) |  |  |  | 0 |  |  |  | 0 | 0 | 0
[8 empty] | Total EC (10159) |  |  |  | 3707498.4199 |  |  |  | 0 | 21400 | 21400
| GRAND TOTAL AWARD # 00083522 | [10 empty] | 7825562.7368 |  |  |  | #REF! | 2623379.99 | #REF!
[8 empty] | GRAND TOTAL UNDP (00012) |  |  |  | 232766 |  |  |  | #REF! | #REF! | #REF!
[8 empty] | GRAND TOTAL EC (10159) |  |  |  | 7592796.7368 |  |  |  | #REF! | #REF! | #REF!
Prgrmble Bdgt
[10 empty] | 30079 |  | #REF!
[10 empty] | 04000 |  | 232766
[10 empty] | TOTAL |  | #REF!
Prepared by |  | Approved by | [6 empty] | Endorsed by
Hendrik van Zyl
Date: |  | Date: | [6 empty] | Date: