## Budget Revision Checklist
Gender Marker revised?  No
 Yes, revised marker is "___" and agreed with Gender Focal Point __________
Cleared _________________________
Cleared by DRR _________________________
Budget Revision Check List
Projectt ID # and title: 00120483, Strengthening civic space and voice of women and youth to enhance the role of Anti-Corruption Agency in Uzbekistan
Output #: 00116672
Rev "A"
| Items Checked | Yes | No
1 | PRRF/WP available/up-to-date | X
Project Information correctly entered into Atlas
2 | Revision Type correct | X
3 | Revision Code correct | X
4 | Justification made | X
5 | Revision reason duly explained (in Brief Description field) | X
6 | Project Status correct | X
7 | Impl. Agents/Resp.Parties correct | X
Financial Data
8 | Atlas GL Details correct | X
9 | UNDP input correct | X
10 | Cost Sharing |  | X
a | Cost Sharing Agreement available
b | Cost Sharing Input correct
13 | Delivery (%)
Monitoring
14 | Quarterly/annual/final report available in Atlas?
15 | Did TPR, Project Board meeting take place?
16 | Equipment Inventory/Transfer done (in case of project closure)
Approval
17 | Signatories correct | X
If Operational Closure: following documents have been submitted:
| Items Checked | Yes | No
18 | Signed FPR with minutes of Project Review meeting; | n/a
19 | Other project reports and minutes of the important project meetings (e.g. evaluation reports, donor reports, annual project review meeting minutes, etc.);
20 | Originals of all previous project budget revisions;
21 | Copies of CDRs signed by NPC;
22 | Copy of the document on Transfer of all Assets procured within the project cycle.
Reviewed by SPIU
signature, date

## Cover
UNITED NATIONS DEVELOPMENT PROGRAMME
GOVERNMENT OF UZBEKISTAN
Project Budget
Project #: | 00120483
Output #: | 00116672
Project Title: | Strengthening civic space and voice of women and youth to enhance the role of Anti-Corruption Agency in Uzbekistan
Start date: | 23/11/2021 | Budget Financing (in US $) | [6 empty] | Variance
End date: | 30/11/2022 | INPUTS | Revision "B" |  |  |  | Revision "A"
|  |  | Total Budget | 2021 | 2022 | 2023 | Total Budget | 2022
|  | UNDP FW | 0 |  |  |  | 198251 | 198251
|  | TOTAL programmable | 0 | 0 | 0 | 0 | 198251 | 198251
|  | GMS (7%) & DPC | 0 |  |  |  | 25749 | 25749
|  | TOTAL Budget | 0 | 0 | 0 | 0 | 224000 | 224000
Implementing Partner: | Anti-Corruption Agency of Uzbekistan
Responsible Partner: | UNDP, Anti-Corruption Agency of Uzbekistan
Revision Type: | Initial
Brief Description:
The annual workplan and budget for Y2022 are prepared to approve and launch the engagement facility on "Strengthening civic space and voice of women and youth to enhance the role of Anti-Corruption Agency in Uzbekistan".
Approved by: Signature: Date: Name and Title
UNDP | [6 empty] | Ms. Matilda Dimovska, UNDP Resident Representative
|  |  | ______________________ |  |  |  |  | UNDP Resident Representative in Uzbekistan
Anticorruption Agency of the Republic of Uzbekistan |  |  | ______________________ |  |  |  | Mr. Akmal Burhanov, National Project Coordinator

## AWP 2022
Annex-2
Annual Work Plan 2022
United Nations Development Programme
Uzbekistan
Year: 2022
Output ID: 00116672
Project ID: 00120483
Project Title: Strengthening civic space and voice of women and youth to enhance the role of Anti-Corruption Agency in Uzbekistan
EXPECTED OUTPUTS (including indicators and annual targets) | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE AGENCY | Department ID | PLANNED BUDGET
|  | Q1 | Q2 | Q3 | Q4 |  |  | Funding Source |  | Budget Line | Budget Description | Budget for 2022
[8 empty] | Fund | Donor
Output 1: Enhanced transparency, accountability, and inclusiveness of the national anti-corruption systems through: - Improved policy making role and capabilities of ACA to develop and implement national inclusive and gender-sensitive anti-corruption policy - Empowered and strengthened civic engagement of women, youth, marginalized and vulnerable groups to exercise public oversight over state authorities, including the ACA; and raise awareness to foster zero-tolerance towards corruption Indicators: 1. Number of policy, legal and regulatory acts developed with integration of inclusive approach, gender equality and human rights components. Baseline: 0 Targets: at least 5 documents 2. Number of capacitated CSOs focusing on gender issues, women’s movements, civil activists and journalists through integration of gender related anticorruption into their activities and programmes Baseline: 0 Targets: at least 10 CSOs//NGOs, media Related CP outcome: Gender marker: GEN 3 | ACTIVITY 1: Institutional capacity and policy-making role of ACA
| Activity 1. Developing institutional capacity and policy-making role of ACA to implement national inclusive, transparent and gender-sensitive anti-corruption strategy, policy measures and legislative framework in line with best international practices, benefiting all strata of the population, including women and youth, vulnerable and marginalized groups with leveraging innovative and digital solutions in the public and private sectors. - Support implementation of digital anti-corruption tools with the focus on gender related indicators. - Provide analytical support for inclusive, gender-sensitive development of the National Anti-Corruption Agency, and other legal documents, ensuring gender expertise and participation of women’s movements and activists. - Conduct training and technical advance for the integration of gender-sensitive and human-rights based approaches in legal/regulatory drafting. | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 71400 | Staff salaries (PM) | 31500
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 71300 | Local Consultants | 10000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 71200 | International Consultants | 15000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 72100 | Contractual Services- Companies | 31000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 72400 | Communication fees | 1000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 74200 | Printing and Publications | 5000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 74500 | Miscellaneous | 5000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 75100 | GMS | 6895
|  | Subtotal for Activity 1 | [9 empty] | 105395
ACTIVITY 2: Civil society organizations focusing on gender issues, women’s movements and media
| Activity 2: Empowering and strengthening civil society organizations focusing on gender issues, women’s movements and media to: exercise public oversight over state authorities providing the most in-demand public services for women; test whistle-blower protection mechanisms and tools; and ensure greater public awareness to foster zero-tolerance towards corruption. - Conduct educational and awareness raising activities, including through PR and outreach campaigns and small grants programs, targeting engagement of CSOs, focusing on gender issues, women’s movements and media empowering women, youth, media to foster zero tolerance to corruption; - Organize capacity development activities focusing on gender issues , including trainings for CSO, women and youth on effective integration and use of anti-corruption components in their activities - Strengthen civil society focusing on gender issues in coordination of the anti-corruption work. | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 71400 | Staff salaries (AFA) | 21500
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 71300 | Local Consultants | 10000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 71200 | International Consultants | 10000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 72100 | Contractual Services- Companies | 25000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 72400 | Communication fees | 1251
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 73100 | Rental and Maintainance | 5000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 74500 | Miscellaneous | 3000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 74200 | Printing and Publications | 6000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 72500 | Supplies | 3000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 72600 | Small Grants | 15000
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 61100 | Direct project costs - (DPC) | 11200
|  | X | X | X | X | 001981 | 58404 | 28610 | 12711 | 75100 | GMS | 7654
|  | Subtotal for Activity 2 | [9 empty] | 118605
TOTAL Programmable | [11 empty] | 198251
TOTAL GMS & DPC | [11 empty] | 25749
GRAND TOTAL | [11 empty] | 224000
Prepared by:________________________ |  | Cleared by: ____________________ Kamila Mukhamedkhanova, Cluster Leader, Cluster on Effective Governance, Policy and Communication
Nariman Muradasilov, Programme Analyst on Effective Governance a.i.
Cleared by: ____________________ Doina Munteanu, Deputy Resident Representative, UNDP Uzbekistan