## CS-2016-20
Communication Strategy Results Framework 2016-2020
OUTCOME | OUTCOME INDICATORS | OUTPUTS | OUTPUT INDICATORS, BASELINES AND TARGETS | MEANS OF VERIFICATION | INPUTS/ACTIVITIES
By 2020, UN is perceived as a credible organization to address issues related to human rights and development | 1. % of national partners who assert the UN as a credible partner and can describe positive results of UN work in Uzbekistan | By 2020, issue-based communication on priority issues addressed by UNDAF and SDGs is enhanced | % of joint and individual communication products and events raising/covering UNDAF and SDG priorities | Copies of communication products; reports on communication events;
| Baseline(2016): not available |  | Baseline: TBD
| Target: at least 70% |  | Target: 100%
| 2. % of web-based media agencies that mention UNDAF and SDGs in their reports; |  | Increase in # of visitors to UN.uz web-site and subscribers/followers of UN page in Facebook (%) | Data on UN web-site visits/Facebook subscribers; Quarterly reports by UNIC;
| Baseline: TBD |  | Baseline: 0
| Target: at least 50% |  | Target: at least 30% increase
|  |  | # of digital campaigns conducted | Annual UNCG reports;
Baseline(2016): 0
Target: at least 1 per thematic area
|  |  | Increase in # of key decision makers who express commitment towards addressing UNDAF/SDG priority issues; | Minutes of high level meetings; | High level meetings
Baseline: TBD
Target: at least 30% increase
|  |  | % of UNDAF RG members that have positively evaluated UNCG contribution to deliver UNDAF commitments; | Biennial work-plan assessment
Baseline (2016): 0%
Target: at least 80%
|  | By 2020, UN agencies communicate in a common voice on priority issues | Availability of common messages on priority issues agreed upon (Yes/No); | Minutes of UNCT meeting/retreat that endorse proposed messages; | Draft communication messages prepared by UNCG in consultations with UNCT
Baseline (2016): No
Target: yes
|  |  | % of joint communication products/events that deliver commonly agreed messages on priority issues ; | Copies of joint communication products; Agency reports on communication events prepared by communication focal points; Monitoring reports by RCO; | Quarterly UN newsletters; UN web-site, UN Facebook page; produced handouts, press-releases and information materials for UN observance days
Baseline (2016):0
Target: 100%
|  |  | % of agency specific communication messages/products being consistent with commonly agreed messaging | Copies of agencies' communication products; Agency reports on individual communication events prepared by communication focal points; Monitoring reports by RCO; | Communication products of individual agencies;
Baseline (2016): 0
Target: 100%
|  | By, 2020, awareness of UN brand and programming is increased | % of joint communication events and UN stories covered and republished by media; | Media monitoring report by UNIC | Quarterly UN newsletters; UN web-site, UN Facebook page; produced handouts, press-releases and information materials for UN observance days
Baseline: TBD
Target: at least 80%
|  |  | # of events/activities organized for staff on brand identity; | Events/activities report | Communication events with active engagement of UN staff (trainings, contest, UN Town Hall meetings, etc.)
Baseline: 1 in 2014
Target: at least 5 (1 per year)
|  | By 2020, partnerships are strengthened with key decision makers and celebrities | Increase in the number of partners that deliver messages in support of UN agenda during joint events; | Events/activities report | Joint communication events
Baseline (2016): TBD
Target: TBD
Increase in the # of celebrities who delivered messages in support of UN agenda;
Baseline: TBD
Target: TBD

## WP-2017
UN Communication Group Workplan for 2017
# | Outputs as per Joint Communication Strategy 2016-2020 | Activities Planned | Target audience / communication channel | Indicators | Date | Leading | Contributing
1 | By 2020, issue-based communication on priority issues addressed by UNDAF and SDGs is enhanced. (focus on substance) | 1.Contribute to organization and highlighting the SDG localization related events conducted in partnership with the Government; | General public, Local mass media, National partners | 1.1. Number of articles about SDG localization results with focus on SDG promotion; | February - December 2017 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline(2016): 0
Target: At least 6 (1 per thematic area)
|  | 2.Preparation of SDG information booklets and other promo materials. (SDG comics in UZB by UN Women, dubbing of movie on SDGs in UZB) | General public, Local mass media, National partners | 2.1.Number of SDG information booklets/fliers in English, Russian and Uzbek prepared and disseminated to partners and public. | February - December 2017 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline: 0
Target: (for dicision makers, public, children and youth);
|  | 3. Preparation of video episodes per SDGs and their implication on ordinary people's lives. | General public, Local mass media, National partners | 3.1. Number of video episodes produced per SDG thematic area; | February - December 2017 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline: 0
Target: 6
|  | 4. Local news at un.uz web-site diversified | General public, Local mass media, National partners | 4.1. Number of agency-specific monthly news at un.uz web-site; | February - December 2017 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline: 2 (average per month in 2016)
Target: 6 per month
2 | By 2020, UN agencies communicate in a common voice on priority issues. (focus on coordination) | 5. Joint media survey conducted | The Government, CSOs, General public, Local mass media | 5.1.Availability of report on media survey. | February - September 2017 | RCO and UNIC | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline: no
Target: yes
|  | 6. UNCG contributed to preparation of policy briefs on critical topics proposed by UNCT for joint UN advocacy; [Note: content of policy briefs are expected to be elaborated by UNDAF RGs. UNCG is expected to be responsbile for ensuring the usage of reader friendly language, design, publicaiton and dissemination] | The Government, CSOs, General public, Local mass media | 6.1. Number of policy briefs produced; | February - December 2017 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline: 0
Target: 6
|  |  |  | 6.2. Extent to which advocacy messages are reflected in communication products (UN newsletter, agency news, press-releases) and speeches (RC/HoA message for UN joint observances, talking points of HoA in bilateral meetings) [fully, partially, not reflected]; | January - December 2016 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline (2016): fully
Target: fully reflected (every communication product and speeches contain at least one advocacy message identified)
|  | 7. Disseminating quarterly newsletters with key joint messages through all available communication channels (UN website, postal services) | Government, donors | 7.1. Number of quarterly UN newsletter issues disseminated to national partners and donors. | January - December 2017 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline (2017): 0
Target: 3
|  | 8.Organize joint observance of key UN days as per the list approved by the UNCT (WHD, WPFD, WED, IYD, IDEVAW, WAIDSD, IDPWD, HRD) | Central Government, national partners, international organisations and donors, UN staff, local mass media | 8.1 Number of UN observances marked with involvement of 2 or more agencies. | February-December 2016 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, FAO
Baseline(2016): 5
Target: 8
|  |  |  | 8.2. Rate of media coverage of joint UN observances. | February-December 2016 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, FAO
Baseline (2016): 40%
Target: 100%
|  | 9. Digital outreach training for UNCG organized | UNCG members | 9.1.% of UNCG members that claim about increased knowledge in digital outreach tools and techniques. | 2017-02-01 | UNCG/RCO | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNIC
Baseline: 0 %
Target: at least 90%
3 | By 2020, awareness of UN brand and programming is increased | 10.Joint event with the Government organized to mark 25th anniversary of Uzbekistan becoming member of the UN. | General public, Local mass media, National partners | 10.1. Opening ceremony of upgraded UN garden with the focus on SDGs conducted; | March-April 2017 | UNCT/RCO | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline(2017): no
Target: yes
|  |  |  | 10.2. High level SDG forum and Joint photo exhibition on UN cotribution to country's development and Uzbekistan contribution to UN agenda organzied; | March-April 2017 | UNCT/RCO | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV, ILO, FAO
Baseline(2017): no
Target: yes
|  | 11.Joint UN Day dedicated to 72nd anniversary organized at high level | Central Government, national partners, international organisations and donors, local mass media, UN staff | 11.1.Number of media that covered UN Day event. | 2017-10-01 | UNCT/RCO | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, WORLD BANK, UNV, ILO, FAO
Baseline (2016): 6
Target: at least 20
|  |  |  | 11.2. Joint townhall meeting organized for staff on brand identity; | 2017-10-01 | UNCT/RCO | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, WORLD BANK, UNV, ILO, FAO
Baseline: 1 in 2014
Target: 1
4 | By 2020, partnerships are strengthened with key decision makers and celebrities. | 12. Organize joint observances in collaboration with national partners and celebrities | Central Government, national partners, international organisations and donors, UN staff, local mass media | 12.1.Number of partners that deliver messages in support of UN agenda during joint events; | February-December 2017 | UNCG | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, FAO
Baseline (2016): 46
Target: TBD
13.2.Number of celebrities who delivered messages in support of UN agenda
Baseline (2016): 15
Target: TBD
5 | Operational support and planning | 13.Get relevant UN agencies subscribed to BBC monitoring news | UNCG members | 13.1.UNCG members have regular access to BBC monitoring news | January - December 2017 | UNIC | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, RCO, UNV
|  | 14.Reflectng on activities of 2017 and Planning for UNCG activities for 2018 | UNCG members | 14.1. Updated workplan with more detailed outputs; | February 2017 | UNIC | UNDP, UNFPA, UNESCO, UNICEF, UNAIDS, UNODC, UN WOMEN, WHO, UNV
14.2. Updated UNCT communication strategy.