Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | Mainstreaming global environmental priorities into national policies and programmes |
| --- | --- |
| Country(ies): | Vanuatu | GEF Project ID: | 5655 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 5051 |
| Other Executing Partner(s): | Department of Environment & Conservation, Ministry of Land and Natural Resources (DEC/MLNR) | Submission Date: | 10 January 2014 |
| GEF Focal Area (s): |  | Project Duration (Months) | 36 |
| Name of parent program (if applicable): For SFM/REDD+ For SGP For PPP | Cross-Cutting Capacity Development | Project Agency Fee ($): | 52,250 |

A.  indicative Focal AREA STRATEGY Framework:

| Focal Area Objectives | Trust Fund | Indicative Grant Amount ($) | Indicative Co-financing ($) |
| --- | --- | --- | --- |
|  |  | 550,000 | 550,000 |
| Total Project Cost |  | 550,000 | 550,000 |

- indicative Project description summary

| Project Objective: To strengthen Vanuatu's capacities to meet national and global environmental commitments through improved management of environmental data and information |
| --- |
| Project Component | Grant Type | Expected Outcomes | Expected Outputs | Trust Fund | Indicative Grant Amount ($) | Indicative Cofinancing ($) |
| Component 1: Improved management of information system for the global environment |  | Improved management information system to measure achievements towards global environmental objectives | Harmonized collection and measurement methodologies of key data and information Existing databases and information systems are strengthened and networked to improve access to environmental data and information Agencies' data management protocols are revised to improve access |  | 250,000 | 210,000 |
| Component 2: Strengthened technical capacities for monitoring and evaluation of the global environment |  | Strengthened individual capacities to monitor and evaluate impacts and trends on the global environment | Training on new and improved data and information collection and measurement methodologies Training on analytical skills to evaluate global environmental impacts and trends |  | 200,000 | 240,000 |
| Component 3: Improved decision-making mechanisms for the global environment |  | Institutionalized monitoring and evaluation capacities | Key agencies and DEC mandates have been revised and strengthened to catalyze improved decision-making for the global environment |  | 55,000 | 50,000 |
| Subtotal |  |  | 505,000 | 500,000 |
| Project Management Cost (PMC) |  |  | 45,000 | 50,000 |
| Total Project Cost |  |  | 550,000 | 550,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | DEPC |  | 300,000 |
|  | DEPC |  | 100,000 |
|  | UNDP |  | 100,000 |
|  | To be determined during PPG |  | 50,000 |
| Total Cofinancing |  |  | 550,000 |

- indicative trust fund  Resources ($) Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount ($) (a) | Agency Fee ($) (b)2 | Total ($) c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Vanuatu | 550,000 | 52,250 | 602,250 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources | 550,000 | 52,250 | 602,250 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for   
    this table. PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Project preparation grant (ppg)

Please check on the appropriate box for PPG as needed for the project according to the GEF Project Grant:

Amount                         Agency Fee

Requested ($)	      for PPG ($)

- No PPG required.                                           		       ___-- 0--________       _  --0--_______

- (upto) $50k for projects up to & including $1 million	       ___30,000________      ___2,850_____

- (upto)$100k for projects up to & including $3 million      ___     ________      ___     _____

- (upto)$150k for projects up to & including $6 million      ___     ________      ___     _____

- (upto)$200k for projects up to & including $10 million   ___     ________      ___     _____

- (upto)$300k for projects above $10 million     	       ___     ________      ___     _____

PPG  Amount requested by agency(ies), focal area(s) and country(ies) for MFA and/or MTF roject only

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |
| --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | Vanuatu | 30,000 | 2,850 | 32,850 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total PPG Amount | 30,000 | 2,850 | 32,850 |

MFA:  Multi-focal area projects;  MTF:  Multi-Trust Fund projects.

part ii:  project JustiFication

Project Overview
A.1. Project Description. Briefly describe the project, including ; 1) the global environmental problems, root causes and barriers that need to be addressed; 2) the baseline scenario and any associated baseline projects, 3) the proposed alternative scenario, with a brief description of expected outcomes and components of the project, 4) incremental cost reasoning and expected contributions from the baseline , the GEFTF, LDCF/SCCF and co-financing; 5) global environmental benefits (GEFTF, NPIF) and adaptation benefits (LDCF/SCCF); 6) innovativeness, sustainability and potential for scaling up

Global Environmental Problems: Vanuatu is an archipelago comprised of over 80 islands, a land area of 12,336 sq km, and a maritime exclusive economic zone (EEZ) of 680,000 km2. Approximately 80% population lives in rural communities, mostly in the outer islands. The large volcanic islands with its rugged terrain and tropical forest mean that villages are generally scattered and separated over large distances. Vanuatu's main challenges to sustainable development derive from their geography of widely scattered islands and mountainous terrain; vulnerability to natural disasters; a small domestic market with little potential for economies of scale; and an increasingly competitive international market for tourism and investment. Despite the relatively small, open economy with many development and structural constraints, Vanuatu possesses important advantages such as: strong traditional culture that promotes social stability and family values; fertile, natural resources and un-spoiled environment. From a biodiversity perspective, Vanuatu's island biogeography has resulted in a high degree of speciation and thus endemism. Vanuatu, like its neighbouring islands, also contains important habitats for migratory birds. However, the impacts of human-induced climate change through increased variability and intensity of weather patterns poses a serious threat to the viability of these habitats for endangered endemic species and migratory birds. Climate-related disasters have had huge impacts on Vanuatu's socio-economic development. As an least developed country, Vanuatu is particularly constrained in terms of financial resources as well as the technical and institutional capacities, which further limit the country's ability to address environmental threats and meet Rio Convention objectives. Through its effects on agriculture and well-being, the impacts of climate change have contributed to a decrease in national income while increasing key social and infrastructure costs. Baseline scenario and associated projects: Among Vanuatu's challenges to meeting Rio Convention priorities is the inadequate consideration of the environment in socio-economic decision-making. This is due in large part from inadequate data and information being collected and made available to decision-making. This is further compounded by an inadequate decision-making process that allows for environmental concerns to effectively influence policy outcomes. As a result, important policy decisions that would help Vanuatu pursue sustainable development alternatives that meet Rio Convention objectives are either not considered due to lack of data, information and strategic analyses, are heavily discounted because the latter do not benefit from a strength of technical ability, or decision- and policy-makers do not adequately understand the critical linkages between environment and development. As with other countries in the region, Vanuatu's existing data and information systems currently contribute to national planning processes as well as to the preparation of Rio Conventions' reporting requirements. A number of agencies and stakeholder organizations make more of a contribution to others in this area, although all are facing increasingly serious limitations due to financials cuts, which further limit the ability to retain technically qualified staff to undertaken the strategic analyses to inform decision-making and prepare the required national reports. Vanuatu's Ministry of Lands and Natural Resources (MLNR) oversees the Department of Lands (DL), Department of Geology, Mines and Water (DGMW), Department of Environment and Conservation (DEC), and the Energy Unit (EU). As such, the focal points for all three Rio Conventions lie within the same ministry. This institutional arrangement should in theory make it easier to coordinate the sharing of data and information as well as for the preparation of technical and strategic analyses. However, this institutional arrangement still suffers from limited financial and human resources to allow the DEC to effectively carry out its mandate to conduct research, promote awareness, and catalyze policy interventions on the environment. There are no specific baseline (non-GEF funded) projects in the way that there are baseline projects for GEF focal area projects. Notwithstanding, the most significant baseline intervention that is relevant to the proposed CCCD project is the establishment of the National Advisory Board on Climate Change and Disaster Risk Reduction (NAB). The NAB is a committee made up of government and non-government members with the primary purpose to act as Vanuatu’s supreme policy making and advisory body for all disaster risk reduction and climate change programs, projects, initiatives and activities. Among its six main duties, the NAB serves as a focal point for information sharing and coordination on climate change and disaster risk reduction. The Capacity Building for the Development of Adaptation Measures in Pacific Island Countries (CBDAMPIC) Project that was completed in 2006 can be considered in part as a baseline project to the CCCD. In this regard, the CBDAMPIC facilitated a good rapport and exchange of information between the Climate Change Country Team (who represent government interests) and the Core Community Vulnerability and Adaptation teams that include community representation. The project also facilitated improved access to weather and related environmental information by rural and resource poor populations so that they can make more informed day-to-day resource decisions to prepare for natural hazards. During the PPG, an in-depth review of the past and present projects will be undertaken and consultations with government planners, decision-makers and stakeholders will confirm which projects and interventions should be appropriately considered as baseline. The baseline projects will be determined on the basis of stakeholder consultations to narrow and define the CCCD project’s system boundary. Proposed alternative scenario: This project will target capacity building activities towards an assessment of data and information gaps and weaknesses, the strengthening of data and information sharing through improved networking, thereby reducing unnecessary duplication of financial resources, and a realignment of organizational mandates to help institutionalize developed capacities. The project will also strengthen the institutional linkage between data and information management systems and environmental decision-making for the global environment, which includes institutionalizing monitoring and evaluation capacities. This project will be closely coordinated with similar cross-cutting capacity development projects in Palau and Tonga to build up a critical mass of developed capacities that can be shared within the region, as well as to create important economies of scale and cost-effectiveness. Co-financing will be leveraged to help assess data and information needs to meet sustainable development priorities, with GEF funds used to reconcile those needs to inform decision-making necessary to meet Rio Convention obligations. This project, as with those for Palau and Tonga, will be implemented in three linked components: 1: Improving existing management information systems to measure achievements towards global environmental objectives. This component will focus on assessing and strengthening those sets of measurement methodologies, negotiating agreements towards harmonizing these and institutionalizing them within the relevant agencies and sharing protocols in a cost-effective manner. 2: Strengthening technical capacities to monitor and evaluate impacts on the global environment. While the first component focuses on strengthening the institutional and organizational capacities for improved data and information collection, management and sharing, this component focuses on the strengthening of human capacities to use improved data and information for strategic decision-making in the interest of meeting global environmental obligations. Strengthening the network linkages with other countries will be piloted with through the Palau and Tongan CCCD projects. 3: The third component focuses on enhancing the institutional sustainability of capacities developed under the project through the assessment and targeted strengthening of monitoring and evaluation processes. As such, this component will be strategically implemented alongside component 1 that serves to strengthen the institutional linkages of data and information systems across agencies and stakeholder organizations. Lessons learned and best practices will be reconciled with those identified through the Palau and Tongan CCCD projects. Incremental cost reasoning: As a GEF medium-size project, the incremental cost reasoning for this CCCD project is rationalized on the basis of leveraging an approximate equal amount of non-GEF financing to undertake project activities. Since the project activities are less proximate in construct to their contribution to global environmental benefits as defined under the three Rio Conventions, setting financing eligibility criteria for CCCD project activities is imprecise. Therefore, baseline and leveraged co-financing will be used to finance those project activities for which funding is clearly available, such as for active participation of government staff and other non-state stakeholders in the integration of environmental data and information management systems and the mainstreaming of Rio Convention priorities into data and information collection and analytics. GEF financing will be used to finance the recruitment of biodiversity, climate change and land degradation experts to prepare targeted analyses and to facilitate mainstreaming exercises. During the PPG phase, a more in-depth baseline and institutional analysis will inform what activities Vanuatu should undertake in its own national interest and of these, which can be readily financed through non-GEF resources. For example, although the MLNR's departments have databases, they are outdated and are not able to provide the information needs to support high quality technical analyses. Other non-state stakeholder organizations also collect and manage data and information, but also suffer from the same lack of financial resources to maintain updated information systems. Significant co-financing will therefore be required to bring these networks up to date, including training of existing and new staff on latest data and information collection methodologies and analytical tools needed to develop and implement national development plans that are more comprehensive. An estimated equal amount of GEF resources will be needed to reconcile these capacity needs to global environmental priorities and obligations. Indeed, in order to ensure that global environmental needs are fully reflected within the national data and information management systems, each capacity development activity under the project will need to be carefully and strategically developed within a Rio Convention construct. An additional activity under this project relates to institutional linkages with other Pacific islands' data and information management systems, in particular the parallel projects for Palau and Tonga. Of the three, Vanuatu's data and information management systems is the least developed. GEF funds will be allocated to help strengthen networked national data and information management systems, partnering with key regional organizations, including but not limited to the Secretariat of the Pacific Community (SPC), South Pacific Regional Environmental Programme (SPREP), and University of the South Pacific (USP). Global environmental benefits: This project responds to three main categories of articles under the three Rio Conventions, demonstrating both the global environmental value of the project and its cross-cutting capacity development strategy. The first set of Rio Convention articles refer to stakeholder engagement, where the three Rio Conventions call for the building of capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue (FCCC: Articles 4 & 6; CBD: Articles 10 &13; and CCD: Articles 5, 9, 10 &19). The second set of articles call for countries to develop capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management (FCCC: Article 4 & 6; CBD: Articles 8, 9, 16 &17); and CCCD: Articles 4, 5, 13, 17, 18, and 19). The third set of capacities refer to strengthening environmental governance, in particular to strengthen capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions (FCCC: Article 4; CBD: Articles 6, 14, 19 & 22); and CCD: 4, 5, 8, 9 & 10). Innovativeness, sustainability and potential for scaling up: As with the CCCD/EMIS project for Palau, this project is innovative and sustainable in that it will develop capacities to create a more resilient environmental management information system that will also be sustainable because of its expected cost-effectiveness. Traditionally, management information systems are organized and operated by individual agencies and organizations. This was a rational development approach due to the limited availability of financial resources that required organizations to focus on their particular data and information needs. Also, having proprietorship of this data and information will allow for greater predictability of the availability and accessibility of the needed data and information. In Vanuatu’s case, data and information is limited by the outdated methodologies and operations for managing data and information. An extension of these information barriers is that decision-making is increasingly being taken on the basis of inaccurate information, or in some instances taken in absence of information. The project’s strategy is to take an in-depth institutional strengthening approach to developing a national environmental management information system that fully integrates principles and features of resiliency and sustainability. All key agencies will be involved in the project from the very beginning during the PPG phase. During project implementation, institutional strengthening will require the appropriate re-negotiation of institutional mandates governing the collection, management and distribution of data and information, as well as building key back-up structures and mechanisms. Barriers to sharing data and information across institutional boundaries will be removed through concerted negotiations among owners of intellectual property. The sustainability of the national environmental management information systems (EMIS) thus requires much more than the basic and simplistic approach of training of social actors that represent present and future stakeholders, though this is certainly one important element of capacity development activities of the project. Additional awareness-raising activities will be required with users of data and information, in particular decision-makers and planners, including those in the private sector, who hold important positions of influence on resource mobilization that can adversely or positively impact the global environment. The value of this project, much like the other similar UNDP/GEF EMIS projects under development in the region, is that they will look at managing EMIS as a more complex dynamic system, rather than take the traditional transactional approach to database management and help move Palau to structuring and implementing an EMIS that will more readily lend itself to a more sophisticated Decision Support System and/or Executive Information System. The demonstration of improved decision-making for the global environment will serve to demonstrate the long-term value and thus sustainability of the EMIS, and provide lessons learned and best practice approaches on how to scale up the project outcomes. The potential for scaling up is significant as Vanuatu requires significant building up of capacities for information management. This project represents an incremental step towards the strengthening of improved decisions for the global environment, and through the creation of an EMIS, future capacity development projects could continue the long-term process of providing training on new and improved methodologies for planning and decision-making for the global environment. The EMIS is intended to demonstrate the long-term value of, for example, taking a holistic approach to decision-making for Rio Convention-friendly sectoral development. Only during project implementation will the true extent to the opportunities for scaling up be evident, as a result of lessons learned, best practices, and absorptive capacities of Vanuatu’s technocrats, bureaucrats, and other social actors.

# A.2. Stakeholders. Identify key stakeholders (including civil society organizations, indigenous people, gender groups, and others as relevant) and describe how they will be engaged in project preparation:

# Key project stakeholders are those organizations, agencies and individuals that collect, share and use data and information for taking decisions and actions that affect the global environment.  The first key stakeholder is the Ministry of Lands and Natural Resources (MLNR) and its subsidiary departments that cover land (DL), environment and conservation (DEC), geology, mines, and water (DGMW), and energy (EU).  As the focal point ministry for the three Rio Conventions, MLNR will implement this project through the DEC, in close coordination with the other MLNR departments.  In addition to these key departments, Vanuatu benefits from other important stakeholders, such as Transparency Vanuatu, which independently identified the need for Vanuatu to give greater priority to environmental issues, indicative of increased funding for effective management and enforcement of illegal activities.

# One of the challenges identified in Vanuatu's 2007 NCSA Action Plan was that there were too many committee that stretched the absorptive capacities of the limited staffs to formulate policy interventions.  The NCSA called for streamlining these committees, which in practice would make it easirer to take a holistic approach to inform environmental policy.  However, the extent to which the environmental committees are strategically linked with sectoral committees that focus on more socio-economic priorities.

# Other key stakeholders of the project include Vanuatu Meteorological Services (VMS), which provides seasonal rainfall prediction services to various government agencies (with support fro AusAid).  Another stakeholder and potential partner is the Vanuatu office of Live&Learn, an environmental education NGO, that is currently carrying a number of environmental awareness and education activities.  During the project preparation phase, key stakeholder organizations will be identified and consulted in terms of their contribution to the strategic design and implementation of the project.  They will play a role in the project, taking part in implementing, as appropriate, specific capacity building activities, as well being beneficiaries of capacities developed under the project.

# Important stakeholders also include a number of regional organizations, such as SPC, SPREP and USP, each of which are eminent institutions in the region in collecting and using data and information for important decisions and actions pertaining to local, regional, and global environmental concerns.  The project will include a set of activities that serve to capitalize in the expertise and comparative advantages of these organizations, with particular attention to them helping achieve economies of scale and reducing unnecessary redundancies.  This includes playing a strategic role in catalyzing cross-country sharing of lessons learned and best practices, as well as facilitating data and information sharing and networking.  To the extent necessary, the project may also help strengthen targeted capacities of these organizations with a view to achieving the project's cost-effectiveness and sustainability.

# With the purpose of the project being to strengthen the availability and access of environmental data and information for improved decision-making on the global environment, key proprietorship of this data and information rests with a range of stakeholders, including civil society.  During the PPG phase, the appropriate types of mechanisms to engage non-state actors, including CSOs can only be determined through consultations.  Notwithstanding, examples include creating or strengthening existing information networks and linking these with technical working groups of committees established or to be established for each of the three Rio Conventions.  The validity and strength of the project’s sustainability will rely on a set of regular dialogues with civil society on information barriers to effectively addressing global environmental issues.  Without prejudice to the consultations to occur under the PPG, one model of CSO participation (and there may well be multiple models) could be the regular convening, e.g., every three months or so within the framework of some existing community outreach programme that may be managed by one or more NGOs, to include an agenda item on priority Rio Convention issues that require civil society mobilization.

# A.3 Risk. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable):

Risk 1: Lack of absorptive capacity to implement activities Level of Risk: Medium Mitigation Measures: Project activities and implementation arrangements would be designed through a comprehensive multi-stakeholder consultation to ensure they can be cost-effectively and feasibly implemented during the project preparation phase (PPG). Project partners will be identified and partnerships created for project implementation. Risk 2: Delays in project implementation due to bureaucratic processes within the Government Level of Risk: Low Mitigation Measures: All three Rio Convention focal points are located with the same ministry (MLNR), albeit three different departments, one of which (DEC), will be implementing the project with direct support from the UNDP Fiji Multi-Country Office. The DEC's absorptive capacity has benefitted from capacity development support through other GEF and donor-funded environment projects. Key stakeholder institutions at the national level contributed to the conceptualization of this project and will be critical stakeholders during the project preparation phase. Representatives from different institutions, relevant local municipalities, NGO and academic representatives will be represented on the Project Steering Committee, and will be directly involved in project implementation. Risk 3: Non-enforcement of land tenure policies threaten project activities' delivery Level of Risk: Medium Mitigation Measures: Land tenure remains a problematic issue in Vanuatu, where a landowner's rights may be subordinated to other economic decisions without due process. The design of this project during the PPG phase will necessitate a thorough examination of the extent to which land tenure policies pose a threat to capacity development activities for the global environment.

# A.4. Coordination. Outline the coordination with other relevant GEF financed and other initiatives:

This project will be implemented in coordination with a few other similar projects. This project would also benefit from the capacities developed under the recently completed Third National Report to the UNCCD. An important project is the Land Sector Framework that targets land sector reforms. Given the overlapping objectives, the LSF and CCCD projects would be strategically coordinated. With UNDP support, Vanuatu is currently implementing a capacity building project to achieve the Millenium Development Goals, specifically to strengthen institutional capacity to collect disaggregated MDG data accurately and consistently for evidence-based policy formulation, planning and budgeting. During project preparation, these and other projects will be identified and assessed to determine the complementarity of relevant capacity building activities. This project will also be closely coordinated with the GEF funded project "Adaptation to Climate Change in the Coastal Zone in Vanuatu", which calls for the installation and maintenance of an early warning system. Vanuatu is also preparing its Second National Communication, which is coming to a close. Lessons learned with respect to the data and information needed to prepare the greenhouse gas inventory and undertake the vulnerability assessments will inform the design of the environmental management information system. Another GEF-funded project with which this CCCD project will coordinate is the regional UNEP project, which takes an over-arching regional approach to developing capacities for managing environmental information. To that end, the UNEP project will focus on the regional architecture, with a number of important national capacity assessments (e.g., 1.1.1 of the UNEP/GEF PIF) and trainings (e.g., 3.1.1 of the UNEP/GEF PIF). These and other activities will be framed towards strengthening a network of national and regional databases. The UNDP/GEF project picks up where the UNEP/GEF stops in that the former will focus on harmonizing and reconciling a wider set of national and local databases that would not only contribute to environmental planning, forecasting and reporting, but more importantly for Vanuatu for integrating information into planning frameworks not covered by the UNEP/GEF project. The resilience of regional environmental management information systems rests on a number of basic redundancies, which in this case would be demonstrated by having back-up systems in the event of a disaster that destroys part of the network. The UNEP/PIF clearly outlines a strategy that relies on a programme of work to be carried out by SPREP to provide technical advisory services to Vanuatu, as well as the similar EMIS project for Palau, among other PICs on improving environmental information management systems. The UNDP/GEF project on the other hand takes more national ownership and active role in the strengthening a more nationally holistic construct of their environmental management information system. At this stage of the project, the details of the differences and complementarities of both projects will require consultations and negotiations to better define each project’s system boundaries, respecting that there is a clear need for a national project to ensure national ownership and more effectively coordinate with national and local stakeholders that is constrained by a regional project and SPREP. There are a number of non-GEF funded projects that could possibly contribute baseline co-financing to the proposed CCCD project, including an AusAID Pacific-Australia Climate Change Science and Adaptation Planning Programme. This project is helping communities across the Pacific region to better understand and respond to climate change impacts, particularly in relation to infrastructure, coastal zone management and cross-sectoral planning. This CCCD project is especially timely in that it will build upon a momentum created by these projects.

Description of the consistency of the project with:

B.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSAs, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.: Vanuatu's 2007 NCSA served to identify priority capacity development actions necessary to address these, among others, challenges to meeting Rio Convention commitments. NCSA objective 2 called for "an environmental information management system to store and protect knowledge, inform and educate, and provide a basis for decision-making". The weakness of Vanuatu's existing databases and environmental management information systems also served as a rationale for NCSA objective 4 (an active environmental education and outreach project to inform and raise awareness and prepare citizens for a more active role in environmental protection and management) and NCSA objective 5 (which calls for the strengthening of organization and individual capacities for systematic observations, surveys and scientific research are weak). Vanuatu’s commitment to sustainable environmental management is evidenced in its signatories to various international and regional MEAs, the incorporation of environmental sustainability and continued alignment to the Vanuatu-UNDP Country Programme Action Plan under the 2008 – 2012 UN Development Assistance Framework (UNDAF). Vanuatu’s latest National Biodiversity Strategy and Action Plan (NBSAP) was approved in 1999, and includes the priority objectives of increasing information and knowledge of the country’s biodiversity in order to improve management and conservation activities. The NBSAP also calls for improving technical capacities for improved management of the country’s biodiversity through training and strengthening the active participation of local communities and land owners. Vanuatu has also drafted a National Climate Change Adaptation Strategy (NCCAS 2012-2022), which like the National Environmental Policy is currently still at the draft stage. The NCCAS lays out an approach to identify and implement efficient and effective activities to manage the existing and anticipated consequences of climate change for the land-based resources sectors in Vanuatu, namely forestry, agriculture, water, livestock, and biodiversity/ natural ecosystems. These sectors play dominant and essential roles in the economy of Vanuatu and contribute to livelihoods and the general well-being of people and the country as a whole. One of the objectives under the NCCAS is to foster strategic coordination, including an exchange of information, experience and tools to significantly improve the sustainability of development interventions. To this end, the NCCAS calls for, among others, an expanded use of new information technologies and technical skills. Recognizing the complexity of climate change, the NCCAS is not calling for the development of a perfect information management system, but rather to strengthen information pathways to facilitate more thoughtful consideration of adaptation options. With support from GIZ, Vanuatu has drafted their National Environmental Policy (November 2013), which will serve as a framework for existing environment-related policies, while at the same time provide a roadmap for Vanuatu’s long-term environmental objectives and actions. This Policy is also intended to serve as a strategic guide for the Department of Environment and Conservation, enabling the improvement of existing governance, coordination mechanisms, and service delivery. The Policy lays out five high-level goals that define the national focus and priorities for Vanuatu’s environmental action within the next five to ten years. As part of the Sustainable Resource Management Programme, the first policy objective is to develop and implement tools and approaches that enable sustainable resource management, in particular “to develop and implement a centralized information management system to house all information and efforts related to the assessment of terrestrial and marine environments, environmental health, quality and production.” As part of the Environmental Governance programme, a priority policy objective is to establish strong environmental communication and coordination mechanisms among national and local government, civil society, the private sector and communities. This will include providing incentives to projects and programmes that actively publicize and disseminate information about best practice environmental and sustainable development initiatives. Another policy objective is to explore the opportunities associated with using information communication technology to disseminate information and strengthen environmental databases. The National Environmental Policy remains a draft as of January 2014, however, these policy objectives are likely to remain in the final approved version given that the draft was validated in late July 2013. During the PPG, identification and analysis of Vanuatu’s other relevant national environmental policies, strategies and plans (such as the Priorities and Action Agenda 2006-2015, Disaster Risk Reduction and Management Action Plan 2006-2016, Land Sector Framework 2009-2018, and National Forest Policy) will be undertaken to reaffirm and map their relevancy and complementary with the proposed CCCD project.

# B.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities:

This project is consistent with programming framework CD2 of the Cross-Cutting Capacity Development multi-focal area, which is to generate, access, and use information and knowledge to improve decision-making for the global environment.  Vanutau's three Rio Convention focal point departments are all located within the MLNR, allowing for easier coordination and harmonization of existing databases and information systems.  However, whereas other Palau and Tonga may experience important overlapping in data and collection, Vanuatu's challenges lie in their existing databases not sufficiently developed.  While Vanuatu has benefitted from targeted technical support to create an e-Registry and the creation of a Zoning and Development Control Framework, these are not sufficiently complemented by updated technology that allows for the collection and management of data relevant to the global environment to inform more comprehensive zoning plans.  The CD2 strategy of the CCCD Programming Framework will address these issues through targeted capacity development support to, for example, strengthening existing zoning databases and technical analyses to be more informed of global environmental priorities.

The above capacity development support will be complemented by targeted cross-cutting capacity development support from CCCD Programming Framework CD5, which focuses on institutionalizing these systems within the decision-making process.  The CD5 strategy serves to assess and provide targeted capacity support to strengthen existing institutional structures and mechanisms for global environmental sustainability.

B.3 The GEF Agency’s comparative advantage for implementing this project:

UNDP has provided extensive support to Vanuatu through a range of development projects through the UNDP Fiji Multi-Country Office.  UNDP plays a critical role for Vanuatu in facilitating partnerships among donor agencies in the region, as well as with regional organizations such as SPC, SPREP and USP, among others.  The UNDP Fiji MCO currently provides programme development and implementation services for policy, technical and knowledge management to Pacific Island Countries (PICs) and has assisted PICs to access financial resources in various environment and development portfolios.  The UNDP Fiji MCO is staffed with dedicated environment officers and is supported by Regional Technical Advisors based in Samoa, the UNDP Pacific Centre in Fiji and the UNDP Regional Centre in Bangkok and also works in close collaboration with Pacific regional organizations for provision of specialized technical services.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Mr. Albert Williams | GEF operational Focal Point | Department OF Environment and conservation | 01/10/2014 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |
| --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Adriana Dinu, UNDP – GEF Executive Coordinator and Director a.i. |  | 01/10/2014 | Tom Twining-Ward, Senior Technical Advisor, UNDP (Green-LECRDs) | +421 2 59337 386 | tom.twining-ward@undp.org |

# Footnotes

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

TA includes capacity building, and research and development.

To be calculated as percent of subtotal.

On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the GEF Project Grant amount requested.

Part II should not be longer than 5 pages.